## Table 1
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [15 empty] | Document # ITP-014
[22 empty] | Revision : 0 |  | Date : 30/11/2020
Client: |  |  |  | Yarra Trams |  |  |  |  | Construction Process: Bluestone Kerb Installation (MCC) Specifications: City of Melbourne Standard Drawings and Specification: 1P 50406 Structure / Component: Bluestone kerb Location: |  |  |  | Prepared by: Name: Aaron Hatch Signed : Date : 30/11/2020 |  |  |  | Reviewed by : Name: Ruan Dippenaar Signed : Date : 30/11/2020 |  |  |  |  | Approved by : Name: Shaun Kent Signed : Date : 30/11/2020
Project:
Contract No:
Lot No: Lot Details: Lot Size/ Quantity:
Item |  | Task/Activity Description |  |  |  | Inspection / Controls and Verification Detail | [10 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility |  | Checked by:
No. | [5 empty] | Frequency |  |  | Acceptance Criteria |  | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  | Project Engineer Site Engineer Superintendent Surveyor Foreman |  | Client |  | Fulton Hogan |  | FH's Sub- contractor |  | Date
1 |  | Preliminary Works
1.1 |  | Check for Correct Documentation |  |  |  | Prior to Commencing Activity |  |  | •Ensure that employees and sub-contractors are using the most current and complete set of drawings |  | Contract Drawings and Registers |  | Visual Inspection |  | This ITP Signed off |  | HP* | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
1.2 |  | Implementation of all measures and controls |  |  |  | Prior to Commencing Activity |  |  | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP |  | EMP, TMP, SWMS, WP |  | Inspection |  | This ITP Signed off |  | HP* | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
1.3 |  | Existing Bluestone Kerb Demolition |  |  |  | Each Lot |  |  | •Care shall be taken in removing existing bluestone kerb •Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone •Bluestone shall be salvaged and re-used in new kerb alignment |  | Work Procedure |  | Inspection |  | This ITP Signed off |  | IP | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
1.4 |  | Setting out |  |  |  | Each Lot |  |  | •Line and level shall be set out according to design plans •Alignment of new kerb shall be marked out using string line |  | Work Procedure |  | Inspection |  | This ITP Signed off |  | HP* | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
2 |  | Construction Works
2.1 |  | Saw cut (if required) |  |  |  | Each Lot |  |  | •Saw cuts shall be made to the following depth for existing asphalt pavements: - Footpath: Minimum 75mm - Roadway: Minimum 125mm •Excavate to allow for design heights |  | CoM TS Sawn Bluestone cl 2.0 |  | Visual Inspection |  | This ITP Signed off |  | IP | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
| Item |  | Task/Activity Description |  |  |  |  | Inspection / Controls and Verification Detail | [9 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility |  | Checked by:
| No. | [6 empty] | Frequency |  | Acceptance Criteria |  | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  | Project Engineer Site Engineer Superintendent Surveyor Foreman |  | Client |  | Fulton Hogan |  | FH's Sub- contractor |  | Date
| 2.2 |  | Concrete Placement and Setting |  |  |  |  | Each Lot |  | •Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness •Gaps of >10-30mm< shall be provided and filled with mortar |  | CoM STD 1P 50406 |  | Visual Inspection |  | This ITP Signed off |  | IP | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
| 2.3 |  | Mortar Mix |  |  |  |  | Each Lot |  | •Joints shall be filled with mixed grout composed of the following: - 16% cement - 16% stonedust - 67% blended wash sand - 1% lime ready mix grout |  | CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406 |  | Verify |  | This ITP Signed off |  | IP | Fulton Hogan Engineer |  | N/A |  |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: | [6 empty] | Position: |  |  | Signature: |  |  |  | Date: / /
Legend
| HP |  | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent | [6 empty] | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | FH Hold Point |  | Work shall not proceed past the HP* until released by FH | [6 empty] | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  | An inspection which must be witnessed by the Superintendent | [6 empty] | SCP |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  | Written or verbal approval given by the Superintendent