## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp |  |  |  |  | ITP-007 - Concrete Track Slab Pour Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
label | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
label | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Mix Design ITP
label | HP*
label | RESPONSIBILITY: FH Engineer / Superintendent
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Weather Monitoring
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Surface Preperation
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
textbox | Date Completed:
checkpoint | 2.3 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
label | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
textbox | Date Completed:
checkpoint | 2.4 Formwork
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
label | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
label | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Reinforcement
label | FREQUENCY: Where Required
label | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
label | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
label | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
label | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
label | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Dowels
label | FREQUENCY: Where Required
label | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
label | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
label | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
label | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Pre Pour Inspection
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
label | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
label | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: FH Track Inspection
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Slump: Concrete Slump shall be 100mm +/-20
label | Compressive Strength: Shall be measured in accordance with CE-019-ST-0033
label | ○ Testing frquency =
label | – 0-50m3, 1 sample
label | – 50-100m3, 2 samples
label | – 100m3+, 3 samples
label | ○ Each sample shall consist of 4 cylinders
label | ○ Test Results will be provided to the Superintendent
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete supplier test sheet
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 2.9 Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure formwork is clean
label | ○ Concrete shall be entirely discharged 60 minutes after batching,
label | ○ Ensure that pouring does not occur from a height greater than 1200mm
label | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
label | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
label | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.10 Compaction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
label | ○ Vibration shall take place until exposed concrete surface is free from air voids
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.11 Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.12 Curing
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.13 Tolerances
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
label | ○ Plan dimension of slab +10,-10mm
label | ○ Thickness of slab +10,-10mm
label | ○ Cover to reinforcement +5,-3mm
label | ○ Finished level of slab +3,-3mm
label | ○ Foundation level of slab +0,-20mm
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.14 Slab finish
label | FREQUENCY: Where applicable - if track is Type 1 structure
label | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C - This is only applicable for T-rail/Vignole rail profiles. The slab surfaces shall be broomed to provide a non-slip finish.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.15 Post Pour Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
label | ○ Ensure no defects are present in slab
label | ○ Complete Fulton Hogan Post Pour Checklist
label | REFERENCE DOCUMENTS: CE-019-ST-0033
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Post pour checklist
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp |  |  |  |  | ITP-008 - Hot Mix Asphalt Rev2
section | Preliminary Works
checkpoint | 1.1 Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
label | INSPECTION/TEST METHOD: Correspondance of receival of mix design
label | RECORD OF CONFORMITY: Superintendent approval Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.3 Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.4 Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.5 Longitudinal Joints with existing Pavement
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | ○ Depth of step to be cut to the full depth of each indiviual layer.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c), Project Specs. Section 3040.06 (d)(vii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
textbox | Date Completed:
section | Asphalt Placement works
checkpoint | 2.1 Tack Coat (CRS 60 emulsion)
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Tack coat (CRS 60 emulsion) to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | REFERENCE DOCUMENTS: Vicroads Spec 407.19, AS2150 11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Spray area
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.2 Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Mix Design Confirmation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
label | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Delivery docket Completed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.4 Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20, Table 407.111
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.5 Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.6 Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.7 Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.8 Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv), Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-014 - Bluestone Kerb Installation (MCC) | itp |  |  |  |  | ITP-014 - Bluestone Kerb Installation (MCC)
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | ○ Bluestone shall be salvaged and re-used in new kerb alignment
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
label | ○ Alignment of new kerb shall be marked out using string line
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Saw cut (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements:
label | – Footpath: Minimum 75mm
label | – Roadway: Minimum 125mm
label | ○ Excavate to allow for design heights
label | REFERENCE DOCUMENTS: CoM TS, Sawn Bluestone cl 2.0
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Concrete Placement and Setting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
label | ○ Gaps of >10-30mm< shall be provided and filled with mortar
label | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Mix
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
label | ○ 16% cement
label | ○ 16% stonedust
label | ○ 67% blended wash sand
label | ○ 1% lime ready mix grout
label | REFERENCE DOCUMENTS: CoM TS, Sawn Bluestone cl 4, AS 3972 CoM SD 1P 50406
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-019 - Line Marking Rev3 | itp |  |  |  |  | ITP-019 - Line Marking Rev3
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Position of Markings
label | FREQUENCY: Prior to application
label | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
label | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Tolerance of Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Raised Pavement Markings
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
label | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-020 - Exothermic Welding | itp |  |  |  |  | ITP-020 - Exothermic Welding
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | ○ Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Materials Check
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made.
label | ○ Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
label | 1. Mould part number:
label | 2. Conductor size:
label | 3. Welding material required
label | ○ Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
label | ○ Ensure a working fire extinguisher is available within 10 metres of the working area.
label | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Preparation
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct.
label | ○ Heat mould to ensure it is dry.
label | ○ Strip & clean conductors, ensure they are dry & clean.
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Welding
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly.
label | ○ Ensure welding material has been insected and is intact.
label | ○ Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
label | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Weld Review
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made.All welds shall be inspected a Fulton Hogan engineer.
label | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: