## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP023 - RBB Install | itp |  |  |  |  | FH-ZU2-QU-ITP023 - RBB Install - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy.
label | ○ Current revision to be obtained via Aconex.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Definition of the work area
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | Reference Documents - Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Materials
checkpoint | 2.1 - Rubberised Bituminous Sealant
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - RBB must be a proprietary polymer modified bitumen (PMB) crack and joint bandage product and have the following properties:
label | – Minimum softening point to be 95°C
label | – Penetration at 25°C between 20 and 50
label | – Flow at 60°C at 5 hours to be maximum 5mm
label | – Viscosity at 180°C to be maximum 3Pa.s
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Verify
label | Record of conformity - Manufacturer’s Datasheet
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.2 - Material Sources – Conformance Test Certificates/Reports
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Test certificates and matching production batch numbers are to be provided for each product used
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Test Certificates
label | Record of conformity - Aconex Reference
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Sealing
checkpoint | 3.1 - Applying Sealant
label | Frequency - During joint sealing works
label | Acceptance Criteria - Sealant bandage is to be between 50mm and 75mm wide or as per drawings.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Protection of Applied Sealant
label | Frequency - During joint sealing works
label | Acceptance Criteria - Installed sealant must be protected from damage by traffic (and possible pick up on construction vehicles and aircraft tyres) until it has cooled to ambient temperature.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Cleaning up
label | Frequency - After sealing works
label | Acceptance Criteria - Any sealant split on surface of pavements must be cleaned off immediately.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: