## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e3d53e95-f578-4f0b-a655-1aa84b32d151 | checklist | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs Rev 0 |  | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
0185b4d9-ca54-478d-bfd6-11b9f7fa3ed3 | section | Details
2b64a5a4-b8ba-4c36-9cdc-0cfa9bfd5f87 | checkpoint-no-value | Referenced Documentation
875b1ce8-2c8c-575d-a77a-c2c9eecfdd3c | note | Document Title: CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
c351b7ca-7d86-53a4-8585-554c2da1576a | note | Checklist Description: Material delivery inspection-Precast Pits and RCPs
4f77f138-36c5-530c-976d-a9a5bda081af | note | Discipline (e.g. CIV/STR/RAIL): 003-Civil
1deae571-a919-51cc-b9f7-b46a10f7197b | note | Revision Number: 0
56c99700-742b-53c9-84e6-59b9136ee966 | note | Revision Date: 6/12/2023
d88fbe70-c8b2-593f-8719-600a0e9abd89 | note | ITP created by: Victor Mira
8f132e27-72bd-5cab-ab3b-a219151ab5be | note | ITP approved for use by: Victor Mira
da61488f-e3b7-4e85-96bd-11ff4ace40fd | checkpoint | 1 - Delivery Details
d42260c0-df66-565e-ac8e-bbd5a4f732e4 | note | Reference -
a3cbf84f-2072-539c-9ccf-1a94019c5b1b | note | Acceptance Criteria - Enter: Delivery Docket Number: [Free text box]:
42d5759a-059f-58fd-a84b-29ff6f8b8098 | textbox | Enter: Delivery Date:
fec7fca9-c8ac-5863-a369-061f9066f40e | textbox | Enter: Element ID (s):
63b0ba05-1797-5047-b034-0683cbf65ef1 | note | ○ Attach: Delivery Docket and packaging Slip
4b2b152a-0e32-554d-94de-676773854644 | note | Method - Document Review, Visual
da486c01-8d98-5ed7-8723-95573fad0b4f | note | Frequency - Each Delivery
19d1fdad-5cd1-58de-ae2f-a6df9c5960a7 | note | Category - IP
2d294c13-612f-5072-9958-b19eeb8933b2 | note | Responsibility - PE/SE
69b6330e-60d4-5d6a-a075-37650a935709 | note | Verifying Documents - This Checklist
8c10e752-9e88-55ce-af73-ef1025633284 | date | Date Completed:
fa573758-39f8-4c13-8cde-a10cd85b2c50 | checkpoint | 2 - Packaging Inspection-Quantity
3280434c-664f-5b17-8b41-5ffc244d35ac | note | Reference -
ce6d3483-0d12-5170-bff2-fca73ce0e70f | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
4df00599-81ad-554b-9f8a-299ec7f2c4c2 | note | Method - Visual
66ffb5b4-8c54-512e-97a1-c615875f1db5 | note | Frequency - Each Delivery
1ddc245d-a04a-5566-a4a0-57784af2a1bf | note | Category - IP
29509a83-7022-58b3-9a61-2864d5c0c865 | note | Responsibility - PE/SE
2edac38b-76d8-5913-bea9-ad933c0b1515 | note | Verifying Documents - This Checklist
ea9f39ed-a883-5eb0-a7a9-240896416243 | date | Date Completed:
7d3215c9-f223-4123-8424-efd2289394e3 | checkpoint | 3 - Packaging Inspection-Delivery Contents
9faba7d5-f123-523e-a403-eed394ea6167 | note | Reference -
1d1ef1a3-fa68-5166-84c0-ced3d2cc1baf | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
20f9578f-21ac-5bdb-a6f5-07eb813c4e7c | note | Method - Document Review, Visual
6a3b6257-5b72-556d-b783-7556806e55a7 | note | Frequency - Each Delivery
0210b7a7-66ff-5731-affe-c898fd5703ae | note | Category - IP
4bc70d62-7b30-5622-b5da-a7e2d270711e | note | Responsibility - PE/SE
451d4602-2339-55d0-8d39-4e2ee263e71a | note | Verifying Documents - This Checklist
29251626-c892-558a-b089-33d3edc48ba4 | date | Date Completed:
ff62109b-9a82-4802-987a-ce65030d65f1 | checkpoint | 4 - Packaging Inspection-Birth Certificate
36dd4061-06bd-5b79-bad6-b440e12c0c21 | note | Reference -
c13fc6f9-3340-583d-ad33-92084d7de150 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
3bf1ed09-c45a-5e6b-9482-4b4a34dcaab5 | note | ○ Precast components are to be marked on the birth certificate.
2659ad95-67ca-5334-a877-90bae700eb4c | note | ○ Cast date and lot are to be marked on the birth certificate.
2b4fd31f-55aa-5521-b67b-9737c3b987bf | note | Method - Document Review
885f63f5-d2cd-5ee6-a2bc-195d127d7855 | note | Frequency - Each Delivery
a9bcefe5-24b6-5a94-a215-0f81b1264626 | note | Category - IP
632b1642-4afb-5c6d-ab27-fbb15c8c6e87 | note | Responsibility - PE/SE
11874622-f9c8-52fc-8100-16fb3ff03143 | note | Verifying Documents - This Checklist
b8a71fb1-d8af-583d-b505-86ffa77d080c | date | Date Completed:
436ae6b4-f3ed-41af-ad89-2277b6d3941d | checkpoint | 5 - Packaging Inspection-Transport
b12ff482-0b62-5b60-bcd2-e8f80c770e6b | note | Reference -
a224ef95-123c-59c9-8174-58ecce3549e5 | note | Acceptance Criteria - Is the condition of packaging acceptable.
2177435d-ddd7-504a-b307-3ebc320a4c0c | note | ○ Precast items are protected from damage during the transport
385c3d17-174a-5f2e-a6f7-5e09940f6d0b | note | Method - Visual
e89bd68f-04db-59a6-8d51-68b39e16eea1 | note | Frequency - Each Delivery
9f8cff80-15ef-558c-859d-a8cbcf2cc12c | note | Category - IP
76eab21d-31c4-5e51-ad7b-5f72ef91abac | note | Responsibility - PE/SE
2622d2a5-7f28-55e4-a754-c047cbf8c1e3 | note | Verifying Documents - This Checklist
b5661c5d-f832-50ae-9579-a256eb20f7d8 | date | Date Completed:
bde8ca9e-1d9f-419b-9e59-4a8cc527848a | checkpoint | 6 - Fault IDs:
347340ff-cc39-577c-9c5f-048fff320c60 | note | Reference -
89b99d54-ab4a-5a8d-8d03-18bbf03f657d | note | Acceptance Criteria - For each precast type delivered, check for the following:
febc8b1c-da88-5dac-abb8-ebcac9bbcc13 | note | 1 - Identification markings match the Precast type
e6d35934-8641-5663-b0eb-1e79e7fa21e5 | note | 2 - Precast Pit fabricated as per drawings - inverts size.
6b1c5a48-8156-53b6-86bb-4c512b9aced7 | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
a6d08161-2d38-5661-95ef-0d135850a4e3 | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
ab9a697d-1aad-5ce6-90f3-e61935d09113 | note | 5 - Precast Pits - Inverts coliding.
9f4b0523-f2f5-5064-8883-d19c80e9a0b7 | note | 6 - Precast Pits and RCPs - Inspect for Cracks.
bdae63f5-82ea-55df-b0ec-13b2f319a0d9 | note | 7 - Precast Pits and RCPs - Inspect for Spalling/Damage to concrete surface.
69ccffab-7c56-5abb-be4f-58c979e19864 | note | 8 - Precast Pits and RCPs - Inspect for Exposed Reinforcement.
6b138135-6cc0-5fdc-ab94-55cecbeaa8d3 | note | 9 - Precast Pits and RCPs - Inspect for correct Lifting mechanism.
efe614f5-0895-5b4a-8c37-a4271cc7ee5c | note | 10 - RCPs - Inspect rubber rings
139b7bb1-dc06-55d3-b1be-ef2233922398 | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
c12ab59a-63c3-5482-9e75-2c8099c3ca71 | note | Method - Visual, Measure
0b3174b4-510b-5e05-b269-1413b2314765 | note | Frequency - Each Delivery
98a0ac3d-19bf-5a85-add6-24157f51bdda | note | Category - IP
9789921f-d9fb-5c91-b399-b5774b370a9c | note | Responsibility - PE/SE
21023909-7708-506e-ae1e-b846f0457628 | note | Verifying Documents - This Checklist
33099aba-4b18-5c03-9949-93cfccafd2c4 | date | Date Completed:
19ae6607-ee93-4832-bca7-e5a68356d625 | checkpoint | 7 - Check for Faults - 1
5d5a82c1-b6ab-53b3-bd56-ebcfdc45544b | note | Reference - Item 6 on this Checklist
88d2b393-7566-5f86-a829-7d2b5dd496a9 | note | Acceptance Criteria - For Each Precast type delivered:
a0b91d07-7667-5484-837c-8eafb20a5dce | textbox | Enter: Panel Identification:
e4c64cf0-9150-5d10-b1a8-56d8862a5808 | textbox | Enter: Quantity:
e05aed2c-3f27-55a7-a426-8abfc1c09249 | textbox | Enter: Fault ID if any:
173158fd-5d09-55d8-8067-94ac23ba35f0 | note | Method - Visual, Measure
3b6b061d-2a5c-5b3a-8068-8b228b29f7a6 | note | Frequency - Each precast type delivered
cdfb7b42-3ba1-5da2-a850-9248af30dd01 | note | Category - IP
b41b7bd6-b026-5443-bdd4-a8db2de623ea | note | Responsibility - PE/SE
ed8e7c07-8f61-5535-96fb-98f636367909 | note | Verifying Documents - This Checklist
060484cc-0a19-58ef-9900-c698d3d06fdd | date | Date Completed:
b1fffe04-b798-40b5-9d38-fc8866361bb0 | checkpoint | 7 - Check for Faults - 2
c0b43eed-9c75-5cfd-bfdb-15087425d1de | note | Reference - Item 6 on this Checklist
9b4adef8-82c9-59bb-a1f6-9ffe48bdfc2e | note | Acceptance Criteria - For Each Precast type delivered:
6184592e-49f0-5541-b173-aed03c574ead | textbox | Enter: Panel Identification:
690d1921-59f4-5b8b-a6a9-975f1f0bee60 | textbox | Enter: Quantity:
b9ca90af-6ce5-5a1e-a3fc-9186d1540aef | textbox | Enter: Fault ID if any:
a1f7a7b9-f93b-5829-84f6-d9b7d6ec4890 | note | Method - Visual, Measure
1a6726b5-4349-51d8-b0cf-1af50da4b951 | note | Frequency - Each precast type delivered
8147d376-4b16-5a56-9b18-ea79d38e6c6e | note | Category - IP
6638ec9a-772c-5401-a78a-4c3b29d095de | note | Responsibility - PE/SE
2f4ad40a-f9b5-5de4-bc79-f6fa2645c648 | note | Verifying Documents - This Checklist
57e6daab-b9e8-5b6f-8884-e3dbd12d75fd | date | Date Completed:
ab08fc55-a293-46c6-8d0d-f74ce9d4a8b7 | checkpoint | 7 - Check for Faults - 3
72080c10-1d99-59b7-80fc-96904456f8e3 | note | Reference - Item 6 on this Checklist
9e7191f8-469c-59c3-a61d-9b270768087d | note | Acceptance Criteria - For Each Precast type delivered:
b34155e5-99c6-5848-a6f1-0fb01d7025de | textbox | Enter: Panel Identification:
24a965b4-e4e3-5469-a027-af07641cf6a1 | textbox | Enter: Quantity:
a8f23341-c17d-5115-b05e-0c3f3576d56f | textbox | Enter: Fault ID if any:
77720c75-1237-539f-b79a-bc9b6851ea08 | note | Method - Visual, Measure
db14efe1-ceae-5fda-b200-ebf394dec791 | note | Frequency - Each precast type delivered
2fd24d5c-262e-5b31-9321-f1930e4f236b | note | Category - IP
6f4b239f-d083-50c8-9a65-29be093235c6 | note | Responsibility - PE/SE
ac4b0d88-f91b-575f-bdd5-c354e5a6ce82 | note | Verifying Documents - This Checklist
941c4d10-f666-59f6-b381-e91e2ea4a636 | date | Date Completed:
f93b4060-6cee-4b9b-9085-0e218f0ed446 | checkpoint | 7 - Check for Faults - 4
8ef39548-9e8a-5178-886a-c22f11029de5 | note | Reference - Item 6 on this Checklist
cb20668e-3405-5dfc-9f61-434488caf1b9 | note | Acceptance Criteria - For Each Precast type delivered:
61b9380a-5932-51db-ae25-58780cbe011a | textbox | Enter: Panel Identification:
14955b34-b91a-52a3-bbf2-2bc16a1f1af2 | textbox | Enter: Quantity:
36c303f2-488a-56fa-82e0-738202f05a05 | textbox | Enter: Fault ID if any:
2ecd06d2-5084-5fe6-a89b-f8083917f6de | note | Method - Visual, Measure
5ea5b9fe-df04-5b9b-aca3-4129026839db | note | Frequency - Each precast type delivered
f79029bb-ad48-5498-8e64-fe112e45a9df | note | Category - IP
a906cace-81ef-5d6d-8935-15ddc33e7237 | note | Responsibility - PE/SE
82d0e298-3a41-5517-bb0d-187c467970ec | note | Verifying Documents - This Checklist
54957289-3d7f-5612-b89e-7e96b4b89a63 | date | Date Completed:
ca12dd9f-2491-49e2-a48e-13b261a7d356 | checkpoint | 7 - Check for Faults - 5
37a2933a-c444-5db5-baab-f49a6f71f37f | note | Reference - Item 6 on this Checklist
f39785ac-ea7e-5eb5-bcc4-6d811a01f35b | note | Acceptance Criteria - For Each Precast type delivered:
c2dc97ec-04c2-5a52-ac98-778839421149 | textbox | Enter: Panel Identification:
c5e1d5b6-d793-55d0-9dc2-04ff437c1e1c | textbox | Enter: Quantity:
6425cf0d-d437-5f86-9a54-9d8c034e98ab | textbox | Enter: Fault ID if any:
78835fb9-8267-5435-bc4c-a17d12092849 | note | Method - Visual, Measure
f3895bee-7d03-511c-b33f-04d47fe81681 | note | Frequency - Each precast type delivered
2967ab88-16de-58d8-8b01-b851483d4288 | note | Category - IP
1b747d03-eaae-514a-b1a2-7d66f0f177f8 | note | Responsibility - PE/SE
a6d2cb1d-02f8-5b7e-ac11-97019e6aaa7a | note | Verifying Documents - This Checklist
c60a427b-855c-5c35-87cf-2204f9206131 | date | Date Completed:
73866b9f-980e-4eac-9f7d-334d97b3349a | checkpoint | Final Inspection
9a6c6abc-75b6-5f9e-8751-0e50fb14d912 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ac4f9ec9-218a-5434-b9f8-56376c74f867 | textbox | Name:
094d6312-5721-57ef-b53b-b34ed0d04ceb | textbox | Position:
6b276d8c-8481-514e-ad13-85fe8b586d32 | date | Date Completed:
a8f0d196-86b2-45e5-b3d8-a32f7f1fec9c | signoff | Sign ITP
1a7e3373-f520-4fa7-b0ca-eaced959f382 | checklist | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation Rev 0 |  | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
0c92049d-ace4-4d94-9a69-148fa3ca802f | section | 1. Referenced Documentation
b8be57f1-6752-4367-a9fa-f2884f88e82b | checkpoint-no-value | Referenced Documentation
23430a07-718b-54bb-b09e-e72631aa7bed | note | Document Title: CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
e47e5cd5-16b7-5d15-a70e-34ed277540c0 | note | Checklist Description: ADL-Stormwater Drainage Pipes Installation
e3fd2e3d-5316-55dc-8a46-0821992aa148 | note | Discipline (e.g. CIV/STR/RAIL): 017-CIV
c44607b3-441e-56bb-81b0-50f14831d193 | note | Revision Number: 0
06696043-7020-5f79-805b-fb169a9711f5 | note | Revision Date: 12/06/2025
b74b1423-01eb-5b25-b0d2-3c63fae6257c | note | ITP created by: Abhi Patel
fc1d9e2e-1137-5c8d-91a4-0bda0cc58c90 | note | ITP approved for use by: Aldrin Guinchoma
7e51c832-75fc-5c30-991f-2ab4069f3daf | note | 1.1 - Non Dependent
cf28f398-4798-5350-926f-043289d84753 | note | Reference - VR 701
fac18fa3-04c9-5064-a328-fe1b1717a7bb | note | 1.2 - Main ITP
e8b287fe-ac9e-524b-9536-edf85479635c | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
849e984e-c264-5fb7-85bf-28f7e1bab70e | note | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
e50c2eb4-601e-5037-bc71-dd0c8d5272e8 | textbox | Enter: Main ITP Teambinder Lot Number
5717e051-9b6d-464c-9e46-03f2e0d55852 | section | 2. Preliminaries - Materials
cec340a2-038b-4305-a09f-0fee9f590296 | checkpoint | 2.1 - Bedding
dd7d3163-1517-58bc-84dd-0ee0f740b9f5 | note | Reference - VR 701
df6888dd-e4e9-5ff2-a12b-20e673bc5927 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
d2d07ac7-ad2b-51d4-8d90-fbc8fb5c477d | note | Method - Document Review
d249e61d-c57a-5aed-8a20-7fb3ca1d98a5 | note | Frequency - Each Lot
062ecdca-192b-5e87-b6ca-089c83cde6a8 | note | Category - HP*
02a7c44e-cf84-53ac-80ba-d0d9565bf6ad | note | Responsibility - SE
e5755a22-94cd-5198-ab19-b4d4b6f56cba | note | Verifying Documents - Material Delivery Docket
98d69033-89de-5246-84d9-40a8119d94af | date | Date Completed:
c9ef817e-01e9-4245-85cb-9be413014d4e | checkpoint | 2.2 - Backfill Material
e2b6ba2b-e5b8-5a85-837b-6d8dc4b06e70 | note | Reference - VR 701
ae2c4960-3ed6-5f8b-a5f8-367b1aafe092 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
feca33fb-85d9-54e3-b340-8324c23ee7df | note | Method - Document Review
d3bc30aa-8bff-5df4-9f26-b32a9153109a | note | Frequency - Each Lot
e4e01f4e-2ec9-51a3-8062-53c449f50d4c | note | Category - HP*
63e6034f-0606-54b7-944b-876aef684826 | note | Responsibility - SE
7a12e0fa-c9af-5346-b3b2-ec4ecccfa1ea | note | Verifying Documents - Material Delivery Docket
2b2ae87f-d084-5ac3-ad5b-c18d242acac7 | date | Date Completed:
f2c3987b-9b52-457a-a59e-fa3593053970 | checkpoint | Stabilized Sand
f4d74a72-cfc9-5b49-b782-912843778b9b | note | Reference - VR 701
1ac93a6d-a414-5710-a0b8-4f6022b68aa5 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
25dd98cb-bb81-57e9-acdf-bb9e9848e621 | note | Method - Document Review
bcf195b9-eedd-50e6-8b42-d0f59bcd9195 | note | Frequency - Each Lot
d92087e5-49ef-5c80-8348-8091f9143a46 | note | Category - HP*
c436c266-520b-5198-8a77-f2374a0b0d9a | note | Responsibility - SE
7c68e4b0-05bd-518d-a38a-308383d7524c | note | Verifying Documents - Material Delivery Docket
6e7a8b2a-217b-5526-b0ef-40b34b994b7d | date | Date Completed:
9e93b01e-118a-4b1f-955a-902934924182 | section | 3. Preliminaries - Procedures & Documentation
761fbd9a-dd98-4de4-a06f-280c27c836a2 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
45230073-b0fb-5ded-b15b-de697b4beb85 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
43f49943-a496-55bb-8e81-b40dc6cd8ad4 | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
ac93cb56-06d0-5547-80eb-2c1f576f3250 | note | ○ ATTACH: Subcontractor Signed ITP
ddac949f-44c1-5e1b-ad49-abf962d3d8de | note | Method - Document Review
395d97d0-d0fa-5595-81f3-f79e300e9aba | note | Frequency - Each Lot (in case undertaken by subcontractor)
a113a7e6-d63a-5760-92eb-6b23d4ad4536 | note | Category - HP*
557bc6da-b1b4-5d3c-8d69-2207166e2778 | note | Responsibility - SE
12fca977-a623-54d7-836e-1819972060f1 | note | Verifying Documents - ConQA Hold Point Release
89bb555b-d91c-5747-8961-e9ab1aefb8d6 | date | Date Completed:
b164afba-e56e-40d0-a78d-4e98e90b3e1e | section | 4. Pre-construction Activities
5b6df943-5dca-404c-8816-7a45e7e129b5 | checkpoint | 4.1 - Survey Set-Out-
67f3a234-f06a-5756-b2dc-6d00e96c5447 | note | Reference - 710.1
1eb9d903-99fc-5703-95dc-15e54499a7b1 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
bf5e333f-930a-517a-82a2-6ea506f43f41 | note | ○ The culverts constructed shall be constructed true to line and level.
acdaa5ec-23af-5035-95b6-41fe70bdc499 | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
2f298ff8-7254-5f62-b4cf-ce18da822442 | note | Method - Survey, Measure
0c4e77c8-83d0-52c1-9353-39a925c7fb37 | note | Frequency - Each Lot
9b7e2d38-49bf-5a6b-b801-f35893a9cfa8 | note | Category - HP*
5efd9385-fa5d-57f9-b118-978d2621e13e | note | Responsibility - SE
814e2c35-44a2-5f0f-aca4-dda156606a5f | note | Verifying Documents - This ITP, Main Lot Map
a1ad8bb5-52ca-5055-a0e8-5f2ff07ec97b | date | Date Completed:
a673f65c-9168-4ebd-9105-f77e7503e15d | section | 5. Construction Activities
d642809b-4c9b-4a60-93f4-0374f992a3c4 | checkpoint | 5.1 - Trench Excavation
3b0e3a12-cc68-5770-9d64-70118bd23326 | note | Reference - VR 701.15
dd61594d-d733-5c84-a1bb-7bd27310726c | note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
90188ba2-ef33-5fa1-9535-7bc9cc35f707 | note | ○ Horizontal Clearance to wall of trench
b32e2c6a-6799-556e-88ea-74de882bf09b | note | Pipe Culverts:
4d54318e-6169-5e97-a48e-f2e3e6071062 | note | ○ 300mm<Horizontal clearance for corrugated metal culverts<1000mm
8fdbc0b4-1a13-5cc9-ba1a-ba54a1786ed4 | note | ○ 300mm<Horizontal clearance for other Pipe culverts<600mm
00f3fb4e-ba85-5e3b-9843-e42349dddf35 | note | Box Culverts:
151c080b-82a5-5e05-ba88-c2bce4b16186 | note | ○ 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
4504d7e0-84ec-52e1-8823-0e6196027437 | note | Method - Measure
4f765936-ba8f-5cec-a14a-c74b757d5800 | note | Frequency - Each Lot
d296fc91-a26d-51df-b631-8bd6f104b732 | note | Category - IP
639da4bd-eac7-5141-877c-43b2c01adc7d | note | Responsibility - SE
efb9b652-1e30-54ae-814e-af9cddc01856 | note | Verifying Documents - This ITP
68e63e28-b89f-58fb-bd27-04a5d17c386e | date | Date Completed:
d951a85d-647e-4057-b954-169482ab5bbe | checkpoint | 5.2 - Trench Base
fe3b0b70-b65d-54a7-b38c-e43b3397e310 | note | Reference - VR 701.15
0a0adaf0-bd0a-5ba9-a6cc-baa87ecc46cf | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant
ce8338ec-3b55-5e61-84f6-79a8e07c3309 | note | Method - Visual
6e8a5267-9c8b-5a69-9224-40209f25994a | note | Frequency - Each Lot
f2f90537-b5e6-5609-b597-eadd4b425134 | note | Category - SP
820c4035-c9cc-51bf-8f76-b75cdba73c9f | note | Responsibility - SE
6c4ab3ba-ff7d-5b65-984c-00c567b0a382 | note | Verifying Documents - This ITP
27051211-773a-5ca9-a538-9ecefc8a197a | date | Date Completed:
81a2aa83-4da6-4582-9a72-b8ac7eae0f70 | checkpoint | 5.3 - Bedding-Placement and compaction
9716c6fa-51c6-5169-b298-5a084f114703 | note | Reference - VR 701.16, VR 701.20 (a)
a3e2f4d6-0e17-5648-aa3d-4be6b1f159b2 | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
5bbd6c06-e859-5aef-805d-b000f8a75f6f | note | — 100 mm where D < 1500 mm
55f601bc-83da-5b93-9cd8-ea465720ea50 | note | — 200 mm where D ≥ 1500 mm
d44ccc01-574a-5de3-96a6-2a55b9220efb | note | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
6c5cd708-761f-5d8c-92d8-a786e36df80f | note | Method - Visual, Measure
a6d3a4b4-c48d-5d1c-9a6d-6b5969e2ad0b | note | Frequency - Each Lot
85a83922-27dd-56e2-82ed-7dc4b24cb1ca | note | Category - SP
c849aac7-a406-5cb2-ba69-e8748602c674 | note | Responsibility - SE
ca903861-ba6a-5124-9b61-fa2c88df6538 | note | Verifying Documents - This ITP
0b8bddd7-7e9a-5f7f-b8dc-96247885f852 | date | Date Completed:
c15d25ed-b623-4728-983e-96e02dabbd3a | checkpoint | 5.4 - Laying pipes-Bedding conformity
4d79191e-3070-596c-a97c-005464f49de6 | note | Reference - VR 701.17
1a92341c-a118-5def-973d-7e113086035e | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
20b060cb-80b7-568e-a773-7c82cbd3f55d | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
49970587-2a40-51d0-b747-a113511a7a22 | note | Method - Visual
b38aef81-cac8-5f8c-8a88-48b92970a66b | note | Frequency - Each Lot
fa9d8fac-d6c9-55ca-bcf0-e44dbdea836e | note | Category - HP*
b864aa3d-fc87-5c70-a323-e6969cd2aca4 | note | Responsibility - SE
cd6c3ddc-1557-519f-b836-29a5dcb317a2 | note | Verifying Documents - This ITP
a2716996-f0ed-512c-955e-78b74f10a89e | date | Date Completed:
905ee30e-e8d1-4197-98dd-ec4108e16f6f | checkpoint | 5.5 - Pipe Laying
1ca5dec3-78df-56e3-bb31-3e2938284873 | note | Reference - VR 701.16, VR 701.17
019f993e-6599-554a-9648-7e3665a4bb21 | note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
9706b725-395f-54e9-a967-f86616f51ec1 | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
05daa6a8-8fea-526e-8ddb-dace4a5cb935 | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
cc8f83dd-afc5-54b3-ad2e-ae61e6d846ad | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
821673f2-d9fd-5b33-9f94-c83acb224736 | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
ee2aa1ed-be36-5cd5-9316-0ebfb234e80e | note | Method - Visual
f0d1be5d-5457-5064-800f-8409c67b8240 | note | Frequency - Each Pipe
f601dae6-1a26-5c8a-a358-c13e0ad3618b | note | Category - SP
041e0fb7-3748-5ba3-bbda-6d0ee84e9048 | note | Responsibility - SE
a04118bf-3a7e-5441-b3e7-1f5506f219e4 | note | Verifying Documents - This ITP
1764afe1-29fd-53e8-8d22-42c6a7f4f10f | date | Date Completed:
76c619bd-ec16-447d-a6b7-d750c37d36fb | checkpoint | 5.6 - Pipe Joints and rotation
2e8c5d48-9edf-5524-b0a2-bfa1ca4a4ad9 | note | Reference - VR 70.18
89d680e5-832d-54e4-b9bb-371e054a0ce8 | note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
e6bc4823-0075-5fec-9fe5-9f9a68d915ae | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
edd63bcb-c6a5-5af6-80e3-b521fb5fa101 | note | Method - Visual
4d24513e-0310-596b-a06b-95fc2625c679 | note | Frequency - Each Pipe
a435f594-c276-5cc2-98e2-711a5cb07bf9 | note | Category - SP
6d5cfd28-5100-54fe-bc70-b4877efb1100 | note | Responsibility - SE
1a260d4e-c583-59b1-8ef9-1a0a9ea11552 | note | Verifying Documents - This ITP
d0bd4003-cd95-533d-990d-709b98810100 | date | Date Completed:
d890ecd9-6688-4719-81ba-c1c3379f5cdc | checkpoint | 5.7 - Conformity with drawings
707a4926-c956-5b7a-9fbb-82d0ed7587d4 | note | Reference - VR 701.10
2ea08427-e72e-5d0e-bbb6-898007213c89 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
5941f08b-466d-5410-956f-dca51c9459ce | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
7e0e957d-c547-5d43-b24a-eba1f54694d0 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
8dd64e4b-1ed3-5cdf-880c-d81ecd365cd4 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
8da693d6-724f-52e4-9489-45a3e4d44b13 | note | (c) invert level of pipes at pits ±50 mm
71d4d610-acac-56ed-983e-f4422f1967c4 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
eac8e392-c653-5196-8965-6bc2c2a106a8 | note | ○ ATTACH: Survey Report
a365d964-17ed-545b-a721-6f5e061ce437 | note | Method - Measure
65e3dde7-aa7a-580c-8324-e09d6b0aa7b0 | note | Frequency - Each Lot
af4db3cf-e029-54d6-bdc6-b5919df02ff9 | note | Category - HP*
3dfb614e-bbc7-5036-8d53-224a19eacaeb | note | Responsibility - SE
59d39290-d143-5c67-8195-3a718db83efa | note | Verifying Documents - Survey Report
ffb46bea-1b73-5a89-98b3-5b268091e6f9 | date | Date Completed:
f7baf61f-2268-4aeb-90dc-771ca490e6bb | checkpoint | 5.8 - Backfill-Under area to be paved
2c94c389-c62e-5733-96e8-696644d1c2dc | note | Reference - VR 701.19 (a) i
d0cff7c5-6328-5320-b2d1-a45375c5f984 | note | Acceptance Criteria - Culvert under area to be paved
b98333f2-2ad9-578d-93f3-2970f7d7f893 | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
a14b8c42-1131-5759-bd8b-113bacb8dba9 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
1216d5f3-e854-5bec-a000-1a54727b7672 | note | Method - Visual
1d80c36d-9a60-5d11-b6c4-b952fe1edf6c | note | Frequency - Each Lot
cc328865-1e92-5e8a-9a5c-7cb946e68221 | note | Category - SP
3cea2e32-04d7-5f14-9e5a-544d0a521887 | note | Responsibility - SE
e0253636-6519-58a5-8c6e-29df312df22c | note | Verifying Documents - This ITP
93b61925-e3d1-55a6-8d77-920d51149493 | date | Date Completed:
2788a8b3-0544-41f1-9489-17576f4f6c7c | checkpoint | 5. 9 - Backfill-Under area not to be paved
e7fa6617-2ec1-595d-8126-499d7caa2556 | note | Reference - VR 701.19 (a) ii
b9c3154c-2813-5daa-a0c9-4005fe517889 | note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
c79f549d-1290-5623-9e31-fa25ea73ed9a | note | Method - Visual
fc4d6084-2882-5392-8904-9fc949cda4b3 | note | Frequency - Each Lot
dc4efda8-2647-5e75-9de8-5e70d2aac97a | note | Category - SP
105e3c6d-2af1-579c-89e1-e2f7b6a3717c | note | Responsibility - SE
b87b5c3b-41f2-5ba2-ac92-4ef75b3544b9 | note | Verifying Documents - This ITP
9d49013f-198f-5b47-b33f-b4b103f47784 | date | Date Completed:
75f1e8f6-cb7d-4dfe-95fd-5a5ea6355c40 | checkpoint | 5.10 - Backfilling with cement stabilised sand
eb1754b5-d460-5df8-ad67-59cf1a5d76f7 | note | Reference - VR 701.19 ( c)
4d9a99ac-ef1a-54d6-8cae-4da425c21014 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
e6e952af-0efa-595f-8db2-68f2b063b179 | note | Method - Visual
2198ce44-4d24-5417-897a-49d995384040 | note | Frequency - Each Lot
fde2660f-5e9f-5db5-b489-107888d7e92a | note | Category - SP
cae9084a-8eb8-5358-b3a1-0ed5892189aa | note | Responsibility - SE
146fa201-c577-5f37-8457-c871853de33b | note | Verifying Documents - This ITP
7e1caf71-cd80-50a3-9362-2cf96ba19031 | date | Date Completed:
17b9c0de-b489-4a89-8dd1-8680efe4ef56 | checkpoint | 5.11 - Backfill Placement
61132126-e79a-5fae-b4eb-8bdadc95901b | note | Reference - VR 701.20
b6a308c8-76e9-5f54-8028-01d7dad49e5b | note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
a0fe64a3-9f11-5b42-8923-dc4893d87646 | note | Method - Visual
bad43252-f414-599f-9471-9064019dbdc2 | note | Frequency - Each Lot
938e449b-5fb9-565d-9d8e-a6ae50e76624 | note | Category - SP
0180cdb1-e178-5250-8421-f2775f13cdc2 | note | Responsibility - SE
c8b83e7b-30db-51e7-a9f0-0e13e8ad9759 | note | Verifying Documents - This ITP
c5945f2c-7ef7-50eb-92c7-fd0a4868833f | date | Date Completed:
2fa785d9-00c4-4398-88c1-7144e0e226e5 | checkpoint | 5.12 - Backfill Compaction
3a61fd20-f9f1-54d6-a971-2023b4edd009 | note | Reference - VR 701 (b)
9985f311-078b-575f-af12-a6dc2425211f | note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
8a176df4-4516-56b3-af5a-b682dab6da6a | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
4749771e-c8af-54f7-8db1-bc959276d0cc | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
27089db6-ea06-5d72-af15-a1a61d0272af | note | Method - Test
c697534f-a0ce-57c9-a3f6-8a59eb9e1b4e | note | Frequency - Each Lot
b60fffff-ac19-542b-91cb-f28039b15bc2 | note | Category - HP*
2cd62205-c6c5-5024-9b07-ecda63103b4a | note | Responsibility - PE
c10ebe33-788e-57e8-9595-bd22fb03ff0c | note | Verifying Documents - This ITP
23ee3d24-378f-56da-907e-d72e11e835a0 | date | Date Completed:
3a3908ce-f9fa-4f77-a5e0-c1b046049899 | section | 6. Post-construction Activities
0930a950-7950-467e-8db0-cf940559d491 | checkpoint | 6.1 - Compaction and Moisture content tests
53844d67-6d7b-54c9-8dec-e00c069b3d14 | note | Reference - VR 701.20
7f724a07-a6f2-5459-a889-a8d9fe57a9c4 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
3ca62449-9721-53b2-bd18-bc0beac2b0a9 | note | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
61a2ca3b-39eb-5736-952f-962b18e8906e | note | ○ ATTACH: Compaction and Moisture content test results:
9dc4d190-2c5d-51ee-9e8b-86c92ef17c4f | note | Method - Document Review
e6aa6551-41da-5943-9e52-c13f592d89bc | note | Frequency - Each Lot
14b1c3ff-153b-5688-b5aa-fb87bb42002b | note | Category - IP
789a7d00-9f33-52d3-8288-2bad742f8ab5 | note | Responsibility - SE/PE
953ea86b-e40c-5f0a-8c32-de4d10f1575b | note | Verifying Documents - Test Results
0c0a9bd4-c4cd-5442-891e-19f66d164a78 | date | Date Completed:
ea1c71df-0458-43c8-aa86-3f45809b45aa | checkpoint | Final Inspection
f872c0ae-c0cd-5f85-a8a9-ee319cf4b7c1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c2c6175c-1b9d-5004-b635-c87231bdd05f | textbox | Name:
29629098-b238-55d7-8201-5dc097724cfc | textbox | Position:
8fa12c4b-703d-5651-814c-8d4386eeda75 | date | Date Completed:
4377beeb-fc26-4a25-8e9c-39874c93a88e | signoff | Sign ITP
e29ea96f-2017-4f02-8394-f27c7ca5ccfd | checklist | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation Rev 0 |  | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
8e132aed-efd4-4368-9e11-baa460ba1745 | section | 1. Referenced Documentation
0cb17564-a9ed-40ed-bc0f-3f06903aaa47 | checkpoint-no-value | Referenced Documentation
5d455c7e-93f4-5ce8-8001-877a46669e71 | note | Document Title: CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
eec8db0e-259e-5f7f-89bb-ac5a1865df2a | note | Checklist Description: ADL-Stormwater Drainage Pits Installation
903844ed-78f8-5c1d-9c91-54228d9d630d | note | Discipline (e.g. CIV/STR/RAIL): 018-CIV
0424176a-73c7-5415-9cec-ab93da8d8a88 | note | Revision Number: 0
0cf034df-e9b4-58a5-b42d-573050484f6a | note | Revision Date: 12/06/2025
954c033a-b16d-55d5-9e4c-6f908f9e9cfa | note | ITP created by: Abhi Patel
64d87d62-a9fa-5cff-a367-41ca98d1e453 | note | ITP approved for use by: Aldrin Guinchoma
42221807-93d1-5d97-ba98-fe6743dbdeec | note | 1.1 - Non Dependent
005ebed4-0a0d-5bdd-bc3a-6f5edb3738f0 | note | Reference - VR 701
0ade695e-9143-51b8-8760-159440d7cb01 | note | 1.2 - Main ITP
348ade3e-c503-5662-ae6d-c64568a73010 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
7c69279b-6d8b-51f2-adc2-b20105326934 | note | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
df91cc4e-3701-5674-bbf1-aefced9dd45d | textbox | Enter: Main ITP Teambinder Lot Number
9edf0ad4-4adb-4217-a01b-a4ecebe2b35b | section | 2. Preliminaries - Materials
55892f3c-ad06-4fc9-b336-a2fc98f8e361 | checkpoint | 2.1 - Bedding
cecacedf-b9e2-5f1a-b02b-4e85418c875d | note | Reference - VR 701
7bd7bc9a-3df6-5026-9808-4406bf325375 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
0563dd18-a618-5ef8-99c0-8f85884ee5a9 | note | Method - Document Review
d5c9e034-8e94-580b-9d56-6d40cd76a030 | note | Frequency - Each Lot
46a7d1d6-efff-5f92-8a19-f2a634dd5327 | note | Category - HP*
16de8cf0-ed36-5f16-ad27-0d7035e6851d | note | Responsibility - SE
ab92d990-95fc-5a91-bb0c-aa17e5320f72 | note | Verifying Documents - Material Delivery Docket
1634fea5-2f5d-5229-83ac-e13112e00981 | date | Date Completed:
1ab873a7-4eed-4ed3-95bd-a139e706623b | checkpoint | 2.2 - Backfill Material
edf3dc55-da77-579b-bba7-b60595ed3026 | note | Reference - VR 701
75ef1475-eddb-5501-9926-25ad597445c7 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
d150a3a8-001f-54e8-a9ad-b8f711db1312 | note | Method - Document Review
f08d0cc8-3871-5407-88c5-4d93430ff95d | note | Frequency - Each Lot
505e3c14-f48a-5a08-b013-22c54b52ddac | note | Category - HP*
a94ca157-4e36-5e4f-bde7-f08634a8feb7 | note | Responsibility - SE
f828fad9-e127-5d8c-aa3d-33a1e56ef5aa | note | Verifying Documents - Material Delivery Docket
776e92a3-3273-5d1c-a6b8-e74fbfaaf8d2 | date | Date Completed:
14a08841-9175-45e5-ad86-75578391e557 | section | 3. Preliminaries - Procedures & Documentation
6a4c161c-a6c2-4971-99f3-f262c712de74 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
b4eb0d03-09e9-523e-8f71-0af990c49334 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
fa17cf1c-4d50-5e51-9e8f-3703b4f46191 | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
7e3c1993-87dd-51d3-916b-a3dde540e5c8 | note | ○ ATTACH: Subcontractor Signed ITP
c3a5de8e-4fbe-5f28-8293-e872cd56252d | note | Method - Document Review
01b9e592-9b86-5b9e-aae9-1f61b9e0ef28 | note | Frequency - Each Lot (in case undertaken by subcontractor)
43380ace-f4d7-5393-a5a6-3b488e831d81 | note | Category - HP*
4b571863-595c-5193-8486-844a7f5511e2 | note | Responsibility - SE
24ad12e3-b7b1-5a85-8c0f-c4b528c2759d | note | Verifying Documents - ConQA Hold Point Release
a4382a72-9149-5d61-987f-fa9fd4c7e087 | date | Date Completed:
a08a4476-efb6-4d04-b303-b692c04f6a3e | section | 5. Construction Activities
00862958-6b83-43d5-ba4f-27b4c9c68907 | checkpoint | 3.1 - Survey Set Out
0a3d7990-735f-580c-90a0-619f940554c9 | note | Reference - VR 701.10
2351f980-917a-5b69-bd3a-60bdef4b84f3 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
dd003b6c-c275-52ce-9c86-7b6bd18daf66 | note | Method - Visual inspection
678f6068-732c-50fc-82c8-d683380bea1a | note | Frequency - Each Lot
b08e11bc-2252-5567-a6dc-ab5ff9ed81b7 | note | Category - HP*
719db574-fd38-5433-bc78-e7d538e8eed1 | note | Responsibility - SE
703984ba-2d94-534f-aea8-52724cab076e | note | Verifying Documents - This ITP
e6a48d7a-f894-5eaf-b12c-a33a5097328c | date | Date Completed:
2529f659-3f22-49a2-a99f-5226aa78701c | checkpoint | 3.2 - Pit Excavation
1daa434d-72d6-5f11-8d8d-70ff58654926 | note | Reference - VR 705.05
6096ab4d-6fe6-54b7-937b-6b05ca44b01f | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
5ea31f81-f3fe-5f5b-b69f-ca5e35611a67 | note | Method - Visual inspection
19227ace-77b4-5f16-b36f-d441e4ab4e4b | note | Frequency - Each Lot
0cb504c2-1cbb-5b2a-b908-0e8f740b1ed0 | note | Category - IP
87f75f51-15ac-5bc0-8f0b-cc13c2eb55d5 | note | Responsibility - SE
5316d25d-3ffc-5d4c-b7f0-50c1803245e2 | note | Verifying Documents - This ITP
00cb4ee3-100e-55cb-b6d1-29d5f325918b | date | Date Completed:
afbd3c75-87c1-4d48-8af7-2e9a70a2d1d0 | checkpoint | 3.3 - Excavation Foundation
c979deb8-9ef0-504d-97bd-7086948f6bd9 | note | Reference - VR 705.05
6b384119-a860-57cb-bb2b-a696d55672f0 | note | Acceptance Criteria - Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
2224f032-0c6c-5e1c-b190-47258eaf03d6 | note | ○ > 80mm for clay foundations
8a6ede6b-98eb-51be-a0e4-851eb5880639 | note | ○ > 150mm for rock foundations
c42bc58a-c9cd-5920-9812-78a030d72e68 | note | Method - Visual inspection
434dffb4-ddb2-563f-9a13-328c2d936cbc | note | Frequency - Each Lot
a8ca552e-73e4-5167-8002-a77ec2c021d0 | note | Category - IP
0de0371b-9925-5f27-b0e1-d54619909e92 | note | Responsibility - SE
2fca786b-6491-5f1b-8b55-b12efb633e51 | note | Verifying Documents - This ITP
a2de2fd5-2506-54fb-a780-15f3422bced1 | date | Date Completed:
531e7554-bac3-472a-ab85-77c363d9629e | checkpoint | 3.4 - Jointing
3dfbcd9d-91fa-529f-98ed-e6d8a99a701a | note | Reference - VR 705.11
bf9cf9ef-5bf0-55ca-bdc6-b6308a3e0ca5 | note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
5868fde4-242b-53c7-b1d2-59b8f52b7b13 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
13587863-eee7-5dab-b143-74ed45c17635 | note | Method - Visual inspection
86ba42ab-6e47-5052-8578-8a9f0aece924 | note | Frequency - Each Lot
eeb7701c-7615-59d6-a6bb-42721d7f973e | note | Category - IP
ff1291aa-7432-538c-b0cb-857a5dfcaf2f | note | Responsibility - SE
da48086f-a355-574d-8150-dea9c8245262 | note | Verifying Documents - This ITP
1b53dcf5-3edd-5bb5-81a7-1710389fa690 | date | Date Completed:
22ac7669-445e-4680-b314-04398e5b566b | checkpoint | 3.5 - Shaping of Floor
92fe2ca4-f614-557c-a9ec-b6cf4e80414f | note | Reference - VR 705.13
64d2b67f-bed2-5d31-a8ce-1e97be39fc59 | note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
c9e9e069-29a1-5408-a6f3-0ba62bee3a95 | note | Method - Visual inspection
d62d28b7-62e4-51ca-8de2-ce6cb5097e25 | note | Frequency - Each Lot
ff84feaa-bc2c-50bf-a8d3-b6c718a06354 | note | Category - IP
4c9e0442-5a22-5d89-809d-6244dec121ef | note | Responsibility - SE
029647c6-9c03-5ac9-82ec-94bfd1b88e12 | note | Verifying Documents - This ITP
2b6032df-0851-5774-b026-58fbf2a97e7d | date | Date Completed:
c32f2274-3220-4d0b-9834-62b3536deb51 | checkpoint | 3.6 - Step Irons
8fa04a6d-208f-5b45-89ac-5626ef8ba223 | note | Reference - VR 705.12
12d93738-bf9d-538c-83ad-30a5fa3dc8cb | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
c6190189-e054-58b2-bea7-f35fbae6b3cb | note | Method - Visual inspection
430c4514-7638-54fc-93cc-db5abf73b6c8 | note | Frequency - Each Lot
756fc0ff-6cdb-5c71-8728-03cc28e9608c | note | Category - IP
3917398d-61d6-5495-80f2-0f99580ebc8a | note | Responsibility - SE
7f49f517-cc9c-5b9d-87e3-ac09f9e25a61 | note | Verifying Documents - This ITP
808e3dbb-03a6-59e9-b70d-88ec45135a79 | date | Date Completed:
a2286366-8ba7-44f3-ac02-a74a7fb7b721 | checkpoint | 3.7 - Fitting of Covers
8d9b09f0-235e-5a91-8b97-ea5699eade46 | note | Reference - VR 705.17
4f45d000-3e24-507d-8c70-e7b7fb74d116 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
f20d0c56-7236-5141-a4e9-11290b9731f1 | note | ○ Height shall be within 10mm of the design level
b1697fc7-16e1-54e8-af0c-cd0bd9b125fa | note | Method - Visual inspection
8afdced9-f8be-57bb-82cf-a6e9cdf932e6 | note | Frequency - Each Lot
b1dd339b-0603-550b-abb1-21d4d859d354 | note | Category - IP
84add1c5-9389-5234-a4eb-c7bb0e1285d7 | note | Responsibility - SE
e2723e9d-b9d7-5efc-9e45-bb07bbf609c1 | note | Verifying Documents - This ITP
4c463f8f-6bf5-5c5c-a711-38c18de8272f | date | Date Completed:
c8a9c20d-a90b-4b4d-82b6-8c7ca53ab553 | checkpoint | 3.8 - Backfilling Around Drainage Pits
b887dae2-434f-5b06-bd08-de6411bcd7f1 | note | Reference - VR 705.18
de30232a-7ec0-58e1-a720-0197b857cb86 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
205a1842-ee58-57b1-b091-a74ad24c8916 | note | Method - Visual inspection
3a551164-3a91-59c0-b626-7592f3f790d2 | note | Frequency - Each Lot
e1ac4057-da34-5a63-8ab7-fcb2c31616f0 | note | Category - IP
b7284fa0-7916-5009-9fe6-f192a20c566f | note | Responsibility - SE
b1bcfdd9-3667-5c94-be28-637080b16dbf | note | Verifying Documents - This ITP
df0a0990-e0d6-5f73-85f8-c2aae1b770fa | date | Date Completed:
562f8152-b166-44c2-96ff-c99dcf675ff8 | section | 6. Post-construction Activities
d741856c-be48-4982-a8c6-c4247fdff7c9 | checkpoint | 6.1 - Placement of Pit-Conformity with drawings
f7daf13f-a89d-5d61-bc52-84b2bc0fa47e | note | Reference - VR 701.10
97e0d0fa-1970-523c-b0ef-360a40665a4c | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
d63ed77d-7603-54e1-9df8-80378d473069 | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
4ed54c6b-6058-56eb-99b5-df3fa589b198 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
8e730b81-0e0b-5fcc-82a5-6f6a1fb73c6a | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
5d57076d-d88b-575f-8191-b2fb8c5f509a | note | (c) invert level of pipes at pits ±50 mm
98e35553-f1e5-5a1d-af65-82072ca7cdc1 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
60f92289-b3c3-5413-a81d-5906a077eafd | note | ○ ATTACH: Survey Report
38b4e9fb-674f-5d6e-aed6-295165772d06 | note | Method - Measure
d057dbfa-1175-5684-ad74-11fb17915fb8 | note | Frequency - Each Lot
e7e7dbd2-9ce4-5358-868e-5c37670c78b6 | note | Category - HP*
3ae32538-4ed5-5d66-848d-e94f21cd087d | note | Responsibility - SE
5c1235ed-7dbf-5f69-80df-5397aee49700 | note | Verifying Documents - Survey Report
8e4da822-5f79-5ed8-9e3d-6f6f0b78f306 | date | Date Completed:
4c3f9735-01b4-45d5-aed2-e7084092f17d | checkpoint | Final Inspection
e080d8dc-e6fa-50c8-8dc1-86eeb4e3b843 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6fa8cbe8-3c1d-5e57-a575-62d6164a518a | textbox | Name:
5fe46054-5f0e-5c8b-abc0-9ecd76568174 | textbox | Position:
2f6d3d38-6db4-5447-b715-d5b04ac9b85e | date | Date Completed:
7daba98a-ce75-4c93-96c5-33b162b1dd69 | signoff | Sign ITP
9e24f68d-f5c5-4ae1-9989-bf0272ff87f7 | checklist | Handover Walkthrough Report |  | Handover Walkthrough Report
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
274f55ef-7d8f-4e7a-84c3-54ddd23c7a88 | checkpoint-no-value | Project Details
4bc67576-c36b-5624-a0d6-330765d434ad | note | Alliance Name: Metropolitian Roads Program Alliance (MRPA)
93ffa6a4-d095-518d-9233-521eb10035a9 | textbox | Project Name
15fe2c86-5b48-527d-ade8-a4fa5a514e48 | textbox | Package Code
298ed052-a3f0-5b9c-8bfb-737f27a1282b | textbox | Project Background
afb6c258-08bf-47fd-9dd6-8c468cbe6e90 | checkpoint-no-value | Walkthrough Details
8199bff5-13cd-57a1-8fd5-078eb31c12a9 | date | Handover Walkthrough Date
5226efe2-cd0b-5a99-b00b-28111118603a | textbox | Walkthrough Discpline
89e6a0be-1ba1-5e41-9351-24cce3e1cf67 | textbox | Detailed Description of Works
e42d319d-a6e1-5fed-93d1-5bf4a69a6491 | textbox | Reference Drawings
49ac1c48-1497-4e8d-8aca-e8493f0b4228 | checkpoint | Walkthrough complete
bc0d4648-6422-5d90-aa1c-cb64df512215 | note | Attendee signatures
d1e97f69-2159-4763-82ce-6f53852aa510 | checklist | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing Rev 0 | itp | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
b30d5927-aa2a-4175-9daa-a1c419f916b9 | section | 1. Referenced Documentation
e5ec234d-1b1d-42a3-bd1c-3a10dca10cb7 | checkpoint-no-value | Referenced Documentation
a8e7e741-f040-53d6-b884-e7eb519ef698 | note | Document Title: ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
5daf2d2e-70bf-57cf-8826-495db92c3874 | note | ITP Description: Rail Delineation Temporary Fencing for Maidstone St
74ebf3ff-1bb9-5e94-930c-6fdf286d80bd | note | Discipline (e.g. CIV/STR/RAIL): CIV
b0795da0-301f-5bc0-b808-a22e646e127c | note | Revision Number: 0
a96b066d-3712-5ac7-a862-b449f6be2df8 | note | Revision Date: 1/05/2025
04c1c6fe-a5cb-5e17-82ca-1d291b52c1d2 | note | ITP created by: Dan O'Brien
d14fb9ac-5528-55e9-9522-d8f106736f9d | note | ITP approved for use by: Aldrin Guinchoma
ba769a3c-ef1f-55a7-892c-33fe9e8a6d75 | note | 1.1 - Non Dependent
a4f65d4f-4495-505e-82e9-d8e8cc3aa71d | note | Reference - IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
301f92e4-91d1-46ce-a32d-dc6d99e8f675 | section | 2. Preliminaries-Materials
7d3893ae-ce4b-4572-93ad-920e6f3d6bc3 | checkpoint | 2.1 - Concrete
967bddab-989a-58ff-a014-d3743906042c | note | Reference - IFC Drawings
0e22a410-778b-5489-9550-0eee8a45933c | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
463d1ef1-255c-5bfe-9550-dd8421c26165 | note | Method - Document Review
1b716367-f4ed-5bee-a233-f7f36098ee35 | note | Frequency - Each Mix
c7af3906-0ae0-5057-b4ed-080c26ebba39 | note | Category - HP*
8189423d-5812-5b4d-891a-bf0702722c51 | note | Responsibility - PE
a9938361-823c-5d27-9eaa-879a388a5076 | note | Verifying Documents - This ITP
c6c1c15e-dbd4-5706-a6ed-3c09c80df184 | date | Date Completed:
cd8d2ab8-a0d4-4a6f-8251-6eaecdd47937 | checkpoint | 2.2 - Steel components
f61ace2e-494f-5f41-87f6-b42e49869546 | note | Reference - IFC Drawings AS41000, AS1163
e2ebe6c4-3578-531b-8dce-0e3b6f4c979b | note | Acceptance Criteria - All Steel must comply with Australian Standards.
cde41fe9-275b-5748-a29d-dbc4e4fc31fa | note | ○ Steel section sizes must be checked on site.
f47932f1-206d-5f98-b799-146125e2d135 | note | ○ Steel posts to be CHS with a grade of C250
6dae5f91-b7b5-5aa8-bb79-543683b02433 | note | Method - Document review, Visual and Measure
728d77b2-40be-572c-8582-fe774106e235 | note | Frequency - All elements
c98bffb7-175a-55b1-a07b-7fb6ff871f97 | note | Category - IP
914b4262-0cf3-5cbb-b2f8-052bebf1f2c5 | note | Responsibility - SE/Site Supervisor
4a7450c0-a084-5359-990f-450b81a9919d | note | Verifying Documents - Delivery Dockets
5fefe35e-b7c1-54a8-b9cb-6ff4f707dad1 | date | Date Completed:
b8eda38d-1e6a-458a-9493-800c896ca93e | section | 3. Preliminaries-Documentations
b54abd41-d0ce-4699-9ec5-4874b33118ca | checkpoint | 3.1 - Excavation works
c2e494dd-26a2-567b-8bf0-611c1fe3e96f | note | Reference - IFC Drawings L1-CHE-STD-005
424ba696-9b01-58af-acb2-bba3b291f099 | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
43e3c5c9-6bad-55b5-a5ac-eeb35a820977 | note | ○ Follow asset owners guidelines for work around their service.
3b724dee-872e-5039-8265-4a56d7178f04 | note | ○ Excavation must use Non Distructive Digging in close proximity to services
8c06b442-ae56-570a-89c0-52ffbe827d4c | note | Method - Visual
f81bb348-dbb8-5f5a-8041-05fb94dda9a3 | note | Frequency -
dfd44f2e-75b6-5a7c-a7b9-16c12b2b1ac7 | note | Category - IP
a9e0058e-a51f-5336-8918-e390bb6fe64f | note | Responsibility - SE/Site Supervisor
702e81e8-096f-57ce-9fcf-e71e0175a56a | note | Verifying Documents - This ITP
8fdf3b48-a006-50d8-9c20-f6b1900e78a1 | date | Date Completed:
b629eadc-5804-4580-9afc-381cf12b73d7 | section | 4. Pre-construction / Pre-installation Activities
a6cb935a-4aad-42bf-b3d2-95519b27e387 | checkpoint | 4.1 - Survey Set-out
32170596-9996-5e5c-b240-b7c5b900ef76 | note | Reference - IFC Drawings
bf3b2e30-38ec-51ea-a81c-18b91d949dde | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
f6491261-4bbf-5ea6-bdd9-0fce4671e946 | note | ○ Offset checked against the running edge prior to installation of posts.
51a2d371-a2b4-58c4-8c20-6938b657640b | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
279b33cc-2da8-5c70-9db2-0f100085d02d | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
34a5b179-e29b-5313-8fdc-ec11b4924a0d | note | Method - Measure, Visual inspect
6c09db2b-8528-51f7-9538-22a93b8c8553 | note | Frequency - Each element
11c34bc9-f08f-5732-8c9b-29b3ea46183d | note | Category - IP
b4c63114-1721-578b-a6fd-15f0ff98f679 | note | Responsibility - Surveyor, SE/PE/SPE
d6d49991-8a86-5c5b-80e3-3c805110d515 | note | Verifying Documents - This ITP
df47be1d-60b2-5ea3-845a-455e0e0f5b3a | date | Date Completed:
3053b6ed-d858-4294-9758-72f08ee38928 | checkpoint | 4.2 - Vibration Monitoring
b89d436c-ad3d-5037-8b85-72ab664b0b11 | note | Reference - Worley vibration monitoring plan
36002666-383e-5eff-8d92-4a426232894a | note | Acceptance Criteria - Vibration monitors installed as required in monitoring plan.
7cbf6c73-e611-581b-9b42-aadc811bc350 | note | ○ Vibration at VIVA pipelines not to exceed 10mm/s
d3705057-7652-54e8-93e1-6986bb219a4d | note | Method - Measure
00104225-2343-56a9-a26d-a5806c38835c | note | Frequency - Each element
927714c4-db1c-5465-99b0-9f5c4467dcf4 | note | Category - IP
fa0b1618-46ad-5fa3-aee8-e35e943053eb | note | Responsibility - SE/PE/SPE
ef6f6b0d-66bd-56c1-a830-390ec7cd4318 | note | Verifying Documents - This ITP
17c61e3c-ab59-552f-8d92-858c74b7f047 | date | Date Completed:
9c7a33c5-df87-417d-8cb9-d4ecb503cced | section | 5. Construction / Installation Activities
7b7ca035-54ad-4775-a6f3-1aa1b35c85ed | checkpoint | 5.1 - Ground Conditions
d558d455-9df2-5020-8955-37fcd753ecf5 | note | Reference - IFC Drawings
b84bfa7b-ba8c-500e-b301-8e38d3d11c8f | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
aa2871a2-9c77-57e5-b65c-5b06141e9aea | note | Method - Visual
2cb182c1-d573-568f-ac88-e5e5c51b6df1 | note | Frequency - Each post
b867af5d-fbac-5524-8601-8f13794f03e7 | note | Category - IP
3e09f592-e222-5796-9b31-1edd94c0daef | note | Responsibility - SE/Site Supervisor
098f7710-cae1-5ee3-a853-1f4ca223bc32 | note | Verifying Documents - This ITP
03b2c1e4-d873-53b5-b3be-6a048b936bf2 | date | Date Completed:
57c5f93c-c12b-4bfc-96f1-22df42bfd74d | checkpoint | 5.2 - Post Foundation
b3790331-f2b6-5ff9-9285-0f81be9db427 | note | Reference - IFC Drawings
cc8f33ea-6fb5-565b-a4eb-8a34f4185b35 | note | Acceptance Criteria - Concrete
a7af24e7-2da6-58fa-bc85-1a8e888c98ea | note | — 300mm Dia
865a1a67-1a5d-5e8b-80dc-0d29d9332b59 | note | — 800 mm Depth
6b8c44b4-b5ef-5637-b44f-1ab2c04de962 | note | CHS Sleeve:
0955d0be-52f6-5e0b-9320-f029d2ccf5b4 | note | — Depth 1400
76cee79d-3334-5932-9c1e-1c7fbba8b929 | note | — Other Dimensions as per IFC
7b2210aa-9ff2-52d6-8ac3-fdab18ab20b9 | note | Direct Driven:
98b5ee57-11e2-51e4-b761-505a06458eb6 | note | — 88.9x4 CHS
a20ef889-63ab-508e-aa79-fd2ca49fd281 | note | — Depth: 1400
96c0cb02-9c05-5467-96ff-8165f79c28df | note | Insulated fence near OLE posts:
089be3cb-93f8-5208-8734-04269c6fd94a | note | — 95x65 Truform LVL
30672cb4-320b-5eeb-a65e-e0b221683a09 | note | — Depth 800mm (post embedment 700mm)
139b792e-3a34-58c2-b6c5-63f28dc798c2 | note | — 300mm diameter
0d966fca-2b7d-563b-ba0e-9f409aa22746 | note | Spacings:
ec713574-0153-5eb6-b518-b03ce8243ee0 | note | — Typical: 2700 max
085c0be7-5a92-5160-9426-33268f0730d5 | note | — Gates: 1350
db01712f-ec6f-5c98-8a92-66e43bb237f6 | note | — Refuge: 1200
1f3b8249-290e-517b-9c71-8f40125ec563 | note | Method - Measure
44b5eb9a-11c8-56ac-87c7-0912faabbf58 | note | Frequency - Each footing
d2a47e23-3507-5fdd-b034-bb41d05f0d91 | note | Category - IP
c7ad1105-5372-5766-8829-ff1da28d2045 | note | Responsibility - SE/Site Supervisor
25d859a9-5e93-5561-844b-85b7f2629063 | note | Verifying Documents - Concrete Dockets
5eccd80f-37c8-59d9-8fbf-27fae94fc049 | date | Date Completed:
cab192f5-429d-4a50-80fa-3f3c83fb2b90 | checkpoint | 5.3 - Post Installation
cd681ce9-b967-58ae-903d-508c6ea51848 | note | Reference - IFC Drawings L1-CHE-STD-005
bf470028-e0ba-5511-a3cc-1f4d2a2625eb | note | Acceptance Criteria - Minimum offset 3000mm from centreline of track.
09c4a939-85a3-5d9d-9c84-0b2a88a1d3b4 | note | ○ Minimum 2m offset to existing OLE structures (insulated fence required)
a45969a5-823c-5213-aa0e-47bef95eb55b | note | ○ Maximum post spacing to be 3m
14d022a9-a93c-5430-82a5-aabaafb0cb33 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
a73d14b9-3b2c-59f6-b7e9-8b8e49e50c1b | note | ○ Max. post height 1800mm above ground level.
49aff54a-6332-5886-b4ad-322491c0ab64 | note | ○ Vertical Tolerance: ±20mm from the design line.
1e8754a7-14e2-5d6c-98e8-63ccd499b2f2 | note | Method - Measure
307ba2c8-ec8c-599a-b934-18e1d79aae05 | note | Frequency - Each post
fd6ae2f1-621d-54a6-8d64-b8eb47fac034 | note | Category - IP
b94c280a-b1d9-598a-bae4-bdc0f09fdc5f | note | Responsibility - SE/Site Supervisor
27c9d2aa-66b6-5cd9-b4c0-fed2bbede3ad | note | Verifying Documents - This ITP
ef4f0635-e943-57d4-bccf-a823bbb7e024 | date | Date Completed:
0b3c0cbf-a5df-414b-a347-0973242bbcaf | checkpoint | 5.4 - Post Installation - insulated fence near OLE structure
5c7ba8e7-f806-5e33-af9d-5a1324be5d64 | note | Reference - IFC Drawings L1-CHE-STD-005
245fb2a8-4474-568c-9281-16ebfa224fde | note | Acceptance Criteria - Minimum offset 4000mm from centreline of track.
115cf64e-4c14-5055-b5cc-43781014d592 | note | ○ Minimum 1m offset to existing OLE structures
922cf335-b90a-56f3-8db7-8b345debab58 | note | ○ Maximum post spacing to be 2.7m
23c1c4cf-b39a-57bf-a0ee-d8ea3e39d1b2 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
f6232f72-27ac-5b0e-a57a-f0d76943ddcc | note | ○ Max. post height 1800mm above ground level.
3a109598-c898-5eda-beee-1920a4558ea2 | note | ○ Vertical Tolerance: ±20mm from the design line.
0c51a0a1-5487-50df-afea-132f88163c4a | note | Method - Measure
ef0487e6-e81c-532a-8cd8-e857d0f6bb1d | note | Frequency - Each post
e055677a-b1d9-554a-8ce8-2e96a1dcce02 | note | Category - IP
9cd7f530-efe4-5579-a2d4-f19848ab61d7 | note | Responsibility - SE/Site Supervisor
bc58d52f-104b-55ff-902d-106cb217a91e | note | Verifying Documents - This ITP
02807b93-682d-586c-8d1d-93104a2ce8e4 | date | Date Completed:
735e7806-93c6-4b09-980d-97347cc97935 | checkpoint | 5.5 - Chain Wire Mesh Installation
3ad57d51-d4c1-53ad-accb-b890e04da40c | note | Reference - IFC Drawings
3276e5ee-3e98-50b5-97c0-e255863e10a2 | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
6ddd682b-2b0b-5a46-ad5c-9ee3c3411920 | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
50179131-d959-5dee-8e6a-3b6f8ec47df6 | note | Method - Visual
c6aa8c93-3f94-5e1a-8c23-7683da055f4f | note | Frequency - Each element
1da61ce7-4827-5a00-b880-bf3e2de8b588 | note | Category - IP
1d5bc33a-1d8b-54b6-837d-7dac0beab93a | note | Responsibility - SE/Site Supervisor
33ab426b-20bb-5e99-9452-48d4d1861928 | note | Verifying Documents - This ITP
9cf3b7f0-4699-57a5-8617-33bf2c81e259 | date | Date Completed:
0c4f76cc-5706-42eb-867d-e6cf03e52e7e | checkpoint | 5.6 - Bracing
f5219dd5-2890-5a8d-82ef-41fc10b3c708 | note | Reference - IFC Drawings
0aeae59b-9001-5cf1-94da-caed533b03f8 | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
7d56837e-dfb2-5f84-9090-4815f826af43 | note | ○ Bracing to be installed on both sides of the fence at the fence corners
59fcfbeb-243b-56ce-ba0a-afb4a36cd9d8 | note | Method - Visual
201672de-d408-5f68-9ce2-02ff936db4ca | note | Frequency - Each element
c0aa07e3-87fa-5e21-9367-edc3fcf1ed0a | note | Category - IP
6d30352e-d64b-5ea9-997f-69f189f617f6 | note | Responsibility - SE/Site Supervisor
afdabd39-16c6-5aea-9feb-93accdede224 | note | Verifying Documents - This ITP
4137af28-a1ff-5c56-b41f-9b111be13368 | date | Date Completed:
fdcde141-9138-4d89-b307-bea9ef6c8943 | checkpoint | 5.7 - Wire mesh and bracing at OLE posts (insulated fence)
46c6e66f-76d4-540d-a964-7d3f5d934b16 | note | Reference - IFC Drawings
6fe89efd-cdea-53d0-b023-53595842dcb6 | note | Acceptance Criteria - Mesh fence to be PVC coated
ad364aad-a92b-5af4-99cc-c7e22c369404 | note | ○ Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws
8d7c4183-64bd-5353-a46f-5a34bf41d6c0 | note | ○ Tension wires to be PVC coated
953a035c-94a3-5fe1-90c2-3377ce7c6a10 | note | ○ Mesh fixed to posts using fence staples at max 200mm spacing
1cf522a5-3e2f-578b-afa6-c51bf1329bfd | note | Method - Visual
508340cf-1852-50bf-a7f4-272daa8c3735 | note | Frequency - Each element
e38b6a57-499a-5387-a3d2-f5612a405f6b | note | Category - IP
ee1e4638-46e0-504b-8908-9df873dee37a | note | Responsibility - SE/Site Supervisor
fc8591b1-5908-55c5-80d7-7ed4f4222444 | note | Verifying Documents - This ITP
7f235e0f-9231-51d2-84af-030ce2bc78d4 | date | Date Completed:
b252e649-e9e0-4cff-ab52-32871f2bf8a0 | checkpoint | 5.8 - Refuge Installation
fbf11d19-e1c4-544b-8e18-fb6273bb2d63 | note | Reference - IFC Drawings
a6d0b2d8-9888-5bcd-8124-f72723b2b825 | note | Acceptance Criteria - Refuge Access to only open from track side.
9661a4d3-1447-513d-b407-936e50ff533e | note | ○ No chain wire mesh to be installed at refuge access.
e4acd58c-37cd-563b-bcf2-3533c6a2fb88 | note | ○ Refuge Access to be located maximum 20m intervals
6cf48143-29db-50f5-9df6-4c99afbe49aa | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
0b4b8292-3965-5f40-aa80-6befb9d979ea | note | Method - Visual
2fb2cfb6-c5d3-5716-8d52-b73a565f5f3c | note | Frequency - Each element
af70bcae-543e-51d6-a358-074ff079ce7c | note | Category - IP
f3e0e1c9-c5b6-5df6-8236-548a374d53d5 | note | Responsibility - SE/Site Supervisor
95c2d7af-459f-5a8d-8c4d-c8cd87cc9320 | note | Verifying Documents - This ITP
0b4e2507-e355-51a8-b7f3-3a4e4fc61cab | date | Date Completed:
c34c7145-0600-419b-a5f1-5b1ecaf30215 | checkpoint | 5.9 - Refuge Signage
f6b1e182-f8d2-5e94-ade7-f3b3a220b70d | note | Reference - IFC Drawings
e87912b2-6464-5240-9d8b-53d65f327d1f | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
4940ad9f-aa25-5018-9eb3-560582cea76a | note | Method - Visual
575ed73a-5b23-551e-9784-7f7f9f9351d5 | note | Frequency - Each element
fb9d979a-8e7d-51eb-b189-0271d3f78f5a | note | Category - IP
009dc2a9-cab4-5a48-b4b4-85aff8485da6 | note | Responsibility - SE/Site Supervisor
095d5d25-ca54-5225-a623-53359e2b2938 | note | Verifying Documents - This ITP
0d9d0a01-7eeb-5244-a6e3-a17ecbed5c76 | date | Date Completed:
a3a50805-960d-4b23-b4d3-449480bc6dc4 | section | 6. Post-construction / Post-installation Activities
141c2044-b4e7-4135-a104-641b66b910ed | checkpoint | 6.1 - Fence Height and Track Clearance
17b44d48-d8be-5ee6-8b3c-e64355d69195 | note | Reference - IFC Drawings
6edbf42c-143b-5812-bb94-d7ad2e41e36e | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
3870fa3b-bbd0-5d32-8c90-21703c288f45 | note | Method - Measure
1899a64f-f296-5f1d-962d-1668817ce3fe | note | Frequency - Each lot
636e2600-6792-5dfb-89df-68b75b8a40d4 | note | Category - IP
5014919b-8412-57d5-851c-3d084025a4bf | note | Responsibility - SE/Site Supervisor
87eeaf9e-a5d4-54b3-9286-f6ffd07b527e | note | Verifying Documents - Survey report
d099666f-be94-51e4-90c9-cfe16c2caff5 | date | Date Completed:
27501c0c-0182-4b24-a1b9-cb7de41f4139 | checkpoint | Final Inspection
81fbc77a-b1d5-5188-b192-23125d1eac79 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fb53e5d9-86ec-548f-8657-03ee7bb1307a | textbox | Name:
878d37e6-793f-5f2b-a526-d20747419764 | textbox | Position:
e453ea52-23ed-572f-93f0-86f2a74deb97 | textbox | Date Completed:
8d1ee2b7-8890-4ed8-acf0-60bfde425fef | signoff | Sign ITP
33e2818a-c0de-401b-a6f2-c588449fb9a5 | checklist | ITP-272-CIV-ADL-Site Clearing and Grubbing Rev 0 | itp | ITP-272-CIV-ADL-Site Clearing and Grubbing
1d481a1b-c2bb-44ce-92f4-59a4b63edfbe | section | 1. Referenced Documentation
2dcea1de-fecc-4c03-a9f8-b0b98b7cd827 | checkpoint-no-value | Referenced Documentation
0304228a-5c28-52c6-8c5a-4992de088a24 | note | Document Title: ITP-272-CIV-ADL-Site Clearing and Grubbing
5d9a7f04-6738-5ac8-aa88-ccace3de2240 | note | ITP Description: ADL-Site Clearing and Grubbing
803da310-8400-576b-bde4-a6ab73ec5996 | note | Discipline (e.g. CIV/STR/RAIL): 272-CIV
08ad79de-74a9-5136-ae18-1079306e0059 | note | Revision Number: 0
39c6eac0-69ba-592e-9beb-d63a72c2fcb1 | note | Revision Date: 20/05/2025
116fac49-f0c5-55d4-bc99-29b203e56c82 | note | ITP created by: Abhi Patel
39943b15-b0d8-5b53-84d4-4904845ad0a0 | note | ITP approved for use by: Aldrin Guinchoma
d077da54-0f62-5813-9714-cc2620af7fea | note | 1.1 - Non Dependent
821b2899-4747-541c-a7b7-b57f971495ad | note | Reference - VicRoads Section 201
deb70b6e-462a-5e29-adaf-5ad23885a2ba | note | 1.2 - Non Dependent
0f479653-1302-5206-a291-35295648d04b | note | Reference - VicRoads Section 204
6108435e-40ab-53be-ba11-765589bdeacf | note | 1.3 - Non Dependent
9c83fd1d-4fe4-5f0c-96de-d7c12f30d659 | note | Reference - IFC Drawings
141cdacc-af6f-4d74-bc7d-c5f06349548d | section | 3. Preliminaries - Documentations
9349d9eb-1146-4dd1-8beb-d6cb3f7a9883 | checkpoint | 3.1 - Environmental Controls
50232dad-5362-5d7c-b5e6-73ff7fc6ed59 | note | Reference - MRPA Environmental Management Plan
f1f10a09-f597-5441-832c-2db629906b7a | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities.
10593464-3a09-527a-b8f9-05f74972fd70 | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
655d3b36-9578-5d66-be08-e94dd2e51a28 | note | Method - Visual
c426a9ec-cfa7-5abb-aab1-e5c527fbf98c | note | Frequency - Where applicable, prior to starting Works
3dd5323f-6402-52a3-8135-2d07ab453f45 | note | Category - WP
ed1b9cb1-eaf4-550d-85cb-71feca85bf50 | note | Responsibility - Supervisor, SE/PE/SPE
83500836-972b-5935-9a91-2d49f5aee3bf | note | Verifying Documents - This ITP Signed-off
bdee3db5-15e9-52a7-8824-1791d7e5e795 | date | Date Completed:
190dfc21-ff0e-4fd0-95e4-238a55ee0078 | checkpoint | 3.2 - Vegetation Removal Permit
8b1e8ba8-ed4e-5e18-94ec-0ed4554176e6 | note | Reference - MRPA Environmental Management Plan
350be7b9-845f-50ca-af30-d0e58fc5e650 | note | Acceptance Criteria - Prior to removing any vegetation or habitat:
39778b84-7e11-5d7b-b84e-aeb4969a1eec | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
601cacc9-8084-5a08-a955-a2461ed7653d | note | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
4d0f6886-fd52-522b-8b09-defa226f41dc | note | ii. fence and sign all sites nominated as No-Go Zones.
ba1c5186-9e99-5104-b630-63feb42aa9fd | note | Method - Document Review, Visual
4b6a5b61-0c47-52e3-8b46-1d69d6b2c84b | note | Frequency - Where applicable, prior to starting Works
4a7364af-f103-5497-95db-d9470eb016a4 | note | Category - HP*
015b5f3a-b7d7-5701-9be9-fbf977c4f732 | note | Responsibility - Supervisor, SE/PE/SPE
13de2958-80a2-5f88-a965-4c59c2e3f92e | note | Verifying Documents - This ITP Signed-off, Ecologist's Report, Vegetation Removal Permit
3e5d1ccd-899c-5075-8fb4-59ad599c1083 | date | Date Completed:
ea6f5683-587d-42c3-bf67-9f476a9845d1 | section | 4. Pre-Construction Activities
6b75c730-b969-4587-8132-88c18e23b0ce | checkpoint | 4.1 - Survey Set-out / Limits of Work
bdaabaaf-0b68-55cf-be09-53a6e45b8eb1 | note | Reference - IFC Drawings Section 201.03
36cbc574-2e64-5250-98ef-33bd4dd0a4e6 | note | Acceptance Criteria - The limits of clearing and grubbing shall be:
cb153443-4cc1-5ca4-a873-6694f7b4ed8b | note | a. the limits defined on the IFC drawings
e40890de-577e-59e4-944f-ea51c2b89600 | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
8732bfc7-8101-5657-99cd-a8bcc6b0477b | note | c. no more than the width required for completion of the Work under the Contract.
32760a7e-c66e-5744-844d-c115c363180f | note | Method - Measure, Visual
8a609701-09d1-55bf-917c-2b026da0da63 | note | Frequency - Once, prior to starting Works
6b5fa055-a8d4-53d9-9710-4c7363317d0d | note | Category - IP
d1e3f844-2c36-5519-b5b1-b6da74b4f1dc | note | Responsibility - Surveyor, SE/PE/SPE
2361863d-ad23-5f8b-ab2c-63c176c40d69 | note | Verifying Documents - This ITP Signed-off
17b44c63-33ee-53c6-8d0e-c97777077226 | date | Date Completed:
2c23d7c8-56c4-4c6e-803f-412b0bcd6940 | checkpoint | 4.2 - Cultural Heritage and Areas of Significance
dec0a27e-aa39-5a37-a2af-a6292d721c2b | note | Reference - MRPA Environmental Management Plan Section 201.10
990e9588-4d4b-51aa-8781-544b7436fb56 | note | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
c80ccecc-6ef1-5499-8c9a-fc7b4f92e88d | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
17d35b8f-f4b8-5e51-a4a8-c3eb41ec3f6d | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
bf5bc31d-4f49-5018-b223-e8363e6479e5 | note | Method - Document Review, Visual
55b65ae9-686e-5810-a2ce-3753bf4e80ef | note | Frequency - Where applicable, prior to starting Works
3ca65e7e-e022-53f9-9dd7-92feba8120da | note | Category - HP*
3d70bfb1-b90c-5683-b0f4-180ddfe62a5f | note | Responsibility - Surveyor, SE/PE/SPE
6b41b017-4ffa-5872-a06d-0ef2d34ff0aa | note | Verifying Documents - This ITP Signed-off, Cultural Heritage Report
d8467764-eeae-5d4c-95a0-e6a39b76c4d9 | date | Date Completed:
cb4e7185-4004-4fac-9a5d-5d3333be6b23 | section | 5. Construction Activities
bf08cf07-2898-43ed-b8c8-2948e3396573 | checkpoint | 5.1 - Stripping of Topsoil
e8058611-e783-5d76-9c8e-bf6edf1ede53 | note | Reference - IFC Drawings Section 204.05
0512edc3-8448-55d8-b0bb-e14353814cd9 | note | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
dca4e11a-0a2e-507f-8ae0-cc3dbdf7c45e | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
04811ce2-f6e3-52c5-bc07-489f37acdfc0 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
0d8f3679-1593-5e50-8756-a4f0156ba2d8 | note | Method - Visual
6c46bf0b-4b6b-5621-88e9-e237538dfb12 | note | Frequency - Each Site
dc1347ca-09b4-50a0-baf0-63e2904fff7b | note | Category - IP
f093ab9e-ce43-5692-b781-d27a040396a1 | note | Responsibility - Supervisor, SE/PE/SPE
b53f1f37-879f-5f85-8e60-fa316c227a2e | note | Verifying Documents - This ITP Signed-off
3696a439-af98-5a51-801c-630363562062 | date | Date Completed:
b304f65b-2812-4269-b867-75f2e58e7859 | checkpoint | 5.2 - Stockpiling
10d0b188-1f72-5e89-8112-9ed75d76d328 | note | Reference - MRPA Environmental Management Plan Section 204.05
e96869e5-c4ef-5120-b35b-34a81fadef28 | note | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
34e36a4a-1494-572b-aeb0-126ce574c9f8 | note | ○ If this clearance is not possible,additional protection shall be provided.
e38de41b-6fde-58e4-8217-cbcf7487870a | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
f3a4063b-444e-543a-9bcd-9360a6ca0c20 | note | ○ Topsoil shall be re-spread as soon as practicable.
8f2b3061-2c59-52e1-b142-129b3da25225 | note | Method - Visual
d4e1304b-955f-52f0-8e2e-4193a1900702 | note | Frequency - Where applicable, each Site
6a941ca9-dd97-5788-ae16-564c0abab26a | note | Category - IP
dba322b6-96f3-5017-bfc3-28ea516b48d5 | note | Responsibility - Supervisor, SE/PE/SPE
cbde1aaa-b1ed-5b64-b791-dd2cc888e2e4 | note | Verifying Documents - This ITP Signed-off
83001b0f-dc44-5afe-9297-8f779ad584e4 | date | Date Completed:
c80070ae-3d7a-4c60-a3ca-6d12aa5b7d2d | checkpoint | 5.3 - Abandoned Services
19e349f0-b4c9-5481-95b3-81cf353f4c2c | note | Reference - IFC Drawings Excavation Permit Section 201.05
d6dd85a5-bb24-5d7b-829f-516ca10233bf | note | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
3ff04773-2e9e-5ff6-b3c2-5ed020d71c52 | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
d8b11319-e95d-5f38-a942-0f20e6b0a992 | note | ○ Decommissioned services to be disposed of in a suitable manner.
c631cfe6-238e-5dbc-88d5-82108c5118c0 | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
df3de554-6f22-520f-9297-c010e83bc50c | note | Method - Visual
da52771e-e381-529d-996d-8cb2b423035a | note | Frequency - Where applicable, each Site
2a0eed87-beca-5398-8df2-2aa26fe51995 | note | Category - IP
fd12a5ba-206d-57f6-b411-2a9eb9fc0eb4 | note | Responsibility - Supervisor, SE/PE/SPE
7ba2db8d-94b1-5179-a703-954747038453 | note | Verifying Documents - This ITP Signed-off
d8e00862-00d0-5396-8342-371479eb970f | date | Date Completed:
65581f34-e9b8-45a9-aa94-43b9c5186ae0 | checkpoint | 5.4 - Clearing of Trees and Vegetation
f29c8fa6-1210-5a18-832b-0f6b96c81230 | note | Reference - IFC Drawings Section 201.04
a94490c3-a622-57ab-a59a-5b82a17a94ad | note | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
9e4f9a45-e584-5fb8-9c13-1d3745aa7970 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
53b041e4-49fc-5a81-8f3c-4512b0c2dab9 | note | Method - Visual
ae13d428-a88b-52f5-a046-23829b9d4a97 | note | Frequency - Where applicable, each Site
da482118-5634-5345-8102-428a756cbc2f | note | Category - IP
e9e44eba-9cad-5a5a-b171-48d6a32d9fec | note | Responsibility - Supervisor, SE/PE/SPE
df6408b2-5676-5b79-92c8-a0ccd20934c7 | note | Verifying Documents - This ITP Signed-off
ee0df769-2d36-5630-b489-ba59c9e89a15 | date | Date Completed:
93cc9b35-a4dc-4908-8f04-23c2667960fc | checkpoint | 5.5 - Grubbing of Vegetation
81140d34-fac4-5afd-8d25-2cb9cff1a7e8 | note | Reference - IFC Drawings Section 201.05, Section 201.06
f7d59364-ffeb-5665-aa23-aba692210aef | note | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
94a78537-63b3-5896-aa5d-eaf595ca112a | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
8c70d6fd-a9a8-500e-80dd-35acabdd6f21 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
5f730986-8ebc-51c0-9417-503bfa415497 | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
2d563ee8-7caf-575c-b180-493166f37294 | note | Method - Visual
8466bf8e-3070-583c-88dc-637f77e0f214 | note | Frequency - Where applicable, each Site
e44901fd-a67e-567e-8a16-7fdcc662e239 | note | Category - IP
092fafc4-4138-5453-8c49-95b88824dd05 | note | Responsibility - Supervisor, SE/PE/SPE
86e47296-3b72-53c7-b61f-498f23d96610 | note | Verifying Documents - This ITP Signed-off
1867753c-3a1f-50fe-9a44-1e913c8d45c0 | date | Date Completed:
e865c5c1-2de6-4052-ba68-fd28a5c11ca5 | section | 6. Post-construction Activities
cc9694a5-e125-42ce-8ade-a88c03a8aeb2 | checkpoint | 6.1 - Disposal of Materials & Vegetation
cd136eb4-493b-528b-8fd4-f92377535f94 | note | Reference - Section 201.07
17fd15d9-3110-59ec-9b42-21d11e29cd2c | note | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
e2908b28-30d3-5f41-928c-d05c05a65b43 | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
eef9689a-bf7a-531e-8b16-169d9292fded | note | ○ Tree trunks and large branches shall be removed from the site.
711e6a9b-e164-5d31-a694-8b3f54a88321 | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
0ecf6eae-fbe4-52b2-9d35-3408e3a0b3ae | note | ○ Attach: Delivery Dockets (for Items sent off Site)
2ddca178-19cf-52a4-9f19-9454dbac8f39 | note | Method - Visual
f26e030e-ce22-5b3a-8515-4f9a5e28cf07 | note | Frequency - Where applicable, each Site
dc43f60d-3013-5f9c-bd6e-6d577bd765b2 | note | Category - IP
95005841-82a2-5679-b5f4-f023623d788e | note | Responsibility - Supervisor, SE/PE/SPE
7faf3292-e1ae-557b-b3fc-4c89bc215f42 | note | Verifying Documents - This ITP Signed-off
286e5179-cac9-50ae-8393-a704f1d8d730 | date | Date Completed:
d6cf56b3-f0b8-413e-a41a-1472f7f2b002 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
19633775-6046-5f87-b36e-0a88f6883573 | note | Reference - MRPA Quality Management Plan
993c6894-f31c-59c4-bf72-78097faf7abc | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2dd0f9d0-55f4-59c1-a992-e56269bb75fe | note | Method - Document Review
4cff97e3-c3c5-5d12-a681-699afb18302f | note | Frequency - Once, prior to closure of this lot / element / Work area
4043a6ea-620c-53e6-88d6-752237f2d38e | note | Category - HP*
62122b52-4018-545a-bd34-caa02decf478 | note | Responsibility - SE/PE/SPE
2202cfac-f70c-500f-8e55-2991a81e7604 | note | Verifying Documents - This ITP
2fd12520-acb8-53be-90e4-c660671f8e24 | date | Date Completed:
51c2f1dd-5cca-445d-9060-35a8b2a64cbd | checkpoint | Final Inspection
7518e5a7-78a2-5697-8f58-ae36ed3a0d54 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2d5ee97f-d4ea-5365-80f1-835f976493fe | textbox | Name:
18babd2e-723b-521c-b42c-52317e7a4beb | textbox | Position:
2212ad70-7de5-5d1a-b0bc-ec03c823a613 | textbox | Date Completed:
778bb575-d48c-45eb-8edd-8c711f97c659 | signoff | Sign ITP
c51f959f-5e83-4e17-bff3-3284a14639f9 | checklist | ITP-273-CIV-ADL-Subgrade Preparation - Road Rev 0 | itp | ITP-273-CIV-ADL-Subgrade Preparation - Road
09dcb07a-8973-4bca-9067-e543401238c1 | section | 1. Referenced Documentation
353d9ccb-e890-4e08-9f76-1640db00d350 | checkpoint-no-value | Referenced Documentation
dd73eff8-f9e5-5c9f-ad8d-094277ca9ad3 | note | Document Title: ITP-273-CIV-ADL-Subgrade Preparation - Road
6b8824ce-1fa0-5bea-ab9a-a23aaecdaa8f | note | ITP Description: ADL-Subgrade Preparation - Road
25e11c32-9e88-5d2d-91e5-d66fb48a909a | note | Discipline (e.g. CIV/STR/RAIL): 273-CIV
ec4d66f9-cf25-5053-a2d8-66c915522cad | note | Revision Number: 0
af7f1121-429c-50bc-8688-c1831de41824 | note | Revision Date: 22/05/2025
9c9aedc7-e900-569f-b412-ae8052a1b34d | note | ITP created by: Abhi Patel
146f2023-6543-5a37-9863-a409add392e4 | note | ITP approved for use by: Aldrin Guinchoma
b4f54757-6daa-5e6b-afec-219505314848 | note | 1.1 - Non Dependent
a1d96ea8-4bea-53db-98d1-49b8d46f921e | note | Reference - VicRoads Section 204
9d1699e6-023c-5bea-b1fc-8b6ae4fbcda7 | note | 1.2 - Non Dependent
101c7c17-8eb0-5f23-bcb3-7ccfd11d0c31 | note | Reference - VicRoads Section 173
a4425afd-17b5-4ea1-8f49-d52972a48ef5 | section | 2. Preliminaries-Materials
7e63927a-923c-44dc-99cd-973137c02a17 | checkpoint | 2.1 - Material Approval
401ea3f0-e3cb-557b-a3ae-140ea64f59f4 | note | Reference - VR 204.04 (C)
9e8e3ce5-d5a1-50d5-973c-e9a18cd038df | note | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
5be372c0-ac7d-5982-b71d-3d961e955d75 | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
6de095b9-276e-5453-b6d0-5a581dbc35d4 | textbox | Enter: Teambinder Material Approval number
563615e1-a1e2-5673-bceb-d0d674d38659 | note | Method - Document Review
67b7a7d3-006b-5669-ba24-2b7af89c6641 | note | Frequency - Once, for each mix material
1807d235-555f-5da7-a7e4-663d765f7fe6 | note | Category - HP*
cc9bef30-22fc-520b-860c-2ff3a2900dfc | note | Responsibility - Nominated Authority
cc4df168-3646-5800-bda5-7fa5e654bea8 | note | Verifying Documents - Teambinder Material Approval
391b00d8-65cb-5ffa-bd59-79b5cf1719b0 | date | Date Completed:
3e64166a-cc93-445e-a977-1d2bcd75998c | section | 3. Preliminaries-Documentations
c85e0726-c626-495a-9490-c3f523e2bfd9 | checkpoint-no-value | 3.1 - Non Dependent
71793db7-9512-4007-972c-61411aa8bb5f | section | 4. Pre-construction / Pre-installation Activities
4a897bd9-8e37-48f5-b988-95ac8530d249 | checkpoint | 4.1 - Survey Set-Out
95e5f64f-96cf-54d5-897f-9aab9a634901 | note | Reference - IFC Drawings
9872fa3a-670d-5919-a11c-1df3222368f0 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
c4365c10-b811-5ea8-9107-7ce0cf79d2f6 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
cf6c600f-8d8b-5c8c-8858-cadccf334e33 | note | Method - Verify
82b64af2-36aa-5491-b63d-9d0e582cc22e | note | Frequency - Prior to commencement of excavation
ddbc0ba6-6861-58b6-ac37-acd5ae798d20 | note | Category - IP
d30a99e6-beb9-581a-b97c-324e3acff50c | note | Responsibility - SE/Surveyor
de7214b3-52fa-534a-aa2e-a8b29e856800 | note | Verifying Documents - This ITP
a12a8f39-ccb8-5876-b74d-8b374a68cc2d | date | Date Completed:
88230224-1661-42ed-843a-af4e0ba8feb0 | section | 5. Construction / Installation Activities
49fa9fb5-affa-480e-b861-769b656f8d5c | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
277a8236-fa47-5abf-a13c-17ea63841617 | note | Reference - Section 204.06 (C), Section 204.06 (e) IFC Drawings
554b40ee-e934-52f2-807a-c4456c716319 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
60953a9a-fd91-5268-aac4-8e527499ed1f | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
971cf373-dfe3-5493-9818-9ac2a0e0eb38 | note | ○ Assigned CBR ≥ 2.5%
179943fd-50bc-565b-88f8-8170abe65ea6 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
0628f244-e236-5bbd-a25f-864043592a94 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
0837b73d-7bfc-5d6e-9de9-d1f9e0b6197f | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
c07b012c-5f40-509d-b50d-fb4e695e9c5d | note | ○ Attach: Laboratory testing Verification:
5ba6cbc8-261f-5159-a0b2-ee76af06aab6 | textbox | Enter: Type A fill Lot Number:
f4c66724-8290-5bc2-a06c-88664c5305a9 | note | Method - Verify-Document Review
8254bf9a-5dec-564b-8850-02aaf3d5b533 | note | Frequency - Each lot
145c758e-6fd2-57f8-a944-3274b8550fe7 | note | Category - HP
1fdde727-56a5-5ebc-a083-1a91bc83cbaf | note | Responsibility - Nominated Authority
0c7614f7-1daf-57aa-b704-bd66fdca6dbe | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
8374593b-f874-56c6-8cbc-89341e6146fc | date | Date Completed:
e309c0f8-cb58-4e8e-9fd5-3f17f18d5daf | signoff | AUTHORITY HOLDPOINT
e8d1e764-d40e-4828-b6b7-91ced75ea20a | checkpoint | 5.2 - Material classified as silt
c21c4d96-721e-5fcf-b4c5-2b57222b24ec | note | Reference - Section 204.04 (b)
43ad4088-6c77-58d3-9f7a-fe303c84d7e1 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
9cb35d49-1ab2-59c9-8b2b-c20450cec117 | note | Method - Document Review
57e8136c-97ad-5632-bb21-251d9adcce61 | note | Frequency - Prior to commencing
dd1ee55e-b89f-53e8-afc4-d1d730b91851 | note | Category - HP
2c7823e2-9c7f-59c1-b35f-c0de91ca06bb | note | Responsibility - Nominated Authority
7ef8a81d-8994-5803-9974-38f2ee02d1d9 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
65e16d0a-73bb-5cc3-a53a-b23843ee360e | date | Date Completed:
dfb4e3f7-35ba-481a-b35e-7db8d2cf4a27 | signoff | AUTHORITY HOLDPOINT
1b80955a-ad3f-4e45-ae76-223fbeff6939 | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
4a7f018d-8ae6-5bcf-943e-519f7872018a | note | Reference - Section 204.06 (f)
5cce6b65-6efa-506d-ace0-4852b7d59468 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
350c2cef-b316-5f4d-a86e-e984038c14ee | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
99cc2acd-6118-52a1-913c-f10dacc0be1f | note | Method - Site Inspection/ Document Review
5a35f4eb-a85b-5471-a199-2df2ddd64614 | note | Frequency - Prior construction of the regulating layer
66bcafad-e065-5a95-8a3c-7749046b4008 | note | Category - HP
f57eb615-ae9b-576f-8133-bec845a90a73 | note | Responsibility - Nominated Authority
54c42940-3163-5db9-abd8-29f9c470eeb0 | note | Verifying Documents - This ITP
24ccf69a-72b1-52e6-afd1-db2535981ac3 | date | Date Completed:
bb4a6ad9-c8c0-4af6-9615-05d638a70e42 | signoff | AUTHORITY HOLDPOINT
402eec62-32c4-47b1-a377-ec490ac58d07 | checkpoint | 5.4 - Unsuitable Material
20066514-5d00-55f2-a4b6-3d45da1f5006 | note | Reference - Section 204.07 (d)
47cd6f98-5066-5734-992d-a79f6de97a21 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
48eb0ade-ce97-5fdd-ae8a-7641018aab78 | note | Method - Visual inspection
5af9ac17-d923-5362-abb3-c7d008423866 | note | Frequency - Each lot
f6c7fbeb-073d-5c79-a572-f21ac2dd986a | note | Category - HP
a3d1fb95-62c5-5038-9048-cf0774092955 | note | Responsibility - Nominated Authority
79bfd0ed-c17e-5a2b-bbdf-b53185ee71e0 | note | Verifying Documents - This ITP
11c2b495-fde8-5dd4-abd9-69c18590d41a | date | Date Completed:
5fdd4def-bd13-494d-ac56-6a9632393938 | signoff | AUTHORITY HOLDPOINT
db2e8e51-802d-4773-ae50-194d0fc0fc37 | checkpoint | 5.5 - Groundwater
a2bcf881-cb3a-5e4b-b78c-4771b141ed5a | note | Reference - Section 204.06 h)
faac3644-a61f-59f2-b37d-6727145cb4c4 | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
21080e1e-1b7f-5eb6-af18-d13db8274485 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
71e524e6-0d90-5bbe-99aa-0fa9a8d0f7b3 | note | Method - Visual inspection
4a338b20-2665-553a-8ac7-c950dc35c6af | note | Frequency - Each lot
220947a7-28ad-5c87-bd79-c34846b27fc9 | note | Category - HP
80d7e92a-de01-5613-b38d-5c29ca54af5a | note | Responsibility - Nominated Authority
aaf18eae-9f73-592f-9938-b61cd473e1fb | note | Verifying Documents - This ITP
b9a9163b-efc4-565c-bb28-3b6963c58075 | date | Date Completed:
dbc38a4b-af68-4f27-a745-ea35e8dce07d | signoff | AUTHORITY HOLDPOINT
adb32f4f-5e4d-4870-9bff-49a69b3b4f9d | checkpoint | 5.6 - Cut to Fill Zones
4f51c306-5033-548b-a790-dd5f61def9fe | note | Reference - Section 204.06 g)
b4254336-d112-5897-8544-44011fcfa945 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
fd23b02b-8b72-550b-8f83-00785814e1fb | note | Method - Site Inspection
436d5b16-7171-5ff4-8865-876feac40239 | note | Frequency - Each lot
0f540ed0-8c65-5aa3-91f7-fadfc85f5686 | note | Category - IP
c0ef740b-a329-5da3-a753-137450861e9b | note | Responsibility - SE/Site Supervisor
ee0a9013-9c8c-55dc-8c13-cb21c8eb93de | note | Verifying Documents - Sign ITP
85505d1d-36c8-502c-bee2-7fbeff0097c7 | date | Date Completed:
71d2a16a-feae-4a72-949d-cb07f2b75b27 | checkpoint | 5.7 - Proof Roll
6817d6e3-ac9f-58e2-9e0b-141b20fdf5dc | note | Reference - Section 173
2e379c93-2b67-5f83-a37c-a12afa0e981c | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
cdcf98ed-1ed7-5e98-8a4f-2a22d6347c97 | note | Method - Visual inspection
cfce6d4a-56fc-5b0c-b4dd-9c19b20ebf16 | note | Frequency - Each lot
94fcb228-3945-5c7a-9272-ec1b16b9b660 | note | Category - HP
401d65b0-9e70-59cc-9489-2884412f5fcb | note | Responsibility - Nominated Authority
e66225e5-fd35-5f0c-916a-1910a413d304 | note | Verifying Documents - This ITP
99c7415c-1b39-522d-84e2-1b7851872b4c | date | Date Completed:
84c3217a-5be7-41be-9c6f-58e8db8ba844 | signoff | AUTHORITY HOLDPOINT
27caee17-76f6-49b6-9d3d-a53e25a8049f | checkpoint | 5.8 - Compaction Testing
adc517dc-9eae-5278-a185-43216197cfbe | note | Reference - Table 204.131
28025764-95c6-5c93-9a19-e52bdd08c316 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
3281946c-27cc-50d1-8a3e-357bd8eca62e | note | ○ Ripped and re-compacted material below Cut Floor Level
c12cb1d3-9ce1-5359-862a-6a8981841002 | note | ○ Scale A: Characteristic Density Ratio 99%.
b4c2a007-9c7b-5141-97ec-ea61285a8d7e | note | ○ Scale B: Characteristic Density Ratio 98%.
998a5270-5f02-595c-b5b2-4da343ab181f | note | ○ Scale C: Mean Value of Density Ratio: 100%
a8dd6b73-6ada-52d8-bfd4-18d54b04a1a5 | note | ○ Attach: Compaction Test Result:
430bc580-e1ef-5dea-983a-b8c97796cbd7 | note | Method - Document Review
92f2960e-bc20-5157-9bc2-135fc56dfaa1 | note | Frequency - Each lot
b98f798d-602d-50f3-a018-6749deea3d92 | note | Category - IP
c19d1b18-fa0d-502d-af00-925e0af8ecba | note | Responsibility - PE/SE
557d34be-b86b-5abe-966e-6d38dcce97c7 | note | Verifying Documents - Sign ITP, Attach Test Report
9debf407-f104-5561-88f2-951f96d2812a | date | Date Completed:
1e64fe55-7aef-4c9e-b1a4-ec7d432bd401 | checkpoint | 5.9 - Post Compaction Material Property Testing
94b88f3e-5330-52de-9849-88719e8514e7 | note | Reference - Section 204.04 (C), Section 204.14 (a) and Table 204.141 For Scal A, Section 204.14 (b) for Scale B IFC Drawings
213ece8f-14d8-5a33-a2c4-e066da23611b | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
491e71bd-323e-52b6-a444-ba5f00286f69 | note | Scale A:
783c0188-8849-5764-bf5d-3f6aca99bfb5 | note | — CBR and Swell as per IFC for design packge:
60b85037-d86d-5e78-83f7-cdd51ca2a2ce | note | — MRP-DPK-087-00-CDR-0002-0
c3abf1ea-f7a2-5a47-bfa5-fc698a67817b | note | — as per table VR 204.141
460e207f-4e05-51eb-9ae8-e524e13ff2ef | note | Scale B:
1c90c618-e86a-5e94-bcb8-0cbd41bf76b1 | note | — CBR and Swell as per IFC for design packge:
26729c03-6f9c-51af-bda1-3bcc4963ce4a | note | — MRP-DPK-087-00-CDR-0002-0
67900d4a-00bb-518c-afc7-4e56dd647485 | note | First Lot for Max Particle Dimension:
89df4476-c4e2-5b1f-b831-c9ca23dda715 | note | — After compaction Type B material shall have a maximum particle dimension of not more than:
915a4c60-0c85-503f-bd48-ecfaad6705fe | note | — 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
be39bb0b-e5a2-57c5-aa57-1eb32857c2f6 | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
a78136dc-3368-53f8-8aab-7e2b81e97c36 | note | ○ Attach: Post compaction test results:
5f4547b3-28dd-5987-ac63-06849e0be2cb | note | Method - Review Document
a809a2b1-a46c-57f4-b013-2869b9662448 | note | Frequency - Refer to Section 204
181eaece-e6a8-5bdd-b75a-029c8bc010ba | note | Category - IP
dc97c7bb-7a87-53a7-b931-753707f0dc6c | note | Responsibility - PE/SE
7201b939-c2e1-5ca2-a2a4-fa977a0fad1e | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
015a5371-5854-5451-aa46-39915541876c | date | Date Completed:
a05cb6bb-3ca7-4ac2-acaf-952af70bb34f | section | 6. Post Construction Activities
95e3c3b0-f72e-4b6b-85f9-0a7448432d7c | checkpoint | 6.1 - Survey Conformance
b27ea5df-064f-5eb5-be92-ce8f49f35436 | note | Reference - VicRoads 204.03f,g and h
638029b3-d4c5-5412-90b2-e6887dfcbdfd | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
050a1922-498f-55b5-8021-af0df7a77ed5 | note | Level tolerances (Scale A):
8017308e-fc44-5ff1-a67f-bf4a9fae2619 | note | — Range x = +5, -15mm
59239228-4857-5ba2-aa90-20df6c04ad3c | note | — Max S = 12 mm
2a350467-b9a6-5261-93b3-6bbcc2b61024 | note | — 80 measurements per lot
a13d987d-67b3-5a63-8996-63da65948161 | note | Level tolerances (Scale B):
e7e7c431-0754-5028-b6d6-224984b17783 | note | — Range x = +5, -25mm
e513662e-39bb-5ecd-9b9c-360552e4234f | note | — Max S = 15 mm
f724a1ae-8408-505e-8ebb-b3b607663d06 | note | — 40 measurements per lot
e3597c80-96e2-55e9-ac64-d38639473da1 | note | Level tolerances (Scale C):
0088500d-e7b9-5e34-8469-404cd700783a | note | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
0f69a527-db3e-572a-9751-d5f9c9bb435b | note | Method - Review Document
f8ed9129-e75d-5f49-b56c-1d7ccae75e34 | note | Frequency - Each lot
36ea462c-b60b-5b88-8925-9676c3a3e3da | note | Category - SCP
4c03fb61-cf9f-5c3e-b253-aea3eb615ff7 | note | Responsibility - SE/Surveyor
bb85935c-5f59-5ab5-b5a6-727463762666 | note | Verifying Documents - Sign ITP, Attach Survey Report
085979d8-bc45-5d74-bb4d-ec35c60fce72 | date | Date Completed:
0e3f5524-22f6-41c6-8c94-efe664b1b126 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
830383a5-2e93-53a2-8ebc-9a7601cb52e9 | note | Reference - MRPA Quality Management Plan
4eef6a52-0ed0-556d-9349-6af7339a32bb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
53012d27-49c1-5773-8928-b6f4b9f20d4b | note | Method - Document Review
2a34738e-37e3-598a-846d-f6a740bc1dcf | note | Frequency - Once, prior to closure of this lot / element / Work area
5cb1a495-db76-57ee-a6ed-1063b011070b | note | Category - HP*
3fb07e5c-2dcb-5d6c-ac45-1533c281b376 | note | Responsibility - SE/PE/SPE
3b067177-c33b-5e19-9a0f-dae7cad63358 | note | Verifying Documents - This ITP
6d6fc070-d3e0-5dca-92ae-43d05ef97963 | date | Date Completed:
e4fd4f10-809b-433a-ada2-443787145b9f | checkpoint | Final Inspection
3dcb02a7-f241-5521-ba17-5e66126cdee6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
03b8855f-d544-5048-9161-15eca2ce1754 | textbox | Name:
57bae9cb-a95a-5350-ae61-7fc2b36b0fc8 | textbox | Position:
f75c926d-e085-56c7-a192-0b66f21bc43f | textbox | Date Completed:
a8dad709-a2c0-4a76-b8db-b76042c49be4 | signoff | Sign ITP
ef1fd386-7fe5-4e65-8d0a-16adff7a9349 | checklist | ITP-274-CIV-ADL-Type A Fill - Road Rev 0 | itp | ITP-274-CIV-ADL-Type A Fill - Road
b255144d-456a-4b49-a127-b49e87dacde9 | section | 1. Referenced Documentation
5c04fd0b-8f67-4951-b06f-2abe83ba3e43 | checkpoint-no-value | Referenced Documentation
69d40f4a-f4eb-5362-8e8e-87b811015b80 | note | Document Title: ITP-274-CIV-ADL-Type A Fill - Road
e6f7b97c-0521-5180-a006-bfbb4d1cac9e | note | ITP Description: ADL-Type A Fill - Road
7524b109-bbf4-5d01-be4c-c41b750095cb | note | Discipline (e.g. CIV/STR/RAIL): 274-CIV
9dc1d6a5-80f6-5d32-9c98-71af2a967513 | note | Revision Number: 0
48abbf27-2e59-543c-893f-313bf8e3fe0b | note | Revision Date: 22/05/2025
c5ff1a73-7cb3-538f-b98b-dfc093e01eda | note | ITP created by: Abhi Patel
52ab9c68-e673-5af1-a7cb-387fd4bc4f0d | note | ITP approved for use by: Aldrin Guinchoma
dd758b6f-4221-58ec-9ba7-038198ae80e1 | note | 1.1 - Non Dependent
bf92bb9c-0b79-57de-b7d9-5ae3212cc247 | note | Reference - IFC Drawings
3dedf8d7-508e-5a5e-8aeb-c682afe3ccb3 | note | ○ VicRoads Standard Section 176
54685c05-fb4c-5463-8b7f-b946a778ba46 | note | ○ VicRoads Section 204
89524db5-1d8b-535f-8dd8-da157a5fd62f | note | ○ Code of Practice RC500.20
3b285dc1-20f4-5cc2-948d-8cc4ce11c985 | note | ○ Code of Practice RC500.5
28f09aa6-3215-4f17-a1cc-d6160c606d61 | section | 2. Preliminaries-Materials
b2023879-f5a8-481f-81ee-205f438692e9 | checkpoint | 2.1 - Material Conformance
25e3f916-dd85-5004-98a3-ee28309f7181 | note | Reference - Section 204.04 b) Table 204.041
07da9808-e588-5dd9-a8ca-65d513bb65af | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
7cdbba44-1e0f-5660-b9b6-1f3c091ca658 | note | Type A Material shall meet the followingPOST FIELD COMPACTION requirements as follows:
2db0c205-c362-5829-87cd-36922906e47e | note | ○ Assigned CBR≥ 6%
7e59fc7c-5ee3-5ed3-8eab-97e574da2252 | note | ○ Swell ≤ 1.5%
3c681f8f-4c93-5f67-a493-28a4aa065fb2 | note | ○ Permeability ≤ 5X10-9 m/s
0340d306-3f17-5df4-bd35-997d560d5aa6 | note | ○ Grading:
cad3fc56-0601-5423-9d94-96fae71a2126 | note | — 75.0mm 100%
e7acfa9b-d930-53b5-a652-df4176ed79ef | note | — 4.75mm 40-80%
0d6529c0-a4e1-5bee-80e7-2fbcda05943a | note | — 0.075mm 10-40%
f474ad2f-2f9a-5eb6-8087-17c9ac5bbf79 | note | ○ PI Range: 6 to 25
1d3fc829-3712-57ad-ab24-2484297e0561 | note | ○ PI x %passing o.425 mm: 1000 max
1773d91c-e4f8-50a9-b5e9-0091417c4844 | textbox | Reference: Material approval in Teambinder:
fb1f15b7-01d5-5827-916e-d561afd89b33 | note | Method - Document Review
d64f9b80-b081-541b-9022-540620abd294 | note | Frequency - Once, for each material type
cee71ede-5e53-5113-889f-1e2878801d1c | note | Category - HP*
d860668e-95ba-5fe7-9c14-fc19baffee62 | note | Responsibility - SE/Nominated Authority
0dc6d567-730e-5043-a8a9-4426668caa22 | note | Verifying Documents - Teambinder Material Approval
73892107-66b8-523b-b07f-bbad6b57170a | date | Date Completed:
d2e8517e-c3a3-4471-8644-15839e913df4 | section | 3. Preliminaries-Documentations
1ee92118-3cec-4997-b30a-bc9e24cdd9fe | checkpoint | 3.1 - Pre-Commencement of Fill Works
8413f968-2dfe-5f2f-bbd6-df5f9a3dfcd4 | note | Reference - Section 204.10 (b)
bc768997-fb07-509e-80a1-440c83dbb75b | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
ce0e6bb2-9610-5a56-a29b-520d30a8a861 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
d99b3d56-048e-588c-a712-d91ac6bcdefa | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
a0ca7931-a39c-542e-91f1-9a43124e1c4f | textbox | Reference: Subgrade Preparation Lot Number:
37dc2bff-8bc2-54d8-85f6-5e71f6e6b383 | note | Method - Visual Inspection
26260b12-4f10-5cc9-b7a1-ede2bdf24fd6 | note | Frequency - Prior to commencement of fill works
0a188b95-8416-5997-8969-35d83eb8d962 | note | Category - HP
26f1578f-3dbf-5abf-9695-991eb97c391e | note | Responsibility - Nominated Authority
8bb38338-9015-5a5f-afea-27c3764eca12 | note | Verifying Documents - This ITP
efec891c-9fd5-5c8f-941d-ea76581cfde8 | date | Date Completed:
8b89ba69-61c0-48b2-8e82-ad30168e6017 | signoff | AUTHORITY HOLDPOINT
10be6132-444e-4d6e-aa65-9ac01df8a553 | section | 4. Pre-construction / Pre-installation Activities
381cb864-de16-4f7e-9a27-e2604718c047 | checkpoint | 4.1 - Survey Set Out
d5b2a507-4962-5bc8-a5dc-3e25e89c5a5f | note | Reference - Design Drawings
4dfea471-4c77-56ba-ba58-62225ea83191 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
67ed877a-a3cc-58ea-974c-dfb3d1e30a60 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
dbf38148-395d-5021-aa7f-d6e660e47724 | note | Method - Visual Inspection
c4a3649e-7122-5ee0-b1c4-4bf6fb0e3e35 | note | Frequency - Each lot prior to commencement
3868e0b6-e248-5b01-ac61-71fd2c2ee616 | note | Category - HP*
f5a356f3-8f2b-57b0-9b5b-caac3da8b2b8 | note | Responsibility - PE
59f12a0b-2011-558f-8181-7e38fe76413e | note | Verifying Documents - Signed ITP, Lot Map
ac6b7ac8-a32b-533f-8674-a90592152114 | date | Date Completed:
efc42326-494a-49b6-be35-b23050065a7c | section | 5. Type A Fill/Verge Activities
5db8d518-4dc0-45c0-83b0-006359072682 | checkpoint | 5.1 - Placing of Fill
0a34e2dd-b48f-5ee8-a3a7-aea7cb9d44b7 | note | Reference - Section 204.10
cf188989-4903-5e8c-bed5-6a2b783bf2fd | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
590a8db8-2ab9-5582-9ced-cf2b44294447 | note | Method - Visual
3c71d492-51be-5c8a-8996-d0fac2877dc8 | note | Frequency - Each Lot
a9a047ab-1da5-57e9-ab7c-8552c384ce31 | note | Category - WP
17da9fa7-b4f0-540a-894c-6269c7b37b6e | note | Responsibility - SE/Site Supervisor
7dd1148c-63de-5582-9c24-289f46c95d4e | note | Verifying Documents - Sign ITP
b491327d-a46d-59e6-9c8a-3963a22b95c9 | date | Date Completed:
1afb1947-5e15-4393-bb6e-c358dd9ff7fc | checkpoint | 5.2 - Test Roll
d349d95b-0797-588b-a6c7-2bf807599b49 | note | Reference - Section 173.03, Section 204.12
ef33aea0-ae70-5af6-bcb4-f20ced431020 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
207d8726-c8ad-5667-acf2-30fceba9f662 | note | Method - Test Roll as per 173.03
c6f6f299-4b55-5cbe-a049-bdad2b63271f | note | Frequency - Each Lot/Layer
78948789-addb-58e8-bff1-84f3a1cdcd8d | note | Category - HP
cde06611-d731-5bb6-8bc6-56d05d13d15a | note | Responsibility - Nominated Authority
61f3c70f-badf-5c2d-9131-b201eef9497f | note | Verifying Documents - Sign ITP
b8150c7a-d73c-54c9-bb7d-001bf47e7654 | date | Date Completed:
ce141adc-7179-41bd-9d87-84cc21ae5d7a | signoff | AUTHORITY HOLDPOINT
7f91f3f1-f5a1-4b4b-9392-6f665eb94544 | checkpoint | 5.3 - Compaction Testing
5876232a-95b3-5106-b032-58b075ffbeeb | note | Reference - Table 204.131, Section 204.14 c) Table 204.142
6e5f679f-5f9e-54dd-bfda-70f97dc56dea | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
4e4cd477-88e6-5d6b-8b76-f84777e10ee4 | note | ○ Standard Compactive Effort
e4b3285a-ffdd-505c-9de5-d35638d6e54d | note | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
694f8604-ad6b-527b-89aa-45d5c4d78b2a | note | ○ Compaction and Moisture content
a9edeb5c-a0aa-57f1-9d59-f931c3106cea | note | — Scale A: Characteristic Density Ratio 99%.
1f1ead93-5b42-5224-8ba6-17105e1d4161 | note | — Scale B: Characteristic Density Ratio 98%.
d24d3c9d-f20d-53fd-a67b-2521be404b89 | note | — Scale C: Mean Value of Density Ratio: 100%
59830395-80d9-50cd-810d-98a7b23fc473 | note | ○ Lot size - the leser of one day's production or 5,000sqm
c0ed5831-8f8a-5d99-b8b7-a07f1b89eef1 | note | ○ ATTACH: COMPACTION TEST RESULTS
2aa09247-598f-5cc2-99dc-f11c3975bbd8 | note | Method - Review Document
3c14dd10-a3b3-5dc8-a3d5-2ec3b6ba3176 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
a88009a2-176f-5dc5-af62-4e3d719b8cf5 | note | Category - IP
d8f35a2f-c087-5e52-91bc-f36450ec2bfa | note | Responsibility - SE/Site Supervisor
53c06543-0074-51a4-b898-c5491eaa8fdd | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
c8b578f9-d612-5575-94bd-aceec0ede687 | date | Date Completed:
09c26bbb-7c6b-4720-bbe6-959708bc825d | checkpoint | 5.4 - Preparation of final surface
b976650a-b2af-5c6a-b759-78f80564c9e7 | note | Reference - Section 204.15, 204.03 (g)
80ebf7d7-1a1a-5658-98c7-1a134ce9febc | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
5a4d791d-75cf-5358-bcd4-329ae9cdfdb1 | note | Method - Measure
05ccb54a-154f-5ac1-96a8-96610aca2997 | note | Frequency - Top layer
d8442e34-4a68-5844-a7a8-64422f6bc658 | note | Category - IP
e18d1329-2dc5-510a-8c98-3232a2ea071f | note | Responsibility - SE/Site Supervisor
59db97c1-d5aa-5b3c-b04a-eee6339cd112 | note | Verifying Documents - Signed ITP
1cfcc00d-0029-53a4-9b07-3a7eb40fbff9 | date | Date Completed:
9a2a2f0b-c560-417b-9b3e-4fc879f4bb41 | section | 6. Post-construction Activities
c888484e-9c63-44b7-a5d7-490dcd723dfd | checkpoint | 6.2 - Survey Conformance
af71c676-f0e1-5aa9-b98c-38c2f0832552 | note | Reference - VicRoads 204.03f,g and h
997a8af5-c284-58e5-a835-89d1723d0882 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
ce132242-302d-5e96-91d7-2da31abaf8f1 | note | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
17f0adfb-63ee-57ef-8301-b145ed4c1a5e | note | Method - Document Review
b76e1871-e357-5977-b51d-e69b224088f3 | note | Frequency - Top of Type A/Verge
f8e955e6-d5da-50b1-83ba-1ae0d3d823e3 | note | Category - IP
80b217e6-4e10-51f8-8bb6-b764c158e926 | note | Responsibility - Surveyor, SE/PE/SPE
16754cfc-22d9-5049-9a72-56e5661b17e2 | note | Verifying Documents - This ITP, Survey Conformance Report
37afd066-a92a-52e1-a648-92898e5eda3e | date | Date Completed:
f3c836f0-341a-45f0-a87d-b0f0a4984f6a | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
d6401255-312b-5a57-8a60-fda2e0dd80de | note | Reference - MRPA Quality Management Plan
c4244885-9f7b-58d0-8844-2a6dc8e37a3c | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
3d017004-de8c-5102-8cb9-8f3d4cd472d2 | note | Method - Document Review
6f1a76ea-1c7c-5465-ba2d-0dac163e9572 | note | Frequency - Once, prior to closure of this lot / element / Work area
8897ae7d-5c1f-5e13-a156-5b233813b2e2 | note | Category - HP*
324fef95-7474-588d-9e6e-764bfb35d4f5 | note | Responsibility - SE/PE/SPE
fcda5bf3-9325-54c6-8a73-0565dd2278b1 | note | Verifying Documents - This ITP
ad3f92d1-b71e-5869-ae19-37cf41d6b98f | date | Date Completed:
a363750a-b312-4572-85b3-b24bab0eee62 | checkpoint | Final Inspection
c4318869-28ab-5977-82be-5e99c25ce3b8 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a7de28b7-e2d0-526f-91df-873727bb71d0 | textbox | Name:
b393fd46-a04a-52b6-8161-f3958e4cbaa5 | textbox | Position:
40049ab7-4d14-5bbb-b6bb-a6d5eac5c7c5 | textbox | Date Completed:
9ea54448-fdb6-4615-8efb-acbdfde340c3 | signoff | Sign ITP
34d01fba-4858-4d72-ada6-314994c4d336 | checklist | ITP-284-CIV-ADL-Stormwater Drainage Rev 0 | itp | ITP-284-CIV-ADL-Stormwater Drainage
cd06952d-9c1f-40ac-9824-0a62f90c7d9e | section | 1. Referenced Documentation
2e72469e-b11b-4416-9e9d-dda633d92da0 | checkpoint-no-value | Referenced Documentation
46b5bc56-ce98-5951-a6a2-1d4d3cb6d19b | note | Document Title: ITP-284-CIV-ADL-Storm water drainage ITP
1a9cee4b-3619-5d27-82db-d572aa171595 | note | ITP Description: ADL-Storm water drainage ITP
9b5d03c3-ee3d-57af-ab0e-43a9e517055f | note | Discipline (e.g. CIV/STR/RAIL): 284-CIV
e6d01d58-abc4-5d9c-8f22-522fdb4c6221 | note | Revision Number: 0
6842a560-e1e8-5a9b-bd21-0d83a82cc19c | note | Revision Date: 12/06/2025
1c5bf5f4-7aa5-5de6-9fef-8051b722e758 | note | ITP created by: Abhi Patel
20e4a723-ac64-5898-9fd8-2dc9fbc52caf | note | ITP approved for use by: Aldrin Guinchoma
91cc6cbc-3180-50fc-a20d-c545067f9f92 | note | 1.1 - Non Dependent
bd918f95-2e8d-52ec-95fd-25c330047e41 | note | Reference - VicRoads Section 701
0f77b24e-55ce-54d7-b44b-82fd1f3bf167 | note | 1.2 - Non Dependent
74ce8dc0-c671-57e7-8c91-eb739907add5 | note | Reference - VicRoads Section 705
d150e2d0-224b-5195-a03a-24b3ed8d552c | note | 1.3 - Non Dependent
d6c8a01e-ac25-54a5-8a04-4b2465860d17 | note | Reference - IFC Drawings
d3d99194-687e-4e23-9323-9835f577c17f | section | 2. Preliminaries-Materials
777d607c-089b-4cdd-a267-d7990ef11897 | checkpoint | 2.2 - Drainage Flexible Pipes
fbd01ab7-f7ef-5d15-b155-6bc11d6cc8ad | note | Reference - Section 701.08
6b057fea-710b-59a3-8344-64b287849638 | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
469c8c89-8972-59fe-a4ac-7c83c59ba207 | textbox | Enter: Teambinder Material Approval number
8907238b-1b9c-5401-bd16-096415015372 | note | Method - Document Review
31f664db-2efa-51e9-8461-f56ba956d58e | note | Frequency - Each lot
79e2dec3-fe21-57bd-b5d7-b74ff1feca4a | note | Category - HP*
e60aa636-c678-527a-80a2-54df1a767f2f | note | Responsibility - Nominated Authority
33514c1d-db7c-5258-a047-a2d222a889d0 | note | Verifying Documents - Teambinder Material Approval
250bb49d-8e99-5310-8af7-746d0e53b612 | date | Date Completed:
b2cacf8e-8334-4c32-9f2e-4a9b8bcb3a8f | checkpoint | 2.3 - Precast Drainage Pit
5a6cc0e7-12fd-5475-ab42-f5266a744304 | note | Reference - Section 705.07, Section 705.04, Section 705.09
ee967f75-140b-5ff9-a990-03ac1373b585 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
e56b8a9d-5b72-52d4-86c0-fff7503724b2 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
1ac7dd6b-f5fe-518c-bb7f-54004002fa61 | textbox | Enter: Teambinder Material Approval number
bd024a08-ac0a-540a-994a-3d625ec8cb23 | note | Method - Document Review
fd159362-db77-5cf4-aa79-9be072abc704 | note | Frequency - Each lot
a0723edc-c85d-5d9b-a797-e74bad678ea5 | note | Category - HP*
6967a3c6-6d8a-5cf2-bb72-a8ace698bf07 | note | Responsibility - Nominated Authority
17209c9b-8a05-5076-a92d-e2239ec7017c | note | Verifying Documents - Teambinder Material Approval
d1e77364-6a74-5f8a-9a33-26a5a3364601 | date | Date Completed:
a3052aac-70cd-4515-a361-d745d8e74ada | checkpoint | 2.4 - Cast in Place Drainage Pit
3bd31697-56e1-57c1-aadc-22d6c9e91a3f | note | Reference - Section 705.06 IFC Drawings
f0674aa0-0553-555e-bccf-adbde05b4ebb | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
55a8b08c-959c-5318-814c-1204f3337b3e | note | Method - Document Review
c955a1f6-e5d9-5cc1-873a-b4af04b0e0bb | note | Frequency - Each lot
00b86ba4-7346-5a75-a946-2d1f3f003da7 | note | Category - HP*
0d2628ad-609b-5aa5-8565-2384809feed3 | note | Responsibility - Nominated Authority
53bcc7f4-3d4c-565a-8fe1-6d0b2a148292 | note | Verifying Documents - Teambinder Material Approval
338660cd-94d4-550e-9b1c-c8e4762b2f2c | date | Date Completed:
88a72648-44fc-4d3c-994f-0041a29e5566 | checkpoint | 2.5 - Drainage Pit - Step Irons
cdfaab5e-b594-5101-8728-217799b89745 | note | Reference - Section 705.04, Section 705.12
f285b4e2-951c-5fcc-97e1-3ab2e21e8629 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
02960a30-02e5-56c2-b0f8-29b3c060c287 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
fcd2c6d5-680d-5fd4-9330-d17831e48282 | textbox | Enter: Teambinder Material Approval number
1e955220-7533-5438-8c44-7ac2d289ba5a | note | Method - Document Review
b388e9a8-5ed7-5693-9027-705d37d01540 | note | Frequency - Each lot
13013716-d658-5e11-8902-85d35b8c175b | note | Category - HP*
e8ec8349-1385-5390-b003-39b57f201b81 | note | Responsibility - Nominated Authority
a531147a-a04b-54d0-9445-6d66e9a39980 | note | Verifying Documents - Teambinder Material Approval
8a94efbd-999b-5ec4-8f11-8e22142bd017 | date | Date Completed:
aa75e470-e0a8-4cda-bea6-9df4912e14fc | checkpoint | 2.6 - Drainage Bedding Material
48c0ffc5-7797-5abb-8ef4-47cf8ea9c929 | note | Reference - Section 701.09
df0e90eb-96c6-52d1-b4b8-662009b0cb61 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
ebf4eca8-907d-567a-ae01-62828aa6e267 | textbox | Enter: Teambinder Material Approval number
ae26a3e0-b092-5c10-aed9-5640c88b2e0b | note | Method - Document Review
3f03f8cd-4cee-5fe0-89c7-96f7976d2119 | note | Frequency - Each lot
4c787bae-9e5a-50bc-aacf-c27eac779f08 | note | Category - HP*
fba2e00c-5f6b-5b69-95ca-589039e8fde7 | note | Responsibility - Nominated Authority
b55a812b-62fb-51cd-b81a-4963f1411d2f | note | Verifying Documents - Teambinder Material Approval
e6d7e29a-8074-5db9-b6d4-9736e35585fc | date | Date Completed:
fe11ff88-60dc-454c-87ac-5e37d8bb620a | checkpoint | 2.7 - Drainage Backfill Material
808cbde2-c380-5339-93c2-626632010e6c | note | Reference - Section 701.09, Section 701.19
ddc30952-b5de-558d-80b5-aafb7c35eab6 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
a0291222-79e3-50b6-af35-64296e9d0cf6 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
d08d13b8-3eff-59da-a650-1ee0698eece6 | textbox | Enter: Teambinder Material Approval number
aebc55ba-29cf-53a8-90f2-a65c19220bf5 | note | Method - Document Review
d22803de-b2b4-5d68-9a61-48690f3d90ff | note | Frequency - Each lot
476bbea8-fb37-590c-8f65-2c4efe3ef313 | note | Category - HP*
8dfceebd-62f7-50ab-8307-8a23726db746 | note | Responsibility - Nominated Authority
12964f12-dfb3-50b6-980f-7bd82eaf8a13 | note | Verifying Documents - Teambinder Material Approval
ffdb0744-ed59-57dc-92e6-c39e56d89357 | date | Date Completed:
1738d718-00d3-4066-8c94-5b95cbfe4dc7 | section | 5. Construction / Installation Activities
c5aa2ac3-4617-470f-a6ee-d26a5d1e53d3 | checkpoint | 5.1 - Pits - installation
a5829353-7ab9-5110-9c46-fa6bc62b757a | note | Reference - IFC Drawings VR 701, VR 705
5470640b-213b-586f-b0a2-ccca787f2d7a | note | Acceptance Criteria - All the pits for this separable package are installed and respecting Lots are closed
eea95f9e-aead-585f-96d0-234dff62c855 | note | Method - Document review
3d4a5f38-34ad-51d0-b439-d02c905b7a2b | note | Frequency - Eachdrainage separable package
b2a60d20-93b1-5303-b07c-62b9aacab7d0 | note | Category - IP
0d61c52f-8576-5635-a29a-444d03f2cc85 | note | Responsibility - PE
9355429b-797e-5c83-b93e-c7b0327ca9c0 | note | Verifying Documents - CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
e695feef-7581-5847-be9a-fd0dd8932591 | date | Date Completed:
2b30f87a-f4da-4dbc-80be-55db0c41d22b | checkpoint | 5.1 - Pipes - installation
8c68666a-50a2-5606-8528-e0d24934a142 | note | Reference - IFC Drawings VR 701, VR 705
3eafb165-7b15-5c4d-b6ec-1fe13e703000 | note | Acceptance Criteria - All the pipe runs for this separable package are installed and respecting Lots are closed
1d53917d-4819-5e04-80c1-ee58df114023 | note | Method - Document review
832f6ec7-4cdb-5436-a164-7ffdf2bd2c86 | note | Frequency - Each drainage separable package
271a50d2-b021-5209-8766-302c817c6422 | note | Category - IP
06757a56-2296-581a-9289-c8afe2a51774 | note | Responsibility - PE
3f204bc7-0f22-59e3-9254-f421194f1719 | note | Verifying Documents - CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
d702a511-9df4-5782-bc48-e61c602c79dc | date | Date Completed:
9b71fb10-1100-4a35-98a6-8c8c578a2b80 | section | 6. Post-construction / Post-installation Activities
3d752f54-b44d-4879-a2ed-5667737a0d41 | checkpoint | 6.1 - Flushing & CCTV
e9eea1e1-2d0e-52bd-9469-bd4417dbd7a1 | note | Reference - Section 701.28, Section 701.30
f96afa70-3f57-52c9-bb39-012e4977b911 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
9e2ba83b-525c-53cf-8c05-8af0af734fc8 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
04c9d10f-e15e-5eef-808c-ca524dffced1 | note | Method - Record Review
a0f8af4b-a914-516b-b438-fd3c862f45e2 | note | Frequency - Each lot
558bb0f3-cad6-5b18-93da-d5a2daeb5a91 | note | Category - HP
5295ecd3-02ea-5e73-8fb5-265b9727256d | note | Responsibility - Nominated Authority
2a58bd29-d057-5d43-9e62-58101686d8f2 | note | Verifying Documents - This ITP, CCTV Reports
effa00c4-a8a7-547f-9614-f92460958346 | date | Date Completed:
599ab5ed-e022-4d62-959e-17708a3c2ad2 | signoff | AUTHORITY HOLDPOINT
13549660-26d3-4488-892a-75b1f2279ee1 | checkpoint | 6.2 - As Built Survey
982b3cad-96d7-5a2e-af07-b31e686a76c7 | note | Reference - Section 701.10
9953a23d-0c0c-553a-b955-53f8f09f92e3 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
3b7b1d53-4a15-5971-85f2-b37574ee8388 | note | Method - Document Review
bfd90593-eeea-5ece-b2fb-4f1e9f29b0fd | note | Frequency - Each lot
25f8445e-70f2-5b46-b358-ef18fa96e8aa | note | Category - IP
589bd7f9-83c4-57b3-b904-15bdb6877bf3 | note | Responsibility - SE
c5bbf102-4ed4-574b-b409-5de4c4d99681 | note | Verifying Documents - This ITP, As Built Survey Report
bd9477bf-0f58-5adf-bed9-eaba7dfcfd07 | date | Date Completed:
d9cad5e6-5302-4226-ad9b-c9dbb1f9f858 | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
948a13f3-93ec-547d-8ff0-a1640569db22 | note | Reference - MRPA Quality Management Plan
1bf6908a-6159-5a73-9900-9beffab0cc88 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
1cc07766-50eb-582d-b221-da39ef52b7d3 | note | Method - Document Review
b19ade9a-c5cd-5c13-bf7d-32e7b5a76657 | note | Frequency - Once, prior to closure of this lot / element / Work area
3888f4e4-2cfe-5832-b91b-6053bf1d7c7f | note | Category - HP*
783d7dc4-9a2b-51de-8469-4ae7da8a9476 | note | Responsibility - PE
7163de31-d4ec-502e-9a0d-839d2ecc5c94 | note | Verifying Documents - This ITP
ced07f6e-1081-5d48-ad24-6f456efe8368 | date | Date Completed:
159164c7-b34d-4aa5-a931-200c73b50df1 | checkpoint | 6.3 - Repairs to Damaged Pipes
796dd5e7-9153-5a6d-8aa9-d722de1589f2 | note | Reference - Section 701.31
4a60bd24-aa23-5e66-842e-d9da337d30fa | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
5dc12a9e-e267-5e67-a746-5e76990910db | note | — cracks wider than 0.5 mm
3575f3ce-bedd-51a6-af6e-96f63a780a6d | note | — spalling of concrete
97de406c-b986-5988-9828-6f854dc84dd2 | note | — exposed reinforcement
cda3834b-f57e-5930-a5bf-3ba9235f91c9 | note | — joints that are not fully engaged.
f615e218-a803-560a-8fdd-d9c1b6b94e52 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
1e434a2e-04c6-5db2-af03-3c552cad766d | note | — longitudinal cracks greater than 2 mm
c58dcb21-0f54-5ba0-8505-095d983d98c8 | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
7c679d4f-c2b6-577f-98d5-04f1131caf15 | note | — circumferential cracks around part of the circumference with width greater than 4 mm
4e9efb97-572f-5dc1-9b6e-b88a93535477 | note | — penetrations with area greater than 400 mm2
2f95123b-90f8-5558-b079-bcccb5e88d9b | note | — pipe joints that are separated.
5d2c1f9b-701c-592e-bb12-79b3b22293c1 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
a4b76e20-2808-57fa-af48-a66e762a6842 | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
2710c214-2d53-5b0e-a855-d170309b4ccc | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
619ec9d8-ccfe-5f20-ad7b-9d5b59e105c7 | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
b3d8ea14-1c22-5b5f-81d4-f8846d26cb0c | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
92baa907-7b4e-5da2-a236-735a777e5e67 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
7666f42b-98aa-5d5e-a51d-a61b8c5589a8 | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
997fcacc-1bd9-5d97-af94-90c31c6e69e7 | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
8a7ec94f-0ef3-5a8e-a06c-b19ffb5b3fa4 | note | Frequency - Each lot
c5ad1fb6-e5fe-509f-a76a-f913dfbaa681 | note | Category - HP
612a0508-3929-52d4-922e-f9225a7d78a8 | note | Responsibility - Nominated Authority
bf50d0e0-7118-590d-97fb-88c4c57c4b5e | note | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
43cada80-ef8f-5b34-8dcc-11957ca44718 | date | Date Completed:
ecfdb17e-341c-4697-9823-99f5d73be25c | signoff | AUTHORITY HOLDPOINT
ccf6a924-a023-4d66-9419-0e0a8e5ed7b5 | checkpoint | Final Inspection
f7cb8f98-f0e1-5e9b-a5d5-f30f1131755b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
52d4bad0-9144-5a0c-9d0d-4b1aae72bbb7 | textbox | Name:
7a1e52c2-806f-5f38-aa0a-cf34f80e0d6d | textbox | Position:
7a034ec8-326d-50ec-b60e-d9d96ece8b48 | textbox | Date Completed:
997c6c05-acb7-4af3-a7aa-63d2532e39bd | signoff | Sign ITP
5be6aa5f-ee1e-4fe9-a705-cc39d5aa59ae | checklist | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C Rev 0 | itp | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C
42779cb4-66d3-4394-a5d2-f5abeb060d82 | section | 1. Referenced Documentation
f44850b0-9f21-498a-b55c-807795640710 | checkpoint-no-value | Referenced Documentation
4d4b02e4-ef20-5d66-b61c-7a785fdbb520 | note | Document Title: ITP-286-CIV- ADL-Unbound Flexible Pavement-Scale C
c1e279c9-cc59-580d-a810-7d33887b08ae | note | ITP Description: ADL-Unbound Flexible Pavement-Scale C
0eb935c5-0e70-550b-8d20-a78e61413a63 | note | Discipline (e.g. CIV/STR/RAIL): 286-CIV-
4413bbd0-5b43-54e3-a7ad-e567c3605671 | note | Revision Number: 0
9c9e9b79-9afc-5aca-840c-b28178bacf4e | note | Revision Date: 20/06/2025
0b1ba540-69b4-5442-a60b-4b2a78cd6887 | note | ITP created by: Abhi Patil
05411262-be92-574a-9a8f-c10e8a47ed0e | note | ITP approved for use by: Aldrin Guinchoma
66c4fe28-4cef-5d7d-916e-5db007de52e1 | note | 1.1 - Non Dependent
167f66ae-772b-576c-8a33-7bb72c255b88 | note | Reference - Reference Documents: IFC Drawings
e63c9613-7ae9-5a92-9225-938f50161a4f | note | 1.2 -
0e4fa3c6-b5b1-54ea-8276-0c00dea48221 | note | Reference - VicRoads Section 173
ecadf879-f1a4-5403-89f5-7cb3dce3c391 | note | 1.3 -
47c780c5-6cae-5461-9fd3-863535c376d0 | note | Reference - VicRoads Section 304
53d297a5-2ac7-5d12-8b73-bc9474801430 | note | 1.4 -
ca7517ce-dc09-5c11-8608-56fceb750bbf | note | Reference - VicRoads Section 801
8dfc1a9c-b1c6-53d7-9db7-6d236baeee9b | note | 1.5 -
8d2b2e21-935e-57ee-9982-068d97c5c9ba | note | Reference - VicRoads Section 812
32c8be1b-1b04-408b-a766-5e7cbcdaa2aa | section | 2. Preliminaries-Materials
4233d6bf-e198-4e9c-b74a-016ce686bec5 | checkpoint | 2.1 - Crushed Rock Mix Design
36257de4-4b11-5f8a-a762-50618b555c02 | note | Reference - Section 304.04, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
33274067-051e-53cb-ab19-b3e7f8aa7d0c | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
85a45ebf-23c6-573b-9650-b2304269b85f | textbox | Enter: Teambinder Material Approval number
3fbf2424-158b-594f-920d-83787ec055c9 | note | Method - Document Review
0639d968-b855-5b2a-ad38-7e96ed69a765 | note | Frequency - Material conformance as per Table 812.121
f39cce3f-f59d-5999-82a3-5e872010cb73 | note | Category - HP*
17e6031e-0d67-5e47-a75e-75793a77d4c9 | note | Responsibility - NA
8676c3a0-b506-5077-b7e5-2f2d33e1a291 | note | Verifying Documents - TeamBinder Material Approval Number
6ff5a8a0-44f6-57df-b363-9a32662dbaa0 | date | Date Completed:
27356614-3fff-4342-be3c-b436d3704c36 | section | 3. Preliminaries-Documentation
688c71c3-df9b-4459-bd53-e5340c774702 | checkpoint | 3.1 - Subgrade Preparation
bcf13046-c5bb-54df-8de4-72bf59d15b27 | note | Reference - 304.05
bd0a763a-6987-51a3-8b2d-22316133e0c2 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
2bb8f264-e1c0-592b-a93d-76a26f10d8b4 | textbox | Enter Subgrade Lot No:
56ff61e8-3c8e-5260-b7c1-7df781600ea1 | note | Method - Document Review
ee44a94d-ce8c-534d-afd3-7985fce382ac | note | Frequency - Each Lot
a81e8283-edf7-5b92-91e0-9e166902dab1 | note | Category - HP*
2c1daed4-e3b4-5c12-9358-c0781e9d703e | note | Responsibility - PE
0b4e383d-93cc-5d37-93f6-51711349b74a | note | Verifying Documents - Underlying layer Lot number
6c1d38c8-c346-589e-b180-b6d13c2b89b5 | date | Date Completed:
5e5c33e3-e56e-4176-82be-15beb65c54e1 | section | 4. Pre-construction / Pre-installation Activities
21ed9d2f-1aed-4433-bf81-82efd748537f | checkpoint | 4.1 - Survey Set-out and Lot size
2e5c9b84-e1e7-55fc-81e0-8e874a5a1f82 | note | Reference - IFC Drawings Section 304.07
77bb14e4-08f0-5f63-8e0a-9ad9332141ae | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
0b94e0c8-bfd4-5ca5-838b-435b31386632 | note | ○ Clearly mark out limits of works as per IFC Drawings and VR 304.07.
67e07c98-2f93-55d8-8b38-e19b116030c4 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
092de049-7cad-5990-a8ed-00e1639d3f17 | note | Method - Survey, Document Review, Measure
07996402-ce3e-51b5-b700-7edbd12d2555 | note | Frequency - Each lot
ae7a6314-a0c2-522a-a5bd-781c14390a9e | note | Category - IP
5b9160b2-de10-5cd7-98e2-1d1d3fb43479 | note | Responsibility - Surveyor, SE
b56c052c-e8d3-5efe-9b7e-0e8e7a917880 | note | Verifying Documents - Sign ITP
2a410873-1a9f-5dc5-ad33-7b8b4516416a | date | Date Completed:
c202c82c-df0a-49e1-bc1f-a5c8b8ef044d | section | 5. Construction / Installation Activities
9e0f8add-f079-46c0-8b58-a901d3b937b4 | checkpoint | 5.1 - Placement of Material
65e2e152-8dc3-5d7e-b9b1-2ee2aae9d68d | note | Reference - Section 304.08
f20fd815-9e49-57d4-92d6-b90a9adf7491 | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
31fba38e-3c49-5f21-ae2d-4640d611bc0b | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
7cf1765b-c38e-5bfa-94ac-a96445062302 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
0389f629-8c3b-51b7-bc8d-99c6fe54cc68 | note | Method - Visual and Measure
c00906ed-1282-5396-b1bc-c38dc6615613 | note | Frequency - Each lot
d0a941ca-dd18-595f-8450-42fa87743a74 | note | Category - IP
3292e2c6-981d-5d62-8050-b7bffbfc2b41 | note | Responsibility - SE/Site Supervisor
d5eb089a-ab70-56e3-9d8f-628e0457bd3a | note | Verifying Documents - Sign ITP
d36acc31-103e-57b9-ab65-b6628456712e | date | Date Completed:
d0eadaaf-0353-4703-a236-1ca20c11a218 | checkpoint | 5.2 - Construction - Jointing
8e46eb34-f1cd-5339-a61f-9b861f7be1cb | note | Reference - Section 304.08
ffc28a52-441f-5506-ab11-38388bda21a7 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
1419bfa8-a9f3-5260-823d-7c8af86eb5c6 | note | (a) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
660b991e-f718-5c3e-8e22-d5411d8ad7ae | note | (b) transverse joints shall be offset from one layer to the next by not less than 2 m;
b4effc79-b5d4-5b17-b0c7-df9c2abb2dfc | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
c5fd583a-dd9e-5a9a-a45c-460062f4ad3c | note | (d) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
c3b9fb00-08f8-52c2-bcb2-50141bc09632 | note | Method - Visual and Measure
bf41961a-2e1a-5c15-a232-d145e5cb7ccc | note | Frequency - Each lot
7738c8d4-820d-5e8f-accd-199d8d22dca0 | note | Category - IP
9f15ba7c-249d-51b8-a1ee-653483069c24 | note | Responsibility - SE/Site Supervisor
d9b84563-4af9-517c-b1e9-252eab440151 | note | Verifying Documents - Sign ITP
e2573251-f3e0-5a73-b66b-347b03662962 | date | Date Completed:
581d68c5-52e9-4c7b-bd33-bdfb51cf891f | checkpoint | 5.3 - Compaction test (Frequency)
ff1ea210-d45f-5953-9391-7f4db99cae5e | note | Reference - 304 .09 (b)
37a98044-4d1b-5c9d-93f4-42e91fdac989 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
5cbb0164-9428-5297-8803-a73993ed9e48 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
bcee1c92-135d-5a59-bb69-42af354f1fb2 | note | ○ Scale C: 3 samples
edd5b538-c582-5896-9f1d-1fa48e07c9c8 | textbox | Enter: last tested lot number
1cf7c365-51f0-5a2f-8e20-b01a71755936 | note | Method - Visual
4c04914a-a34e-57bf-9a7c-3af00ea31bda | note | Frequency - Each Lot Where applicxable
957f1c4a-eb07-54bb-8859-4bd472df3753 | note | Category - IP
2cf91b28-284c-524a-81ac-11fce3bb17db | note | Responsibility - SE
46c497ba-fdf5-5bb6-9d62-8ddc4ac5b899 | note | Verifying Documents - Sign ITP
e5ee2f7d-8974-59cb-ae9d-70ca5369653a | date | Date Completed:
b846a639-5913-4411-b362-40d70ae6bd1b | checkpoint | 5.4 - Post Compaction Materials Testing (Frequency)
c64e9eed-bb6d-5b7b-8c71-eb1ef2ced6b9 | note | Reference - 304.11
c6056a83-6379-51d4-896b-d36b0623a7c4 | note | Acceptance Criteria - SCALE C: Atterberg Limits and Grading
9eeebde6-e76c-564e-bee4-737667f7b712 | note | Method - Visual
3bfaa809-b731-5200-a171-09ffbd2a3df7 | note | Frequency - Each Lot Where applicxable
35758695-f763-51ec-9e2d-4f520e0edde1 | note | Category - IP
9ff873fb-83f3-5787-8b88-87ccfc477564 | note | Responsibility - SE
5e8ba609-6e5e-5b33-b1da-104d55fd9528 | note | Verifying Documents - Sign ITP
548ba973-f0e1-5307-bb2d-f91d49976280 | date | Date Completed:
2e945b60-8e6c-4921-8b14-98614a699860 | checkpoint | 5.5 - Proof Roll
9fac54c9-b450-5cdb-96cb-7be43c8e7cbe | note | Reference - Section 304.09
cc2ca2ff-e5de-5880-8ebd-fc1f32b470a2 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
708918b1-2c39-5551-a80e-c40249b63bd1 | note | Method - Visual
e59c866b-4bf0-58c5-9613-f2741a131e60 | note | Frequency - Each lot
0fe6229b-a70a-58e9-b096-2611aa95d8fb | note | Category - HP
67b78268-c5e7-53a8-a773-25bda0dc6ec9 | note | Responsibility - Nominated Authority
3019776c-6cbc-582d-9a1f-1c896e40fcbe | note | Verifying Documents - Sign ITP
4df6c903-0230-5cd9-be31-cd66940c8a0f | date | Date Completed:
a5cdd3e3-f0ec-447f-853e-59b898ab1f16 | signoff | AUTHORITY HOLDPOINT
9eae96f9-6896-4c05-84e9-73c420436124 | checkpoint | 5.6 - Protection of compacted layer
c0b921fc-c065-5f19-b54e-2bcfc0e4a501 | note | Reference - Section 304.10
a59cbf71-30e3-5e60-a0d4-b61435ec1863 | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
07446ea6-b8ad-56a2-bb23-cf8684c6ba33 | note | Method - Visual
6f82d288-2bd2-5923-8d14-914a61192af7 | note | Frequency - Each lot
0943f563-63d8-5099-a715-df20b520c9f9 | note | Category - IP
8c82e632-5b50-5f7f-9d90-1c3c6df2b78e | note | Responsibility - SE/Site Supervisor
e03896bc-a57b-5e22-a46c-26ad78314806 | note | Verifying Documents - Sign ITP
bee7b0c8-3f42-539b-930d-2ec041e5331f | date | Date Completed:
63b2761b-1570-4901-a2b3-dac9d7be523d | section | 6. Post-construction / Post-installation Activities
bb408391-76ef-4627-9f23-aecd2699bad4 | checkpoint | 6.1 - Compaction Testing (results)
8217c44f-c730-58b1-98bf-451a624f7a33 | note | Reference - Section 173, Section 304.09 Table 304.091
31316666-8f5e-5482-8e5c-f2e8aadff2c0 | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
629e715d-4e4a-51a8-8e30-cf33abf209d0 | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
2642f632-c32a-5764-b028-7d2947048322 | note | ○ Scale C:
f40b509b-2ad8-524a-b369-e576a6702083 | note | — Subbase Layer CDR ≥ 98%
b52a7054-f09e-5c11-bd36-9d1881bdd7a6 | note | — Base Layer CDR ≥ 100%
2cd0a7c3-c767-5a0e-9133-ec250d0885b1 | note | ○ 3 tests per lot
53798202-fc2c-513d-9442-d2d27182beec | note | ○ ATTACH: Compaction Test Results
d68e769e-9190-5d62-8ea4-490ea0eb5af7 | note | Method - Document Review
051f107b-a4fc-5a77-8519-7bae08e1b6ef | note | Frequency - Each Lot Where applicxable
c49ed077-aa8c-5cda-b423-c98ba5270b9c | note | Category - IP
bb02a174-e701-5129-a880-2377b41d297b | note | Responsibility - PE
fd78be75-61e9-5fa9-b0c6-bfd505bcf8da | note | Verifying Documents - Compaction Test Rersults
661ec649-1702-548a-9a1e-0c5a93429eb4 | date | Date Completed:
00e7e106-c8f2-44b7-8af1-0160740dc46e | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
3308ea8f-0823-5bf7-99ea-4a21ce9b0171 | note | Reference - Section 304.10, Section 304.11 RC 500.02
9f8933e5-f9ec-50bb-bc11-1daca60f0ae3 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
a1079418-7f17-5877-9358-5da54cf1862e | note | 20mm Class 3:
10e7d7c3-c239-531f-b717-c63db4dea420 | note | Grading
cdae8dc0-981d-5c7b-9e70-3bcb1871dc5a | note | ○ 26.5mm 100%
e4484177-2ab6-54f5-9221-06e1fb5609e3 | note | ○ 19.0mm 95-100%
143fa684-8589-5884-96e1-7d55e235839c | note | ○ 13.2mm 75-95%
b6f8b1ac-8357-5d74-ad38-b4222421faee | note | ○ 9.5mm 60-90%
062d4fc3-d184-500d-b0e7-6033e56f3daa | note | ○ 4.75mm 42-76%
b0cdb435-11cf-5e90-a5f4-10df7946f16d | note | ○ 2.36mm 28-61%
3e4527d5-124f-5e72-984a-97bb0e586950 | note | ○ 0.425mm 14-29%
3859ae57-92ca-5c6c-8f75-ef08245349a0 | note | ○ 0.075mm 6-14%
e885b52d-5412-5b94-b196-b9420001aada | note | PI between 0 to 10
4acccf1f-e174-5af7-9484-85ebcf35c8c6 | note | 20mm Class 4:
a565e08e-45b8-5144-a5ae-87777cd96deb | note | Grading
7a64b99f-f528-5329-b2d3-3572205987ce | note | ○ 26.5mm 100%
289bf61d-3c51-59c2-ad66-268b3615585f | note | ○ 4.75mm 42-76%
b308e6b0-fc2e-5cc2-bdb6-824d336886a1 | note | ○ 0.425mm 10-28%
2455b50c-2f14-5986-93a0-27457d9f1b18 | note | ○ 0.075mm 2-14%
92ea1770-1a56-5859-bad2-109e1332ccbb | note | ○ PI between 0 to 20
90b24778-0e1f-5681-b97b-f9bfbd919b93 | note | ○ PI x % passing 0.425 mm sieve (max) 450
c2c34fe8-81ec-581a-b8af-354aee257472 | note | Scale C: Post compaction material testing is not required (Choose NA)
e531f342-84e5-5986-a71d-c586fb7f679a | note | Method - Document Review
c787a246-9219-50aa-b901-2fcda2a388d2 | note | Frequency - Each Lot Where applicable
79210cb5-231b-5496-a42c-19d3101981f9 | note | Category - IP
59611245-5aa2-5c32-ac77-bab1463da3d6 | note | Responsibility - PE
b44aef57-a9b6-58d3-aee1-145c4fa111f8 | note | Verifying Documents - Compaction Test Rersults
1c1f8fd2-b248-563f-beea-ed41c2e89091 | date | Date Completed:
f5ed849a-fede-4124-af03-efe5e442b63e | checkpoint | 6.3 - Survey As-Built - Width and alignment
701ba4ab-c42e-58b4-8f76-218ef1df01a0 | note | Reference - 304.07 (a)
ecd79cca-bb83-53ac-9d28-8d271c0ea56c | note | Acceptance Criteria - The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
bafe5ebf-1e2d-574a-8a2f-fba47fd6a197 | note | ○ Attach: Survey Report
43fb7307-bcdb-5d6a-b64a-a2c0bca793aa | note | Method - Document Review
ed4245aa-40a1-5867-b476-ecee9491ed61 | note | Frequency - Each lot
bf7dbbce-52c5-54a2-9706-7ec8ddee4fbe | note | Category - IP
a66b5ecd-9855-5187-ab0c-9ed1db7467ab | note | Responsibility - PE/Surveyor
420516a2-0328-5dd0-9911-f5cd1e7e907b | note | Verifying Documents - Survey Conformance Report
6372231a-fc4c-5f21-b988-5ad06caa967a | date | Date Completed:
eefcf55b-197a-4f81-985c-96a70c4b1c44 | checkpoint | 6.4 - Survey As-Built Thickness of Pavement Layers - CARPARK PAVEMENT
8a2c8235-f7e3-513f-afeb-847ecc973662 | note | Reference - 304.07 (c )
1e8abef6-e305-5209-a360-b88818e5b719 | note | Acceptance Criteria - Subbase course shall be not less than the specified thickness by more than 15 mm.
ac612b73-3f5d-5b2b-a7ad-d694291be05c | note | ○ Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness.
c9facc08-41e6-59fa-992e-b662828a29c4 | note | ○ The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm.
ccdc7b40-975d-58ed-b578-1cd73a122f13 | note | ○ Attach: Survey Report
39b14d7b-9937-5aa6-98f6-aea875a96cd8 | note | Method - Document Review
91b5bc0e-3b2c-5294-97ed-d85c573665cd | note | Frequency - Each lot
d123fc8b-7511-5f1b-aba8-85a993701a81 | note | Category - IP
b8e73348-ef9c-585d-b56f-5bf53b3746f6 | note | Responsibility - PE/Surveyor
cf241f68-e8cc-5d46-8c8c-5f9e8d16276c | note | Verifying Documents - Survey Conformance Report
183dbb7e-9461-5f7d-9582-29ec415a8982 | date | Date Completed:
4ff42b25-1084-4980-afbb-37e7c171c8dc | checkpoint | 6.5 - Survey As-Built - Surface Level - MAIN ALIGNMENT ONLY
e0c0ef56-8b44-5647-9479-c2679e7a2f17 | note | Reference - IFC Drawings Section 304.07 (b), VR 304.07 (d) Table 304.071, Table 304.072
aa6cead6-d83b-5407-a654-e234d3723db4 | note | Acceptance Criteria - - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
6e07cfc2-108c-5576-bf0f-5489ad811bcc | note | — At no location shall water pond on the surface of any pavement layer.
aa74ed12-360c-50ee-8f85-1122360e9d3d | note | ○ Scale B: A minimum of 40 measurements per lot
aa8341ca-bb05-594d-816b-99275f396144 | note | ○ Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
e3af192c-ca36-5c9e-829a-2b5ae12321a1 | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
612006e2-bc5d-55d6-868e-b1f680e72636 | note | ○ Attach: Survey Report
34d65c32-0c3d-5d32-b770-d9bbcff16dbb | note | Method - Document Review
89e4fd06-2604-5543-a9eb-20167dd896e3 | note | Frequency - Each lot
eca38ab7-56a1-5e06-aa49-3558b967d983 | note | Category - IP
d4a38ca2-560b-5b91-ae55-c65e7d4fa254 | note | Responsibility - PE/Surveyor
382be2da-3dd0-5414-b8c8-ec29b05c0e25 | note | Verifying Documents - Survey Conformance Report
98baf3da-2ab5-5dcd-849c-111103503c86 | date | Date Completed:
022ed2c1-76c2-4c4a-9e89-0ddc9455775e | checkpoint | Final Inspection
548cc930-d8ca-5582-a864-7569fdb7d42f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
38a9224a-485d-5897-b10f-c9fa955ec39b | textbox | Name:
6401c245-7ee1-5ed1-8419-d1fa8f45415c | textbox | Position:
9d6b2524-dda7-57ad-8564-225e68c1dda5 | textbox | Date Completed:
c5fa05ec-d5a5-4f16-86ae-0a3c19ae6667 | signoff | Sign ITP
dee6e990-ec2d-407b-93ba-1fedbed6c7af | checklist | ITP-289-CIV-ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath Rev 0 | itp | ITP-289-CIV-ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath
6b00d0d5-7af0-4ac4-aadb-5dee462194c7 | section | 1. Referenced Documentation
690590cd-ac87-473c-b37e-20d104c9c2f1 | checkpoint-no-value | Referenced Documentation
9dfa3c68-5d26-5c36-b171-0f25bce59210 | note | Document Title: ITP-286-CIV- ADL-Unbound Flexible Pavement-Scale C
1f25bf63-c343-5044-bca3-4aa61c07ec6e | note | ITP Description: ADL-Unbound Flexible Pavement-Scale C
afbdac83-e61b-56b1-8a86-625db1176447 | note | Discipline (e.g. CIV/STR/RAIL): 286-CIV-
c58ebd29-562b-578b-80b0-fc20bf76d113 | note | Revision Number: 0
ec0b2b14-c404-5559-8b71-a2279fe761be | note | Revision Date: 20/06/2025
9061e500-c7e4-5637-800d-f41ce79ee336 | note | ITP created by: Abhi Patil
6b8707dc-37c8-5683-a4b0-6352ac9644ad | note | ITP approved for use by: Aldrin Guinchoma
a84fbb89-f429-5b02-bdb2-bffa27371947 | note | 1.1 - Non Dependent
e0e1080a-0ef4-5276-8c00-5927a3138b60 | note | Reference - VicRoads Section 304 August 2013
16151eeb-3a3f-5dfa-b81b-c36b2bcc6672 | note | 1.2 - Non Dependent
bd51c458-c0d2-5ddb-8dee-5e1db529e51a | note | Reference - VicRoads Section 703 April 2019
2102c728-55ae-51bb-ac3b-fbf32011b7a3 | note | 1.3 - Non Dependent
0ad8f28d-4356-52a5-93be-79f09c913d3e | note | Reference - Council IDM SD 250, IDM SD 236, IDM SD 205
72fed05f-51bb-5fdc-8f6e-20b5e8609670 | note | 1.4 - Non Dependent
48ddd0de-40c9-51bb-bc0d-1f192ba20bf6 | note | Reference - AS 1379-2007
b1e37c28-bbb5-5cdf-a753-c06daa30ca47 | note | 1.5 - Non Dependent
bb762a5e-a316-574e-8f15-74010cec1676 | note | Reference - VicRoads Section 812 July 2016
cb477870-46ba-5b36-97c3-631694daf9bb | note | 1.6 - Non Dependent
ca0070a9-66f9-595e-961c-f400be398621 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
0d6f7a0a-89d1-4cbc-a6e5-6372da8006b9 | section | 2. Preliminaries - Materials
679fc1f6-90f6-47bb-8220-ba6259d0a281 | checkpoint | 2.1 - Bedding Material Placement & Compaction
c1365c5f-129d-5a56-a40c-01ffd89ad6c8 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
345f1459-8abe-5a40-9ac6-d4832eae8a66 | note | ○ 812.04, 703.21
8ee7064f-80c1-5711-8226-45ad03fd3de0 | note | Acceptance Criteria - Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
8ce0395d-aeb7-54b2-8a5e-f230b1881aea | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.3
ae3a2712-65cb-5ee0-8424-11bb5c68b0b4 | textbox | Enter: Teambinder Material Approval number
e5ceb974-61a6-591f-a115-2c225c76390c | note | Method - Document Review
3d4109b0-966c-5f17-8261-53a7fd2d7f51 | note | Frequency - Each Lot
36a5927f-2579-5395-9bee-01c15d939d52 | note | Category - HP
0bf824c6-3fe5-504f-a9b9-9736d14cebb0 | note | Responsibility - Nominated Authority
1c207ad1-9cf6-555f-8a66-10d6641d976d | note | Verifying Documents - ConQA Hold Point Release
b2947b53-87ef-5169-8552-e256c5393c9b | date | Date Completed:
6ea24a7b-e028-47c9-9df7-0fe1e6f6598a | signoff | AUTHORITY HOLDPOINT
fe225bc9-95b7-49e7-8f36-0b8b1675dc95 | checkpoint | 2.2 - Concrete Mix
e541e858-8f82-5223-97c3-6ed2fc2745a2 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
aedd9853-c60c-5029-9f5d-104e4f507f23 | note | ○ 703.05 (a), 703.07
82cb5e43-c79c-52cd-91a8-6f9441105d91 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
e83fe8af-0c98-5849-a5df-7899051933dd | note | ○ Heavy Duty Vehicle Crossing (PA1):
4fa31fff-4ead-5c87-86d5-ca6e24505d60 | note | — Concrete Strength: 32Mpa
7432715a-885d-5570-b8dc-6321f4b8a2f0 | note | ○ Shared Use Path (F1):
4e4c7d76-b242-52b4-825c-12abbec81c87 | note | — Concrete Strength: 32MPa
6b91751b-b9d4-54a2-9cbe-d8d121432f8e | note | — Min 30% SCM
ae22dd9a-dfba-51a2-a514-44543a22ecc2 | note | ○ Footpath (F2)
f259620c-5a90-5b7b-93d3-730c9c088ccc | note | — Concrete Strength: 32MPa
d5f88bee-47a3-50d8-b41e-ced4f800f5e0 | note | — Min 30% SCM
12de84b5-5f19-5a97-a183-ae5f721a6a0b | note | — Macro-Synthetic Fibre Reinforced Concrete can be used in lieu of steel reinforcing path given council approval
d1306ff5-a31a-5bda-8e4d-667cd9218f43 | textbox | Enter: Teambinder Material Approval number
158e6c2f-f179-542c-983e-510265775ede | note | Method - Document Review
ecb4d208-65ce-526e-a49f-81bfa5e53c31 | note | Frequency - Each Lot
b5769535-becd-556b-ad51-948cb899dd2b | note | Category - HP
f973339d-a48b-58d2-9e3a-ed1f3987300c | note | Responsibility - Nominated Authority
d13025d5-54f5-562b-a08f-45ae84947c1e | note | Verifying Documents - ConQA Hold Point Release
8b68eba2-274f-548f-b63f-edd4ed9ec2d1 | date | Date Completed:
c665615b-cea4-4ec0-a93f-794d01b82616 | signoff | AUTHORITY HOLDPOINT
41c4ffa2-9293-41cf-a435-ef8e4cb497c2 | checkpoint | 2.3 - Reinforcement
c9d9c342-25ee-5405-9b0b-d302e59c319e | note | Reference - IFC Drawings
1851c03c-a9ad-5ab1-99c5-57fb56f40219 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
57979344-64d2-51ef-b5c2-3e462627d3fa | note | — 703.16
773c0b6a-0fcb-5bfe-89fd-dda5fd6e05ac | note | Acceptance Criteria - Reinforcement shall comply with AS4671. Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
2698c9cc-81a9-580a-a441-1d7e8347ae8b | note | Following steel mesh requirements shall apply as per IFC Drawings:
b8ee2045-a66e-58cb-ba1e-080e28cd2a78 | note | ○ Heavy Duty Vehicle Crossing (PA1):
65b4df25-1d6c-5374-8291-b72984c78e9b | note | — Two layers of SL82 Mesh (Top Cover Min 60mm)
23ef6b84-3e00-5551-afb9-93c2ffdadf8c | note | ○ Shared Use Path (F1):
09c409d2-44b3-52ee-ad4b-c84eb6f99dea | note | — SL82 Mesh Placed Centrally
d46bd227-554e-5607-a4cc-2eb53a8bf1db | note | ○ Footpath (F2)
2bad65e4-9421-59a9-a4e6-1c185c8b56fd | note | — SL72 Mesh (Min 50mm Cover to All Edges)
472e31f7-51f7-5062-8426-0d92ffe95146 | textbox | Enter: Teambinder Material Approval number
df2d5e42-59bd-5cf5-80a9-2774b71c1d71 | note | Method - Document Review
24463e2b-657c-58d8-bb75-1535fa278350 | note | Frequency - Each Lot
7f9e5954-d59a-5589-953f-91e7d567a3a3 | note | Category - HP
4ca8ff9b-f22d-5d07-b2d5-75e26698a6d0 | note | Responsibility - Nominated Authority
e682a6a4-756d-5623-a381-e41625dabe2d | note | Verifying Documents - ConQA Hold Point Release
194475fd-dce9-5052-a855-64b949dd94c2 | date | Date Completed:
2d3d4e0a-eca9-44bd-9071-3bb3d941fe16 | signoff | AUTHORITY HOLDPOINT
57b6a59a-6540-405a-884c-2568c89ae18d | checkpoint | 2.4 - Evaporative Retardant
90f51e9d-5935-549a-91a4-1ba451b8ad61 | note | Reference - 703.09, 610.17 (f)
8ba06c18-3bba-5770-a41e-61a039715e1a | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
95095497-e35e-5722-83fc-4d49911c836e | textbox | Enter: Teambinder Material Approval number
91b35a8b-16af-5e29-b272-5b198c389f7a | note | Method - Document Review
3bd9995a-febf-5e14-9412-0e8df09ec750 | note | Frequency - Once, for each product, prior to placement of concrete
8f811458-c201-5ebd-8e05-18d46eea640e | note | Category - HP
a979980a-bb12-5de0-906b-8b4bc78893de | note | Responsibility - Nominated Authority
000c0642-3449-50b5-bdfb-f05a0e1648ae | note | Verifying Documents - This ITP
e9b0328e-7613-5541-9eef-03c7bff90550 | date | Date Completed:
17a59767-c3f1-4205-95e5-f9e1be82e1f3 | signoff | AUTHORITY HOLDPOINT
0478264b-c4be-465e-96a9-b77646857561 | checkpoint | 2.5 - Curing Compound
ea237233-27f3-5adb-a7c8-0dce7f2ab2a3 | note | Reference - 703.10 (a), 610.23 (d)
21259750-46a0-5987-90e5-267727b67937 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
469fd15c-5557-52e3-8af5-9666a511312d | textbox | Enter: Teambinder Material Approval number
330a2339-7f26-5a7c-8172-bda79bd77ae5 | note | Method - Document Review
0fdc0cbe-9eaf-57b2-a3e9-c637431b4193 | note | Frequency - Once, for each product, prior to placement of concrete
83dbbbd9-fd16-5555-9719-60e42104d2a5 | note | Category - HP
f977cf4d-5278-5122-8c63-6eab1db5c087 | note | Responsibility - Nominated Authority
cad6e33e-8073-5604-ad59-3cc56beabcb5 | note | Verifying Documents - This ITP
e4d6ee3c-c91b-555a-b2cb-b6cbc6d73558 | date | Date Completed:
de91bbed-99f6-4c7f-8443-5da64bb61f83 | signoff | AUTHORITY HOLDPOINT
2fcb1973-fc24-48f2-9c35-6170718ec19d | section | 3. Preliminaries - Documents
bd4d7054-1348-4bd8-9b5c-76263da8b75f | checkpoint | 3.1 - Survey Set-out
18c3bf35-7461-5235-9a94-689cd3721fc9 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
4f3d89c7-bbec-5f18-b52b-8468aa274990 | note | ○ 703.17
190d957e-d67d-58d1-9bfa-808c4537f2a3 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
20906e1d-d987-5ac8-8f23-7778ac5da3ea | note | ○ The Nominated Authority will review and confirm the set out.
614f9d31-02f0-5117-a236-8dc240debf7b | note | ○ Attach: Survey Report
04dc3e29-4734-597a-b1a1-a2496b2651d5 | note | Method - Document Review, Measure, Visual
0e23622a-0a27-5828-87a5-6256e539f173 | note | Frequency - Each lot
05a62350-5aaa-5fad-a36e-d0803d22ec52 | note | Category - HP
550c3874-3be2-5d19-8376-29e59e7ad986 | note | Responsibility - Nominated Authority
8fdd3ec7-2fe1-578f-a62a-0b2c4db31dbf | note | Verifying Documents - ConQA Hold Point Release
2f3a7633-9476-5583-82af-4be4a38eaa10 | date | Date Completed:
c7b5a64e-97f1-4ced-a6ed-028b37a5e708 | signoff | AUTHORITY HOLDPOINT
7aee4994-bd4a-42b0-9453-519cfce3bb70 | checkpoint | 3.2 - Lot Map
4ee6a3ef-fb16-5012-86b6-df1502bac0ab | note | Reference - MRPA Lot Management Plan
b5b376bd-da38-5017-891c-5ebf61effcde | note | Acceptance Criteria - Attach Marked drawing indicating the location of this Lot
4aaee557-1225-5300-b2ff-f67da43312c3 | note | ○ Attach: Lot Map
716af710-373d-5499-868b-f504af9e9b2c | note | Method - Document
f94735b8-68df-535d-baa2-c55cb26f1b08 | note | Frequency - Each Lot
6ddf328a-7826-502b-9f99-4ba6e6aa91d6 | note | Category - HP*
1a04ae3d-5274-5723-b22c-285ea140ba32 | note | Responsibility - SE/PE
ea61569f-9909-5c9b-ab3d-624cd6349ffe | note | Verifying Documents - Attached Lot Map
1d9a4e6d-960e-5260-859a-a2911b5740be | date | Date Completed:
97f44105-030c-496a-ab68-94451d5ab741 | section | 4. Pre-Construction Activities
69c1b18c-de04-4bfa-9086-b2467e6694bc | checkpoint | 4.1 - Site Clearing & Grubbing
47676e0a-41f3-54a2-81e0-6769f7551489 | note | Reference - IFC Drawings
d5035978-f9ec-54d9-854c-ae440940bd55 | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
03baf9b4-6ee9-570c-8274-9700b3e1a67f | note | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
bb94737b-4088-5bc9-953e-abc6e0e76680 | note | Method - Visual
581352f4-9f52-50e5-bee0-c73385c0fcca | note | Frequency - Where applicable
11e76ddd-e0f4-50bd-88fb-7ef6338b6359 | note | Category - IP
195b0a22-b988-5408-bd35-53ee6bde5c15 | note | Responsibility - SE/PE/SPE
1c5a3638-b210-589c-8215-a49f5411254f | note | Verifying Documents - This ITP
ea5b3091-331b-5a79-840d-26e577aa0e45 | date | Date Completed:
7969f56c-e711-4d90-a3de-3c7b969a5b9a | checkpoint | 4.2 - IFC Drawings
cf0a6b13-7401-538c-8835-565da90ba6a6 | note | Reference - MRPA Quality Management Plan
6ab8063b-7710-5412-97a4-0fce447e2198 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
28a6f09d-ca11-5670-bf56-19a431068f30 | note | ○ Using the correct and complete set of drawings
cb3d7efa-1c56-5961-92fa-770167b051cc | note | Method - Document Review
e8d55265-af1d-5d13-964f-1762679257d5 | note | Frequency - Prior to starting Works and at regular intervals
3d9d9947-6bb0-5dab-8fbd-b7601fc1195a | note | Category - HP*
475c555b-553c-5be4-8ffb-6ed7671e9dd3 | note | Responsibility - SE/PE/SPE
930e2c83-b98e-5970-bf9a-a27038d22426 | note | Verifying Documents - This ITP
6a70bf84-734d-5a59-b97c-9d6759127de6 | date | Date Completed:
df8a68fa-bfb2-4885-af99-c97e2b8130b6 | section | 5. Construction Activities
d748097f-23f5-4c7e-828e-fb7089572f36 | checkpoint | 5.1 - Excavation
6fb09a30-26ac-595e-b970-5eb424dd1b19 | note | Reference - 703.20
0e70024b-c29e-5329-a241-862378e78d64 | note | ○ IFC Drawings
adf31466-b97b-5ae4-bd8e-40a28e50b249 | note | — IDM SD 250
6ab2b016-c388-56cb-aa6a-22a1fd92da54 | note | — IDM SD 236
e25ba1c1-477b-53b7-8d1d-c13f27f6a517 | note | — IDM SD 205
0240102c-0839-5519-a4ef-3315ed10ef5e | note | Acceptance Criteria - Where the new vehicle crossing is proposed at exostomg vehicle crossing locations, the existing granular subbase can be compacted and retained under the new base.
bd690a47-6d29-5c0e-8a6a-2b3ad2a66707 | note | ○ Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
81e7964d-ece8-56b7-bcc8-6ad67c37ff89 | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
1bc6e722-1feb-5f39-9f3b-675fd83d2793 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
0df3e917-533f-507a-9266-063f78536529 | note | Method - Visual, Measure
470763bc-a3fc-5461-911a-25f984f0ef1d | note | Frequency - Each lot
2fa65bbc-1aac-5772-96f5-a6c6201feae0 | note | Category - IP
4f0dd5eb-94cd-536a-9c41-545a8b424e13 | note | Responsibility - SE/PE/SPE
53a1ba19-4edb-5e8f-828b-380308199c2f | note | Verifying Documents - This ITP
15e7919a-f8a7-54b5-94a1-f2cbcaaf671e | date | Date Completed:
e1a84d0c-fc27-47a2-b9ab-c2193f44ff10 | checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
f6060537-a179-55b3-b402-e1c9d4c93c00 | note | Reference - 703.21
4db253b4-313a-566c-8cb2-5b1942bbe46d | note | ○ IFC Drawings:
e16ecbbd-00c4-5f40-92f2-461cf0644ec1 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
4586cfae-f2e4-5a96-a8d7-8889bbf7b3ff | note | ○ Relevant Council drawings:
f0abec57-f2d5-509f-92f0-5bcabf7ebf09 | note | — IDM SD 250
a6d48346-3207-5581-94c4-3d708b4b1407 | note | — IDM SD 236
9ccd7351-a9de-5921-95ac-c5e32cefe570 | note | — IDM SD 205
ac2be723-5af0-5711-8174-6e31eed6e1fe | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
f7b7782b-62ad-5e7a-a0f6-4ec1b74270ce | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
5df437b7-306f-5cc1-af9e-91cb1355e728 | note | Method - Visual, Measure
47d10e58-c7ca-5fb7-ac83-eb1329e72bd9 | note | Frequency - Where applicable, each lot
3d46da93-296f-59d9-a424-74da925b22bd | note | Category - IP
63025b69-046e-5a6a-b128-20d3c1c9dbd9 | note | Responsibility - SE/PE/SPE
d0812f53-2c90-5ad8-a9da-b74c8adf34bc | note | Verifying Documents - This ITP
7fd994e4-a27d-5c98-8c77-ed5d6316eb12 | date | Date Completed:
86477289-9bdf-4fc7-a24b-b43df4296d17 | checkpoint | 5.3 - Bedding Material Placement & Compaction
3e057b27-46bc-598f-a6e1-86f0fa6dbb47 | note | Reference - 703.21
d406d886-75e1-5ede-81ec-a5cc2066280f | note | ○ IFC Drawings:
0b2e3fab-1aaf-5653-b1de-0923acb0ffce | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
2164a054-13df-5bb0-8f7b-eb8fab55c565 | note | ○ Relevant Council drawings:
99d1d0b9-d5d5-5a9f-86a3-fa2a634348fa | note | — IDM SD 250
94ab9661-1e92-5dc9-bd71-036f0629cdd0 | note | — IDM SD 236
bfc12e37-d489-5277-8d4c-765028b6fcc6 | note | — IDM SD 205
c81a00f2-a791-5ae8-a8cb-14df2b3c6374 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
79634473-36bd-5e45-94fa-695c4af8a466 | note | ○ Heavy Duty Vehicle Crossing (PA1):
f4068e8a-00d8-540f-966c-5c18c6f7bc0f | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
16a1d7fe-5a6c-5ff5-a7b0-1d1246593692 | note | ○ Shared Use Path (F1):
552695ac-a508-58b4-a94f-1bd544278ed8 | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
c2b3906e-1777-540a-a6b1-ad735f8ce5b9 | note | ○ Footpath (F2)
b63d37b5-0ae1-5389-bd6d-a23800482a5d | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
02c51d2f-6a18-504f-860e-d47fcbf3f2a4 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
c75658f1-cbc1-5c68-ac01-f11da7374838 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
477b91e8-0cfe-5976-909f-951772149c10 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
97a2324b-4d38-5407-ac1b-b62dc8ff6a27 | note | ○ Attach: Bedding Material Delivery Dockets
9f68d7cf-596f-5a49-8b7e-fd775c089522 | note | Method - Visual, Measure
94261dea-55c6-5f39-9844-25d2b8c88820 | note | Frequency - Each lot
c0f8fc5f-7dc7-5c1e-af99-6ec336c4b78c | note | Category - IP
dbbdd297-799f-5050-82b4-7afe8ef678a8 | note | Responsibility - SE/PE/SPE
789d0dfd-3396-5397-8e0f-1556dd429a04 | note | Verifying Documents - This ITP
d5e0b586-7f9a-5fbf-8db7-543f97fad880 | date | Date Completed:
105ca73a-d7bd-4d28-ba63-523ce3f518e9 | checkpoint | 5.4 - Compaction Testing
32a7889a-186f-5532-aef0-ee67cb1aa620 | note | Reference - 703.21
dc625e7e-736d-527b-83fd-8b7ca6c49ce4 | note | ○ 304.08 (a) & (b)
af110688-5f42-5ac0-9176-4c5ca5a7aa15 | note | ○ 304.11 (a)
8324ca0e-e676-5755-ba37-f4e5b331536b | note | ○ IDM SD 250
cb3e2385-1a5a-5dc1-9122-e4a97d883438 | note | ○ IDM SD 236
063ff10a-8b22-5289-9582-531c7241cee4 | note | ○ IDM SD 205
5d645444-66c9-5ff7-ad86-ae44a5441a26 | note | Acceptance Criteria - Compaction shall meet the following requirements:
50b522e6-2732-5cf2-b953-827cbefd778c | note | — Scale of Surface Level Measurement = Scale C
716b3d6f-e226-5097-b277-4efd7f668f8e | note | — Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
8218b975-628d-5d06-9cd8-e4c5951771a7 | note | — Mean Value of Density Ratio % (3 tests) not less than 100%
a93ec91e-e9da-5b36-8788-0c5871618988 | note | — Modified Maxmumum Dried Density (3 tests) not less than 97%
dc98e188-6fe6-5f7d-88b3-5b22785814d2 | note | ○ Attach: Mean Value of Density Ratio or Modified Maximum Dried Density
69743d81-5cd5-5f00-8c78-d6258e94a251 | note | Method - Document Review, Visual
e3bb1c7c-62ec-53dc-b58a-854aac840fe0 | note | Frequency - Where applicable, each lot
49efd976-362f-5e1f-8caf-8504add3ce7d | note | Category - IP
091db48a-1c05-5336-8f88-72d18cb1b133 | note | Responsibility - SE/PE/SPE
0d3b52ad-9f6d-5e33-937c-bb8327ff5289 | note | Verifying Documents - This ITP
05e39ba8-c0e6-5b7b-8bf5-a09f3ba2d181 | date | Date Completed:
27b31762-ed3b-48e1-855f-56f4d65b0f69 | checkpoint | 5.5 - Formwork Construction & Placement
c8acedec-5097-5912-bb1a-1b20e3040155 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
74acfc57-6657-5dad-ae61-007c2d5b71db | note | ○ 703.12
d9cd6afc-ed58-532a-8528-0b28b4697eaf | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
b7cfb45c-3d16-5584-8c1f-feecd929aa92 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
58cfe98b-7de2-5b8f-9541-1286b2cc4e63 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
23a3658f-c7e2-5698-9ea9-adb78c0b085c | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
75ae6ae4-919f-52cb-b847-47071e91e569 | note | Method - Visual, Measure
7324c31a-0dd7-5b0e-902c-31483f14a149 | note | Frequency - Each lot
5a06b00d-bb89-57f0-939d-dd2d2fa552e5 | note | Category - IP
133b15d4-7198-52d5-af40-b727333f1292 | note | Responsibility - SE/PE/SPE
c1c2309e-7927-55db-bc50-c83b15e74c92 | note | Verifying Documents - This ITP
2a7cee75-642b-5f72-9eba-1ea41555cf3e | date | Date Completed:
8eda80d4-8649-4063-9ebf-f947c617e9f8 | checkpoint | 5.6 - Construction Joints & Matching Existing Surfaces
5dfcac81-7815-5f24-830a-be117f93238a | note | Reference - IFC Drawings
362ea7c6-28f6-5402-b15a-08ff47cba1a7 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
9b91cf49-343b-5f18-937f-7b4e99fa6779 | note | — 703.24
753c37a7-24df-59d9-8ab6-c62c1d70d11f | note | ○ Relevant Council Standard Drawings
d93f1ba0-1a95-5e4f-bc62-0be0eb11616c | note | ○ Relevant Council drawings:
47738c57-60b8-5225-b8c6-a21aa3bef072 | note | — IDM SD 250
ada5ac54-4af3-56ef-af47-9f6dd07c11b6 | note | — IDM SD 236
f46ce00b-59b1-5e47-a1a6-2bd12a5525ee | note | — IDM SD 205
21cebdc3-e942-5fc3-9013-9a4a920a2f88 | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
fa27517c-d0da-5045-96fe-21e734996e75 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
69b5f6d2-a796-595b-9671-8ca3d9d8dfb7 | note | i. Concrete cutting of a shear-key
223864b5-ca86-5b52-85ca-1a698229636a | note | ii. Surface roughening
a12fb1f4-bba2-5fd7-8b62-91274961d2d2 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
b45032d0-ca3f-5474-aab6-e78ad8a04ee2 | note | iv. Cutting a groove for sealant
b53214f9-b81a-5df0-9584-03d8590a8cdb | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
027545b0-e691-59d5-824e-f76c6fe62c46 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
4616f8df-aa7b-5eb3-b811-7adff169a674 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
b517570b-bb24-5ea8-a9d7-cea2193e14e4 | note | Method - Visual, Measure
48270baa-efc5-539b-ae2c-d099571e37fd | note | Frequency - Where applicable, each lot
4b28b43c-5383-5255-89c3-c9fbebc628f2 | note | Category - IP
d574cae7-453a-55fe-af6d-22c3233000ee | note | Responsibility - SE/PE/SPE
022c11f7-420a-59fb-8145-c56b38edd8a8 | note | Verifying Documents - This ITP
8ed7855a-3212-53f1-9f75-f7b39786a3ec | date | Date Completed:
5d6d9b92-718d-4745-8043-edd772f60d0f | checkpoint | 5.7 - Isolation Joints
7ac5a57c-27af-5670-b8e6-9e87b27473e4 | note | Reference - IFC Drawings
b045ad23-08e6-5c0d-90bc-b1b8767a1913 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
2299ce11-1003-5e8f-8a5f-b396e602a17a | note | — 703.26 (c)
89094ebd-d06b-5819-a45b-cb0bb0565457 | note | ○ Relevant Council Standard Drawings
6195cd2d-3c9f-5267-9c05-98ccd5e08fe2 | note | — IDM SD 250
b728355f-cf8b-5aaf-9c75-9487bc424ea5 | note | — IDM SD 236
65ff3c7e-8fb1-5b1d-a736-39d8159e2c19 | note | — IDM SD 205
427384b6-c766-5ee8-b9c4-b3ff2c6fc4d3 | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
28fe6e13-69ae-5c5b-8b9e-64938d0ed43f | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
d39b375c-c52c-5979-bf34-41dc8f7fc9d3 | note | ii. at any location marked on the drawings
167e2f93-9b2a-5558-8bc5-ccf9a5880391 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
284f49b6-51c7-5d2d-80a7-eb23006a826b | note | Method - Visual, Measure
878f24df-3e21-5e34-8788-f01a97c8629f | note | Frequency - Where applicable, each lot
7e4f9b93-75fa-5868-8dfc-c8ffb87c317e | note | Category - IP
e481473d-cc1a-5ea3-8df2-814fb6f4a11c | note | Responsibility - SE/PE/SPE
c2c9c114-2fa1-5c0f-91b0-821f0656c424 | note | Verifying Documents - This ITP
2bf0116a-712e-504e-b39c-3d2d97404a92 | date | Date Completed:
ee6149a7-212c-48ac-b083-d517c0598988 | checkpoint | 5.8 - Expansion Joints
2da2f4e4-826c-5a06-84a1-4584d6a6f118 | note | Reference - IFC Drawings
e7ae094f-d21d-5cbe-8917-78e5de87be99 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
4b14457e-0d09-59dd-9f88-02955bfb2599 | note | — 703.26 (a) (ii) & (b) (i)
ee62e3a6-de27-5225-8f07-f0d9311059ab | note | ○ Relevant Council Standard Drawings
d4bc075b-fbfa-554e-bb69-ce62c3c30d23 | note | — IDM SD 250
4979d237-bcb1-5543-a88d-02ded12e54a5 | note | — IDM SD 236
1b2c4b72-5723-577a-b736-835eea17b3f7 | note | — IDM SD 205
821a9b5a-3885-5948-bd79-880d5b6aab07 | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
11741bb7-3448-5fb7-a08e-5c1646f7e793 | note | i. on either side of vehicle crossings
c13b92bc-5e91-5221-a234-559fe409b7a6 | note | ii. at junctions with existing footpaths and shared use paths
b8fde9ff-cf01-512f-aeba-ff962f3b44d6 | note | iii. at junctions with bridges
fcd1ce76-be93-55a8-a870-e3ee2da220d4 | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
00e64f7c-b7af-56bc-8a81-13d74502d846 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
1512e746-13e9-50de-8a8b-2ef9f17e925b | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
eff02cba-fda2-55fd-9f9f-bf28b5f1c8d1 | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
a0e40574-c4ed-5fa3-bd05-4489369d8a19 | note | Method - Visual, Measure
71d6e00b-e586-5b3a-bde4-f7f9babcbd79 | note | Frequency - Where applicable, each lot
6e035bdf-57d8-5c59-9eb9-b7d1f25c8246 | note | Category - IP
1c5841ab-8ac9-5a13-8da4-c15bcd3ca3bf | note | Responsibility - SE/PE/SPE
89eb804b-bf70-5a78-8ada-9b6c0bf6858e | note | Verifying Documents - This ITP
719590dc-f74e-58e3-aa8d-6b8f3174646d | date | Date Completed:
7210277b-8371-4e49-b1a8-8e89e258b2e6 | checkpoint | 5.9 - Reinforcement Placement
dc4585b3-d170-52e1-ba3f-89a1163b9ed9 | note | Reference - IFC Drawings
93e29170-ba1d-5f45-b634-4f19fcf4adef | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
aa041474-93c3-5f33-b8e1-ef06058a7635 | note | — 703.13
4e2ca409-dcd0-5225-ad8f-4428a76512e7 | note | ○ Relevant Council Standard Drawings
ba48bb13-19f1-505a-bd57-4b4639ea0435 | note | — IDM SD 250
0a973945-41e9-5249-8923-130d8fa8d020 | note | — IDM SD 236
2729adc8-0880-53fc-b645-1ac7b2e6d9ce | note | — IDM SD 205
2bd0f193-39c1-5d98-864b-8c0db7f93231 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
d7be0f75-3d34-5a65-b8e5-29a8de753c06 | note | ○ Heavy Duty Vehicle Crossing (PA1):
4407d6dd-6f46-5d99-9a09-b8c43e20075f | note | — Two layers of SL82 Mesh (Top Cover Min 60mm)
8d8aaa69-d458-5cac-9805-c1c66da85863 | note | ○ Shared Use Path (F1):
0a350650-9011-5393-b5e6-53b5d7f77c61 | note | — SL82 Mesh Placed Centrally
1d7119a6-1cc0-57f0-9409-cf77ebfc1a16 | note | ○ Footpath (F2)
588c39ba-083f-58d0-9f6e-ed43ab4195cb | note | — SL72 Mesh (Min 50mm Cover to All Edges)
04753973-d273-529f-be6a-7f2e1d951e50 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
0f7704b5-97a4-52a7-8e97-edd6af03a968 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
efc666a0-5666-52f5-891e-013ab21ab707 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
c9e7777a-0ba2-5daa-9c4e-4f7233788655 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
dfa7e829-5b78-5a4b-af5f-af96d78efb9c | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
93755c6b-d475-51c4-9016-88360b130fc4 | note | Method - Measure, Visual
d2afd590-d469-5b34-9afb-8eeaca9ef189 | note | Frequency - Each element
097fd99f-b03f-5d5c-b507-8d4336c36cf8 | note | Category - IP
6d63826a-f1c5-5e4a-b24b-fac4cee68644 | note | Responsibility - Foreman, SE/PE/SPE
ab5e5ee1-f7bf-59c9-a4b7-42b50d3c7c1e | note | Verifying Documents - This ITP
d364d9bd-60f9-578b-8d1f-2de7ac363784 | date | Date Completed:
c1ec3578-4b1f-47f2-83b4-98d60ecf4570 | checkpoint | 5.10 - Pre-pour Survey
dda77c5e-4591-514b-bfb3-4defc38d5b2d | note | Reference - IFC Drawings
73d28cfd-f8ed-5fb0-bfd3-796883898813 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
6fdd67c8-a150-57c1-8c42-a9634c9f9262 | note | — 703.15
d1855de5-6e8c-50f9-af74-89fe98bbc091 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
1565d85c-3e7a-58ba-b777-ef38cff0c457 | note | ○ Erected formwork and base layer within the tolerances below:
669636fb-3c42-58e0-a71d-7f7086c9fcca | note | — Departure from RL = ±10mm
a27555ac-f0d7-5cf1-b981-edba5141af40 | note | — Departure from alignment = ±10mm
2929fe68-b383-5f02-aa43-0a89f25951a2 | note | — Rate of change of deviation from RL or alignment = 10mm in 10m
8438a581-1df2-58c5-a03d-9ee24348a9fd | note | — Irregularities in alignment = 5mm in 3m
c10c4fe7-72cf-51f6-abab-51e4589f07ae | note | — Section dimensions = ±5mm
7f0d5c9b-41d3-5f62-a15b-f9d8049132be | note | — Section dimensions (less than 25mm) = ±3mm
127bf911-db91-5579-bc9d-842135b74c43 | note | — Width of pavement = -5mm, +15mm
1d23dcdf-b038-59a7-9309-1ec9c5c8707c | note | ○ Attach: Survey Report
aa2712ed-6ca1-5295-86f0-10c1a74b4027 | note | Method - Measure, Visual
f7d434d8-6449-51d6-9035-924f5d2aeb8a | note | Frequency - Each lot
a74d193e-1932-5e8f-ae19-0c1bb9509f3d | note | Category - HP*
0859d350-4003-5527-aa07-81ccc15b259a | note | Responsibility - Surveyor, SE/PE/SPE
0253f853-3f80-53d8-a105-e265f5eb8ee6 | note | Verifying Documents - This ITP
655bf98a-37c0-5868-b3f6-64d729d34e08 | date | Date Completed:
01c09d0a-8df7-45fd-a44f-1899662dd9bf | checkpoint | 5.11 - Pre-pour Inspection
ed814cae-221f-51ef-8077-e3d5ba809942 | note | Reference - Section 703.09, Section 703.21 Section 610.17a), b) & c)
3aee96cd-1e89-51a6-a3d3-039de42524a3 | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
2ddbba63-666b-57e9-ab93-322d8ecf7181 | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
e52e8dc0-49a3-537b-b00c-0cead8fc7c3d | note | Method - Measure, Visual
1b12f4e1-8b9b-53f0-a2ca-095282b8c7c1 | note | Frequency - Each lot
3be67e0e-5c31-51e0-8999-ae1ef35e6060 | note | Category - HP*
1adc0953-5ab9-5e29-901e-3d2b12bbaf36 | note | Responsibility - SE/PE/SPE
2a514a18-1be4-56c5-a1bb-47e0cb8b3ab9 | note | Verifying Documents - This ITP
ec36c4a0-578f-5900-b505-0b7ea47fda7c | date | Date Completed:
106b20b6-380f-4bb8-8195-e0acdac20503 | checkpoint | 5.12 - Weather Conditions & Evaporation Limits
64059af9-de74-5270-bcca-a929e31f62f1 | note | Reference - 703.09, 610.17 (a - f) Table 610.171
d97ff5e7-ae56-5edc-9e21-d02315c0f487 | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
4875c1b6-66d2-5ff3-bd51-93aca68a1252 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
afe9bfe2-6d6e-56cc-ad75-8937ccb758b3 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
678e3a2f-b88d-585f-a8c6-70df7090d775 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
a539226e-9023-5aaa-8e3c-98b60ea75d5a | note | ○ Record: Required information on the Concrete Pour Record.
2da371d6-8771-51b4-bb14-c1d3928cd0ff | note | Method - Measure, Visual
8443f6b4-f7cf-550a-992a-24fdd2435925 | note | Frequency - Each lot
45644eb3-cdf3-5883-a79d-e52606f5ccaa | note | Category - IP
897f4bc3-68a1-582f-a933-4b74fe3b05e2 | note | Responsibility - Foreman, SE/PE/SPE
50a090a7-339c-5899-9338-807bbaaae84a | note | Verifying Documents - This ITP
a5661be4-9a8b-511f-a657-9057d566a19d | date | Date Completed:
0f707b0d-40f9-4c27-867e-82321462c7b5 | checkpoint | 5.13 - Concrete Testing - Sampling Frequencies - Footpath, Industrial Driveway, Traffic Island
7f083d90-8462-5c5b-ab4c-db1262523490 | note | Reference - 703.11, 610.16 (b), AS 1379-2007 Cluse 6.2
203a2ecc-746d-5341-b2f4-eb32c403a359 | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
2fc021f6-f74f-5233-889f-9bae1b1db408 | note | ○ Correct quantity of cylinders manufactured per sample.
e4f06785-22d2-5eeb-a3f2-1eccd2991b3d | note | ○ Correct quantity of cylinders manufactured per sample.
17421e71-f540-5017-a5d1-396d6210dbb5 | note | ○ Record: Required information on the Concrete Pour Record.
aff39707-4324-5a25-817e-932c6e98de3c | note | Method - Test
cffe3b55-918d-5c1e-98d4-c45d91c04216 | note | Frequency - Each lot
e2a21433-bb25-50f4-abc6-b653553e5e4a | note | Category - IP
ddeeaa40-be1b-546e-9577-e5271400ba8d | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
eba01b0a-ca4a-51d8-8091-f353edbb129d | note | Verifying Documents - This ITP
0720fc72-734f-57bd-bd1a-4fd53512ce42 | date | Date Completed:
75de23d6-4470-49c1-953d-2510adb6ae68 | checkpoint | 5.14 - Concrete Testing - Slump
17dd4b7e-86ad-51bf-a03e-5579c51a4a4c | note | Reference - 703.11, 610.16 (c)
5ab2bf85-edcf-5791-807a-e7f9b403dca4 | note | Acceptance Criteria - Slump testing tolerances =
b78fa946-9c05-51a6-9002-e4fc84a278ae | note | <60mm = ±10mm
4ee8fb37-350a-50ff-b0ba-0f217264ce72 | note | ≥60mm to ≤80mm = ±15mm
851b6c16-825a-58a6-8653-c0b476143d13 | note | >80mm to ≤110mm = ±20mm
c44ab2e6-0a4a-52e1-a9e1-0dda70f3fdc5 | note | >110mm to ≤150mm = ±30mm
ea8917ef-66cf-5de1-94ab-6a3d507efd83 | note | >150mm = ±40mm
d5976835-b3d3-5f79-95f0-25186fe92beb | note | ○ Record: Required information on the Concrete Pour Record.
bb032942-6be7-5c42-ae0d-0e92ac52d55f | note | Method - Test
7cf259e4-13ec-52c5-a9c7-875f7c9bc0ac | note | Frequency - Each sample
6c94d8ca-e474-52fb-8e06-ce67c2693a23 | note | Category - IP
a7497985-6163-57f7-92c4-9e48363e145c | note | Responsibility - Concrete Tester
46936f8a-8532-5931-ac2e-74ba29bc070c | note | Verifying Documents - This ITP
2cfc416b-a1be-51b2-98e9-6622b3e6054d | date | Date Completed:
116584f7-1cfa-4cfb-945c-92106cfae85b | checkpoint | 5.15 - Placement & Compaction
8de465a2-edef-5551-b2be-218fd6a04b05 | note | Reference - 703.08
001af3fa-3bce-5672-bd46-afb9c9ae1a06 | note | Acceptance Criteria - All concrete batches are traceable.
e5e08fb3-3271-50d5-a97b-6616e0ae1b85 | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
78181ebb-b434-5082-b8b2-2585da82b137 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
ad79081c-7b05-5932-966d-66ab88a8d4a2 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
caace30f-6266-5b0e-8b6a-32e48b9a774d | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
69dbfaf9-2031-549a-9357-1b428c9d1e56 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
bb3d151c-6215-54f7-9442-5da943f58e69 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
9943a7c9-ac77-58d9-98ac-37b6afb12114 | note | ○ Record: Required information on the Concrete Pour Record.
f2bcc7da-5cb2-594a-b8cc-bffac91f5ba8 | note | ○ Attach: Concrete Pour Record
625ea765-6d6d-5767-9325-5a3c7fe7477c | note | ○ Attach: Concrete Dockets
cba461cf-f7a1-51aa-bff0-612a8dfafb47 | note | Method - Visual
35713094-5975-58a2-af4f-444b51f52caa | note | Frequency - Each load
a5346427-9899-5dc9-9bb0-5c4494b7add5 | note | Category - SP
87a75593-86db-51ee-ae56-dd904cdeec7e | note | Responsibility - Foreman, SE/PE/SPE
c1277c21-cf66-5272-b47b-2c714fa028ea | note | Verifying Documents -
0acd3936-d60a-50af-b401-f6cb3e6f3e25 | date | Date Completed:
a7c5fe30-5ec2-4ef6-9bc0-7a3627196370 | checkpoint | 5.16 - Surface Finishes
0d395e63-7de3-5c63-9a65-70b68c91532b | note | Reference - IFC Drawings
b91fbaf6-4e59-5e2b-87b2-04eb1e805391 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
5d810729-e093-561d-ae6e-557d3c05ca7e | note | ○ Relevant Council Drawings
d5c7b10e-85b5-5179-a4bf-1f12a06de75a | note | — IDM SD 250
79099fe7-cc0b-548b-8701-faeeedf2a250 | note | — IDM SD 236
a4a482cc-6948-54fa-a871-7f81539bd2bf | note | — IDM SD 205
be9d104f-a6c4-5ff1-aab9-70fc8cceaa44 | note | — 703.25
e0fa3f96-bb9f-5e88-9698-1195eaf78996 | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
1294120b-a0b1-5feb-aad8-10bb48ef6296 | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
f3bf106b-74d0-5299-9ef3-b41d404c7bed | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
5b37b35b-9d68-5dda-b918-6ca5e03b3d06 | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
553a4fc0-0b94-5cff-8612-e312d15d1d80 | note | Method - Visual
a7bfdcb5-ba7d-5e25-85bb-c14c4f851633 | note | Frequency - Each lot
582b28a0-3f88-554d-95b7-ea95bd887761 | note | Category - IP
3295050e-07d1-504e-bf49-1978c9016dd9 | note | Responsibility - Foreman, SE/PE/SPE
02b9454f-5b42-518f-ac46-abadce0498b1 | note | Verifying Documents - This ITP
9e016af7-1e3c-5033-aa71-e8ea88e19673 | date | Date Completed:
d078a269-d0ee-4f1c-92b2-84dba599b978 | checkpoint | 5.17 - Crack-control Joints / Weaken Plane Joints
395e04ac-46fb-5617-b4c8-c5fb45cc84e2 | note | Reference - IFC Drawings
266c799e-8587-56b0-a3b3-7774e8740202 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
03961830-e9e4-5927-a549-36aab2922270 | note | ○ Relevant Council Drawings
8ac1b815-e310-5f78-bb2b-f9d4332b2078 | note | — IDM SD 250
084b800a-51f5-5534-aa11-5498e5f825be | note | — IDM SD 236
68c1f413-8c7f-5bc1-8145-a025fabf087a | note | — IDM SD 205
7243bc91-77d5-5d8b-a11c-9600305f7904 | note | — 703.26 (b) (ii)
ee4cda49-f6b6-577c-91b9-b23cbf0d0937 | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
f79311c5-dde2-5418-a44a-6e20b2d938d9 | note | Method - Visual
29cfc5aa-5d17-55bb-af94-4e0c0db6155e | note | Frequency - Where applicable, each lot
78ff3feb-23ee-576e-bbd3-9df52960ca9c | note | Category - IP
8d98325f-0412-5ca9-8f23-e8b3b4fc2dfe | note | Responsibility - Foreman, SE/PE/SPE
976507c9-bd39-5f03-acd2-314ab24a717a | note | Verifying Documents - This ITP
3a8fcbd3-f31f-519a-8989-893287bf967c | date | Date Completed:
d977e315-686c-4fe0-a859-f1c0111843c7 | checkpoint | 5.18 - Curing
01cd18a7-3ba3-52c2-b947-0ec9aa969b0f | note | Reference - 703.1
b69d912e-cc16-54e2-b586-20049a8905fb | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
832a7862-34a4-5a74-83d7-eb5b13ed1409 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
c2304ed3-97cd-59aa-9af7-fa32917bf764 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
039809d3-96da-5dde-a25f-6d6db266b9dd | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
051dc7a7-ada1-5e89-a97f-25a23a11e05c | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
475a0072-534b-5125-acee-acacba7cc867 | note | Method - Visual
4ee0392d-478b-525d-b04b-b971538a00f9 | note | Frequency - Each lot
2136425d-7ed9-5ea8-bea6-4f52920a57de | note | Category - IP
fe0454b7-d2f3-55bb-bdea-0649769dd085 | note | Responsibility - Foreman, SE/PE/SPE
3fedd4d0-ef86-5758-876b-c4827e8469bc | note | Verifying Documents - This ITP
5986733d-69b6-5dcc-92ae-52673635caaf | date | Date Completed:
0f55904e-6f67-4d82-bd7a-6e653ce2d86b | section | 6. Post-construction Activities
2141ebfb-17fa-43a1-bca2-6439ab3e96b1 | checkpoint | 6.1 - Crack-control Joints / Weaken Plane Joints
5e29e77a-007f-5e56-b363-bfe240c0cefc | note | Reference - IFC Drawings
1c79a1b0-8929-5f51-b5e3-bf178605997f | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
d1a9cfcc-4534-5667-83e2-f5014abb895d | note | ○ Relevant Council Drawings
064eb192-0555-5690-b819-01322f151949 | note | — IDM SD 250
ddb81a6a-f910-5283-baec-4ee822f29ad9 | note | — IDM SD 236
011111d2-3efc-5ea8-8323-22fb2b58c83d | note | — IDM SD 205703.26 (b) (ii)
f436f206-f417-58b3-b386-de4f2f80e329 | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
4575b321-0941-5bce-ab8b-d23ad1648e14 | note | <20°C = within 24 hours of finishing operations
60bb5a57-5c4a-5c34-a402-d2383e5dbd1c | note | ≥20°C - 35°C = within 4 hours of finishing operations
88410e01-de43-511f-b8d0-a10786af1f44 | note | Method - Visual
c6796d6d-f5a5-58c0-a199-6ca11b4738fc | note | Frequency - Where applicable, each lot
69fed1d0-a3aa-5bbc-802e-89a2cb296f1d | note | Category - IP
4ee0f2f8-41b9-5ddb-8bd8-d6b4542f6acd | note | Responsibility - Foreman, SE/PE/SPE
0c3b556c-4492-564c-abb0-2e3730cf80e0 | note | Verifying Documents - This ITP
b112d7d7-52ef-541b-a0e2-111c3c3eab49 | date | Date Completed:
85f0331d-643d-4628-885c-d5f88ffe74a6 | checkpoint | 6.2 - Protection of Newly Poured Concrete
48449f3d-414a-5bcd-b0d0-fa3f0754a0b3 | note | Reference - 703.27
3de0d4f0-07c5-5ea5-84fd-95c3c6114e31 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
25b264bb-a4ec-533c-8047-9aedc913c973 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
586c6048-81de-55d5-9b87-4645f8984079 | note | Method - Visual
345d927f-51d5-518c-a318-60d1f2c6e54a | note | Frequency - Where applicable, each lot
521af398-1021-5d0b-865b-f1f8b51a8ea4 | note | Category - IP
34a8e3bc-23a3-50df-bb8e-0cf6a8d2a97d | note | Responsibility - Foreman, SE/PE/SPE
2f38a874-006b-551e-9a8c-56b95b88ebc6 | note | Verifying Documents - This ITP
87012ffa-36f5-5059-b94d-74f24a92969e | date | Date Completed:
0e7569e9-3f05-47ac-8e34-8c2c02274239 | checkpoint | 6.3 - Stripping Formwork
86acbcfa-f0dc-565a-af93-d9150e52449f | note | Reference - 703.12, AS3610 Table C2
5016f042-8831-53f2-afd2-51663dd48e7e | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
c66e6e0d-ec59-5b36-91f0-1c5ebc3dc4d2 | note | i. 2 days for vertical formwork on external surfaces; and
b29992ed-b641-5f41-b366-91e6af736709 | note | ii. 1 day for vertical forms on permanently hidden surfaces
2288a16b-33ed-5d9c-ae98-6dcb900410e6 | note | Method - Visual
2111e6c7-5bae-5ecd-b4a9-1ecf27ea176a | note | Frequency - Each lot
675b8f77-9e7d-5242-be7c-45f2723f6fcd | note | Category - IP
1df21cf6-1c06-5cbb-a468-53a304171759 | note | Responsibility - Foreman, SE/PE/SPE
33db9bdf-6f88-5a07-9d69-7c0b7819a09a | note | Verifying Documents - This ITP
d6e9263e-bed6-512a-98b2-20550f46b834 | date | Date Completed:
4a063afc-8210-4ed9-ad87-a27fe87b171e | checkpoint | 6.4 - Backfilling & Pavement Restoration
3c1a5b71-e25a-5018-8b0d-893abe56c8dc | note | Reference - 703.29
8cfdcaad-88f8-5ae4-9746-c7f62c7fa7b9 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
b9624318-82b3-5dbb-a272-e38f7537932c | note | Method - Visual, Measure
28cab7f5-d65e-50ca-a3e7-9c70b271f70d | note | Frequency - Each lot
c0744259-830a-5e23-8e5d-dd64f16225bb | note | Category - IP
51ef797f-483d-5906-ad25-cecb80fe907f | note | Responsibility - Foreman, SE/PE/SPE
ca804119-e0c7-5f81-b1fd-541d5aaa8719 | note | Verifying Documents - This ITP
17aee34f-aa56-5b83-b9a4-6c2e81ce6478 | date | Date Completed:
6ed80ef8-9fca-44b7-aacc-d7bec4bae69f | checkpoint | 6.5 - Surface Inspection - Cracks
e07752cd-3d57-51c2-9fd2-45d9c7a0e2c0 | note | Reference - 703.3
dea6d92a-76dc-550d-b672-9a2dffeaec37 | note | Acceptance Criteria - No cracks greater than 0.2mm.
4c28b0bc-04a8-5ba2-a31f-6a843cfd3842 | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
f3beaec1-17b6-5d7d-8c2c-14c8be1bf632 | note | Method - Visual, Measure
314f559e-8db5-52c2-a606-500402f060fc | note | Frequency - Where applicable, each lot
d789c63a-e21e-5764-b142-44fb83cdd7cb | note | Category - IP
7823594a-ae84-56b7-84d8-d8b1cca75557 | note | Responsibility - SE/PE/SPE
d6bace36-8a29-5b3b-9156-96042c832191 | note | Verifying Documents - This ITP
0c963a69-b6fe-5aa7-bb96-2facaeb2a5db | date | Date Completed:
83d48e79-0193-48e0-a5b9-a5e6a54af037 | checkpoint | 6.6 - Surface Inspection - Surface Finish
ba39a52d-5afa-5f3d-88c0-ac079cda4311 | note | Reference - IFC Drawings
08032dc7-a2cc-588d-bef6-43011da2d387 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
26bd390d-d702-5d64-9e19-0fa623a88256 | note | ○ Relevant Council Drawings
aecd6425-46d3-529d-9c3f-0b45ea427feb | note | — IDM SD 250
e6dc0c07-d4a6-5aec-9683-ab4208767160 | note | — IDM SD 236
e3870dc8-b0a2-516d-b8e1-bcf8f3ccf01d | note | — IDM SD 205
879693f7-f387-538e-823c-cb2e41cf9860 | note | — 703.25
3cf5dd55-6837-59ee-9027-27d4f066f875 | note | — 703.10 (a)
7326f244-670b-5c82-b12e-e697ba316677 | note | — AS3610 Clause 3.2
7c4613ed-15a7-5aed-8cba-60504f4b2333 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
e9fcb3e7-5bfd-5705-aca6-d8a255c77cd9 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
e4132a05-43e9-5c41-9825-129b285d0908 | note | ○ Class of finish:
2f55bedf-9922-5c5e-ad40-bf3d6cee8b6b | note | — Permanently hidden surfaces = Class 4
6e248fba-f7de-5562-8ff1-0b58c1000b2a | note | — All other surfaces = Class 3
bfa0b11e-0364-5c0d-9870-a4c73ad5cc23 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
27366ddc-c95e-5c15-8252-96c41d1bff99 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
5da815b1-4b88-513e-b17f-db13271b233f | note | Method - Visual
2d24a72b-6234-5d16-adda-2ff77e88aa73 | note | Frequency - Each lot
02cc790f-c1a6-5f4f-8119-579249da074e | note | Category - IP
e88791fb-7a4e-5815-9d4d-2481007f947e | note | Responsibility - SE/PE/SPE
38ef48e7-e3ec-555c-90f3-be4387db3452 | note | Verifying Documents - This ITP
3c893c9a-d962-5861-99da-50bf3dcc112d | date | Date Completed:
92d52c14-e80a-47c3-b001-6cc11ca25956 | checkpoint | 6.7 - Compressive Strength Test Results
134faccd-0dd8-578e-9291-eca73e75777b | note | Reference - IFC Drawings
248fe39c-9909-5e49-8c4c-4e8c3e4a8c07 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
9ca12349-0495-561c-8fd0-c629e4df6b68 | note | ○ Relevant Council Drawings
8faa8bfc-dcfe-5737-ba0b-6d6d1552aae1 | note | — 703.11 Table 703.111
2b5728bc-c925-5079-ac6f-65826c05a889 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
67214a5a-04a3-5b26-af65-7480cbae98ac | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
d333641a-7f71-5a4a-90ea-87191b34b965 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
7fc72417-d07b-5a7e-99e1-806e29f5a0e3 | note | ○ Attach: Compressive Strength Test Results
ffd6f37b-d2ec-53d3-b507-3b649aa72a2d | note | Method - Document Review
93e8be78-376c-53c6-9387-70e5e82bd0cf | note | Frequency - Each cylinder
736eb35a-1779-576a-a702-cc34d2bd285c | note | Category - IP
8efc96f7-1411-5d2e-9241-84a638144632 | note | Responsibility - SE/PE/SPE
96f16f05-4ae1-5bad-9b02-509595e610d8 | note | Verifying Documents - This ITP
5b254200-9463-5791-a26f-62d811db00c1 | date | Date Completed:
a7536efa-69f2-4761-a486-10e3b57f1a80 | checkpoint | 6.8 - As-built Survey
aa20041f-82ed-5b85-b659-492054924398 | note | Reference - IFC Drawings
75fbaaed-39c3-5fad-8378-602fc7ebf625 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
d5c0eb49-45e8-50ff-b90b-5ce011e97909 | note | — 703.15
9ef5668f-1836-5117-a7fa-cc4fb0866861 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
ececf87a-d386-5d39-bb58-b058c5b03e8d | note | — Departure from RL = ±10mm
3c905fbb-37aa-5a41-8135-df7119d23e85 | note | — Departure from alignment = ±10mm
57ca0656-acd1-529b-a29e-f6ec2482577c | note | — Rate of change of deviation from RL or alignment = 10mm in 10m
2793c90c-0bab-50e0-a378-15a31438b8ff | note | — Irregularities in alignment = 5mm in 3m
169febaa-af7f-56ca-9f51-62588869e375 | note | — Section dimensions = ±5mm
835a0e20-1942-552c-b56b-dfb235d8e6f5 | note | — Section dimensions (less than 25mm) = ±3mm
dd4c5d5b-ae5d-582e-aee3-c871fab312b6 | note | — Width of pavement = -5mm, +15mm
d60fa11b-4063-56e5-95a3-fe2676168442 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
efcbb82f-aa99-5bf9-ab3f-c4970ad287b4 | note | ○ Attach: Survey As-builts / Survey Report
c47718e6-cbc0-5080-974a-a66f40ebf4ea | note | Method - Document Review
eedd817b-089d-5fad-a292-d22111f301ea | note | Frequency - Each lot
9d5a9c86-10d8-5486-80ca-08effe575228 | note | Category - IP
19f52d6d-c840-531c-8001-775f4f9011a1 | note | Responsibility - Surveyor, SE/PE/SPE
8b873771-d0a1-5b90-a86d-3f843ec92367 | note | Verifying Documents - This ITP
c2dff475-6267-5bc6-ad58-77af182b05e3 | date | Date Completed:
42e4a03a-97eb-4704-a694-d171a20f4359 | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
c1e465e0-3bff-51f2-8076-d88495c01c0b | note | Reference - MRPA Quality Management Plan
f331935d-f2ee-5f9e-a27e-31c31e1f1aeb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
bdd6654d-2938-5311-b0b7-7e011c273914 | note | Method - Document Review
d03b2b74-271c-508b-90e6-9ea23b0d9a6f | note | Frequency - Once, prior to closure of this lot / element / Work area
bb59af41-6e0b-5fda-9211-cc716a49766f | note | Category - HP*
d86f9455-272c-5c0c-8520-b334823b9ae3 | note | Responsibility - SE/PE/SPE
4d9a8c63-d79d-5d06-a19d-fb1672609a15 | note | Verifying Documents - This ITP
1d79146c-84e3-5c33-8a2a-4c39b5079104 | date | Date Completed:
739ec113-8b5f-48d3-a63c-ec0f69ace02d | checkpoint | Final Inspection
46b56c0d-4ac1-5543-8c0b-2d32b094756c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fbf8e859-f71a-50c1-8506-f1bda86315c0 | textbox | Name:
e7d383f3-a6c9-5136-95e3-776122529ffb | textbox | Position:
0c806a69-86d1-5c9e-8576-622bb6a36eea | textbox | Date Completed:
2fbdd468-8e0a-4bdb-958b-5b72b0635160 | signoff | Sign ITP
d8d5d221-ad02-4f05-bf7f-a93609b77666 | checklist | ITP-292-CIV-ADL-Kerb Channel (Supply and Install) Rev 0 | itp | ITP-292-CIV-ADL-Kerb Channel (Supply and Install)
41b24c6d-9dde-4b1a-8e60-282d8d984c54 | section | 1. Referenced Documentation
12e488ed-6015-49df-a776-6a4b04a50381 | checkpoint-no-value | Referenced Documentation
8a8bf20c-bbcc-599d-9dcb-d45b4651a597 | note | Document Title: ITP-292-CIV-ADL-Kerb and Channel (Supply and Install)
69b7bb75-5f83-5aaf-8c30-69d7c17c038c | note | ITP Description: ADL-Kerb and Channel (Supply and Install)
62decb48-5b18-5323-9670-a22d61d6b6fb | note | Discipline (e.g. CIV/STR/RAIL): 292-CIV
fc21044d-2bde-572f-a599-119975798bc7 | note | Revision Number: 0
13879a1f-e4fc-5781-861a-166a23a0d1e1 | note | Revision Date: 1/06/2025
56cf1d1b-0451-5f52-af2e-646b014ffa76 | note | ITP created by: Abhi Patil
5ab6b9cb-90a0-51a7-80ad-3d2d4f878054 | note | 1.1 - Non Dependent
ec309afa-8063-57fd-8079-ca20c83b38e4 | note | Reference - VicRoads Section 703 (August 2021)
7d64d712-df38-58e0-a1f2-12a567249355 | note | ○ VR SD2001
5c2c609c-739a-50c6-b9a5-bb22247e29f8 | note | ○ VR SD2102
ab8fd2e2-4a9b-5651-b914-f5568d6709b1 | note | ○ AS 2876
ea08031e-b6d4-58ce-b91c-b1969bb907d5 | note | ○ AS1379
ace09f23-86ac-4169-afb3-dacddf43828d | section | 2. Preliminary - Materials
21db3fb3-4787-4603-baec-897a1b700046 | checkpoint | 2.2 - Mix design
c944270d-5ca5-5a4d-8391-2e9fc8b5405c | note | Reference - SD2001, AS1379 Section 703.05, 703.06, 703.07
ff4ab938-8e56-51a2-bc09-68885d691330 | note | Acceptance Criteria - Approved VR mix design to be used.
865aae95-5f9b-5467-b02e-8c3b0c3ce83b | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
e90d3ba6-7f1e-5244-9fe0-bb2bda5e6eb3 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
31002104-0c0f-52ba-ac23-a544e16cdc8b | note | ○ Attach: TeamBinder Material Approval Ref No.
59441e1a-53bb-5a91-b39e-b45f86736ce4 | note | Method - Verify, Document Review
62a73c0e-a42b-5b63-9605-0160c5df881e | note | Frequency - Prior to commencing any activity
82cbbf03-5cbb-5b6d-b70d-253c5ce113bf | note | Category - HP
cff8a1cb-2a99-5889-9cee-b3000d7329ea | note | Responsibility - Nominated Authority
7dd7c27b-0e73-5ab3-8aa4-91e4aaba82ca | note | Verifying Documents - Conqa HP Release
4238d639-1dc7-595d-b9be-0f8552840c05 | date | Date Completed:
0e2f4caa-3b83-4436-8541-e53e06336d83 | signoff | AUTHORITY HOLDPOINT
b0573f9a-6181-413b-a9ca-f8dca0130044 | checkpoint | 2.3 - Bedding Material
a9b27c6e-de44-59e4-a296-ba82bd756838 | note | Reference - Section 703.21 IFC Drawings
5650eb93-c5ee-5848-95fb-3188e4762b05 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
cafa0e59-4f00-5553-a04d-ed15a5d5cb4c | note | ○ Attach: TeamBinder Material Approval Ref No.
24d525bd-881d-5538-8999-5cd9d3c0bfad | note | Method - Verify, Document Review
58a8c329-9597-539c-800b-a01039c76628 | note | Frequency - Prior to commencing any activity
fb0b892e-348d-5aa7-9665-2e43cee206e2 | note | Category - HP
6446f4ca-2c44-598b-a10a-cc395b98d6dc | note | Responsibility - Nominated Authority
13d9698f-fac1-562a-ae74-fda593137347 | note | Verifying Documents - Conqa HP Release
0c23ca89-e507-50ac-b344-68e4149bef7f | date | Date Completed:
a79d05be-71b5-442a-bfb4-f83c722e7ae9 | signoff | AUTHORITY HOLDPOINT
a2af8dc5-2048-46e9-81bc-8cec6f85abcb | checkpoint | 2.4 - Curing Compound
023929ba-f007-57db-b24a-6a8536e8b1ee | note | Reference - Section 703.10
260fd231-a442-56f2-ba9c-ec6b86e8724c | note | Acceptance Criteria - Curing compound shall comply with AS3799
210c0a14-020e-590d-9c5f-7e17a1a1998b | note | ○ Attach: TeamBinder Material Approval Ref No.
a3149643-3e27-58e9-a64f-a5cfa239c926 | note | Method - Verify
632da26d-e25a-5d1d-888b-e9b8749139b3 | note | Frequency - Prior to commencing any activity
2af01229-9699-5360-bae3-ba53c1a4fd06 | note | Category - HP
ffed3b0f-b99f-5c2a-a94d-9514bf89bdef | note | Responsibility - Nominated Authority
c2a0b249-024a-5064-a2ee-044b2225b515 | note | Verifying Documents - Conqa HP Release
c52e4b5d-dbd4-5e99-b3fa-e4d6ea829879 | date | Date Completed:
13720e50-dee3-4dd2-8480-5f09305631c8 | signoff | AUTHORITY HOLDPOINT
fed0ab85-2e20-4857-bba8-fed5a5680cb7 | section | 3. Preliminary - Documentation
654e5434-b081-4299-a512-1fcd6e438f3d | checkpoint | 3.1 - Check for correct documentation
2bab44ca-0a18-5aac-884f-0cb7017bb389 | note | Reference - IFC Drawings
469b0a68-1704-5283-9bd1-79e9a6681361 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
37f5a406-3440-564b-8fb6-c43779cca676 | note | — Using the correct and complete set of drawings
98569bf5-0306-5a75-986e-ae5e0528ab72 | note | — All drawings are the latest version
d87967aa-7571-57f1-b2d3-ede885b6e4b1 | note | Method - Visual inspection
f6135d86-9fc2-5b20-9f5b-35ea8f5e96e7 | note | Frequency - Prior to commencing any activity
921b6cde-73fe-5051-80e3-1c5ad8e665b4 | note | Category - HP*
e955ee35-6656-5f51-bb4e-3dda291f38e3 | note | Responsibility - SE/Site Supervisor
97358bb4-169d-5aa3-80c8-59a862036c07 | note | Verifying Documents - ITP Signed
e2e5a311-b446-5140-88a9-2b58f0116b89 | date | Date Completed:
49086ba4-4adb-4740-a0e6-03c23bcb1f61 | section | 4. Pre-construction / Pre-installation Activities
22e62f9a-d142-4d24-8669-e4d80352cdec | checkpoint | 4.1 - Setting out
12784118-9e02-55b1-a0e4-8258eebb33fc | note | Reference - Section 703.17 IFC Drawings
9cab28a6-edac-54f5-89aa-57e1395b2a5e | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
12eaee67-2a01-5e36-a4c1-ea42693fe8d7 | note | ○ The superintendent will review and confirm set out.
8f821c52-cd7f-51f5-8f86-9a4c60a34d87 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
caeef032-f59c-53b3-9d06-f1044150007b | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
43755f09-fd38-576d-9aa6-e2e3cdbc138e | note | Method - Verify
a2620d8e-6835-52d6-ac50-6aa08f698492 | note | Frequency - Prior to start
9bbffab4-c61d-5bdb-bffc-75d95c869d42 | note | Category - HP
44c93a18-a154-583d-bfaf-63061e11f1ab | note | Responsibility - Surveyor/Nominated Authority
ca61e474-efb8-5d01-a060-6e0d85ac9993 | note | Verifying Documents - Conqa HP Release
adb6515d-0650-5bcc-8f46-9dd543d348cc | date | Date Completed:
a5b654f1-78c0-4dd0-87e8-78c71c1303bd | signoff | AUTHORITY HOLDPOINT
9cccadb9-62ec-4d80-ac2d-69516d880977 | checkpoint | 4.2 - Temporary drainage provisions
ce5772f5-a641-5774-9a40-4f9c57439e55 | note | Reference - Section 703.18 CEMP
846ece53-ce5e-5a1d-9a5a-a891274772ad | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
d25613f2-fa4c-5423-afa9-a9335f340e60 | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
ce9369a1-976c-5c92-9226-b53f902aac61 | note | ○ Attach: relevant written approval from relevant stakeholder.
350fa3cc-c21e-5a00-9f64-e69dcd22e5fc | note | Method - Visual inspection, Document Review
ba055a70-18e5-5599-b637-2b81083d6bdb | note | Frequency - Prior to start (where required)
f0da8d8f-cdc6-5f0a-89ae-2c9c921aa30d | note | Category - HP*
95c140bd-4b57-5ab7-8717-d8d2bc944f58 | note | Responsibility - SE/PE/Site Supervisor
f235d5ae-f135-5997-b4eb-b49550a2acad | note | Verifying Documents - ITP Signed
f4dc087d-62ba-5f79-9837-f27a28c2d57a | date | Date Completed:
be2e817e-45ce-470f-9afc-de803113f62c | section | 5. Construction / Installation Activities
cddc9843-6b86-4763-937a-9c8fdb4cefb5 | checkpoint | 5.1 - Bedding
ad5262dd-28aa-5022-b682-634847396fca | note | Reference - Section 703.21
59064a9c-66c1-5e35-abb3-e624a8b9e054 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
a0756f07-1943-58e6-ad39-394b4c10eaeb | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
85c8a42f-6065-566b-8a21-8761b07784d1 | note | Method - Visual inspection
ee225932-6f7a-5b25-9402-3201f2f567bd | note | Frequency - Each lot
94d9babb-4f70-5932-b17c-af536191a9cc | note | Category - WP
d60c4e83-362a-531e-b447-2eb846bfe53c | note | Responsibility - SE/Site Supervisor
3c1eb766-5767-5d17-af4d-02311175cf3e | note | Verifying Documents - ITP Signed
200c21c4-2438-5d66-828f-7a4a0fa4eb36 | date | Date Completed:
27fca514-d8bc-4a49-bf6c-e6290e2dec26 | checkpoint | 5.2 - Formwork
ab8fb6b3-bba0-5594-b827-b309d187f7b2 | note | Reference - Section 703.12 AS3610
86bcae6c-c277-5099-b7dc-73541ae0e116 | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
1b601e8b-751c-58f0-bad7-33d8742db250 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
8b3b72d9-acac-5ebd-a00a-af490d6764b9 | note | Method - Visual inspection
889ae981-64d8-5ff1-95a2-bcc5e5407e2b | note | Frequency - Each lot
fd450281-6c03-5029-82d0-280d8283b8df | note | Category - WP
267161cb-91e9-5675-a46b-09e82d91717f | note | Responsibility - SE/Site Supervisor
c315d35b-ac83-5fae-a89a-45ad97537b5f | note | Verifying Documents - ITP Signed
6784e982-f6c5-5133-b450-1c592e0ce825 | date | Date Completed:
f1e70e86-f0eb-456b-ad41-98ddddf79bb1 | checkpoint | 5.3 - Pre Pour Check
6ffc18f8-651e-5dd5-866e-8afd938cb77e | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
1e2a55eb-373d-5f81-9a8f-9bef61b2013f | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
5b72ac75-b971-5d91-8e5e-bd28445bca3f | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
8ff42e4f-83ff-56a4-80c3-3994917594b1 | note | ○ Attach: Pre-pour Inspection Record
25f52f5d-141f-5890-a055-359ebf2d6f4f | note | Method - Verify
0762638f-98b4-5e26-bbe5-9ad53b291712 | note | Frequency - Each lot
b9b80c20-0def-5df6-ae9c-110a1e149ad2 | note | Category - HP*
f56c6eea-3369-5b88-9ffc-451478ed8150 | note | Responsibility - SE/Nominated Authority
0fc02bdb-fa0c-527c-8f5b-d798c3dd929f | note | Verifying Documents - ITP Signed
a6e73743-f455-54bd-9748-a723e568755b | date | Date Completed:
aef4e000-4490-40b6-9a84-d2874e21b966 | checkpoint | 5.4 - Concrete placement
1fea84b6-2083-5b94-8cb4-c980c91d0710 | note | Reference - Section 703.08, Section 703.23
b4c38adc-5a09-5962-bce2-9d9fca128f73 | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
1b95fe29-0f4a-5a12-9993-a991b58997bc | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
b249b788-01cc-5f95-939a-043ff4795b64 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
bd72e0d3-7843-5316-ad3e-36ccb77521bf | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
36b90355-6bad-5166-a9a4-ffb661ab3def | note | ○ Attach: Concrete Pour Records
85facca1-4d50-50cc-9574-974e23d196ab | note | Method - Site inspection
fad3433f-f1b1-509b-b4a5-755a4859370e | note | Frequency - Each lot
023b8467-7bc3-5b0e-b544-83f932920e8c | note | Category - IP
01deebd4-a3e8-598f-9e3d-2d9c6be7eee6 | note | Responsibility - SE
c55ac425-1b43-5f65-aa61-2d398026a4a9 | note | Verifying Documents - ITP Signed
383f8b23-dc4c-5cd2-84eb-f1657c2ebe00 | date | Date Completed:
9110fdc5-f469-48df-9c21-2bf0d95f4ee6 | checkpoint | 5.5 - Transitions
bf3e3101-58ce-5152-8acf-52e2c73c3fb8 | note | Reference - Section 703.24
0e0dca17-1a1a-5e92-99eb-c2247698930a | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
eade9436-351a-5a2d-8353-8d90310e6e08 | note | Method - Site inspection
1ce3a9f7-36cf-5c3d-a43f-18b8c1d44677 | note | Frequency - Each lot
8879cda7-b109-5d1b-b0f8-303eef3b38dc | note | Category - IP
1dbc481d-d489-53b0-ac70-727ac4e57343 | note | Responsibility - SE
fb6217c1-f724-5c09-beab-9b3c70f24809 | note | Verifying Documents - ITP Signed
6521960e-31c1-5068-b509-1cf1c4e70eb0 | date | Date Completed:
e49aa3de-64f1-4f3d-bc53-aef7cdd89bbd | checkpoint | 5.6 - Surface Finish
0f0e9b32-fc93-551e-ad6a-7d57bc26d03e | note | Reference - Section 703.25
2deb9319-eec6-5bc6-b140-e834148e46a9 | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
33fba777-3029-5c6a-92c2-4af22eac91a7 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
78488366-73b6-5bbc-a853-8d61b8a4d4bc | note | ○ Concrete to have a neat appearance and uniform colour.
73fac3b3-15d1-51a3-ae64-8d313967d601 | note | ○ Class 3 finish required for external surfaces.
35b1bf50-554a-5923-8bab-cc1b9a40fb82 | note | ○ Class 4 finish required for permanently hidden surfaces.
487a5d41-6637-59a6-a117-0b6c12b86ca2 | note | Method - Visual inspection
f6cc12a3-eed9-56b7-8f13-ac80f0aff223 | note | Frequency - Each lot
c43cdcc8-168b-5f0c-b9d8-64f19ffcddd5 | note | Category - IP
24cac554-4543-5dac-a800-fad86eb5d636 | note | Responsibility - SE/ Site Supervisor
895ce5eb-da62-5232-acc5-6927e5008987 | note | Verifying Documents - ITP Signed
2afba734-7a8f-59cc-8efb-58d9a458e87b | date | Date Completed:
ce0443fe-cf18-4c82-8cc8-60b116250e10 | checkpoint | 5.7 - Formwork Stripping
679ff832-6e30-55df-bf0c-4c2a82f44c14 | note | Reference - Section 703.12 AS3610
f62351c7-691e-56f7-9e2a-6b3aadad031b | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
5c2d28be-e356-53e8-ad45-e39faa12c798 | note | — External faces 2 days
96c9a77a-e980-5c60-ad98-977a5208333c | note | — Permanently hidden faces 1 day
2fb6a320-4f31-51b9-9a64-25cff9f7bd4a | note | Method - Visual inspection
546340b2-f521-5d40-a7ad-2cacdbc1d774 | note | Frequency - Each lot
5f043000-2de3-5977-b780-af3a750ef4de | note | Category - HP*
f64eccca-0701-551c-8fcf-3b55b897aa7b | note | Responsibility - SE/ Site Supervisor
c7300dd4-1c5f-5768-a53c-c9e2c07590b8 | note | Verifying Documents - ITP Signed
e4af147b-60a0-5348-9f74-173a6229473c | date | Date Completed:
02921d77-f346-4f34-9402-407c3d78f8aa | checkpoint | 5.8 - Tolerance
28c7e97e-628c-5c5c-887a-9f83472c8427 | note | Reference - Section 703.15
45ea9153-4cf1-5649-96cd-b8fe56067c65 | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
8f091b68-0291-55f6-8161-d9d2fa60a218 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
2f17671c-4228-52b4-9f21-dd562033f288 | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
bf51c627-fe72-58ac-b0c0-3cb9460cfd5f | note | ○ Attach: Post-pour Inspection Records
2cfe95fb-9894-55e5-803f-6d783ec2ce9f | note | Method - Verify
58e04620-e7d2-58ee-ae28-b9c73bd4eb09 | note | Frequency - Each lot
1695f99d-f174-5c69-824f-dd727317e9b3 | note | Category - IP
e52847e8-efad-5236-af87-1a8e330ba26f | note | Responsibility - SE/Surveyor
36737fbb-ca7d-5dd7-a892-b728b46b237d | note | Verifying Documents - ITP Signed
e69432de-ddd1-52a5-a7c6-a0768f277ba2 | date | Date Completed:
9d811b6e-d2fc-432c-b418-3c664b9c6045 | checkpoint | 5.9 - Curing
49f2353c-ecf9-5467-bf33-3160274a4fec | note | Reference - Section 703.10
e583a81d-53e5-5eda-a2a0-abcd78f73376 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
e250a720-aa17-5fe1-929b-74471408445c | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
066c085d-c829-5a66-9f86-31b4bf57cd3d | note | Method - Visual inspection
57fc17cb-9f42-504f-9d2b-a034abbd9225 | note | Frequency - Each lot
aac37e40-8b8b-5a59-bcf3-e9ad1178e75a | note | Category - IP
799f5f2f-20d7-51c8-b08a-a9de985649ed | note | Responsibility - SE/Site Supervisor
10cdfa7d-4595-5cd3-9e99-5a92dd07b9a9 | note | Verifying Documents - ITP Signed
1f83296e-f95c-56ea-bc1d-f03cfbb51e16 | date | Date Completed:
3c99b5d1-7d67-4062-a7e7-91e3b659e531 | checkpoint | 5.10 - Joints
e000539f-cc53-5f79-8d54-61591072da78 | note | Reference - Section 703.26
8cda6387-95d9-5215-a552-3d361acd9af3 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
8b73aae7-c2fe-5074-a3b3-159d7d64458a | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
5517c01d-7816-5e0f-bce4-29f1f0058ead | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
816ae395-dbc9-5991-bb8a-b82b4e3554b6 | note | Method - Verify
9afb2d1c-1363-5952-83bd-0d2843e76690 | note | Frequency - Each joint
fce917c5-013a-5537-856e-007b0d37571c | note | Category - IP
43e1d16a-4230-5d4d-b6b9-93b131f0ad6a | note | Responsibility - SE / Site Supervisor
64baea37-494f-5fde-844d-78752fa63775 | note | Verifying Documents - ITP Signed
f56e85af-d4e5-5a42-9f80-dca880c45201 | date | Date Completed:
d5bf06f6-a22f-4088-9b4e-cbc6a9f4de4d | checkpoint | 5.11 - Protection of Concrete
dd73873b-85f1-58bb-87bd-c4d215c026d4 | note | Reference - Section 703.27
adf8a517-cee5-56e1-880a-28958f0ba8e0 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
dc864bab-002e-53d9-be14-c459b944b94c | note | Method - Visual inspection
143b3bd0-0bf5-5e8e-953c-192eeb112c79 | note | Frequency - Each lot
4b03d0e3-49ab-557a-8208-cc52d2b6875e | note | Category - IP
63311496-2eaa-5710-bda8-4f2b4f502755 | note | Responsibility - SE
810327f4-a671-57a6-a92b-3b7fa0c1cbf3 | note | Verifying Documents - ITP Signed
1ac94a1b-a8d7-5cb7-9812-8f013c10c2f9 | date | Date Completed:
0cb9269d-d346-4eb8-8920-4a75e10e113f | checkpoint | 5.12 - Bus Stop Kerb Height
47b0b6e8-3656-552b-ac0d-b58fd60f015b | note | Reference - DoT Handover Process
666a8cf4-c59b-533d-a36a-f75031fe06c8 | note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
61cbe7d7-6ebd-546d-94bc-b542e6577ccb | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
24210ff6-fc18-58b0-a6c7-d31d23cb28be | note | Method - Visual Inspection
0170d329-cd6e-58f9-9c26-58bae9a974ba | note | Frequency - Each lot
1ba353b1-5ed0-5b24-a255-4a08a1b7b698 | note | Category - HP*
92a9f12a-84c8-57d6-a7da-82bb49a85258 | note | Responsibility - SE
30250e55-bc25-5911-9c13-4018d87b856d | note | Verifying Documents - ITP Signed
8416ea5d-aed9-59b9-a701-98e481750611 | date | Date Completed:
c38c2658-336c-4ef5-82db-355ba6fa9986 | section | 6. Post-construction / Post-installation Activities
ec2d37e4-2ccd-4ddb-8b2a-877bd96e6f6d | checkpoint | 6.1 - Backfilling
be1c90d5-885f-5ee7-9e43-c9001cee4572 | note | Reference - Section 703.29
dbfdbefe-7075-5785-a54b-ac428dd48f7a | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
d4339554-7fa1-5c30-8ce1-e5ac63b6dc60 | note | Method - Verify
3a15009b-c74a-5de3-bd8b-a91b96945727 | note | Frequency - Each lot
2daae748-b6a9-5092-a823-04cacb63986d | note | Category - IP
21bf1e5d-8e8d-5f9b-b64e-f4430f55f642 | note | Responsibility - SE
f4aeb131-9fbc-5fb5-8210-dec1de171088 | note | Verifying Documents - ITP Signed
500e7670-fc4a-5b49-8f35-4faf811b62b4 | date | Date Completed:
3e2fea04-863b-4d1b-953c-43263c793c8a | checkpoint | 6.2 - Cracking of Concrete
b82b02d7-2e65-5e6a-a2e1-6b5c859ccdae | note | Reference - Section 703.30
984cfbe0-d985-585a-b22d-2ff3fa7dfec3 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
54faa997-5ba1-5b88-94e4-693e0befb029 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
add575f8-2c2e-541e-a700-bac48ce85b8b | note | ○ Attach: Pot-pour Inspection Record
b464952d-dfb6-5e58-9da3-b59537bb1bac | note | Method - Visual inspection
90134277-19f3-5517-addf-f75ea4180131 | note | Frequency - Each lot
6ab5337f-b356-566b-ab38-b288a1117d3b | note | Category - IP
ea9211ee-2471-5ef5-9aea-edd5817b8782 | note | Responsibility - SE
7716ed08-c8bc-5bfc-98d1-6d3bf9ac34d1 | note | Verifying Documents - ITP Signed
a4ed1f7b-0b6d-569a-aaa0-43b1ed3a876d | date | Date Completed:
c2dcc45f-9290-41ad-912c-2a86206c6b3c | checkpoint | 6.3 - Survey Conformance
0e66c7c2-1fb5-5a21-9ef1-4eda9e2e65c1 | note | Reference - Section 703.15
dc98f890-ac7d-59e1-9b9c-9a0bb58fea94 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
71afe6f8-0d6a-548c-bf3a-ece865885aa5 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
de757ed0-fbae-5e6f-9390-a84f9b38b681 | note | Method - Document Review
d43ee5b2-938f-5883-b08e-718b19c3eedc | note | Frequency - Completion of each lot
26112cf0-1400-5712-9baa-85bcdc757c4f | note | Category - WP
90e16df2-c2b5-5643-a52f-cb1c2508a316 | note | Responsibility - Project Engineer/ Surveyor
45387c71-4eec-5152-9cc6-0071165b6827 | note | Verifying Documents - As-built survey records
6a3bafed-6193-5f58-b1da-60afd614f1af | date | Date Completed:
371cd95c-3f4d-4d46-ad1d-e1010b36a19c | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
1cc47107-d3d0-5f42-99b7-e26f8a643efe | note | Reference - MRPA Quality Management Plan
202fddeb-466d-5bb8-a6b8-37d4a1a56219 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
0349c763-0603-5ba1-9120-2b1a5651a5c2 | note | Method - Document Review
b6c466f2-ad03-5a1f-8649-4b8633171a66 | note | Frequency - Once, prior to closure of this lot / element / Work area
08c35714-f026-512b-91ab-c4e4d406904e | note | Category - HP*
d6613723-f111-5d27-a117-6107e4f35143 | note | Responsibility - SE/PE/SPE
d055903f-19bf-5f6b-ab26-d12fae1a1b79 | note | Verifying Documents - This ITP
82f4db77-4235-53bc-a088-fc6905383712 | date | Date Completed:
27942f24-5ac8-4390-bd8a-4dea3316600f | checkpoint | Final Inspection
df6b5651-b058-5ba5-bb6b-8818ee247e0a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
771158d3-d103-5a04-8599-4e0f17eb8088 | textbox | Name:
0e2dd523-8b91-5f5c-9a82-4cfaf8d09ada | textbox | Position:
dbce6ec0-3d6f-5711-9649-3d587b4a5f85 | textbox | Date Completed:
9276009f-80e9-44af-a150-943439f7b87d | signoff | Sign ITP