## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d8d5d221-ad02-4f05-bf7f-a93609b77666 | checklist | ITP-292-CIV-ADL-Kerb Channel (Supply and Install) Rev 0 | itp | ITP-292-CIV-ADL-Kerb Channel (Supply and Install)
41b24c6d-9dde-4b1a-8e60-282d8d984c54 | section | 1. Referenced Documentation
12e488ed-6015-49df-a776-6a4b04a50381 | checkpoint-no-value | Referenced Documentation
8a8bf20c-bbcc-599d-9dcb-d45b4651a597 | note | Document Title: ITP-292-CIV-ADL-Kerb and Channel (Supply and Install)
69b7bb75-5f83-5aaf-8c30-69d7c17c038c | note | ITP Description: ADL-Kerb and Channel (Supply and Install)
62decb48-5b18-5323-9670-a22d61d6b6fb | note | Discipline (e.g. CIV/STR/RAIL): 292-CIV
fc21044d-2bde-572f-a599-119975798bc7 | note | Revision Number: 0
13879a1f-e4fc-5781-861a-166a23a0d1e1 | note | Revision Date: 1/06/2025
56cf1d1b-0451-5f52-af2e-646b014ffa76 | note | ITP created by: Abhi Patil
| note | ITP approved for use by: Romualdo Magpantay
5ab6b9cb-90a0-51a7-80ad-3d2d4f878054 | note | 1.1 - Non Dependent
ec309afa-8063-57fd-8079-ca20c83b38e4 | note | Reference - VicRoads Section 703 (August 2021)
7d64d712-df38-58e0-a1f2-12a567249355 | note | ○ VR SD2001
5c2c609c-739a-50c6-b9a5-bb22247e29f8 | note | ○ VR SD2102
ab8fd2e2-4a9b-5651-b914-f5568d6709b1 | note | ○ AS 2876
ea08031e-b6d4-58ce-b91c-b1969bb907d5 | note | ○ AS1379
ace09f23-86ac-4169-afb3-dacddf43828d | section | 2. Preliminary - Materials
21db3fb3-4787-4603-baec-897a1b700046 | checkpoint | 2.2 - Mix design
c944270d-5ca5-5a4d-8391-2e9fc8b5405c | note | Reference - SD2001, AS1379 Section 703.05, 703.06, 703.07
ff4ab938-8e56-51a2-bc09-68885d691330 | note | Acceptance Criteria - Approved VR mix design to be used.
865aae95-5f9b-5467-b02e-8c3b0c3ce83b | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
e90d3ba6-7f1e-5244-9fe0-bb2bda5e6eb3 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
31002104-0c0f-52ba-ac23-a544e16cdc8b | note | ○ Attach: TeamBinder Material Approval Ref No.
59441e1a-53bb-5a91-b39e-b45f86736ce4 | note | Method - Verify, Document Review
62a73c0e-a42b-5b63-9605-0160c5df881e | note | Frequency - Prior to commencing any activity
82cbbf03-5cbb-5b6d-b70d-253c5ce113bf | note | Category - HP
cff8a1cb-2a99-5889-9cee-b3000d7329ea | note | Responsibility - Nominated Authority
7dd7c27b-0e73-5ab3-8aa4-91e4aaba82ca | note | Verifying Documents - Conqa HP Release
4238d639-1dc7-595d-b9be-0f8552840c05 | date | Date Completed:
0e2f4caa-3b83-4436-8541-e53e06336d83 | signoff | AUTHORITY HOLDPOINT
b0573f9a-6181-413b-a9ca-f8dca0130044 | checkpoint | 2.3 - Bedding Material
a9b27c6e-de44-59e4-a296-ba82bd756838 | note | Reference - Section 703.21 IFC Drawings
5650eb93-c5ee-5848-95fb-3188e4762b05 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
cafa0e59-4f00-5553-a04d-ed15a5d5cb4c | note | ○ Attach: TeamBinder Material Approval Ref No.
24d525bd-881d-5538-8999-5cd9d3c0bfad | note | Method - Verify, Document Review
58a8c329-9597-539c-800b-a01039c76628 | note | Frequency - Prior to commencing any activity
fb0b892e-348d-5aa7-9665-2e43cee206e2 | note | Category - HP
6446f4ca-2c44-598b-a10a-cc395b98d6dc | note | Responsibility - Nominated Authority
13d9698f-fac1-562a-ae74-fda593137347 | note | Verifying Documents - Conqa HP Release
0c23ca89-e507-50ac-b344-68e4149bef7f | date | Date Completed:
a79d05be-71b5-442a-bfb4-f83c722e7ae9 | signoff | AUTHORITY HOLDPOINT
a2af8dc5-2048-46e9-81bc-8cec6f85abcb | checkpoint | 2.4 - Curing Compound
023929ba-f007-57db-b24a-6a8536e8b1ee | note | Reference - Section 703.10
260fd231-a442-56f2-ba9c-ec6b86e8724c | note | Acceptance Criteria - Curing compound shall comply with AS3799
210c0a14-020e-590d-9c5f-7e17a1a1998b | note | ○ Attach: TeamBinder Material Approval Ref No.
a3149643-3e27-58e9-a64f-a5cfa239c926 | note | Method - Verify
632da26d-e25a-5d1d-888b-e9b8749139b3 | note | Frequency - Prior to commencing any activity
2af01229-9699-5360-bae3-ba53c1a4fd06 | note | Category - HP
ffed3b0f-b99f-5c2a-a94d-9514bf89bdef | note | Responsibility - Nominated Authority
c2a0b249-024a-5064-a2ee-044b2225b515 | note | Verifying Documents - Conqa HP Release
c52e4b5d-dbd4-5e99-b3fa-e4d6ea829879 | date | Date Completed:
13720e50-dee3-4dd2-8480-5f09305631c8 | signoff | AUTHORITY HOLDPOINT
fed0ab85-2e20-4857-bba8-fed5a5680cb7 | section | 3. Preliminary - Documentation
654e5434-b081-4299-a512-1fcd6e438f3d | checkpoint | 3.1 - Check for correct documentation
2bab44ca-0a18-5aac-884f-0cb7017bb389 | note | Reference - IFC Drawings
469b0a68-1704-5283-9bd1-79e9a6681361 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
37f5a406-3440-564b-8fb6-c43779cca676 | note | — Using the correct and complete set of drawings
98569bf5-0306-5a75-986e-ae5e0528ab72 | note | — All drawings are the latest version
d87967aa-7571-57f1-b2d3-ede885b6e4b1 | note | Method - Visual inspection
f6135d86-9fc2-5b20-9f5b-35ea8f5e96e7 | note | Frequency - Prior to commencing any activity
921b6cde-73fe-5051-80e3-1c5ad8e665b4 | note | Category - HP*
e955ee35-6656-5f51-bb4e-3dda291f38e3 | note | Responsibility - SE/Site Supervisor
97358bb4-169d-5aa3-80c8-59a862036c07 | note | Verifying Documents - ITP Signed
e2e5a311-b446-5140-88a9-2b58f0116b89 | date | Date Completed:
49086ba4-4adb-4740-a0e6-03c23bcb1f61 | section | 4. Pre-construction / Pre-installation Activities
22e62f9a-d142-4d24-8669-e4d80352cdec | checkpoint | 4.1 - Setting out
12784118-9e02-55b1-a0e4-8258eebb33fc | note | Reference - Section 703.17 IFC Drawings
9cab28a6-edac-54f5-89aa-57e1395b2a5e | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
12eaee67-2a01-5e36-a4c1-ea42693fe8d7 | note | ○ The superintendent will review and confirm set out.
8f821c52-cd7f-51f5-8f86-9a4c60a34d87 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
caeef032-f59c-53b3-9d06-f1044150007b | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
43755f09-fd38-576d-9aa6-e2e3cdbc138e | note | Method - Verify
a2620d8e-6835-52d6-ac50-6aa08f698492 | note | Frequency - Prior to start
9bbffab4-c61d-5bdb-bffc-75d95c869d42 | note | Category - HP
44c93a18-a154-583d-bfaf-63061e11f1ab | note | Responsibility - Surveyor/Nominated Authority
ca61e474-efb8-5d01-a060-6e0d85ac9993 | note | Verifying Documents - Conqa HP Release
adb6515d-0650-5bcc-8f46-9dd543d348cc | date | Date Completed:
a5b654f1-78c0-4dd0-87e8-78c71c1303bd | signoff | AUTHORITY HOLDPOINT
9cccadb9-62ec-4d80-ac2d-69516d880977 | checkpoint | 4.2 - Temporary drainage provisions
ce5772f5-a641-5774-9a40-4f9c57439e55 | note | Reference - Section 703.18 CEMP
846ece53-ce5e-5a1d-9a5a-a891274772ad | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
d25613f2-fa4c-5423-afa9-a9335f340e60 | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
ce9369a1-976c-5c92-9226-b53f902aac61 | note | ○ Attach: relevant written approval from relevant stakeholder.
350fa3cc-c21e-5a00-9f64-e69dcd22e5fc | note | Method - Visual inspection, Document Review
ba055a70-18e5-5599-b637-2b81083d6bdb | note | Frequency - Prior to start (where required)
f0da8d8f-cdc6-5f0a-89ae-2c9c921aa30d | note | Category - HP*
95c140bd-4b57-5ab7-8717-d8d2bc944f58 | note | Responsibility - SE/PE/Site Supervisor
f235d5ae-f135-5997-b4eb-b49550a2acad | note | Verifying Documents - ITP Signed
f4dc087d-62ba-5f79-9837-f27a28c2d57a | date | Date Completed:
be2e817e-45ce-470f-9afc-de803113f62c | section | 5. Construction / Installation Activities
cddc9843-6b86-4763-937a-9c8fdb4cefb5 | checkpoint | 5.1 - Bedding
ad5262dd-28aa-5022-b682-634847396fca | note | Reference - Section 703.21
59064a9c-66c1-5e35-abb3-e624a8b9e054 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
a0756f07-1943-58e6-ad39-394b4c10eaeb | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
85c8a42f-6065-566b-8a21-8761b07784d1 | note | Method - Visual inspection
ee225932-6f7a-5b25-9402-3201f2f567bd | note | Frequency - Each lot
94d9babb-4f70-5932-b17c-af536191a9cc | note | Category - WP
d60c4e83-362a-531e-b447-2eb846bfe53c | note | Responsibility - SE/Site Supervisor
3c1eb766-5767-5d17-af4d-02311175cf3e | note | Verifying Documents - ITP Signed
200c21c4-2438-5d66-828f-7a4a0fa4eb36 | date | Date Completed:
27fca514-d8bc-4a49-bf6c-e6290e2dec26 | checkpoint | 5.2 - Formwork
ab8fb6b3-bba0-5594-b827-b309d187f7b2 | note | Reference - Section 703.12 AS3610
86bcae6c-c277-5099-b7dc-73541ae0e116 | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
1b601e8b-751c-58f0-bad7-33d8742db250 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
8b3b72d9-acac-5ebd-a00a-af490d6764b9 | note | Method - Visual inspection
889ae981-64d8-5ff1-95a2-bcc5e5407e2b | note | Frequency - Each lot
fd450281-6c03-5029-82d0-280d8283b8df | note | Category - WP
267161cb-91e9-5675-a46b-09e82d91717f | note | Responsibility - SE/Site Supervisor
c315d35b-ac83-5fae-a89a-45ad97537b5f | note | Verifying Documents - ITP Signed
6784e982-f6c5-5133-b450-1c592e0ce825 | date | Date Completed:
f1e70e86-f0eb-456b-ad41-98ddddf79bb1 | checkpoint | 5.3 - Pre Pour Check
6ffc18f8-651e-5dd5-866e-8afd938cb77e | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
1e2a55eb-373d-5f81-9a8f-9bef61b2013f | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
5b72ac75-b971-5d91-8e5e-bd28445bca3f | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
8ff42e4f-83ff-56a4-80c3-3994917594b1 | note | ○ Attach: Pre-pour Inspection Record
25f52f5d-141f-5890-a055-359ebf2d6f4f | note | Method - Verify
0762638f-98b4-5e26-bbe5-9ad53b291712 | note | Frequency - Each lot
b9b80c20-0def-5df6-ae9c-110a1e149ad2 | note | Category - HP*
f56c6eea-3369-5b88-9ffc-451478ed8150 | note | Responsibility - SE/Nominated Authority
0fc02bdb-fa0c-527c-8f5b-d798c3dd929f | note | Verifying Documents - ITP Signed
a6e73743-f455-54bd-9748-a723e568755b | date | Date Completed:
aef4e000-4490-40b6-9a84-d2874e21b966 | checkpoint | 5.4 - Concrete placement
1fea84b6-2083-5b94-8cb4-c980c91d0710 | note | Reference - Section 703.08, Section 703.23
b4c38adc-5a09-5962-bce2-9d9fca128f73 | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
1b95fe29-0f4a-5a12-9993-a991b58997bc | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
b249b788-01cc-5f95-939a-043ff4795b64 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
bd72e0d3-7843-5316-ad3e-36ccb77521bf | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
36b90355-6bad-5166-a9a4-ffb661ab3def | note | ○ Attach: Concrete Pour Records
85facca1-4d50-50cc-9574-974e23d196ab | note | Method - Site inspection
fad3433f-f1b1-509b-b4a5-755a4859370e | note | Frequency - Each lot
023b8467-7bc3-5b0e-b544-83f932920e8c | note | Category - IP
01deebd4-a3e8-598f-9e3d-2d9c6be7eee6 | note | Responsibility - SE
c55ac425-1b43-5f65-aa61-2d398026a4a9 | note | Verifying Documents - ITP Signed
383f8b23-dc4c-5cd2-84eb-f1657c2ebe00 | date | Date Completed:
9110fdc5-f469-48df-9c21-2bf0d95f4ee6 | checkpoint | 5.5 - Transitions
bf3e3101-58ce-5152-8acf-52e2c73c3fb8 | note | Reference - Section 703.24
0e0dca17-1a1a-5e92-99eb-c2247698930a | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
eade9436-351a-5a2d-8353-8d90310e6e08 | note | Method - Site inspection
1ce3a9f7-36cf-5c3d-a43f-18b8c1d44677 | note | Frequency - Each lot
8879cda7-b109-5d1b-b0f8-303eef3b38dc | note | Category - IP
1dbc481d-d489-53b0-ac70-727ac4e57343 | note | Responsibility - SE
fb6217c1-f724-5c09-beab-9b3c70f24809 | note | Verifying Documents - ITP Signed
6521960e-31c1-5068-b509-1cf1c4e70eb0 | date | Date Completed:
e49aa3de-64f1-4f3d-bc53-aef7cdd89bbd | checkpoint | 5.6 - Surface Finish
0f0e9b32-fc93-551e-ad6a-7d57bc26d03e | note | Reference - Section 703.25
2deb9319-eec6-5bc6-b140-e834148e46a9 | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
33fba777-3029-5c6a-92c2-4af22eac91a7 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
78488366-73b6-5bbc-a853-8d61b8a4d4bc | note | ○ Concrete to have a neat appearance and uniform colour.
73fac3b3-15d1-51a3-ae64-8d313967d601 | note | ○ Class 3 finish required for external surfaces.
35b1bf50-554a-5923-8bab-cc1b9a40fb82 | note | ○ Class 4 finish required for permanently hidden surfaces.
487a5d41-6637-59a6-a117-0b6c12b86ca2 | note | Method - Visual inspection
f6cc12a3-eed9-56b7-8f13-ac80f0aff223 | note | Frequency - Each lot
c43cdcc8-168b-5f0c-b9d8-64f19ffcddd5 | note | Category - IP
24cac554-4543-5dac-a800-fad86eb5d636 | note | Responsibility - SE/ Site Supervisor
895ce5eb-da62-5232-acc5-6927e5008987 | note | Verifying Documents - ITP Signed
2afba734-7a8f-59cc-8efb-58d9a458e87b | date | Date Completed:
ce0443fe-cf18-4c82-8cc8-60b116250e10 | checkpoint | 5.7 - Formwork Stripping
679ff832-6e30-55df-bf0c-4c2a82f44c14 | note | Reference - Section 703.12 AS3610
f62351c7-691e-56f7-9e2a-6b3aadad031b | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
5c2d28be-e356-53e8-ad45-e39faa12c798 | note | — External faces 2 days
96c9a77a-e980-5c60-ad98-977a5208333c | note | — Permanently hidden faces 1 day
2fb6a320-4f31-51b9-9a64-25cff9f7bd4a | note | Method - Visual inspection
546340b2-f521-5d40-a7ad-2cacdbc1d774 | note | Frequency - Each lot
5f043000-2de3-5977-b780-af3a750ef4de | note | Category - HP*
f64eccca-0701-551c-8fcf-3b55b897aa7b | note | Responsibility - SE/ Site Supervisor
c7300dd4-1c5f-5768-a53c-c9e2c07590b8 | note | Verifying Documents - ITP Signed
e4af147b-60a0-5348-9f74-173a6229473c | date | Date Completed:
02921d77-f346-4f34-9402-407c3d78f8aa | checkpoint | 5.8 - Tolerance
28c7e97e-628c-5c5c-887a-9f83472c8427 | note | Reference - Section 703.15
45ea9153-4cf1-5649-96cd-b8fe56067c65 | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
8f091b68-0291-55f6-8161-d9d2fa60a218 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
2f17671c-4228-52b4-9f21-dd562033f288 | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
bf51c627-fe72-58ac-b0c0-3cb9460cfd5f | note | ○ Attach: Post-pour Inspection Records
2cfe95fb-9894-55e5-803f-6d783ec2ce9f | note | Method - Verify
58e04620-e7d2-58ee-ae28-b9c73bd4eb09 | note | Frequency - Each lot
1695f99d-f174-5c69-824f-dd727317e9b3 | note | Category - IP
e52847e8-efad-5236-af87-1a8e330ba26f | note | Responsibility - SE/Surveyor
36737fbb-ca7d-5dd7-a892-b728b46b237d | note | Verifying Documents - ITP Signed
e69432de-ddd1-52a5-a7c6-a0768f277ba2 | date | Date Completed:
9d811b6e-d2fc-432c-b418-3c664b9c6045 | checkpoint | 5.9 - Curing
49f2353c-ecf9-5467-bf33-3160274a4fec | note | Reference - Section 703.10
e583a81d-53e5-5eda-a2a0-abcd78f73376 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
e250a720-aa17-5fe1-929b-74471408445c | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
066c085d-c829-5a66-9f86-31b4bf57cd3d | note | Method - Visual inspection
57fc17cb-9f42-504f-9d2b-a034abbd9225 | note | Frequency - Each lot
aac37e40-8b8b-5a59-bcf3-e9ad1178e75a | note | Category - IP
799f5f2f-20d7-51c8-b08a-a9de985649ed | note | Responsibility - SE/Site Supervisor
10cdfa7d-4595-5cd3-9e99-5a92dd07b9a9 | note | Verifying Documents - ITP Signed
1f83296e-f95c-56ea-bc1d-f03cfbb51e16 | date | Date Completed:
3c99b5d1-7d67-4062-a7e7-91e3b659e531 | checkpoint | 5.10 - Joints
e000539f-cc53-5f79-8d54-61591072da78 | note | Reference - Section 703.26
8cda6387-95d9-5215-a552-3d361acd9af3 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
8b73aae7-c2fe-5074-a3b3-159d7d64458a | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
5517c01d-7816-5e0f-bce4-29f1f0058ead | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
816ae395-dbc9-5991-bb8a-b82b4e3554b6 | note | Method - Verify
9afb2d1c-1363-5952-83bd-0d2843e76690 | note | Frequency - Each joint
fce917c5-013a-5537-856e-007b0d37571c | note | Category - IP
43e1d16a-4230-5d4d-b6b9-93b131f0ad6a | note | Responsibility - SE / Site Supervisor
64baea37-494f-5fde-844d-78752fa63775 | note | Verifying Documents - ITP Signed
f56e85af-d4e5-5a42-9f80-dca880c45201 | date | Date Completed:
d5bf06f6-a22f-4088-9b4e-cbc6a9f4de4d | checkpoint | 5.11 - Protection of Concrete
dd73873b-85f1-58bb-87bd-c4d215c026d4 | note | Reference - Section 703.27
adf8a517-cee5-56e1-880a-28958f0ba8e0 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
dc864bab-002e-53d9-be14-c459b944b94c | note | Method - Visual inspection
143b3bd0-0bf5-5e8e-953c-192eeb112c79 | note | Frequency - Each lot
4b03d0e3-49ab-557a-8208-cc52d2b6875e | note | Category - IP
63311496-2eaa-5710-bda8-4f2b4f502755 | note | Responsibility - SE
810327f4-a671-57a6-a92b-3b7fa0c1cbf3 | note | Verifying Documents - ITP Signed
1ac94a1b-a8d7-5cb7-9812-8f013c10c2f9 | date | Date Completed:
0cb9269d-d346-4eb8-8920-4a75e10e113f | checkpoint | 5.12 - Bus Stop Kerb Height
47b0b6e8-3656-552b-ac0d-b58fd60f015b | note | Reference - DoT Handover Process
666a8cf4-c59b-533d-a36a-f75031fe06c8 | note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
61cbe7d7-6ebd-546d-94bc-b542e6577ccb | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
24210ff6-fc18-58b0-a6c7-d31d23cb28be | note | Method - Visual Inspection
0170d329-cd6e-58f9-9c26-58bae9a974ba | note | Frequency - Each lot
1ba353b1-5ed0-5b24-a255-4a08a1b7b698 | note | Category - HP*
92a9f12a-84c8-57d6-a7da-82bb49a85258 | note | Responsibility - SE
30250e55-bc25-5911-9c13-4018d87b856d | note | Verifying Documents - ITP Signed
8416ea5d-aed9-59b9-a701-98e481750611 | date | Date Completed:
c38c2658-336c-4ef5-82db-355ba6fa9986 | section | 6. Post-construction / Post-installation Activities
ec2d37e4-2ccd-4ddb-8b2a-877bd96e6f6d | checkpoint | 6.1 - Backfilling
be1c90d5-885f-5ee7-9e43-c9001cee4572 | note | Reference - Section 703.29
dbfdbefe-7075-5785-a54b-ac428dd48f7a | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
d4339554-7fa1-5c30-8ce1-e5ac63b6dc60 | note | Method - Verify
3a15009b-c74a-5de3-bd8b-a91b96945727 | note | Frequency - Each lot
2daae748-b6a9-5092-a823-04cacb63986d | note | Category - IP
21bf1e5d-8e8d-5f9b-b64e-f4430f55f642 | note | Responsibility - SE
f4aeb131-9fbc-5fb5-8210-dec1de171088 | note | Verifying Documents - ITP Signed
500e7670-fc4a-5b49-8f35-4faf811b62b4 | date | Date Completed:
3e2fea04-863b-4d1b-953c-43263c793c8a | checkpoint | 6.2 - Cracking of Concrete
b82b02d7-2e65-5e6a-a2e1-6b5c859ccdae | note | Reference - Section 703.30
984cfbe0-d985-585a-b22d-2ff3fa7dfec3 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
54faa997-5ba1-5b88-94e4-693e0befb029 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
add575f8-2c2e-541e-a700-bac48ce85b8b | note | ○ Attach: Pot-pour Inspection Record
b464952d-dfb6-5e58-9da3-b59537bb1bac | note | Method - Visual inspection
90134277-19f3-5517-addf-f75ea4180131 | note | Frequency - Each lot
6ab5337f-b356-566b-ab38-b288a1117d3b | note | Category - IP
ea9211ee-2471-5ef5-9aea-edd5817b8782 | note | Responsibility - SE
7716ed08-c8bc-5bfc-98d1-6d3bf9ac34d1 | note | Verifying Documents - ITP Signed
a4ed1f7b-0b6d-569a-aaa0-43b1ed3a876d | date | Date Completed:
c2dcc45f-9290-41ad-912c-2a86206c6b3c | checkpoint | 6.3 - Survey Conformance
0e66c7c2-1fb5-5a21-9ef1-4eda9e2e65c1 | note | Reference - Section 703.15
dc98f890-ac7d-59e1-9b9c-9a0bb58fea94 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
71afe6f8-0d6a-548c-bf3a-ece865885aa5 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
de757ed0-fbae-5e6f-9390-a84f9b38b681 | note | Method - Document Review
d43ee5b2-938f-5883-b08e-718b19c3eedc | note | Frequency - Completion of each lot
26112cf0-1400-5712-9baa-85bcdc757c4f | note | Category - WP
90e16df2-c2b5-5643-a52f-cb1c2508a316 | note | Responsibility - Project Engineer/ Surveyor
45387c71-4eec-5152-9cc6-0071165b6827 | note | Verifying Documents - As-built survey records
6a3bafed-6193-5f58-b1da-60afd614f1af | date | Date Completed:
371cd95c-3f4d-4d46-ad1d-e1010b36a19c | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
1cc47107-d3d0-5f42-99b7-e26f8a643efe | note | Reference - MRPA Quality Management Plan
202fddeb-466d-5bb8-a6b8-37d4a1a56219 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
0349c763-0603-5ba1-9120-2b1a5651a5c2 | note | Method - Document Review
b6c466f2-ad03-5a1f-8649-4b8633171a66 | note | Frequency - Once, prior to closure of this lot / element / Work area
08c35714-f026-512b-91ab-c4e4d406904e | note | Category - HP*
d6613723-f111-5d27-a117-6107e4f35143 | note | Responsibility - SE/PE/SPE
d055903f-19bf-5f6b-ab26-d12fae1a1b79 | note | Verifying Documents - This ITP
82f4db77-4235-53bc-a088-fc6905383712 | date | Date Completed:
27942f24-5ac8-4390-bd8a-4dea3316600f | checkpoint | Final Inspection
df6b5651-b058-5ba5-bb6b-8818ee247e0a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
771158d3-d103-5a04-8599-4e0f17eb8088 | textbox | Name:
0e2dd523-8b91-5f5c-9a82-4cfaf8d09ada | textbox | Position:
dbce6ec0-3d6f-5711-9649-3d587b4a5f85 | textbox | Date Completed:
9276009f-80e9-44af-a150-943439f7b87d | signoff | Sign ITP