## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-292-CIV-ADL-Kerb Channel (Supply and Install) | itp |  |  |  |  | ITP-292-CIV-ADL-Kerb Channel (Supply and Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-292-CIV-ADL-Kerb and Channel (Supply and Install)
label | ITP Description: ADL-Kerb and Channel (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 292-CIV
label | Revision Number: 0
label | Revision Date: 1/06/2025
label | ITP created by: Abhi Patil
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 703 (August 2021)
label | ○ VR SD2001
label | ○ VR SD2102
label | ○ AS 2876
label | ○ AS1379
section | 2. Preliminary - Materials
checkpoint | 2.2 - Mix design
label | Reference - SD2001, AS1379 Section 703.05, 703.06, 703.07
label | Acceptance Criteria - Approved VR mix design to be used.
label | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify, Document Review
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bedding Material
label | Reference - Section 703.21 IFC Drawings
label | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify, Document Review
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Curing Compound
label | Reference - Section 703.10
label | Acceptance Criteria - Curing compound shall comply with AS3799
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Verify
label | Frequency - Prior to commencing any activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminary - Documentation
checkpoint | 3.1 - Check for correct documentation
label | Reference - IFC Drawings
label | Acceptance Criteria - Ensure that all employee and sub contractors are:
label | — Using the correct and complete set of drawings
label | — All drawings are the latest version
label | Method - Visual inspection
label | Frequency - Prior to commencing any activity
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Setting out
label | Reference - Section 703.17 IFC Drawings
label | Acceptance Criteria - Set out work in accordance with IFC Drawings.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
label | Method - Verify
label | Frequency - Prior to start
label | Category - HP
label | Responsibility - Surveyor/Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Temporary drainage provisions
label | Reference - Section 703.18 CEMP
label | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | ○ Attach: relevant written approval from relevant stakeholder.
label | Method - Visual inspection, Document Review
label | Frequency - Prior to start (where required)
label | Category - HP*
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Bedding
label | Reference - Section 703.21
label | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.2 - Formwork
label | Reference - Section 703.12 AS3610
label | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.3 - Pre Pour Check
label | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
label | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | ○ Attach: Pre-pour Inspection Record
label | Method - Verify
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.4 - Concrete placement
label | Reference - Section 703.08, Section 703.23
label | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | ○ Attach: Concrete Pour Records
label | Method - Site inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.5 - Transitions
label | Reference - Section 703.24
label | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | Method - Site inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.6 - Surface Finish
label | Reference - Section 703.25
label | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/ Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.7 - Formwork Stripping
label | Reference - Section 703.12 AS3610
label | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
label | — External faces 2 days
label | — Permanently hidden faces 1 day
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/ Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.8 - Tolerance
label | Reference - Section 703.15
label | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | ○ Attach: Post-pour Inspection Records
label | Method - Verify
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.9 - Curing
label | Reference - Section 703.10
label | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.10 - Joints
label | Reference - Section 703.26
label | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | Method - Verify
label | Frequency - Each joint
label | Category - IP
label | Responsibility - SE / Site Supervisor
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.11 - Protection of Concrete
label | Reference - Section 703.27
label | Acceptance Criteria - All concrete shall be protected from damage from early loading.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 5.12 - Bus Stop Kerb Height
label | Reference - DoT Handover Process
label | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
label | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
label | Method - Visual Inspection
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Backfilling
label | Reference - Section 703.29
label | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | Method - Verify
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 6.2 - Cracking of Concrete
label | Reference - Section 703.30
label | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | ○ Attach: Pot-pour Inspection Record
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - ITP Signed
date | Date Completed:
checkpoint | 6.3 - Survey Conformance
label | Reference - Section 703.15
label | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
label | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | Method - Document Review
label | Frequency - Completion of each lot
label | Category - WP
label | Responsibility - Project Engineer/ Surveyor
label | Verifying Documents - As-built survey records
date | Date Completed:
checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP