## Table 1
Project: PEACOCKE BRIDGES Owner: Hamilton city council
Component: |  | Bored Piles
Location: |  | Peacocke Whatukooruru Drive
Reference: |  | Peacocke Whatukooruru Drive: HCC 1298/2022 - Bored Piles
Master ITP Ref |  | QA061 Version 02
Project Code – CLL: |  | PEADOW2211S
VERIFICATION ACTIVITY |  |  |  | SPECIFICATIONS AND CRITERIA SOURCE
|  |  |  | Document Ref: |  | Title
H | Hold Point |  | Work not to proceed beyond hold point until formally released by the organisation imposing hold point | HCC 1298/2022 |  | Peacocke Whatukooruru Drive – Project Specification: HCC1298/2022 April 2022
W | Witness Point |  | Item to be witnessed by the organisation imposing witness point | BBO SS 2110 Rev 9 |  | BBO- Standard specification - SS2110 Rev9 BORED CAST-IN-SITU CONCRETE PILES
S | Surveillance |  | Item to be subject to ongoing monitoring | ASGPILES-Rev G |  | Auckland Structural Group Piling Specification” Rev G - 12 March 2002
R | Review |  | Review of reports or other documentation required under ITP | BBO SS 2140 Rev 5 |  | BBO- Standard specification - SS 2140 Rev 5 CONCRETE
|  |  |  | BBO SS 2146 Rev 4 |  | BBO- Standard specification - SS 2146 Rev 4 CONCRETE CONSTRUCTION
|  |  |  | SPERW |  | ICE Specification for Piling and Embedded Retaining Walls, Third edition, 2016
RESPONSIBLE PARTIES |  |  |  | VERSION CONTROL
|  |  |  | Rev | Date | Detail | Prepared By | Approved (DO) | Reviewed (BBO)
HCC | Hamilton City Council |  |  | A | 2023-02-23 | Issued for review | TF
BBO | Bloxam Burnett & Olliver Ltd |  |  | B | 2023-03-08 | Issued for review | HC
DO | Downer New Zealand Limited |  |  | C | 2023-03-17 | Issued for review (BBO comments) | HC
CLL | CLL Engineer |  |  | D | 2023-03-22 | Issue for approval | HC
Sub | Subcontractor/Supplier

## Table 2
Item No. | Description | Standard/Spec Reference | Acceptance Criteria | Frequency | Responsibility | Hold Point H/ W/ S |  |  |  | Verifying Record | Completion Sign off |  |  | Comment
[6 empty] | Sub | DO | BBO | CLL |  | Sub | Dow/BBO | CLL
1 | Pre-Construction
1.1 | Accepted Method Statement | Project specification | Engineer’s acceptance | Once prior to commencement of piling | CLL |  | H | H | H | Email Confirmation |  |  |  | To be submitted at least 10 days in advance.
1.2 | Accepted Inspection and Test Plan |  | Issue | Once prior to commencement of piling | CLL |  | H | H |  | Email Confirmation
1.3 | Accepted Safety Plan - SSSP |  | Issue | Once prior to commencement of piling | CLL |  | H |  |  | Email Confirmation
1.4 | Accepted support fluid details |  | Issue | Once prior to commencement of piling | CLL |  | H | H |  | Email Confirmation
1.5 | Permits issued |  | Issue | Once at commencement of piling | DO |  | H |  | H | Site Hardcopy
1.6 | Concrete Design Mix Verification |  | Issue | Once prior to commencement of piling | DO/ BBO |  | H | H |  | Email Confirmation
1.7 | Reinforcement Steel – mill cert |  | Project specification | Post Construction for every pile | CLL |  | H | H |  | Issued by supplier- email confirmation
2 | Pile Boring
2.1 | Client Notification |  | Issue | Once at commencement of piling | DO |  | H | H | H | Email Confirmation |  |  |  | 48 hours’ notice of pile drilling commencement.
2.2 | Check drill tool diameter | As per HCC 1298/2022 | Visual Inspection | Prior to commencement of piling | CLL |  | W/S |  | W/S | As per pile QAC |  |  |  | Minimum agreed diameter is 870 mm for 900 DIA piles, due to ID of permanent casing supplied by DO, and 1200 mm for 1200 DIA piles.
2.3 | Check depth gauge/instrumentation of piling rig | Operators Manual | Visual Inspection | Daily | Rig Operator |  | W/S |  | H |  |  |  |  | Operator daily checks
2.4 | Ground penetration and extraction with due diligence | Operators Manual | Visual Monitoring | Every Pile | Rig Operator |  | W/S | S | S |  |  |  |  | Operator to penetrate/extract with due diligence, no adverse effect on bore integrity.
2.5 | Check pile position/pile numbers | Drawings | Visual Inspection | Every Pile | CLL |  | W/S |  | W/S
2.6 | Pile Setout/Offsets | Drawings | Hz +/- 10mm | Every Pile | DO |  | W |  | W | Survey record |  |  |  | Due to tight plan tolerances set-out is critical
2.7 | Casing Inspection | As per HCC 1298/2022 – note minimum agreed diameters at ITP item 2.2 | Visual Inspection | Length/diameter/Wall thickness at start of piling, RL every pile | CLL |  | H |  | H | QAC - Pile Card |  |  |  | RL check pre-concrete & pre- drill
2.8 | Measure and check position and verticality | As per ASGPILES - Rev G | Visual Inspection Permitted deviation from vertical shall be not more than 1:75 or 0.8 degree. | Every Pile | CLL |  | W |  | H | QAC - Pile Card |  |  |  | Spirit level has a +-0.5 degree accuracy. Verticality of pile to be checked via use of electronic level on the side of the casings & against Kelly bar.
2.9 | Bentonite checks | Fluid Specification | Visual Inspection/Testing | Per batch, each pile prior to concreting | CLL |  | W |  | H | QAC - Pile Card
2.1 | Bentonite level | As per construction specification - Methodology | Visual Inspection Bentonite head to be maintained at 0.5m above groundwater level or adjusted as required. | Each pile | CLL |  | W |  | H | QAC – Pile Card |  |  |  | Any significant fluid loss/stability will be addressed with Project Engineer.
2.11 | Soil logging and bagging | As per HCC 1298/2022 11.7 | Visual Inspection Engineer Inspection | Every Pile | DO/CLL |  | S | S | S | QAC - Pile Card Labelled, bagged core samples |  |  |  | Boreholes are to be continuously logged on QAC - Pile Card. Material from the base will be bagged, labelled and securely stored on site for Engineer’s inspection.
2.12 | Confirmation design minimum toe depth achieved | Construction Specification/ Drawings | By means of weighted tape Designer Hold Point: Maximum depth exceedance | Every Pile | BBO & DO Rep/CLL |  | H | H | H | QAC - Pile Card |  |  |  | Visual inspection not possible due to drilling under fluid. Engineer to agree correct drill depth. Designer to be notified if drilling reaches >300mm below design RL for pile toe. Maximum depth exceedance to be 40m from piling platform.
2.13 | Base cleanliness | Construction Specification | By means of weighted tape | Every Pile | BBO & DO Rep/CLL |  | H | H | H | QAC - Pile Card |  |  |  | Visual inspection not possible due to drilling under fluid.
2.14 | Pile Boring Monitoring | Construction specification | Visual Monitoring | Every Pile | Rig Operator |  | S | S | S | QAC - Pile Card |  |  |  | Depth check, possible collapse, changing ground conditions, any unexpected occurrences
3 | Pre-Pour Inspection
3.1 | QA check on previous pile | Engineer Specification | Client notification/Engineer’s Approval | Every Pile Ongoing Engineer’s approval | DO Rep/CLL |  | H | S | H | QAC - Pile Card |  |  |  | Engineer’s approval to proceed with subsequent piles
3.2 | Reinforcement Cage inspection/ check spacers, pile bore tolerances | BBO SS 2110 Rev 9 | Alignment lesser of +- 4% DIA or +-75mm | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card |  |  |  | Pre-installation check required of all pile sections
|  |  | Height +- 50mm | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
|  |  | Reinforcement Type- As per drawings | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
|  |  | Concrete cover: 75mm, 50mm minimum | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
|  |  | Bottom of pile position lesser of +-1% pile length, +-12.5% of shaft diameter, or +- 400mm | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
3.3 | Stabilising Fluid Verification | Construction Specification | <4% sand content acceptable | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
3.4 | Pile cage installation | BBO SS 2110 Rev 9 | Engineer Inspection | Every Pile | BBO/CLL |  | H | H | H | QAC - Pile Card |  |  |  | Pile cage to be installed immediately after Engineer inspection and acceptance
4 | Concrete Placement
4.1 | Verify Concrete Mix – batch times, mix | BBO SS 2140 Rev 5 | 401T4504R | Each delivery | DO Rep/CLL |  | W/S | S | W/S | Concrete Docket
4.2 | Slump/ Spread test | BBO SS 2140 Rev 5 | Slump 100-130mm +- 25mm Spread 500mm +- 100mm | Each delivery | DO Rep/CLL |  | H | S | H | QAC - Pile Card
4.3 | Concrete level | BBO SS 2140 Rev 5 | Design +50mm | Every Pile | DO Rep/CLL |  | H | S | H | QAC - Pile Card
4.4 | Concrete placement | HCC 1298/2022 | ITP Item 3.3 | Every Pile | BBO/CLL |  | W/S | S | W/S | QAC - Pile Card |  |  |  | Pile to be concreted within the same day as Engineer’s acceptance of reinforcing cage installation, ITP Item 3.3.
4.5 | Concrete pouring – Check volume | Construction Specification | As per QAC - Pile card | Each delivery | DO Rep/CLL |  | W | S | W | Concrete docket, QAC - Pile Card |  |  |  | Concrete volumes and Tremie records to be maintained as per QAC - Pile Card
4.6 | Pile concrete overpour | HCC 1298/2022 | Visual check - Sign off by Engineer | Every Pile | BBL/CLL |  | W | W | W | QAC - Pile Card |  |  |  | Pile to be overpoured and slurry at the top of the head removed until only sound concrete is present.
4.7 | Formation of construction joint |  |  | Every Pile | DO Rep/CLL | [8 empty] | Formation of construction joint by others.
4.8 | Concrete curing (tops of piles) | BBO SS 2146 Rev 4 | 7-day wet curing required | Every Pile | [9 empty] | Concrete curing by others. Curing requirements will depend on the thickness of concrete which to be removed after concreting and weather conditions.
4.9 | Compressive Strength Sampling | NZS 3112 | 28 day - 40MPa | Batch plant sampling and testing per piles – 4no cylinders – 1no @7 days, 3no @ 28 days | Concrete Supplier – samples cast at plant | H | S | S | S | Lab. Test Record |  |  |  | On site independent testing to be done by others. Samples to be taken at batch plant.
4.1 | Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check. | As per Auckland Structural Group Piling Specification | Alignment lesser of +- 4% DIA or +-75mm Height +- 50mm Concrete cover: 75mm, 50mm minimum | Every Pile | DO Rep/CLL |  | W | S | W | QAC - Pile Card |  |  |  | As builts by others.
5 | Close out
5.1 | Pile Cut off level verification | Construction Specification | +/- 10mm | Every Pile | DO Rep |  | S | S |  | Survey Record
5.2 | Pile & Reinforcement Cleaning | Construction Specification | Visual | Every Pile | DO Rep |  | S | S |  | QAC - Pile Card
5.3 | Reinforcement to specification | Construction Specification | Visual | Every Pile | DO Rep |  | S | S |  | QAC - Pile Card
5.4 | Pile records | Construction Specification | Collation and Submission of records | Within 24hrs of completion Every Pile | CLL |  | H | S |  | Email Confirmation