## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Checklist Name
Site QA
Tier 2: First Fix; Tier 3: Zone 1; Tier 4: Fibre Works; Tier 5: Cabling | Fibre Works
Tier 2: First Fix; Tier 3: Zone 1; Tier 4: Cable Containment; Tier 5: Catenary Wires | Catenaries
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Floor Penetration | Floor Penetrations
| First Fix | Zone 1 | Office | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Assist | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Open Plan Office Space | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 2-Pax Meet (Gridline 4-5) - w/in Open Plan Space | Cabling | Lighting |  | Lighting Circuits First Fix
| First Fix | Zone 1 | 2-Pax Meet (Gridline 5-6) - w/in Open Plan Space | Cabling | Lighting |  | Lighting Circuits First Fix
| First Fix | Zone 1 | Meet / Brain Storm | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Meet / Collaboration Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 4-Pax Meet (GL1-2) - near Meet 1 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 6-Pax Board Room Meet (GL2-3) - near Utility | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 8-Pax Board Room Meet 1 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Meet 2 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Meet 3 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 8-Pax Meet 4 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 4-Pax Meet 8 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | 8-Pax Meet 9 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Meet / Focus | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Meet (Gridline 0-1) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Quiet 1 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Quiet 2 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Quiet 3 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Quiet 4 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Wellness | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Male Toilet | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Female Toilet | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Comms | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Utility (Gridline 1-2) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Utility (Gridline 3-4) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Utility (Gridline 4-5) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Utility (Gridline 4) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Vend Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Phone (Gridline 3-4) | Cabling | Data |  | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 1 | Phone (Gridline 5) | Cabling | Data |  | Data First Fix
Tier 2: First Fix; Tier 3: Zone 1; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Open Plan Office Space | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Meet (Gridline 7-8) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 10 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 10-Pax Meet 11 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 12 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 7-Pax Meet 13 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 14 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 15 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 16 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 17 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Meet 18 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 19 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 20 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 21 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 6-Pax Meet 22 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 16-Pax Meet 23 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 24 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 4-Pax Meet 25 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 10-Pax Meet 26 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Meet (Gridline 13-14) - between Open Plan & Meet 13 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 6-Pax Meet (Gridline 11) - near ELT Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 6-Pax Meet (GL 10-11) - near Tea Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | 6-Pax Meet (GL 10-11) - near Utility & Meet 20 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Meet Area - along Corridor 2 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | ELT Meet | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Focus (4nos) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Focus (2nos) | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Store 1 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Store 2 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Store 3 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Showers | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Unisex 1 Toilet | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Unisex 2 Toilet | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Utility (GL 7-8) - near Meet 10 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Utility (GL 10-11) - near Store & Meet 12 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Utility (Gridline 13-14) - near Store | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Utility (Gridline 11-12) - between Meet 15 & Meet 16 | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Wait Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Reception / Wait Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Comms | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | ELT Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| First Fix | Zone 2 | Meeting/Breakout Area | Cabling | Power |  | Power Circuit First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Lighting | Lighting Circuits First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 6: Data | Data First Fix
Tier 2: First Fix; Tier 3: Zone 2; Tier 5: Flush Boxes | Flush Boxes
| Second Fix | Zone 1 | Cable Containment
| Second Fix | Zone 1
| Second Fix | Zone 1
| Second Fix | Zone 1
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Office; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Assist; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Open Plan Office Space; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 2-Pax Meet (Gridline 4-5) - w/in Open Plan Space; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 2-Pax Meet (Gridline 5-6) - w/in Open Plan Space; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet / Brain Storm; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet / Collaboration Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 4-Pax Meet (GL1-2) - near Meet 1; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 6-Pax Board Room Meet (GL2-3) - near Utility; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 8-Pax Board Room Meet 1; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet 2; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet 3; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 8-Pax Meet 4; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 4-Pax Meet 8; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: 8-Pax Meet 9; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet / Focus; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Meet (Gridline 0-1); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Quiet 1; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Quiet 2; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Quiet 3; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Quiet 4; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Wellness; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Male Toilet; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Female Toilet; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Comms; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Utility (Gridline 1-2); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Utility (Gridline 3-4); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Utility (Gridline 4-5); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Utility (Gridline 4); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Vend Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Phone (Gridline 3-4); Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 1; Tier 4: Phone (Gridline 5); Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Open Plan Office Space; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Meet (Gridline 7-8); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 10; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 10-Pax Meet 11; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 12; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 7-Pax Meet 13; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 14; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 15; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 16; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 17; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Meet 18; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 19; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 20; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 21; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 6-Pax Meet 22; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 16-Pax Meet 23; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 24; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 4-Pax Meet 25; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 10-Pax Meet 26; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Meet (Gridline 13-14) - between Open Plan & Meet 13; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 6-Pax Meet (Gridline 11) - near ELT Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 6-Pax Meet (GL 10-11) - near Tea Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: 6-Pax Meet (GL 10-11) - near Utility & Meet 20; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Meet Area - along Corridor 2; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: ELT Meet; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Focus (4nos); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Focus (2nos); Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Store 1; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Store 2; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Store 3; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Showers; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Unisex 1 Toilet; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Unisex 2 Toilet; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Utility (GL 7-8) - near Meet 10; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Utility (GL 10-11) - near Store & Meet 12; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Utility (Gridline 13-14) - near Store; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Utility (Gridline 11-12) - between Meet 15 & Meet 16; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Wait Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Reception / Wait Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Comms; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: ELT Area; Tier 5: Power | Power Circuit First Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 4: Meeting/Breakout Area; Tier 5: Power | Power Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Lighting | Lighting Second Fix
Tier 2: Second Fix; Tier 3: Zone 2; Tier 5: Data | Data Second Fix

## Project Resources
Type | Name | Values | Template Name | Template ID
Checklist | Cable Containment |  | Catenaries
checkpoint | Supported correctly
checkpoint | Correct locations
Checklist | Floor Penetrations |  | Floor Penetrations
checkpoint | Penetration/chase marked as per plan
checkpoint | Depth/width correct for conduit/floor box
Checklist | Power Circuit First Fix |  | Power Circuit First Fix
checkpoint | Cable schedule
checkpoint | Cable size correct
checkpoint | Cabling to correct location as per plan
checkpoint | Position on elevations confirmed
checkpoint | Droppers / Starters wired
checkpoint | TV locations wired
Checklist | Flush Boxes |  | Flush Boxes
checkpoint | Correct location
checkpoint | Correct height
Checklist | Lighting Circuits First Fix |  | Lighting Circuits First Fix
checkpoint | Cabling to correct location as per plan
checkpoint | Emergency lighting cabelled
checkpoint | Number of fittings correct
checkpoint | Local switch wire installed
checkpoint | Sensor control wire installed
checkpoint | Cabinet lighting confirmed / cabled
Checklist | Data First Fix |  | Data First Fix
checkpoint | Cabling to correct location as per plan
checkpoint | Cables to floor box
checkpoint | Data for TV locations
checkpoint | WAP locations wired
Checklist | Fibre Works |  | Fibre Works
checkpoint | Cable size - Number of Core
checkpoint | Cable route
checkpoint | Splicing
Checklist | Power Circuits Second Fix |  | Power Second Fix
checkpoint | Outlets installed, level and labelled
checkpoint | RCD outlets correct rating for space 10mA/30mA
checkpoint | Starters installed
checkpoint | Floor boxes fit off
checkpoint | Kitchen outlets / Isolators / HW kits
Checklist | Lighting Circuits Second Fix |  | Lighting Second Fix
checkpoint | Correct light type installed
checkpoint | Correct number installed
checkpoint | Correct location
checkpoint | Local switching installed
checkpoint | Sensor installed
checkpoint | Emergency lighting type installed
Checklist | Data Second Fix |  | Data Second Fix
checkpoint | Outlets installed, level and labelled