## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b18356c1-5f8a-437c-83e5-9720811232d0 | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
2e12ca9a-75d1-4db9-bd33-e67b895aa82f | section | Details
b93dd107-ae84-404a-b853-635a850413a2 | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
a9f81f30-296e-582b-9f04-1481ba6302bd | note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
ee64ff38-89fb-5f9e-8dcd-ef4083b76437 | note | Check Item - Check Item
66f25b62-6cac-538c-9cc8-b091600dc981 | note | Reference - MRTS02 Cl. 5.2
861af258-a629-4185-a101-02312914c715 | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
7c2aa7d2-544b-5313-bb7d-0dc5f5fc3a8d | note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
78cd9ce7-f2ca-52ed-9a03-65c4c670a006 | note | Check Item - Hold Point 1
f55f12f9-ea7e-518e-a8db-22f359aa15f3 | note | Reference - MRTS02 Cl. 5.3
c0b8c8d8-0319-46c4-8ab2-72acd1a2d74b | signoff | HOLD POINT
307d939b-1351-4d4d-99a7-1654240bb071 | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
39480fd6-3e00-5449-8707-4c6eed768da1 | note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
d971856c-b19d-5661-8ee9-7199b124e267 | note | Check Item - Check Item
44598ef7-2007-5041-b4a2-21de17bafb65 | note | Reference - MRTS02 Cl. 5.6.4
662ed944-9099-4541-b304-4af86c6a01b0 | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
15fd7952-09a6-5ec3-a419-d0e98064e396 | note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
9b463d14-2d94-50bb-a1b9-9433d53738cb | note | Check Item - Check Item
601fbbb1-1db9-5614-b4eb-2d24458a35e1 | note | Reference - MRTS02Cl. 5.6.5
b44ab435-8e11-407a-a5b0-09ff7422fefd | checkpoint | Traffic may be altered from its existing route via the following Cl 3.8 MRTS02.1
a7f18632-4381-5556-9a2e-c57c34229db4 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
c580e7af-7d76-5c1c-80c1-e7e7911bb895 | note | Check Item - Check Item
85da46c5-576b-53a6-87ef-fd3996f24b80 | note | Reference - MRTS02.1 Cl. 5.7.4
f82c6a86-4a27-4f66-b613-9d66eca7a3c5 | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
f51423c1-1aef-512c-826b-ff36f01a1fe7 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
0039ff46-5c31-55e5-ad70-e7a324e7ec1a | note | Check Item - Hold Point 2
8f3b1239-5c76-5bb4-9066-4df1d3681729 | note | Reference - MRTS02 Cl. 6.2
134457f3-01c8-4eee-99fd-3892233f2547 | signoff | HOLD POINT
be59f750-7b75-4822-9de6-8ebc86402319 | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
54057a35-84cd-5894-8f1d-57968c28bed1 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
0790c79c-9347-5d81-b84a-eb53768da20f | note | Check Item - Milestone
4e08b119-6208-5c37-881e-7e42a10527c8 | note | Reference - MRTS02 Cl. 7.5
c14218a3-5839-4bc5-a809-51164e9a96ea | checkpoint | The following requirements for side tracks shall apply as Stated in MRTS02.1 Cl 5.7
29b40d4d-8791-5e41-9804-4f5c83c012ef | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
525178cf-8387-57e1-a9dc-59d4f4651d8f | note | Check Item - Check Item
49a629b5-1d17-57d6-a4ab-15dd34a49663 | note | Reference - MRTS02 Cl. 6.5.3.3
f1659213-d85c-4881-a49e-b2bdfa46d2b1 | checkpoint | The following additional control measures are required to mitigate end of queue crashes as stated in MRTS02.1 Cl 5.8
54edf8a8-9065-54a5-8a8b-26ed297d1d0a | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
653ee4c4-b84a-5d7b-9d62-dbb145d427de | note | Check Item - Check Item
a15e5937-c7b5-5149-8c14-270eaced693a | note | Reference - MRTS02 Cl. 6.5.7
d60a74a8-0df4-4dc4-b728-9a845c222e0d | checkpoint | On asphalt and bituminous surfaced pavements, when permanent linemarking will not be in place outside working hours, temporary raised pavements markers (Stick and Stomps) are to be installed and maintained on centre lines, lane lines and edge lines at spacing of not greater than 25 m (except for side-track tie-ins where spacing shall not exceed 5 m). Temporary pavement markers shall only be in use for a maximum of 48 hrs and shall be replaced by linemarking after such time. If the Contractor is unable to complete line spotting by the end of each day’s work and the road is to be trafficked, the Contractor shall delineate all separation and lane lines as above. Existing longitudinal lines are to be removed by abrasive blasting or approved other method approved in writing by the Administrator when temporary lanes are in place
4c048cab-87be-5e0f-8a28-e4b9005ecc41 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
4b63884b-1d4d-59e7-b474-a424cd1d9651 | note | Check Item - Check Item
1a317992-aa1e-51e5-873c-9998f17d7072 | note | Reference - MRTS02 Cl. 6.5.8
a80e2db6-0095-43f8-ae5b-3e8c9271b4f2 | checkpoint | Temporary road lighting shall be installed in accordinance with MRTS02.1 Cl 5.12
7dd9adbf-342b-50ab-b864-beb78216f5f8 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
c24b255e-4110-5a59-a109-f1c159477ec4 | note | Check Item - Check Item
d8caf43f-a798-549b-8827-077c856506f8 | note | Reference - MRTS02 Cl. 6.5.13
756c41d6-3d0c-4113-93c5-900f936909b0 | checkpoint | In addition to the requirements of Clause 7.1, there is a need for an independent review to establish conformance with the approved TMP and TGS and with the performance requirements of MRTS02 – Provision for traffic
f8175400-7e63-5d13-9c7e-6bb0dcb7a841 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
58c3a22d-284f-5804-a9aa-1deefdb29474 | note | Check Item - Check Item
83cf0267-6ab9-59bb-a8cc-1cd546153bd7 | note | Reference - MRTS02 Cl. 7.1
8960719d-5134-4417-80ed-bde1cb3cbbad | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 8
9a138c96-c60c-5167-981c-278b0e541062 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
ee5d7700-1358-591d-a106-f4e7f234fa02 | note | Check Item - Check Item
ac634eb1-2d3f-5662-a749-f75ecd5e1302 | note | Reference - MRTS02 Cl. 9
7e49a44a-20a6-4d0b-8f8c-6b1a02c85b62 | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 9
2a5e76c8-131c-5147-9090-7fcc8e6ad652 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
61fa3710-2943-545f-a07d-035b4b906653 | note | Check Item - Check Item
abd38891-a594-5f09-8e12-1c513300bce7 | note | Reference - MRTS02.1 Cl. 9
beaffb40-c63c-463c-93fd-b42ce218db8b | checkpoint | Final Verification
25f0a74f-4eed-5e4c-a2de-bad60dc6005d | note | Project Manager Verify that the Above has been Constructed according to Specification
1632aedc-1fcb-5814-860f-542f1325e76b | textbox | Print Name:
0d8bfe38-c459-59c1-87f6-c8f25277b42a | date | Date:
9da09b64-4f5c-5ac7-8800-668bcca80b6a | note | Client Verify that the Above has been Constructed according to Specification
a0a8b147-994c-597a-a8cf-9d11bf29d3d4 | textbox | Print Name:
b4b1afbd-5181-580d-836a-4b8913385007 | date | Date:
ce0652da-eb9d-4e55-bcc2-22baf022e1c4 | signoff | Signature
b1129ed0-8fae-40db-9161-44217223b6d2 | checklist | 03.41 - Rock Protection | itp | 03.41 - Rock Protection
3cd09632-e18b-4e45-85db-146dd0ccd4a3 | section | Details
bd077679-8a76-438d-bfe6-8470a5b595c8 | checkpoint | Rock complies with size requirements specified on drawings, otherwise shall be not less than 150mm and not greater than 500mm. Rock shall be well graded with not less than 50% larger than a size twice the minimum specified
f8a0de25-0e7e-5910-b943-9f9071071cf0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e83db44-f325-50ec-8745-6f42fbfca493 | note | Check Item - Check Item
f6dbba65-89ec-5f39-ad4d-62eab26eb7f4 | note | Reference - MRTS03 Cl. 35.2
c95e0151-3951-40e6-9794-b468956c1a4b | checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
8622933d-cfba-5061-a4d8-cb02b809fb42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3f0dabe2-f6f8-5661-b155-bee066b13507 | note | Check Item - Check Item
c3a2af08-73d7-5afe-8c6a-1f403bdf9013 | note | Reference - MRTS03 Cl. 35.2
df099ca4-7e9c-4510-8b47-bf41e1f2efd3 | checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
b555c07a-3094-5cac-9397-d7f0a2f7cdaf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b76bbec1-b437-5c34-ad17-97b055c5bcb4 | note | Check Item - Check Item
d04c6c04-0e74-5961-aef0-8459259763d2 | note | Reference - MRTS03 Cl. 35.3
85730f3e-d9ba-4ec5-aa88-d7034a08bf38 | checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
b75ed5aa-f215-5d19-a7ac-9d942f267d99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4d44fad5-76e9-56a4-bd9c-d39ff43454ea | note | Check Item - Check Item
20c39408-d61e-5402-a0ba-28702272602c | note | Reference - MRTS03 Cl. 35.3
3ef1d4b8-0284-48a9-aa48-16d10e2b76a4 | checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
d99c03d1-1206-5b7d-806b-e2129ff878e2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b515c9aa-c5e3-5b6f-9339-fdcc1e990f9e | note | Check Item - Check Item
8fee6002-4dfd-566d-86ab-f8d41bcade92 | note | Reference - MRTS03 Cl. 35.3
8284bbd2-ba97-4a30-8447-89d244c51c1d | checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
a069d796-cb64-5050-997d-f4523baeacdc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8131191c-c210-58c0-9f20-1723dd7d11f6 | note | Check Item - Check Item
dd649b77-add1-5ae2-9e30-a213367439c2 | note | Reference - MRTS03 Cl. 35.3
8fc82d45-57db-4cde-8c5e-c711138adc97 | checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
d7e9fe5f-bdc3-5cbb-b9a5-2131a563926b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
be8d8647-b7c8-5f9e-b4d7-053e11bdcf0c | note | Check Item - Check Item
e5446081-d264-5251-8847-a0cd52009391 | note | Reference - MRTS03 Cl. 35.3
c9b5ea6c-3ab2-4acc-ad63-21523f6b9ae0 | checkpoint | Final Verification
ac16e7d4-3eb1-5eb5-bc62-807ef93a348f | note | Project Manager Verify that the Above has been Constructed according to Specification
563e6757-89ed-5887-8e3c-4256440ab3d4 | textbox | Print Name:
3fdfeabe-16a7-5f78-b0c3-5cc2495f697a | date | Date:
c2a5ba59-6ef5-576a-832b-65dcd4d2a78e | note | Client Verify that the Above has been Constructed according to Specification
ee369afd-55fc-58fb-8111-851cbedf4b16 | textbox | Print Name:
a540780c-f6ce-5f91-b4e3-a11c8d3be91d | date | Date:
821a9d5f-a6b6-4198-a5ff-f716c4092498 | signoff | Signature
b963ae48-a399-4988-ace9-e8d202b092fa | checklist | 03.49 - Soil Nails | itp | 03.49 - Soil Nails
e11b119b-e2b5-468a-b37c-33bc190443da | section | Details
ffd546f4-28d5-4eb8-a139-617690243b74 | checkpoint | At least 14 days prior to commencing any work which involves the installation of soil nails, the Contractor shall submit to the Administrator a construction procedure which details the method of drilling, installation, grouting and testing of the soil nails. No work shall commenced until the Administrator has deemed the construction procedure suitable. Including corrosion protection method
d79faadd-6ee1-5a95-85a4-691c33501c4b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
871b4e2f-9b62-5ec7-abde-473666298d27 | note | Check Item - Hold Point 1
bcf7d766-479b-5301-ba6d-0003282a1da0 | note | Reference - MRTS03 Cl. 49.2
d215469e-803e-4e68-8d46-6bce89c35ce8 | signoff | HOLD POINT
37d7a8ec-5eff-44ae-abff-1c67b1b8110c | checkpoint | All materials shall comply to the design drawings. Soil nails shall be DYWIDAG GEWI bar. Couples and spacers shall be as per the manufacturers requirements.
d1f24530-e70f-5332-adb3-b5ea3e662810 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2ac79963-2cb1-5086-a8a9-98f18463fc4d | note | Check Item - Check Item
fdcbdf55-40c5-531d-85a1-e3169c3b34a9 | note | Reference - Project Drawings
ba7410e1-5f02-4800-9e7b-f7eff7a335c6 | checkpoint | Cement Grout shall have a minimum characteristic strength of 40MPa
5be35f04-8212-522c-8c10-4b4a38ad1095 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
deecac89-817b-51ce-b400-028ab0279100 | note | Check Item - Check Item
fd65b69e-816b-5a46-805f-20fe4320ee52 | note | Reference - Project Drawing
32117b94-b811-4c2c-9e1d-dbf2d4480e01 | checkpoint | Soil nails shall be installed in the locations and in addition, with the details specified in the drawings. Drawings detail 3m vertical spacing and 1.5m horizontal spacing
b670d1ed-2145-5a3a-b651-1faefe224d92 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a4581332-5522-5654-ba01-ed72fc1b02af | note | Check Item - Check Item
b86d2830-71ce-5e2e-a7f0-5a11fd04699c | note | Reference - MRTS03 Cl. 49.4.1 & project drawings
010c4892-98f0-44e1-a409-676440ac8897 | checkpoint | Prior to soil nail installation, clean the debris in the drill hole by air flushing or any other acceptable method. Reinforcement shall only be installed in a clean hole free of debris and foreign matter. Grouting must be carried out within one hour after installation of reinforcement. A sacrificial grout tube shall be attached to the bottom end of the soil nail. The soil nail shall be carefully positioned into the hole with a minimum of disturbance to the surrounding soil material. Soil nail installation and grouting shall be carried out 24 hours after the holes are drilled
c472506f-7c59-5411-aacb-1fa17ee30b60 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c02760f8-1382-5db8-9df0-24efbebbf9d5 | note | Check Item - Check Item
230b0447-8e4e-58fb-b9b5-eebfc5ed6798 | note | Reference - MRTS03 Cl. 49.4.3
1775eb47-b4a2-499b-ba4f-75709927b9e5 | checkpoint | All soil nail testing shall be undertaken in accordance with MRTS03 Table 49.5. Acceptance of the test results for soil nails shall be subject to the approval of the Designer.
21fff43f-7019-5eb6-8c24-4f4f734dbcd4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
398153af-57f8-54ae-a87e-eb6400b3ac5a | note | Check Item - Hold Point 2
1222c8a0-aa75-5844-8c5d-7325393fe32c | note | Reference - MRTS03 Cl. 49.5
f49e43cf-9509-429e-b0e9-9090b539cebc | signoff | HOLD POINT
9f8f4716-ca73-4f1b-a0c1-029b3f35d6b8 | checkpoint | Final Verification
7384ba33-be2d-5d65-94d8-91c9ef659224 | note | Project Manager Verify that the Above has been Constructed according to Specification
db717f9a-2ce5-5dd8-8c6d-8852deef1954 | textbox | Print Name:
87bf1a11-c499-530c-b748-c337cb29bc38 | date | Date:
0c30cd0e-afe4-540e-bb50-2fb8d77e9eff | note | Client Verify that the Above has been Constructed according to Specification
3c0686e7-dc81-51d2-9ea5-0e30084f6f99 | textbox | Print Name:
41a31f26-84e2-5156-8546-ff8145cd737b | date | Date:
ed5bd708-aa49-4f11-b840-3713c69933b8 | signoff | Signature
36f8c227-644d-47bf-9481-f337f44103d5 | checklist | 04.01 - Clearing & Grubbing | itp | 04.01 - Clearing & Grubbing
c73f4815-f1c6-458d-a21f-cae173e589f9 | section | Details
4b3c0de7-31df-4e98-9773-17c571461561 | checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
5ffe9436-572e-5a2a-82ff-1b9486895833 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6efa0fc9-86a4-59c3-a943-88289f001282 | note | Check Item - Check Item
e833c70b-358c-5e9b-b13c-f0c943923d5b | note | Reference - MRTS04 Cl 7.2.1
607af010-4c63-4af5-b3c4-1e452f759047 | checkpoint | Tree Protection Zones installed as per Arborists recommendations
e8fd987c-5898-5608-aec2-9b0ba9c2ed23 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c9b2e8c2-7772-562b-bd32-47ea1a74729c | note | Check Item - Check Item
01333fa0-aafb-57dc-8050-3dc7f96f04bc | note | Reference - MRTS51.1 Cl 9.1
ee9e48d6-1bc7-47ca-95f1-fc1283d0532b | checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
afceadcf-5e3c-5660-8850-d067486b7b05 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f543db90-5bd2-521e-ae31-5ea84f87d18b | note | Check Item - Check Item
a3cbbf25-30c6-5cbe-8a3e-9a02e6714d27 | note | Reference - MRTS51.1 Cl 9.1
9f316cc9-1953-4ac3-bd63-8deba2e56475 | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
5d161239-6229-5bd5-9f5e-d6d685bab4d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
33b528d6-e2fd-5161-b0ec-263bd9f8988c | note | Check Item - Hold Point 2
c65f449c-b83f-5ddd-9de9-537fb53d1e71 | note | Reference - MRTS04 Cl. 7.2.2
4ed12a3d-de58-452a-b39d-4a6b4d745427 | signoff | HOLD POINT
2f8863df-c251-430f-beb7-bfb21f178b1a | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
520271a6-03ce-558e-95da-f51d281d3d78 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8d8b6687-aef9-5c0f-8afd-e721ea68118b | note | Check Item - Hold Point 3
5b74bc61-3711-5d83-88be-3d9a341cf708 | note | Reference - MRTS04 Cl. 7.2.3
ddad088c-3c2f-48a5-9342-8849e5fa3e9e | signoff | HOLD POINT
224e6ea6-7932-4f0b-9c86-bd9324ad8caa | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
18c7edcb-2a92-50e4-81a2-6a87eb222ccb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b841397a-d46c-5e37-b2e6-bec2262fbf18 | note | Check Item - Hold Point 2
0e39e5bf-cfbd-5ea7-b9af-049ea8a7b9cf | note | Reference - MRTS52 Cl. 7.1
b413155a-7825-4305-847b-a35119acccc1 | signoff | HOLD POINT
7e33b6ba-5e9c-48eb-a024-82ae7dffd131 | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
16509741-6ca2-5c72-b658-82f2c565da72 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
59d3d948-fae4-5999-8173-68d8a412e047 | note | Check Item - Check Item
fb944140-f83e-5d75-a96b-8cb97cb42e1c | note | Reference - MRTS04 Cl. 7.2.5
468655c8-74ac-462e-b7cc-958de924f1eb | checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
0a253041-45b9-5136-9b3c-4e5618ffdd0a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e07041e0-4206-57ba-ac6d-9abef4f3163b | note | Check Item - Check Item
a118dd61-1534-50c4-97c5-b8e9c8463b4a | note | Reference - MRTS04 Cl. 7.2.7
a2af99ab-b569-4113-a202-a523d7c38c04 | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
636485af-e854-5538-b5ca-7205b508d36e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9f80d802-2a67-5269-a5bd-32d09f0ca3bc | note | Check Item - Check Item
49abc2de-77fa-556b-a090-ad6cd82c750b | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
c252d98f-e185-4f46-bc14-f277655c86a9 | checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
97279222-83dc-51c4-8655-4f55b28ee3ba | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3d74112b-adb1-57d9-b865-6e95343abee5 | note | Check Item - Check Item
a8e6c5d9-d66e-5d2c-be8b-8f18a2e39f4a | note | Reference - MRTS04.1 Cl13.1
9b61e292-28e1-4e32-a3b7-9915b29dcf82 | checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
ab00e3df-32f2-5cd1-bdca-4d13a271aebf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
50907235-ef66-5f5d-8ab9-d32c100e473f | note | Check Item - Check Item
71f7ae0a-bb80-5bef-ba6d-47f53fd39bd3 | note | Reference - MRTS04.1 Cl. 1.1
60326519-3ee7-4eec-ace0-1ae76edb5dc1 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
a49d87e0-1051-55bd-ac80-49141fdcd645 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
92b59f96-9847-5db9-9063-8621e7840458 | note | Check Item - Check Item
fcf7a50d-425a-5ae8-983f-3c6369844d8b | note | Reference - MRTS04 Cl. 8.4.3
7088bb62-7bc0-45ec-bc81-a5f942932b29 | checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
8b887f41-bed3-53c5-bd7c-518c20d00e38 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
69d35f1d-960a-5eb3-8bf2-339227a0e16b | note | Check Item - Check Item
52d50079-c4f1-500a-858b-46e0531efcf0 | note | Reference - MRTS04.1 Cl 1.4
3c7499a5-0dda-469e-98df-a101807f0de9 | checkpoint | Final Verification
cf6eb950-ad1e-54a2-92e8-2bc66997dd24 | note | Project Manager Verify that the Above has been Constructed according to Specification
5be08f34-5fd7-5155-81a1-3ad255c91b96 | textbox | Print Name:
5471b0b2-7d40-5cd7-9f6c-776872f9b0ef | date | Date:
a719ae0f-1db0-572d-8c9a-2b9026f1b82f | note | Client Verify that the Above has been Constructed according to Specification
e2d5b0a4-ef25-5da8-bf33-78404cfac132 | textbox | Print Name:
8542f1db-0868-5ed0-9737-a065190585a9 | date | Date:
b816f3c6-df25-4596-999e-43111bf43280 | signoff | Signature
40c6fea1-cecc-46fa-9d69-43254e30d9c0 | checklist | 04.04 - Ground Surface Treatment | itp | 04.04 - Ground Surface Treatment
9834bfc2-ea61-4ddf-876f-190972f3b58c | section | Details
20a69a72-a617-4e98-9c63-b80054a1b845 | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
51ad0194-1c0a-50a3-873d-1c1b829ab640 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6994a461-8f40-560e-9b47-05dc7124c095 | note | Check Item - Check Item
6a8c78d4-db1e-5f81-ba40-188529950110 | note | Reference - MRTS04 Cl12.2.1.1
e7fe31d6-90c3-4b36-9f9e-f9b4ecf3c23b | checkpoint | Holes and local depresions filled with similar material and compacted in accordance with Cl15
e3567150-6732-5d2d-9ffb-adb046b56c37 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d7f7dbb8-f10e-57ce-bd38-5017824e3f67 | note | Check Item - Check Item
0ef971f7-5fd2-5e10-b4b9-3cc4f0c26a25 | note | Reference - MRTS04 Cl12.2.1.2
a1c77c11-631e-4bbb-a2f0-0578ad161490 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a depth of 300mm using appropriate methods.
cb83718f-60da-506e-8207-04a86da9bf9d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3c839308-19c0-5908-897c-3d5e97614a46 | note | Check Item - Check Item
826c9f4b-e14c-5c92-bbf3-c6aa46379029 | note | Reference - MRTS04 Cl12.2.1.3
84ab949e-d135-4dd3-bbd6-22caed4f0fa9 | checkpoint | Construction Testing Requirements: Test Method
2fc77800-8dbc-5e39-8e8c-936ce1373f0a | note | Acceptance Criteria and Frequency (Project Specific) -
a3979412-abf0-50bd-9b83-796f72d9505b | textbox | Max. Lot Size
49640964-f455-5c8f-b406-e55083963846 | textbox | Min. Testing Frequency
a695aac4-f1df-5e70-a9a4-ab7098291b0a | textbox | Min. No. of Tests
b8319cc1-c8ff-5719-a5cb-7356413f3bae | note | Check Item - MRTS04
1e6390e1-b3c5-5830-b80c-330085b74eaa | note | Reference - Table A1
43c4612f-fa1a-4705-ac92-b2e4660f0b27 | checkpoint | Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
2c9b7447-8a6e-5ae3-b224-8e5616369b8d | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: 5000m2
7e62df70-4fc8-5feb-ab1d-d6e46043fb46 | note | ○ 1 per 500m2
8b1a9155-3cd7-5f9b-afba-9be6e76db545 | note | ○ 1 per lot
a553ea4d-91df-5ceb-a4eb-4c4cbd15bade | note | Check Item - Check Item
6d3eb4a1-e5d8-5a1d-9c23-896f633c2876 | note | Reference - Table 15.3b
03bb9c32-5626-4767-a8af-075bf4b93ba4 | checkpoint | Final Verification
a2076b31-186c-5a11-b9ce-2d6fe9170d62 | note | Project Manager Verify that the Above has been Constructed according to Specification
fc3972a2-7f33-5fc9-baf1-a88d5a680968 | textbox | Print Name:
44076eed-ed93-5880-a744-9b769c936c9c | date | Date:
00dbec3d-e2d0-5a87-9c85-7da1b541afd1 | note | Client Verify that the Above has been Constructed according to Specification
b7abb15a-7ce8-5603-b626-6a025d2ddade | textbox | Print Name:
5373f80c-d301-5968-bfcd-6806746e2bd1 | date | Date:
8ad9bd92-de36-4256-b300-b90b7cace225 | signoff | Signature
8e4c73fc-4336-410c-bb06-cc72a6a671ad | checklist | 04.05 - Embankment | itp | 04.05 - Embankment
b685baf0-4bf0-446c-8bae-7b3f42e48adb | section | Details
3736bcec-20c5-401a-bbe7-0a5d21bfe733 | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
477c6c2e-cae9-56af-82a5-29d63c7d967c | textbox | General Fill Class:
183b4996-c709-5227-bc0e-03fe2345a621 | note | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
7f8358b4-d378-57ff-a8bc-215bedeb331b | note | ○ WPI< 1200, PI>= 7,
9e73fe51-dd93-5fd7-bb60-5b5a3cc27475 | note | ○ % passing .075mm 15 - 30
c23ed425-a490-5edf-b28c-152f62646b80 | note | General fill material Class B
66f236e5-52ec-5e02-b891-66c041fd8daa | note | ○ 1200 < WP < 2200
249bc18d-4ff4-5784-a5bb-cf7a6cf0711f | note | General fill material Class C
b6c2a2f6-b281-573b-8940-a80369e28b6e | note | ○ 2200 < WP < 3200
f77ebce1-bfdf-554a-a47e-127cb455ebda | note | General fill material Class D
f44777c9-2118-5f56-8795-b68d311a2dfa | note | ○ 3200 < WP < 4000, PI <=50
baae737c-0a61-54c7-ac2a-bd7b07733ea9 | note | – CBR as Specified
5bba0be5-8ef0-51fe-b531-58fb34a2825e | note | Check Item - Check Item
24c5a33b-f576-5428-bd18-a53f3f8f997d | note | Reference - MRTS04 Cl14.3.1 Table 14.3.1
a0f1c358-9465-4352-9bfe-b3a2ed0e0277 | checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
aa4d289d-90d8-5dfd-a267-d3034a40d102 | note | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
0ac8b57d-1edb-58ea-943a-67cae6a20db7 | note | Check Item - Check Item
5d2ae24b-d859-566e-973d-8844181881ac | note | Reference - MRTS04 Cl14.2.3
48801216-aaec-4a49-bd49-59d3ec0506d8 | checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
5d641c65-06cc-5db2-84a4-93b2a8c9f35b | note | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
7b777ad8-60fe-5cdb-8d8b-67c7f0cd8529 | note | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
aa917101-ec38-5156-8ac8-3640b7495335 | note | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
1778cc08-70a2-5640-912e-8e74f527212a | note | Check Item - Check Item
2f4971da-b59b-4c08-aa35-4a8e73f39fee | checkpoint | Compaction methods suitable for material type
31ae2148-d8c6-5577-abbf-3a6b7fdb39f5 | textbox | Compaction Method:
1b3841ff-3db9-5991-ab1b-7870657cacb6 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
eadf6c57-d757-5796-ab53-8a6e1f68eba9 | note | Check Item - Check Item
08b90306-fb52-5d0f-86c3-9bf3b25af97a | note | Reference - MRTS04 Cl15.2
420bcab3-18ab-4f13-b48e-29efa01dfc4a | checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
1f927365-60cb-51ee-917c-2286e69cc61d | note | – General Fill 150-300mm
d337d64a-bb99-5d7f-9fed-0bea32714be1 | note | – Fill in Water Retaining Fill 150-200mm
15628084-aff3-5efd-85ac-59f00757a582 | note | – Subgrade 100- 200mm
10b72e56-6932-5bfa-82f0-fbda3e65d46d | note | – Backfill except Sand 100mm-100mm
4748b359-d156-5e68-9667-0b02169d5551 | note | – Sand 150-300mm
8a304d34-1228-5f05-8c85-8f1807f7e6d5 | note | Acceptance Criteria and Frequency (Project Specific) - RDD%
84b107f9-a3e5-59b8-ba10-13c62321fa7c | note | ○ Insitu - >95%
44fe0528-97bf-5e26-91f4-257247b1c136 | note | ○ Bottom of Excavations - >95%
97272e27-0ad4-52b1-ba5d-dd29ba0cc5fa | note | ○ Subgrade (A/B) - >97%
ccdf5e91-1302-511e-b62e-f07f8ab39a75 | note | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
abcd4ad0-1580-577b-be37-50603cafc2e9 | note | ○ Road Embankment(A/B) ->95%
f0bcdbcc-461e-5b68-94ba-4a52b692c98d | note | ○ Road Embkmnt(C/D)' -90<96%
7e41e1f5-799f-5b0d-aaf3-315cabfd2626 | note | ○ Road Embkmnt(C/D)* ->95%
ec22f4e8-f176-553c-a4fe-14297ad2e344 | note | ○ Levee Embkmnt(A/B) - >97%
2de0ff73-df62-510b-8acd-9d41f6c286f8 | note | ○ Backfill(Sand) - >70%
576ee5d1-1232-596c-8ab6-e173c5ae6746 | note | ○ Backfill(Not Sand) - >95%
295dc138-c78e-5bd7-aa2b-ca597d7dbab5 | note | ' High Rainfall Zone
3f9d54de-371e-5212-b44c-c1f97d898080 | note | *Low Rainfall Zone
aff23774-8c58-5754-92ca-392e1b47d104 | note | Check Item - Check Item
f1c495fe-aa39-50c3-bf77-06699960b762 | note | Reference - MRTS04 Cl15.3
81408654-5043-4d8c-9108-1c74ce9b140b | checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
c92999b5-61c6-5763-a3cc-36ed8785165b | textbox | Rainfall Zone:
6e121335-6e50-5181-b9f6-8361209ab4d1 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
f1ffae78-358f-56e5-93f5-7f53d97089ca | note | Check Item - Check Item
a9dcd6a6-23c0-53ad-a7b9-65e0241099fc | note | Reference - MRTS04 Cl15.3
5e2710c5-8532-46c0-a23f-0acd0342da35 | checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
b672088d-188d-5dac-a456-4d4c6528919e | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
1083cd9c-7bce-5622-9c54-862223e4bb99 | note | Check Item - Witness Point 4
8ddf53e7-16f2-56cd-b2e5-c5acc922c831 | note | Reference - MRTS04 Cl15.4
2b58c803-977b-45ea-ba21-4f1a8a40dd48 | checkpoint | Geotextile placed at interchange between compaction methods
86a0af1c-653b-5e20-b816-45d30dd5cb96 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
21ca3dfd-2713-5908-8fe5-07851f97c35b | note | Check Item - Check Item
0a444605-869a-512c-b73f-e703977393cb | note | Reference - MRTS04 14.3.2
999ba28f-a325-456a-8828-0b7070102e72 | checkpoint | Within Geometric Tolerance
063175fc-ce21-57c5-b27f-17bd36bc0b5b | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
b6984ae2-06e7-52a1-9933-8fae13bc1a68 | note | Check Item - Check Item
10d40536-1d93-5daf-adb5-fb049d92c5f3 | note | Reference - MRTS04.1 Cl1.2
9ad5ecd2-ddc8-4667-8020-688356efe71f | checkpoint | Construction Testing Requirements: Test Method
27cbea48-53c5-524a-bbf5-9dfb9cfe7b7d | note | Acceptance Criteria and Frequency (Project Specific) -
143967af-d4a8-5c0a-99a8-c65a50211023 | textbox | Max. Lot Size
b2fb1149-d83c-5a81-af94-7d657ed12e2c | textbox | Min. Testing Frequency
1bb2afff-9a50-5429-9823-435d1999ecfe | textbox | Min. No. of Tests
4604325d-6f77-59ba-92cc-51e6c9c4d5eb | note | Check Item - MRTS04
46b6efe7-e2ad-5ec1-92b3-081cfb9ee779 | note | Reference - Table A3
a977fcd8-c2c7-585a-bf90-d824a9be0b28 | note | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
23ae7057-bc4f-4819-ab9a-de3d4c5582f2 | checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
32bda170-9163-5383-bad8-514042ceb5a6 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
a192d4e9-3b60-5303-acad-647975783332 | note | ○ 1 per 500m2/per layer
6a39b130-739e-5f67-83c8-6001d14ad30c | note | ○ 4 per lot
6b58e746-a586-5618-a6b0-02f069873a98 | note | Check Item - Check Item
a351fe3b-f547-523c-8995-25b434393843 | note | Reference - Table A1
9cf61eb6-aaa1-4743-ae2a-8725cbe87ab1 | checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
69134843-f5ca-52ef-8b95-42eaeead37cc | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
476372c8-4f7a-5b45-bc52-27a21f1c980d | note | ○ 1 per 500m2/per layer
131a04f5-5434-5c85-9e7b-98ab56cd7c6c | note | ○ 4 per lot
38d9d23e-232a-592d-8e32-c5372e6f9025 | note | Check Item - Check Item
2d510139-bbcb-5b47-8c86-9df0f5d5f0d8 | note | Reference - Table A1
1851d425-c314-42f6-9853-7d988968b42f | checkpoint | Grading: Q103A
db19788f-8b64-5d49-9571-995dfa5098b0 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
9debfb71-4548-5b42-b224-a754be8de91c | note | ○ 1 per 1000m2/per layer
30273e1f-c878-5070-b53f-7f497b15f665 | note | ○ 2 per lot
1828cc9f-679f-5b51-b06d-7078a9721ae6 | note | Check Item - Check Item
8fa79f5b-a245-5e78-8169-ed95397bab79 | note | Reference - Table A1
cc6fef5d-7322-42d9-a49c-56cdeea53b35 | checkpoint | Plasticity Index: Q105
777bf6dd-4d3a-59a5-8015-d804ec15e652 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
28c02ccd-a2a9-5bc9-9054-bb71ef174c14 | note | ○ 1 per 1000m2/per layer
30ef1f99-0161-58be-9d87-06192cc44ed5 | note | ○ 2 per lot
2d6aa551-cf44-579b-8e91-44ffe6755661 | note | Check Item - Check Item
50c11df2-3d9f-5e4b-8779-5894a669ebf8 | note | Reference - Table A1
bbff3f76-5542-4eb9-90eb-271202d9ed6a | checkpoint | Stockpile Testing Requirements: Test Method
c6ef4897-429e-545b-ae83-adeed3b19680 | note | Acceptance Criteria and Frequency (Project Specific) -
ce5f7e44-e7c3-5316-9165-63cabbb7da78 | textbox | Max. Lot Size
3fcb8774-5362-5bb0-b393-a44b43b0f048 | textbox | Min. Testing Frequency
1efc5c54-e2ca-5e6a-94ac-61a4658eca2a | textbox | Min. No. of Tests
e42c7548-aabb-5608-a063-17c37a8ed0a0 | note | Check Item - MRTS04
767abd7f-069e-57cc-ab40-72ef52006a76 | note | Reference - Table A3
dfa9bd43-df6f-4c75-9e4a-679d58801c19 | checkpoint | Grading: Q103A
8d970149-4924-5041-93e6-05694f395d24 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
d85c1bcd-0b34-5cc3-9409-98fd762146bb | note | ○ 1 per 1000m3
d7a4df26-a354-5676-913a-3dce0eadaca9 | note | ○ 2 per lot
e66a91fc-9c3b-54d1-a3de-4d3984320852 | note | Check Item - Check Item
66c9cb8c-dfe6-5070-bc6b-c5ea3bcc4335 | note | Reference - Table A1
d1769a2b-6b6f-4ed3-b9c4-b5295db99dd9 | checkpoint | Plasticity Index: Q105
4b413dd9-7267-59fb-8a0a-f37cc4d4da96 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
2e945d2c-087b-5d8e-b2a6-25f1f988017d | note | ○ 1 per 1000m3
445e74df-b4d7-59f9-886e-8862994aa7bd | note | ○ 2 per lot
717b2b12-dfbd-508d-b4c8-af5706c04505 | note | Check Item - Check Item
56f9db72-26ab-5d57-8430-d674ff6572d8 | note | Reference - Table A1
b9d3f870-9185-41a9-9151-728fa360aae0 | checkpoint | Emerson Class Number: As 1289.3.8.1
46cb2dc4-a176-51fc-98cc-5004b18a4fba | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
0b1acd92-905b-58a8-8fae-e99d8a75b65a | note | ○ 1 per 1000m3
cd85c4d8-eab3-542d-b094-7c7f19fb88db | note | ○ 2 per lot
2ec31e5b-e9bf-5079-aa71-3e654d62eee0 | note | Check Item - Check Item
11b5c336-bb0a-54b2-be22-30ad2082bb46 | note | Reference - Table A1
c3e04380-9761-4ce6-8631-63519ce0e1a0 | checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
d7cecef1-d122-52ef-bc82-d95f982ce28e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
89d92f85-8414-5cd7-89a4-0234cf5cffa1 | note | Check Item - Hold Point 8
84115944-9aea-52f2-8dfb-f1f4b84fc001 | note | Reference - MRTS04 Cl. 14.2.1
2bcf0ce6-60dc-408c-9962-17e61c1a4736 | signoff | HOLD POINT
1967962e-9125-445d-9ac2-8c9e88e41729 | checkpoint | Final Verification
34034a8f-887c-5a1f-9ab2-d83560b155cc | note | Project Manager Verify that the Above has been Constructed according to Specification
be6f1e9c-eec0-545d-b88d-6b5090981d49 | textbox | Print Name:
82a25dcf-3c61-54e8-9cb5-5f9a0769093d | date | Date:
d31fcc56-dacf-5141-bac9-f11a6feade85 | note | Client Verify that the Above has been Constructed according to Specification
2ddccbf9-1fb2-53ae-bf74-55ea95eb7cb3 | textbox | Print Name:
086eba70-7293-5119-843a-13080f157cc1 | date | Date:
fd9fc5a5-f515-48f8-80c0-45d96f2d95a1 | signoff | Signature
5f44e249-67fb-48a3-90f0-22f17f894cdd | checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation
4c9d1e23-6497-4280-92e5-286438e89c70 | section | Details
ca65a336-c6c2-436f-a7a4-96e013a12fc4 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
62822380-963b-5f72-832c-c703fad18838 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
289752b2-0786-5b73-b137-410dd2440120 | note | Check Item - Hold Point 4
8d48d36f-c3a4-5903-9ab4-b0b32acb22e6 | note | Reference - MRTS04 Cl. 9.4
f174e539-1e84-46a6-96a0-2e70c266992e | signoff | HOLD POINT
88455864-7493-490d-85fa-7df41cf54cb3 | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
7ca27b59-8026-528d-87c9-d23d27a4fee5 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
62f61cb8-1061-5948-9c01-14fe47903299 | note | Check Item - Hold Point 6
99fbc2cd-d85d-53a5-9d8c-707879c8f2ce | note | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
9e087d28-610a-4165-b05d-057c4fce1fa3 | signoff | HOLD POINT
c31978bb-f2f7-4a9a-85c8-a794a0d5c145 | checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
e5fafb27-fb70-523b-ba4c-d54df3e2f1bf | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
3526cc00-0184-5a19-91e1-2ce996a6f633 | note | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
98fbf577-7d35-510f-8942-da2177ff76e7 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
a512f76b-b533-5416-9ad9-c1536b9f226a | note | Check Item - Hold Point 6
fcb66b15-b06c-546f-b414-4d5d52492d89 | note | Reference - MRTS04 Cl.13.3.2.2
21f0058a-8316-4946-a1bd-5ef1c3075ed7 | signoff | HOLD POINT
36aff4c9-e414-43a4-8abe-1cb9d453282d | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
f884fe45-e203-54e9-883c-ad391166edf5 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
747a2e48-5ad8-54f7-92a2-6322586abb62 | note | Check Item - Check Item
9cd1427a-976f-5c22-91cc-9fb3583313f1 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
81882432-e897-48b3-a323-e8b28e9315e6 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
d23221c9-dc32-5517-bdc0-d8f447f43771 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ce5a1f11-8dc0-55af-b240-74b4d6aac898 | note | Check Item - Check Item
e0106efe-eb76-5c4f-ac4e-ab8744614633 | note | Reference - MRTS04 Cl. 13.3.3.3
155469f4-94ee-4dee-acce-6bc09a8fea7c | checkpoint | Dewatering of excavations shall comply with requirements of EMP
bf19cc3c-2351-526c-a331-3d52b370c969 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f2881ef6-edfc-5e02-bd2b-1004a6bec30e | note | Check Item - Check Item
e9e3ccd9-1407-53bb-8a40-bc7f83ae8328 | note | Reference - MRTS04 Cl. 13.3.8
d2cda90e-22de-47b7-a31c-e2fbe3efbc22 | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
81ef2136-15fd-5754-95fc-f612eaa8910f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ea156ae6-7dd6-5c2f-988e-7d030c7cddac | note | Check Item - Check Item
6dd58d1b-d1bb-595c-b1ac-d10baf03108b | note | Reference - MRTS04 Cl. 16.1
115d634e-89ef-4416-80ef-1051823993e9 | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
86c29772-748e-5c0d-8397-3b35b4667a07 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a29ae8ab-9997-574a-9d67-0be2ed559de4 | note | Check Item - Check Item
a5eca7d7-c2b5-5685-a4b4-bec3867d69f5 | note | Reference - MRTS04 Cl. 13.3.2.4
ecd44b48-0bb1-4e7f-a38b-4b079b1c56ad | checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
b78af405-feab-55ef-afab-db04f4234561 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
102feb42-cd95-5666-b6e3-2647beadc1aa | note | Check Item - Check Item
04b5c4fa-f173-5d11-868f-dbfe03080b6d | note | Reference - MRTS04 Cl. 13.3.3.1
5f321813-5892-423a-ba2e-fb86735c15f3 | checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
32168bdf-a759-5aa0-8650-d6e7404c1e00 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2fee71ed-6a26-5e85-9bcd-1ce7f030dcdc | note | Check Item - Check Item
847ded59-3b7c-514b-bf74-9aaf012ae31e | note | Reference - MRTS04 Cl. 13.3.3.2
9fdeac59-32c5-492a-a695-fa657b8761ca | checkpoint | Final Verification
3d24949b-f02e-5685-93d3-7749eefcfe0b | note | Project Manager Verify that the Above has been Constructed according to Specification
7f40c4ad-000a-5265-a9c0-189103149f71 | textbox | Print Name:
bbbdc336-ecf6-5e91-8333-627e8b2f1e36 | date | Date:
35984f3b-ec6e-5237-b1b3-69656c759379 | note | Client Verify that the Above has been Constructed according to Specification
62575e0c-b8fc-5466-a935-ff85143bd9f3 | textbox | Print Name:
4915d86f-bd4c-5c3d-9bdb-e5b5bb89395f | date | Date:
ebf9c710-5300-45d4-ba94-24c764042d5a | signoff | Signature
997ee584-1c4e-499a-8883-d682da87ccb7 | checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil
8a0d399f-f422-4d4e-9acb-3e0226358640 | section | Details
14975a73-47b8-4c67-b5ef-6d7a099e1b39 | checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
04f3bf15-2339-54b0-b353-5919734c25da | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e6b4980e-da79-581f-9f2f-4139a12b30e4 | note | Check Item - Check Item
d5a0aaea-7e8f-5ed8-a662-8bfae024003e | note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
14c452fa-1f82-4925-9502-a87d3a6afca3 | checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
a4f75933-95f6-538c-824f-4d905e2f70be | note | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
b29299d8-0c2e-50d7-83a4-a6a2ea6022b6 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
d787468f-b1fd-5ad4-b1b3-3cc8ef530f6a | note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
070c21db-0a3c-5f8b-8da7-5025fd2f6097 | note | Check Item - Check Item
5711d517-632f-56a1-a139-774a91bdd612 | note | Reference - MRTS04 Cl. 8.3
8ee2db65-b22b-4394-b9e7-abeb3eed7469 | checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
2b8b09e7-b3c2-5968-94d0-0e7002fa61f5 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
f9172530-99a1-5808-b567-fb6026b5c50f | note | Check Item - Check Item
580afadb-737a-59eb-9304-75b14fafad46 | note | Reference - MRTS04.1 Cl. Cl. 5
b8cfe1f8-343f-48fd-938a-305410114f23 | checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
6c57dfc1-c1ec-5e74-89fc-c3e3f59b5f4a | note | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
19787187-7426-5553-959b-a7a52d1fbc3e | note | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
2ababd4e-b632-566e-ae06-d0a9018cab6a | note | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
66813ff6-5215-54a5-b9f7-2dd5a750e401 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
7739731b-a287-52fa-84eb-55837cfa23a1 | note | Check Item - Hold Point
4f3039d1-6c50-5967-97c4-f0d23fc64305 | note | Reference - MRTS04.1 Cl. 2.2
200ce81b-2242-46a9-a17b-88dc896b681f | signoff | HOLD POINT
9b3623f9-599a-4d36-8a4c-d2db58e261e7 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
d0ee1245-076c-50a1-af8c-22d922330e15 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
7327a3ee-57a3-580b-bee5-40cfa85218b1 | note | Check Item - Hold Point
fcc5d8e4-c654-50b1-b511-d3a5a24a9f92 | note | Reference - MRTS04 Cl. 8.4.3
98a7a82f-dfaf-4268-95e4-8d968743457c | signoff | HOLD POINT
70366a06-a021-4f9b-afe4-d0c38c1e25e8 | checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
a1549426-b60b-5ac5-aa9e-9384f890b0ba | note | Topsoil Stockpiles are;
89e85704-5347-55c3-ae56-34d08508a158 | note | ○ Less than 3m High
bd0f15f6-9a99-5f1a-ab91-c1e4e441ac47 | note | ○ Less than 10m wide
228b72d5-a397-506f-8fc2-06c1985def7f | note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
f2910cd4-bc09-5607-9d52-c018267db39b | note | ○ Stockpiled for the minimum duration
77e96812-c00d-50ee-b18f-291fc300b62a | note | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
307b4a79-5c7b-5473-9d74-94f8c010c306 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b4e0e75f-20d7-571d-9cdb-6cb9709865cc | note | Check Item - Check Item
6634c7bf-3735-5779-bcbd-3e2b006f14c1 | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
a53c0e4e-e36c-4672-ae68-706228519864 | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
4e7c2d3e-70c7-5f21-9f63-c0460c30ff76 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
462758d9-251d-5ea7-8454-78583d2d3b60 | note | Check Item - Hold Point 2
d5b2540f-a822-5f93-9fb1-b67c105804eb | note | Reference - MRTS52 Cl. 7.1
e8eb5d16-6086-4b53-8aa0-f9542253682f | signoff | HOLD POINT
5a9a473a-1a87-46b5-a3fb-18e4d3d12988 | checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
5b252f5d-b6a8-5da4-a108-efbfeae91533 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
67c12b03-c36d-518c-8db4-ae2553f9759c | note | Check Item - Check Item
95021e4e-c4c4-5e03-9096-e6bd64f61903 | note | Reference - MRTS04 Cl 8.4.5
81894b36-dbab-4760-9a17-960fb73fe081 | checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
e0e0efed-5d7d-5f0c-83fd-006f8665155d | note | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
5a25702f-1729-50e0-81f2-be1f643359c2 | note | Check Item - Survey Report
fd27c362-c2cb-5d14-8ca7-6d511de1cc75 | note | Reference - MRTS04 Cl 8.4.5
77a41ca1-41fc-42c2-8a49-4bdb038e7761 | checkpoint | Final Verification
13e4c424-7c58-5309-9ac4-6ab0a53c3c01 | note | Project Manager Verify that the Above has been Constructed according to Specification
f732049c-33c9-5eb8-bfc9-f1047c760a63 | textbox | Print Name:
f86a71f1-30f0-5e2d-bd35-bc9bd528f561 | date | Date:
9b230565-1932-5485-a2aa-df964279bf0b | note | Client Verify that the Above has been Constructed according to Specification
aed05484-38c2-5e03-8e25-051823f33964 | textbox | Print Name:
4a90de6f-b14e-5edc-8855-d3168b15c0ff | date | Date:
cf9e9570-2d1e-438b-8203-79eca1610865 | signoff | Signature
ec336096-a380-4f14-bf23-2376c25edc68 | checklist | 04.09 - Subgrade | itp | 04.09 - Subgrade
24633fc2-379d-485a-9cb9-a339c47beefd | section | Details
a39025d3-92d0-451f-81be-54cfd58307f6 | checkpoint | CUTTINGS: Tests conducted in accordance with MRTS04 Cl 18.3.3.2
711d845b-cbb9-50fa-bc0a-4c41b3ad9437 | note | Acceptance Criteria & Frequency (Project Specific) - RDD
26494c5f-4ad1-5d3a-a689-6b607c2d0357 | note | Check Item - Check Item
94a10583-5539-5ab2-bec8-061f532666be | note | Reference - MRTS04 Cl 18.3.3.2
8464b670-2c95-48e4-8c65-00ec28026e7b | checkpoint | Work stopped when excavation has reached sugrade level. Contractor shall carry out the requirements of the relevant provisions of Clause 13.3.2.1
81fad2b7-155a-573c-b2b1-a83446d63cdb | textbox | Specified Subgrade Treatement (A-K):
f2ec2d17-2c3b-5549-abad-cd7335ef69b4 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 Table 15.3-A, Table 15.3-B
6df1ad83-c89d-541a-835f-9ee29073ad1b | note | Check Item - Hold Point 8
148804fb-9693-53c5-8aad-73e78030000b | note | Reference - MRTS04 Cl13.3.2.1 Cl18.3.3
dfb7bdf5-4684-40f7-8c81-f24cb10b8bdc | signoff | HOLD POINT
7a506cef-65a1-4fd1-83bb-202f9c3c90ac | checkpoint | General fill material used for construction of subgrade where embankment or cutting treatment using general fill, if used in road embankments must comply with Cl 14.2.4
38f3c601-4e5e-55a9-8030-9c3af0317e14 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Embankment ITP or Related Lot)
734f9583-46ef-555d-a4be-dcaabd596142 | note | Check Item - Check Item
ec1b06e1-731f-5613-86e4-c3e973ae9974 | note | Reference - MRTS04 Cl 18.2.1
1f8b3dab-bc1b-48eb-b482-b287a170f48e | checkpoint | Unbound pavement material shall conform with the requirements of MRTS05 Unbound Pavements and shall be at least of the subtype specified in Clause 12.1 of Annexure MRTS04.1, or where no such subtype is specified, at least subtype 2.4.
8b143b46-2a44-5c20-992c-4e002b553dda | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5eb033a6-1ca1-5abe-95d8-8e49761f1564 | note | Check Item - Check Item
b237ce87-2590-55e6-96d5-db5b6b4ac032 | note | Reference - MRTS04 Cl 18.2.2
5574be4d-271d-452f-8d6d-7d83c6d548c7 | checkpoint | Quarry Registration Certificate submitted to Administrator 7 days prior to sourcing high permeability drainage materials.
fcc9d3fc-f676-56b6-bca2-bec7753cefcc | note | Acceptance Criteria & Frequency (Project Specific) - Written
6e036846-1413-54ea-8949-1e3cf24de98f | note | Check Item - Milestone
a1179932-cda8-5959-a786-83e8a2d98de3 | note | Reference - MRTS04 Cl18.2.4.1
892a66ea-c3c0-4b6c-b6b9-0f9ef4ca365f | checkpoint | A mix design shall be submitted atleast 14 days prior to commencement of subgrade stabilisation
49ff86e6-a094-53e1-af0a-86c48eeda4b7 | note | Acceptance Criteria & Frequency (Project Specific) - Written
da81c700-ea0e-5583-ba16-3038f2ff5b06 | note | Check Item - Hold Point 11
803123a6-ebd5-5938-9a7d-2fbe80e5a9e7 | note | Reference - Cl18.2.5.4
efccaffa-d2ba-4bd5-970d-7afb9bfcd5bf | signoff | HOLD POINT
037e1371-c6a6-48e5-81fe-a0856f1a40a4 | checkpoint | Subgrade and underlying work tested and conforming prior to placement of pavement.
bb5feffb-2ad9-52e9-9e32-5cf56e7e9863 | note | Acceptance Criteria & Frequency (Project Specific) - ITP
3bef8d2a-7138-56f1-9e90-9aa1537c508e | note | Check Item - Hold Point 12
b82b7649-dae5-52ae-9d26-80d51a202399 | note | Reference - MRTS04 Cl18.3.1
8d8aa541-a0b1-469b-b7f1-b54aa5dbce8c | signoff | HOLD POINT
59b9162d-6bfb-4f58-a459-d0a8f923eff6 | checkpoint | Subgrade material provides a stable dense surface displaying no vertical movement under proof roll
cac4022c-ff1b-57a0-bf35-8edbc7432b24 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Delfection, Continuous
5407ebbc-bd9f-5878-bdd3-f9fd05ec7f58 | note | Check Item - Witness Point 8
a54a0c67-0454-5d34-b950-d39ad6c3963b | note | Reference - Cl18.3.2
29d18155-4145-4feb-a2e6-1f0e0ea134b3 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
87ea8dd8-d7ea-58d3-944b-93f0220e4ddf | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Tolerances: Table 6.3.1, Subgrade (individual results) = +25mm, Subgrade (average) = +10mm
c45100e7-730b-532d-bfec-ab9bccde488c | note | Check Item - Check Item
5bd1cdbc-35cc-5d73-b276-715f84af33e8 | note | Reference - Cl 18.3.3.1
caf43e06-54c0-4cb5-a88f-952be5e52ea3 | checkpoint | Quality Verification Requirements Test Method
b30c5d3e-6a91-58f9-a7d0-ef3c7f899922 | note | Acceptance Criteria & Frequency (Project Specific) - Max. Lot Size, Min. Testing Frequency, Min. No. of Tests
36b26ee7-d3c6-5c59-9e94-dcbd224f821c | note | Check Item - Check Item
ab5afcd7-e1c1-5abb-83a9-c004de7d21b9 | note | Reference - Table A.2
a75b1f37-34da-4072-aad2-514239196a89 | checkpoint | Compaction/Moisture Ratio: AS1289.5.4.1 or AS1289.5.7.1
625f8ee3-8398-5b2e-8f32-befc9c91183b | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 500m2 (per layer), 4 per lot
74e956c2-6b9a-575a-8727-4da4584e9734 | note | Check Item - Check Item
48ebccba-e90f-5beb-9922-71488e00e564 | note | Reference - MRTS04 Table A.2 No. 2.11
b3c95692-be9c-46cb-997a-edcd4657024c | checkpoint | Grading (AS1289.3.6.1), PI (AS1289.3.3.1 or AS1289.3.3.2), WPI (Q252)
fae207bb-fd47-5976-8782-36619a74f872 | note | Acceptance Criteria & Frequency (Project Specific) - 2000m2, 1 per 1000m2 (per layer), 2 per lot
af4ef3a4-4066-52ee-b42b-3f01672e94d9 | note | Check Item - Check Item
d9b307c3-d598-521a-bbdd-e427372dc2fc | note | Reference - MRTS04 Table A.2 No. 2.11
61dadce4-1783-4904-a8bc-49aef097cf34 | checkpoint | Geometrics, Horizontal Position
49622f98-eb64-5a18-ad1f-1a64be53c360 | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
b8ee1def-33e6-5b7b-946d-e42bc3c077c5 | note | Check Item - Check Item
5ec33e32-452b-5052-985d-fed1da9af047 | note | Reference - MRTS04 Table A.2
884e02c4-86c3-45f5-92e2-a9809d6d1ae2 | checkpoint | Geometrics, Vertical Level
46dfc255-9df8-5e3e-b728-bc252502e417 | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
e7c6dcd7-8e75-5f2d-aedd-2011b38f29e6 | note | Check Item - Check Item
a02fdf28-f548-583f-8945-6597cec34699 | note | Reference - MRTS04 Table A.2
7ada1866-a06b-488e-90ab-d3d34299cd99 | checkpoint | Geometrics, Deviation from a straight edge < 25mm
134ffb2e-5ff5-5808-b1d3-e066b171d453 | note | Acceptance Criteria & Frequency (Project Specific) - All edges and interfaces (at 20 intervals)
a589f8c5-6c5c-5489-902a-5188549ea8b5 | note | Check Item - Check Item
3586303b-f7e0-566b-995d-80d639351f0a | note | Reference - MRTS04 Cl 6.3.2
268727a4-0c4e-4ff0-915a-3f5c3264a70c | checkpoint | Final Verification
73e6a7cd-4dc6-5608-a354-d6704e5ec6fb | note | Project Manager Verify that the Above has been Constructed according to Specification
09de2e19-f903-585b-8ed7-dae4e4ed22d1 | textbox | Print Name:
7121303e-7cd7-5cb8-afa5-2ef6aefd0278 | date | Date:
2817b983-dbc9-5d11-8d9f-b97e9fa62c20 | note | Client Verify that the Above has been Constructed according to Specification
f3d99a53-f5cc-56cf-9299-2558ed8dabfe | textbox | Print Name:
f53fe233-4b61-5d7b-88a6-d49cc5faa503 | date | Date:
b243f02f-1f28-4b22-a070-4ed1c5366c9d | signoff | Sign ITP
7daa646b-c995-4838-9b5b-0313c9a247ac | checklist | 04.10 - Backfill | itp | 04.10 - Backfill
ded4fcc8-2891-4d81-af27-dd9bd65ec92f | section | Details
bf642076-9a40-4536-94c2-55e6d48e5dde | checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
60e9acc6-98d3-536e-9042-5632c7902793 | note | Acceptance Criteria and Frequency (Project Specific) - Written
93af2f53-8c69-580d-a52a-5eebbcea2b14 | note | Check Item - Hold Point 11
597cca8c-a570-5d7a-a229-03048bcc5509 | note | Reference - MRTS04 Cl19.1
5143a177-fb90-40b4-820a-bdf731ccc370 | signoff | HOLD POINT
860dde3d-1b2f-4996-af94-95816690739d | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
830fe5c1-666d-5af6-803c-66df7dd61ae1 | note | Acceptance Criteria and Frequency (Project Specific) - Grading
ed32fab0-085b-54a8-a92b-9d0943cf66d5 | note | Check Item - Witness Point 6
9348bfa3-f30e-58f8-b7e1-a78de8c75a09 | note | Reference - MRTS04 Cl19.2.2, Cl19.3.1
e4528943-9e3a-4674-af6b-06df1d7b08d6 | checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
36b3ba36-aaff-559e-8b8f-aafa3fc7e988 | note | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
27b2171b-43a7-57b7-ba62-5b4992cbdfb6 | note | Check Item - Check Item
1d294fb6-1142-5505-af87-6f804d479df9 | note | Reference - MRTS04 Cl19.3.1
ddc1ced0-1f5e-4a9c-b96e-23e53069bfcd | checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
350ac207-6f22-5f1c-8b73-f55bebbe6f1c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5d163c03-4d78-5420-b045-667e31ffb015 | note | Check Item - Hold Point 12
8b002460-6e80-5e4f-94f6-98ba21184f6d | note | Reference - MRTS04 Cl19.3.3
3117b118-bf32-4d91-9d17-b037aab8fb40 | signoff | HOLD POINT
dcb334e6-8e57-47c4-9786-72dfdc237eff | checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
f5cecaef-416a-5800-8f90-4b1c9aa2ec71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5d130e1e-bbfc-5759-8e73-ad2b08394f54 | note | Check Item - Check Item
a802638f-54db-5f4a-b1c7-9f10e6ed588b | note | Reference - MRTS04 Cl19.3.3
faae71da-0c1b-4196-81b3-39c7d2df8a2b | checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
920bf159-0886-5126-9d3d-237cd0d86b8e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
45fbe877-547f-5578-8eda-ac078a8a1eee | note | Check Item - Check Item
832cbb58-0245-5979-84fa-d6903b53effc | note | Reference - MRTS04 Cl19.3.4
91b9595d-1d38-4f2a-9845-324651d8d3e7 | checkpoint | Construction Testing Requirements: Test Method
40a41ed0-fc48-5e23-8c9c-4261ccfeec10 | note | Acceptance Criteria and Frequency (Project Specific) -
a28ed50d-efec-5442-b4f9-0093e98ab7a6 | textbox | Max. Lot Size
f631bd2a-0d47-573f-9b43-d9f5a6306fe6 | textbox | Min. Testing Frequency
7eb00a69-d925-587e-9e2e-b76ab0300a6a | textbox | Min. No. of Tests
6a5070b0-cd14-518d-bff5-63e101d3da57 | note | Check Item - MRTS04
820dffcf-901f-5cf4-a278-2f43f7216b2d | note | Reference - Table A3
daf6d285-2d38-495a-8bd6-26396807ebbb | checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
6a6c8077-0f8d-5cc0-bb95-d434b25eb535 | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
9e81e547-b93d-58cd-9d38-2f71fac05f69 | note | ○ 1 per 100m3
42080133-bf5e-57d1-923f-04e2be4c4e86 | note | ○ 2 per lot
dfb249f8-82c8-5ae4-bf9d-d2a3bc3e5c2c | note | Check Item - Check Item
aa3a9c36-9f03-57ba-9587-2b71ba6c70b4 | note | Reference - Table A1
ddf19131-50c5-4492-9d57-18b99f83f87b | checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
b6b879fb-2d4c-5f2b-9b08-630ab88347ed | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
84d1b098-6eb7-5e82-834f-09b0b38174cd | note | ○ 1 per 100m3
23d838e4-b6a2-533b-b4f8-95e54cbb07f3 | note | ○ 2 per lot
0ec7a6ba-5977-550a-9869-18ed51de3007 | note | Check Item - Check Item
bc31e2b0-b469-52d3-b16b-8850840a9f44 | note | Reference - Table A1
0f0b4b73-349a-4832-b87c-8b3bfae6519b | checkpoint | Stockpile Testing Requirements: Test Method
f092187f-7541-5bbd-8759-304199060434 | note | Acceptance Criteria and Frequency (Project Specific) -
fad00509-ab0d-5927-9abe-919e87c19f16 | textbox | Min. Testing Frequency:
b1f5a6ef-c5c1-5633-a806-86c0b0c985c6 | textbox | Quarry Source
dd5ec569-3518-5dbf-9382-99f325553a92 | textbox | Other Source
9970bf5c-dd53-5a53-ad65-3433dac5cfec | note | Check Item - MRTS04
b625b9eb-f204-53d3-a5f5-ac6de0f96b03 | note | Reference - Table A3
06ddd579-301c-4c72-951c-09839f9ec135 | checkpoint | Grading
77f95028-ae9d-583e-a9fb-4dd382b20a4f | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
aead7438-d4c8-5861-bfae-48b223b47bfb | note | Check Item - Check Item
e0e203f4-00cb-529f-9c23-815cff365b59 | note | Reference - Table A1
8fcdb329-f743-449b-bca4-76e1dc1fdfe9 | checkpoint | Plasticity Index
05ddb942-a8f0-584d-9c68-a75a6dbeeebf | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
09478273-aba4-5cb5-8c27-1e7f7cfc9622 | note | Check Item - Check Item
f0dfd47a-5294-5da6-b0f1-24679ae6f07b | note | Reference - Table A1
5709d91a-0d20-42b8-bb45-b308df6bb511 | checkpoint | Linear Shrinkage
5ef44ad4-4304-5e1b-bc08-cfce29bbf3dd | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
fe5cfe09-4ce3-5826-948e-3e6b210828b5 | note | Check Item - Check Item
27f3190f-ed7d-5142-987d-239419894bf9 | note | Reference - Table A1
14190194-15fb-44b1-b7d7-baacf5baa965 | checkpoint | Emerson Class Number: AS 1289.3.8.1
cae5897e-9918-5b71-8b76-9f994210fda3 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
f348c5f7-64d5-5cf9-82f5-335fbfdfeebe | note | Check Item - Check Item
5b02328b-6cef-5a51-a500-95712272459b | note | Reference - Table A1
daa5d653-ff4e-4f35-9cff-b8aa95637c90 | checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
dac9ca73-de26-5978-9aa5-1bdd240b95e8 | note | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
091356d6-02c0-5b58-b777-2830c585108f | note | Check Item - Check Item
4615282e-011e-57f1-8305-64cbe4398e37 | note | Reference - Table A1
abc4428d-432c-4dd4-9e5c-c578de05cf01 | checkpoint | Final Verification
518e6e75-ec2d-56c0-939e-dd2e75dcc1b8 | note | Project Manager Verify that the Above has been Constructed according to Specification
39e821f5-20d9-5993-bbdf-524b3a4e795f | textbox | Print Name:
5797ebe3-d940-57a5-99ef-0da5dc96e360 | date | Date:
bfaabee5-79c8-5c98-acee-17f29978242a | note | Client Verify that the Above has been Constructed according to Specification
5f36967d-01ef-596f-81ba-fa87ed2697a3 | textbox | Print Name:
84cce927-b8f6-5cf0-8cf0-1413f6145d77 | date | Date:
d17a1eaa-1f59-41e2-b7e9-a2aa673cea30 | signoff | Signature
e7ae398f-80d4-4ce1-b59d-426c3d5348ac | checklist | 04.11 - Fencing and Gates | itp | 04.11 - Fencing and Gates
6ec21295-0448-4b6a-b81b-ce04ec08dc7e | section | Details
14d82508-40ff-4446-8d92-e3d4686d6d99 | checkpoint | Material Requirements are as per the design documentation or as shown on Standard Drawings: 1600, 1601, 1602, 1603 and 1604.
4215187c-8d96-598c-874a-d1937b7a6ab0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
070857f9-fd85-5518-8c39-2463a07ebc4b | note | Check Item - Check Item
77695f90-86b0-5b66-a3ef-93474e163eb9 | note | Reference - MRTS14.1 CL.11.3
db92a8ab-96b6-43eb-99eb-fb04d9d5260e | checkpoint | Fencing is constructed in the locations and to the details shown in the design documentation
a4753f68-9dbf-5634-904e-7b61e6f9ad23 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1e71d6b9-f3a5-55f6-9950-fc2406496d13 | note | Check Item - Check Item
16296182-a8d4-5d70-8198-4fd622847022 | note | Reference - MRTS14 Cl.11.4
19667056-f7c1-46cd-84b3-ee87ea7a8241 | checkpoint | Where possible, in undulating country the fencing has been erected so that the post tops follow a smooth line
91e28edc-c53e-5d3c-b7c5-ea476f4520ae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f987c6d8-3dc9-5bfc-97cc-e820c951965a | note | Check Item - Check Item
b46115cd-d8c8-5557-9bdd-622b6fc3e929 | note | Reference - MRTS14 Cl.11.4
0f35c57c-5ed7-4948-94a4-2e80b1ea16a9 | checkpoint | Gates are installed in the locations shown in the design documentation or as shown on Standard Drawings: 1600, 1601, 1602 & 1603.
7079919b-c97c-580f-907b-6cde7a10b190 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec54070a-9ce3-5b56-880f-26b2bcc48159 | note | Check Item - Milestone
16da157b-b61a-51bb-8c46-6d71dc584095 | note | Reference - MRTS14 Cl.12.4
b9f53e7a-2b8e-45ec-85f1-76c82e4eac49 | checkpoint | Final Verification
006f953d-fc09-51a2-b52b-5dcb970afd97 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
a2e391d2-0a6f-5b02-b7b4-f564f8f45db0 | textbox | Print Name:
1195dd51-e576-59b0-89c7-7dd83bc03c91 | date | Date:
c411f90b-3f93-5c06-b656-38558f9a6d72 | note | Project Manager Verify that the Above has been Constructed according to Specification
31a92019-dbcf-53e8-b86c-4599356c8aa9 | textbox | Print Name:
0f6248ab-41bf-5337-8545-ec79668b37c0 | date | Date:
3f9d5c62-598e-42a1-8498-e1f52d30d562 | signoff | Signature
13135480-4884-4ec0-b9cc-5faec02e2bad | checklist | 04.18 - Subgrade Testing | itp | 04.18 - Subgrade Testing
2f06fae0-303b-4b23-8fb3-28e6af3d8375 | section | Details
14c1cd9f-fa9d-448b-aa4f-fe366f23c2ea | checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
cc5db88e-bc53-54d6-8956-e4fece163dc1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fc384169-cbb5-562d-9971-c8ca1307b134 | note | Check Item - Witness Point 5
7e45fdc5-e3be-5215-ac70-cfcf6efeab75 | note | Reference - MRTS04 Appendix B.3
7b172e72-1e6d-4793-a4c5-4f36eb02ade8 | checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
e37878fb-bfa6-55e2-ad48-668a04695571 | note | Acceptance Criteria and Frequency (Project Specific) - Testing
973fcecd-9049-5b91-93ca-f316629d26aa | note | ○ 1.5m below subgrade in CUT
7995103e-4ea9-510b-bcd0-1429041ce4e2 | note | ○ 2.0m below subgrade in EMBANKMENT
68a6f8fe-b8aa-5fda-95dc-1b1b693614a1 | note | Check Item - Check Item
72f0488c-185d-5b92-b5a8-f67de9bf6aa7 | note | Reference - MRTS04 Appendix B.3
5eb926c3-db98-4422-adc6-395b9d9239af | checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with RMS Test Method T103
989e8706-466a-5c56-918a-c60674b10535 | note | Acceptance Criteria and Frequency (Project Specific) - Testing
453d6eca-c15a-59cc-b99d-04a3223abd38 | note | Check Item - Check Item
53f329a1-5617-5ca1-b2e3-d777443a8f88 | note | Reference - MRTS04 Appendix B.3.1
d5ea735f-fc64-4cb0-a0c4-7a2ccc67e85b | checkpoint | Fill Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include: – Lab preconditioning, – Field compaction using construction methods propsed for the works. The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5.
f8551027-18be-548d-b4c1-5d3b6d6cf53e | note | Acceptance Criteria and Frequency (Project Specific) - Pre-Conditioning
253e193e-219a-50d6-9670-6c483fb1c9b4 | note | Check Item - Check Item
65e02c20-f9c0-58f3-8b04-0952f9da7b76 | note | Reference - MRTS04 Appendix B.4
1a2095d1-09ea-436b-862d-7902f295ba80 | checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
c4db6b28-a857-559b-8394-c24fc979daea | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports
af679b17-76ee-5f20-a960-3c5391829397 | note | Check Item - Check Item
58e6b1a7-469c-5b08-9845-e18d0cc8a62e | note | Reference - MRTS04 Cl. B3.2.2
2c81a138-adb7-4ee7-a074-358a6763dfee | checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
29c6ce7e-533b-52d4-99bb-6e65da0cb5d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
944a75b1-a64e-5b12-9e4c-bb99c6621c77 | note | Check Item - Witness Point 6
0d012cab-1ab7-57b4-a864-6d115baf25be | note | Reference - MRTS04 Appendix B.4
f3c1458f-00ed-4c9f-a742-b0fd2a09abaa | checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
a39a9dd2-6440-5051-b300-10968724dc8c | note | Acceptance Criteria and Frequency (Project Specific) - Testing per material type
0d4caec2-1997-5df2-a374-7c497af272fb | note | Check Item - Check Item
ebe5599a-c659-548d-b641-693d25f26214 | note | Reference - MRTS04 Cl. B.4 & MRTS04.1 Cl 3
91976340-c50c-4f4e-aa20-fdfb093cb0ba | checkpoint | Final Verification
d4b48dab-e594-5b26-a066-8d8cbfd06f5a | note | Project Manager Verify that the Above has been Constructed according to Specification
b533977a-0e10-5c9b-9dea-9bfd8284cfee | textbox | Print Name:
239cebc1-643d-530a-af03-b4496b6a170c | date | Date:
d74a802b-2463-5c1a-a49e-ea001f84cbb8 | note | Client Verify that the Above has been Constructed according to Specification
2601f395-fae9-59d0-8687-a34e8c49e838 | textbox | Print Name:
9c0fa97a-19c0-5e56-9319-1b0771c6c106 | date | Date:
4d025e9c-178a-4eb0-9d89-cca04f066986 | signoff | Signature
2558eeda-32e5-4579-8dc3-5504f0bea5fa | checklist | 05.01 - Placement of Unbound Pavement | itp | 05.01 - Placement of Unbound Pavement
1675ae85-acdd-4dc8-90a5-2a787121081f | section | Details
5d4f8fd6-b49d-4e0c-914b-32ada94bdc01 | checkpoint | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
e451e901-e83a-562f-a89a-7c48a2950188 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7c93d610-1791-5acb-986a-003dab47e6bb | note | ○ Layer Thickness: 75mm - 250mm
1773561b-b8a9-54f9-a320-363379aefb34 | note | Check Item - Check Item
e588dd82-5c84-5652-b69a-164e1959b316 | note | Reference - MRTS05 Table 8.3.3
94f92a98-0425-4a22-8074-963c23bbefc5 | checkpoint | Relative Dry Density Requirements: C.V of RDD >= 100% MDD for Type 1 Materials, = 100% SDD for type 2.3, 2.4 and 2.5
0309b1b5-5901-5138-be7f-3f8aa3cf440c | note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD (1 test / 500m2, min 1 / production day, min 4 per lot)
d481ad42-384e-5416-bc26-5e997b02772c | note | Check Item - Check Item
acff873d-862c-59ad-a1db-9d581c39142f | note | Reference - MRTS05 Table 8.4.3
6f93367c-901b-478c-a08b-612450c21cae | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
c8c8181a-b2a4-5011-bbb4-fa51d42b9cad | note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
4d969b60-7b25-5e96-b011-612aebefa596 | note | Check Item - HOLD POINT 3
12154df8-409f-5b78-b34d-23d25a964d25 | note | Reference - MRTS05 Cl. 8.2
59958735-4e92-4f58-b0db-d1775688ebab | signoff | HOLD POINT
bc1b78fd-c847-4422-b8f5-0b442e69e16c | checkpoint | Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
7c192a58-77b3-56d3-82b6-fea130ec1b26 | note | Acceptance Criteria and Frequency (Project Specific) - S < 60% (1 test / 500m2, min 4 / lot)
bcfb5766-fb3e-5047-903a-227ffe65bfcd | note | Check Item - HOLD POINT 4
03fe1671-93be-5e53-9ce7-9c62bce83f2c | note | Reference - MRTS05 Table 8.3.4.1
af9a6177-b159-4a1c-8722-57ffb5edcba4 | signoff | HOLD POINT
eb5297bb-9a6e-4780-abf4-9b4c3a831213 | checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
6abcd9c1-ae34-575a-8ec6-02794832e57c | note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
d17c47b6-70df-5112-94bd-72752d5c9555 | note | ○ Additional tests as directed by the Administrator
0fecdd28-6dab-597d-baaa-c37714715251 | note | Check Item - Check Item
e93e21aa-8d6d-5701-9d73-1e5ec929a019 | note | Reference - MRTS05 Table A3
4b506919-9d58-4f3f-a254-fd82f16d59f6 | checkpoint | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
1cbec559-f50d-5a30-bbff-dfe72da1ab86 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
e6294e33-bd37-5a25-b916-cbd7bba19261 | note | ○ ±15 mm in all other cases (1 test / 20m)
b043c7f8-5652-54f6-b758-e26b6b551d48 | note | Check Item - Check Item
1c6e020f-0aaa-563a-9e15-bbc227a1b078 | note | Reference - MRTS05.1 Cl.8.4.4.3
864e90a6-3c9e-4ce7-9642-754e770dc636 | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
bbd9b111-4146-5928-9a37-66146a0f8054 | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
76fd7aad-c217-5888-a4d9-0b854949a5da | note | Check Item - Check Item
1ccf801b-f072-5956-9e18-cfb5c95ce728 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
c328db7c-43cf-429e-a951-32b8d0d4d522 | checkpoint | Deviation from a 3m straight edge shall be less than 5mm.
215e3605-27d6-5c68-9d06-d1953b24b5a3 | note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
9f9aea89-0301-5316-ba57-b656eb2dd209 | note | ○ Less than 5mm
89eee3f3-21c0-5212-8fa8-4a76d769531a | note | ○ 1 test per 20m
42722681-cee1-5071-9e0d-1f6714f8287f | note | Check Item - Check Item
c30c1996-9812-5e96-bfca-891e5c497fbe | note | Reference - MRTS05 Cl. 8.4.5
fe89fcad-5a0c-4c00-814e-75a53c30cf39 | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
270eeebc-8cd4-540c-9914-db93e3d3558e | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
bff67986-2ca7-5e9a-9ad6-27618ebbe5d8 | note | Check Item - Witness Point
74ef2445-6849-5ef3-86e3-461bbd9b7163 | note | Reference - MRTS05 Cl.9.4.7
da6c2cd0-5529-4932-a2ae-34edae19aed1 | checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
d6a491b5-cdf4-5bbb-a7a2-d99781087105 | note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
5ddde3fa-a37f-5f7a-8640-9d8ca3bc0409 | note | Check Item - Check Item
b7218641-cb5a-5753-8a82-9571707796da | note | Reference - MRTS05 Cl.8.4.4.4
8c56c4f0-0a9b-4bb9-b970-668caa352a7b | checkpoint | The finished surface of any unbound pavement layer shall: – be hard and homogenous in apperance, – not have any loose, segregated or contaminated areas, – have the coarse particles slightly exposed, – not be affected by delamination, and, – not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
89f19ad1-4381-5e7d-95b3-bc7a062f955b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b045dcd2-52c3-5282-bb23-10084673f255 | note | Check Item - Check Item
2fc4b261-72da-5129-8570-ad26ed12fab7 | note | Reference - MRTS05 Cl.8.3.5.1
5818b30c-69c6-4a2c-a93f-2d92343c25b0 | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
dd591efe-e75f-5047-a6c1-ae773f0b1316 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
90a67238-dce5-5d3e-889b-41b657ee3fc8 | note | Check Item - Hold Point 5
4023c9df-1378-533b-9b87-6f79716b1fb9 | note | Reference - MRTS05 Cl.9.1
f4c899f4-f556-4018-a329-0671cd54f1a8 | signoff | HOLD POINT
1b62126f-e675-4f0e-ba6f-2d572770adda | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed, b) the surface finish of the layer complies with the requirements of Clause 8.3.5, c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator, d) the layer has been presented to the Administrator for inspection, and, e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
c19f5e78-c755-5ac4-b2b0-c5230b932ec9 | note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
0089c95c-8f37-5e6c-bbbc-1e8ff936b5ba | note | Check Item - Hold Point 6
1af78385-070d-5306-ba8f-b7f433f2ff67 | note | Reference - MRTS05 Cl.9.5.1
3ca29fdc-9fff-406d-b165-9dd1f997e5d7 | signoff | HOLD POINT
7b223b99-33eb-4f1a-8d2d-845dfb93c75d | checkpoint | Final Verification
cc5b8dfe-f37a-5197-9f6a-0a1445ad951c | note | Project Manager Verify that the Above has been Constructed according to Specification
e6c22ba1-79ff-54d5-ae29-66f83573b3b2 | textbox | Print Name:
60d8ed9b-e9bf-57f8-9777-42d419f89556 | date | Date:
5d8a3778-1227-5894-9a79-07382c8729e5 | note | Client Verify that the Above has been Constructed according to Specification
2c038e72-6743-5e4a-9fb2-eecc411553e2 | textbox | Print Name:
5a8449fb-f14b-5364-adc0-c7c934667697 | date | Date:
55be8727-8320-4f33-8054-3d8b77d18c95 | signoff | Signature
18bbc46f-9eeb-45bd-a211-d32b3a5862bf | checklist | 05.02 - Supply of Unbound Material | itp | 05.02 - Supply of Unbound Material
b200db6b-ca69-4bd0-bebc-59cc589a4ae6 | section | Details
8a83a6fd-d87c-4e89-8f02-8699f00c24b1 | checkpoint | No unbound pavement works shall commence until all relevant construction procedures have been accepted by the Administrator.
1573e619-6f2a-5e47-bb04-2b5690246ffc | note | Acceptance Criteria & Frequency (Project Specific) - Visual
33991e84-54dc-580a-989d-bc2fc5aaa54e | note | Check Item - Hold Point 1
3936a98f-1164-5343-b1ec-ee437aee269a | note | Reference - MRTS05 Cl. 5.2.1
c291d0ce-7645-4705-92a0-6603ff28c466 | signoff | HOLD POINT
a8bc5475-be2d-47ba-99c5-a9d36346d817 | checkpoint | The aggregate production procedures shall be submitted to the Administrator at least 7 days prior to commencement of material production
a1bc3953-bac1-52f8-997d-deafb6af5657 | note | Check Item - Milestone
3a3e3e43-5a3c-591e-9b34-bd71f380fe12 | note | Reference - MRTS05 Cl. 5.2.2
ef82a0b7-5098-4fbf-b2ee-99f3fcf08a47 | checkpoint | The unbound pavement construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement works
378f9dab-900d-5561-b541-d121a1cb9245 | note | Check Item - Milestone
cadd41aa-a2f4-5aba-a4d6-680a7acc8e27 | note | Reference - MRTS05 Cl. 5.2.3
c7d362a7-1a92-493a-836e-5badfe0c50e7 | checkpoint | The current TMR Quarry Registration Certificates for Type 1, 2 and 3 materials, shall be submitted to the Administrator at least 7 days before a material's supply or use.
5ed4081d-c8fb-5f54-955f-b1386d327f9b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9782f909-a4c7-5f2a-ab9c-9db912f55ac9 | note | Check Item - Milestone
55e6d174-169c-5af9-9be8-1d18b8baf1a4 | note | Reference - MRTS05 Cl6
921e1c31-e14e-464c-ac6a-4bd5a42f7bbc | checkpoint | Material from a quarry shall not be used until the quarry has been approved by the administrator.
25416471-f13c-56b8-adfe-af3ca964abdd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2406e1e6-d884-5b28-9c7c-1ca479bb0ca5 | note | Check Item - Hold Point 2
418bb644-4b66-5a29-89f2-fd7bacbb1078 | note | Reference - MRTS05 Cl6.1
2484b433-62da-4d14-8ecc-b19c3d24feae | signoff | HOLD POINT
4c8246a7-0534-4a52-b7e8-80e37e92c72a | checkpoint | Type 1, Type 2, Type 3 and Type 4 materials to comply with the respective material properties from clauses 7.1 to 7.4.
f844f0aa-57d0-5265-877d-59aa8e60725c | note | Check Item - Check Item
be0e1f44-8379-59b4-a9ee-ffc9a0413a91 | note | Reference - MRTS05 Cl. 7.1 - Cl. 7.4
2f2ec9a0-5f36-4389-97cf-e9d133d04a27 | checkpoint | All pavement material incorporated into the finished pavement shall be free from sticks, organic matter, clay lumps and other deleterious material or contamination.
f85b1c23-5747-580f-b54a-924bab7d54a8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8000fdf6-f05e-5faf-8abd-0edc6c206533 | note | Check Item - Check Item
19038f17-9e1a-5f0e-9ba2-5fdd61363540 | note | Reference - MRTS05 Cl7.5
70a979f2-dbfe-4c0e-873e-0523d49445b2 | checkpoint | Stockpiles located as specified in MRTS05.01 Cl. 2.4 or if not specified, on clear, even, firm, well drained ground where it can be clearly identified with individual stockpiles separated by at least 2m.
b48ef1cb-f83c-5ef1-b95e-dba222121773 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d7876c04-4f56-5ee7-bf69-f04b4e589139 | note | Check Item - Check Item
77ec854f-43f6-5cd9-ba3b-ee21c57c6cf4 | note | Reference - MRTS05 Cl7.7
823652e9-0c00-456f-8b73-accf916b0dae | checkpoint | Separate stockpiles for each production lot, or stockpiles incrementally created from a single material subtype with each added lot tested and approved prior to subsequent lots being added.
6678fa7a-8a0f-5536-b95e-255edfc711db | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9e183772-6a6f-5228-98ba-adf5b6a52ea3 | note | Check Item - Check Item
509ac125-b448-59e0-a115-f695decd1121 | note | Reference - MRTS05 Cl7.7
68bfffd8-90ae-4ff6-8586-23464d302750 | checkpoint | Final Verification
0959b003-6209-585d-bd67-fbbc7ec0f050 | note | Project Manager Verify that the Above has been Constructed according to Specification
88b036c3-026b-5051-8131-d43d3ebadc86 | textbox | Print Name:
eb285dea-c056-57d3-ade4-f4f6d36d1c1b | date | Date:
5840838b-b16d-52af-8fcb-042b6e6577ab | note | Client Verify that the Above has been Constructed according to Specification
7a93f0bb-ad80-5c63-9b03-40e519df117a | textbox | Print Name:
4428c815-17c2-5d64-b3fb-3513bac0ce24 | date | Date:
cdbe9844-6f0a-43de-b20c-101994602e69 | signoff | Sign ITP
09298c66-7aae-4df3-905d-48960f51a763 | checklist | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | itp | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements
7101ecf5-d96f-4f30-b63b-af9f30499992 | section | Details
95c1570c-464c-47b5-a915-cf6b5a8bf373 | checkpoint | No lightly bound pavement works commenced until all relevant construction procedures have been accepted by the Administrator.
03d24033-9c1b-515f-8709-83b540de3c9b | note | Acceptance Criteria and Frequency (Project Specific) - Written
29c54842-eec0-54d1-a064-5259eaceaa12 | note | Check Item - HOLD POINT 1, Milestone
9e13ae20-8c77-51af-9a15-59e1fe44048f | note | Reference - Clause 5.2 MRTS10
5dd030fd-c554-4f57-a7d4-120efd47653e | signoff | HOLD POINT
a61a1cc8-7fbd-47bb-bcf5-4a1d85752f05 | checkpoint | Lightly Bound Pavement Constution Procedure submitted to Administrator at least 14 days prior to commencement of pavement works.
73198be8-b55c-5e76-a162-1a8ef4d2e7f8 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
2b46648d-a0fb-5263-bac8-c0eb8a949ed1 | note | Check Item - Milestone
6ac17cfc-efe0-59c8-b868-e56e96cb5fec | note | Reference - MRTS10 Clause 5.2.1
08f8e903-3eaa-4a59-8623-5eecb2d2100b | checkpoint | The unbound pavement material to be used as part of the plant-mixed lightly bound pavement conforms to the requirements of MRTS05.
f673a9d1-ab52-53f8-b3d2-409012bc4411 | note | Acceptance Criteria and Frequency (Project Specific) - Written
559b1eb2-ce5f-5feb-b7ac-7cb7a0a58b5a | note | Check Item - Hold Point 2
52305b49-4d42-5559-9a5a-88fac23056e2 | note | Reference - MRTS10 Clause 6.1
d1856017-3867-4892-977a-20e588929df8 | signoff | HOLD POINT
fff67cf4-ec37-43f9-a21c-ed2bc0f34bfb | checkpoint | Regsitered mix design and terget content of stabilisation agent nominated and submitted to Administrator along with: 1. Stabilised Mix Design Certificate, 2. Quarry Registration Certificate
9a1f7bd2-e789-56f9-9cfc-25a317eb4274 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
f72d5263-7a5e-5b30-a9de-6116f068974c | note | Check Item - HOLD POINT 3
d50ff18c-71ba-558b-b3d6-06c3c0dfb8f3 | note | Reference - MRTS10 Clause 7.1
eddf027f-526e-4476-9832-202bd31240c0 | signoff | HOLD POINT
8a2bfaf1-7d51-4ee0-a7cc-2447d92fe7bd | checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
e955321f-9e20-5dfa-8292-95466307d4de | note | Acceptance Criteria and Frequency (Project Specific) - Visual
84c6755b-8a95-503e-bf20-3e9a3ffb955d | note | Check Item - WITNESS POINT 1
2781925e-6fb6-5174-9162-ba043e626dc9 | note | Reference - MRTS10 Clause 8.1
aa0e6f4e-1990-471d-b517-883b7c9a1c80 | checkpoint | Prior to continuing works after completion of the trial, records which demonstrate compliance submitted to the Adminstrator for acceptance.
2c9373aa-7ad4-5845-b93e-085a69cce904 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c1c4a614-836b-5551-8552-e0fd082bdfe8 | note | Check Item - Hold Point 4
21876060-d418-56af-8fef-349593d42271 | note | Reference - MRTS10 Clause 8.1
60b5fcef-f621-4379-9de9-b3e98e4b57d8 | signoff | HOLD POINT
1743f8a3-890c-430e-94c7-cf7f68b80af5 | checkpoint | Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
7fae9893-bab6-55af-8e2f-c81f6b3e49dc | note | Acceptance Criteria and Frequency (Project Specific) - Written
b2f0decb-cac3-5c30-bc4f-3b23d7ccf511 | note | Check Item - Check Item
166727be-c45c-5120-aac4-00046fd9d208 | note | Reference - MRTS05 Clause 7
1cb4c726-e30b-4576-96a0-87a0bc827460 | checkpoint | Equipment as specified in approved construction procedure.
42ee2aa2-640e-5d11-81ca-3f0720bf1a0c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
55036fd1-ad0a-5591-95d5-a2dd39dec6c3 | note | Check Item - Check Item
cec152f9-bd3f-5f17-8d28-fd5c178bb844 | note | Reference - MRTS10 Cl.8.2.1
6be1c82d-92cd-4068-bd14-dd8f2b47966e | checkpoint | The time between the commencement of mixing the stabilisation agent into the unbound material and the completion of compaction of a single layer is less than the allowable working time. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Tested working time shown on the mix desing certificate, b) Four hours
7f192d90-e06d-56e6-82f3-e34ae3cf3e45 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0d39387a-bc91-5580-bd02-811e8082c8dc | note | Check Item - Check Item
54fd70fa-d813-5902-9be0-8405cc842a62 | note | Reference - MRTS10 Clause 8.2.3
9d05a34f-a4b1-4675-9c22-3140e81ee7dc | checkpoint | Lightly bound pavements not constructed when: a) air temperature is less than 10°C or greater than 40°C, b) during rain or when rain is likely to fall during placement, c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the pavement layers
f610b304-054f-5f1a-8d19-163618d14a0f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d6dddf8b-b5d1-56cb-872a-f25227a25453 | note | Check Item - Check Item
d2976b52-263d-5211-b46c-aabd703f6aea | note | Reference - MRTS10 Clause 8.2.4
174cc36c-4831-4526-a3e1-88d6797e44ca | checkpoint | Individual compacted layer thicknesses in accordance with Table 8.2.7.1. Minimum - 125mm, Maximum - 250mm
a6590b93-872c-5b2f-b66c-097db0e217cd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
99dac938-8349-5e48-85ee-53c90bbf59bb | note | Check Item - Check Item
392820bc-228d-5865-891e-3a94a41ee650 | note | Reference - MRTS10 Clause 8.2.7.1
145c000e-9380-4f55-be4a-f2821de12a40 | checkpoint | Where a lightly bound pavement layer is to be overlaid directly with another lightly bound pavement layer, the finished surface is hardcut to uniformly roughen the surface across the full width of the layer.
63ab0269-3272-57b5-8726-2fb275b596ce | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e7bf7c75-673b-5f1a-8071-5703243ae39d | note | Check Item - Check Item
d5dfdeb7-bfe1-55ec-bb3a-2771ef615be2 | note | Reference - MRTS10 Clause 8.2.7.2
f29015ed-b70d-41d9-8d85-05a0eda12693 | checkpoint | Unless constructed in the same shift, a cement slurry is applied to the hard-cut surface prior to placing the next lightly bound pavement layer.
69500ab8-055b-5843-b777-c018d2fd64fb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
818a58f2-fc3c-504d-b8b7-8e635ecc9a03 | note | Check Item - Check Item
a75bbb4c-ac06-58fc-bb26-4cca2156c5fa | note | Reference - MRTS10 Clause 8.2.7.2
20040a78-e887-4ea1-ada0-7c5328226f60 | checkpoint | Each layer of lightly bound pavement cover with the next layer or bituminous surfacing within seven days of placement. Lightly bound layers not covered with a sprayed seal or prime within 48 hours of placement.
7103ef70-3476-52af-8276-a2768a9f1819 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a4c47bf7-347d-5dac-84d9-fdc4b230bd28 | note | Check Item - Check Item
017273a2-c905-58c3-b648-00051cbb9c88 | note | Reference - MRTS10 Clause 8.2.9
372cd405-df39-484c-85d0-f1a066fd5f63 | checkpoint | Longitudinal joints offset by a min. 150mm from joints in underlying layers, located away from wheel paths and in the final layer coincide with the lane-marking or change in crossfall. Transverse joints offset by a min. 2.0m from joints in underlying layers.
dff6e4f2-f8f6-56b6-b408-297bc6863a1d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3227a9ca-b344-54ca-8786-21ac523c9282 | note | Check Item - Check Item
d232fc34-495c-51ba-ad88-0b2b07f6992d | note | Reference - MRTS10 Clause 8.2.10
961cc862-517b-4ee2-8979-3f7cc31d15fd | checkpoint | For fresh joints between adjoining or adjacent run, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
0aa69930-3e79-538a-923c-0b38d6f5d5cb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c669ddf7-fb04-578d-a541-e5bc1142b6b1 | note | Check Item - Check Item
7ff34c6b-4454-517c-b8f5-0441eb35e9e9 | note | Reference - MRTS10 Cl. 8.2.10.1
9f00f279-ae58-44bc-b6f7-025a505c4022 | checkpoint | Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
2236eb33-89b1-5475-9766-e0a624894331 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1eb39916-01bf-5af4-87f5-5c803cd21a72 | note | Check Item - Check Item
172ed9d3-9bdf-5bbd-9b2d-01e5fe89f545 | note | Reference - MRTS10 Cl. 8.2.10.2, Cl.6.4
6ac321ff-372c-49e1-9bef-93d78685b49e | checkpoint | With the exception of vehicles directly involved with curing, compliance testing, sealing operations and construction of overlaying pavements and subsoil/pavement drains, lightly bound layers not opened to traffic until the lost has been tested and passes proff rolling.
7817ba2d-0e9e-5a17-842a-351232e74a99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b7e62d83-d6fe-520f-bf77-d6a1f5712feb | note | Check Item - Check Item
f44cbbe4-355a-55ef-a956-66bb64d63a54 | note | Reference - MRTS10 Clause 8.2.11
af1a0d06-c6bd-4d58-8094-c91dd348175e | checkpoint | The actual content of stabilising agent for each lot complies with the requirements in Table 8.3.2. Min/Max Value = Target Content +/- MPV (Mixing-Plant-Variability)
5793b701-fd6e-5128-9162-99d1d60b2932 | note | Acceptance Criteria and Frequency (Project Specific) - Written
4a0e0418-68c3-5c1c-b279-d516afdc8688 | note | Check Item - Check Item
e41797c7-5e0d-5007-9057-9344bfdd3314 | note | Reference - MRTS10 Clause 8.3.2
8ebb2d8c-66c3-4c50-9b67-af2a6f3d66a5 | checkpoint | Unconfined compressive strength between 1 - 2MPa
ad8b5c7c-5266-51e6-a56d-6f8057ca7dc3 | note | Acceptance Criteria and Frequency (Project Specific) - Written
6daec21a-8501-5276-9738-c0c99befdd90 | note | Check Item - Check Item
404c92bf-f23d-5d63-ae49-e4f14fa13822 | note | Reference - MRTS10 Clause 8.3.3
014bbacb-a264-45f3-8ca7-dc4e22c0d421 | checkpoint | The characteristic value of relative compaction shall not be less than 100%, except for the upper most layer of lightly bound base which shall not be less than 102% Compaction testing will be conducted at the 4hrs working time after batching.
e3764612-acb9-564c-af20-bff8b423f7f9 | note | Acceptance Criteria and Frequency (Project Specific) - Written
c5d4d106-868f-5abb-8e5c-b6c609ef7b09 | note | Check Item - Check Item
aea2f8cf-b1ec-5c3c-a8ce-5178f4a4762a | note | Reference - MRTS10 Clause 8.3.4
b9839a48-3cae-4465-9f0f-541a71fbad00 | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
649aa44b-811e-5677-ab3f-04632c2ef4a0 | note | Acceptance Criteria and Frequency (Project Specific) - Written
596d2906-d081-53cf-930a-59a5568b237b | note | Check Item - Check Item
50cf876d-cf54-50ba-bb55-a771713aaedb | note | Reference - MRTS10 Clause 8.3.5.2
3e47d6b3-1a43-4701-9a0a-088acec635ae | checkpoint | The primary tolerance for the Lightly Bound Layer shall be ± 10mm. Further, the total thickness of the constructed Lightly Bound Layer shall be within -20mm, +unspecified of the specified thickness.
f70ae9df-468a-5af1-90b9-1d69630d1269 | note | Acceptance Criteria and Frequency (Project Specific) - Written
62006b35-c974-5c1a-a70b-d0e51504d70f | note | Check Item - Check Item
af243d21-6fce-58ba-8b5d-69881634d7f2 | note | Reference - MRTS10 Clause 8.3.5.3
e6fd6e55-9a6a-496b-b3be-851c863cd0cd | checkpoint | Deviation of a straight edge placed anywhere on the surface shall not exceed 5mm over 3m
dc4d445a-21d0-5c65-a373-ce0b0aa9cf1d | note | Acceptance Criteria and Frequency (Project Specific) - Written
c6bb25e8-6795-5efd-a870-e0669a74ac6a | note | Check Item - Check Item
018606aa-6d97-57b3-916b-f3c108eb79c7 | note | Reference - MRTS10 Clause 8.3.6
9ec9d4d7-b7db-4358-9e7b-d8177f8e2c76 | checkpoint | Crossfall shall not differ from the designed crossfall by more than 0.5% absolute.
c0389e5a-d23d-5cdf-8b3c-7dcdb8f65250 | note | Acceptance Criteria and Frequency (Project Specific) - Written
a4169e3a-d809-5abb-bdb4-55d52d3aefc7 | note | Check Item - Check Item
2c1afb06-4ce9-553b-bdc1-10f7969714af | note | Reference - MRTS10 Clause 8.3.5.4
89c5e804-8492-492d-aee9-76269e836282 | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
2991397c-c7cb-52af-aafa-e611db33eaf8 | note | Acceptance Criteria and Frequency (Project Specific) - Written
deac9ff6-f365-5175-9336-b9d413d371de | note | Check Item - Check Item
71be8a3e-ba5a-5985-bcbc-a4c9910bf11b | note | Reference - MRTS10 Clause 8.3.5.2
fa945065-7ad5-44f8-86ef-1e66930eebb9 | checkpoint | The Maximum Road Roughness shall not be greater than (Rs) "2.31m/km"
85d7d8e8-f88c-52a6-bcae-13a3e2676a1a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e9764f9d-55fe-5960-9821-9cd2aaf93f7b | note | Check Item - Check Item
b62bacbb-39fc-53f9-8fb6-8c89f19018ac | note | Reference - MRTS10.1 Clause 8.3.7
a502fd91-ea59-4c35-bae6-b4708f48b584 | checkpoint | For lightly bound layers that are to be covered by a sprayed bituminous surfacing, the maximum ball penetration is less than 3mm
ae5b18f8-a7db-59df-bd06-7f6ed46fcb8b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc66c289-d22c-5d62-b27f-efbcb38fac4f | note | Check Item - Check Item
f6f77937-baff-5998-b5fe-ab201a8edd19 | note | Reference - MRTS10 Clause 8.3.8
a06f32e1-d208-4cc7-9d91-1aaf5fec4464 | checkpoint | The perceptible surface deformation test shall be undertaken in the presence of the Administrator
1387f1a4-ead3-529e-9e08-2099d051623f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9f4bf0ad-31c8-5948-a73b-65a26fc546a9 | note | Check Item - WITNESS POINT
a6ebb925-fe5d-5848-ae1e-087dca90fdbf | note | Reference - MRTS10 Clause 9.4.10
71f10fd7-516d-4b95-9fc7-ae188e58d0e0 | checkpoint | No lightly bound layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed, the surface finish comlies with Clause 8.2.7 and the layer presented to the Administrator.
4f04e314-204e-5bce-b5bd-68d2342ba4d0 | note | Acceptance Criteria and Frequency (Project Specific) - Written
3e846c4c-9d04-5e5d-a1b5-e44ab565a8e1 | note | Check Item - HOLD POINT
27cd61a4-961e-58de-a056-989983ba771b | note | Reference - MRTS10 Clause 9.5.1
152a335b-e1f8-4bc7-a92c-13dcd20967c4 | signoff | HOLD POINT
77016348-786e-4a65-878b-e23c2b30be6f | checkpoint | For each lightly bound pavement lot, the Contractor shall submit control charts in the ITP appendixc which show the following properties for that lot and all previous lots of the same lightly bound material produced under the Contract: Liquid limit, Linear shrinkage, UCS, Stabilising agent content, and Actual moisture content (sampled at plant)
6d830d96-33ee-5f67-a45a-e6d2db44c81f | note | Acceptance Criteria and Frequency (Project Specific) - Written
be7eacef-dfd7-50fd-9cc0-717bf51f86c3 | note | Check Item - Check Item
699aa73c-c41f-5db9-830e-5189feb5b6f8 | note | Reference - MRTS10 Clause 9.5.2
3691a000-d521-4a15-a81b-2e08b1b3afac | checkpoint | Final Verification
20e22695-8ada-5d7b-ac42-31ae4d9802d2 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
9e4e76c2-8a20-51c9-b0db-d50fb52c8e56 | textbox | Print Name:
9b6f7a76-057c-57f8-8b45-12f004bb4ea3 | date | Date:
d1338012-5890-5a8d-8afc-ea064fa46134 | note | Project Manager Verify that the Above has been Constructed according to Specification
cb5287b0-c779-5d70-91bb-5aea24aee007 | textbox | Print Name:
b15b8d8b-2fb3-5ea6-ab99-5318086136d2 | date | Date:
8fb09829-2ba8-453e-bc04-dddd5edb85d7 | signoff | Signature
2163751f-b66e-40de-9178-f695c7d2c0d5 | checklist | 14.01 - Supply and Installation of Road Signs | itp | 14.01 - Supply and Installation of Road Signs
088bccfa-6441-4507-8b1a-2c9d9eaae3d9 | section | Details
39776e05-239d-484a-95c5-a67274604dbc | checkpoint | Dismantling of items to be salvaged
dee1163f-2512-5009-84e6-8aba5feac94e | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
0bb14a1a-1e13-58cb-8524-420fbdb7325a | note | Check Item - Hold Point 1
5d7c0adf-617a-572d-ad5b-0f921a51b967 | note | Reference - Cl8.2
f291aef1-a877-4e66-99ff-50cee4841720 | signoff | HOLD POINT
85062f4d-dab0-4b5d-bc3e-31b20c5e6623 | checkpoint | Dismantling of items to be re-erected
0fd5ebf6-7d25-531d-b3d4-c8b286a85d7a | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
71ed37f2-1a48-5609-b0a2-f878f92b0396 | note | Check Item - Hold Point 2
f3a3ceec-39f4-5059-bf4c-039b2b459218 | note | Reference - Cl9.2
931d96c1-58fe-4b74-89e9-f8b5aa552bd9 | signoff | HOLD POINT
6cf40c32-7bdb-432d-9055-1c51efc5c643 | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings
fe072d42-ee5c-55d6-902f-a8beb7f450c3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6d089c94-cc18-51f7-9895-7b33680bec21 | note | Check Item - Check Item
034d1cf5-0ce9-5f29-ace3-78fbec27f3da | note | Reference - MRTS14 CL 13.2
dca0ad4f-d78f-4740-b4d6-b5eb92c169c8 | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744
b97bbe45-97b8-5e36-bb45-0853e0c32142 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
260e7b62-82f5-538c-949e-85ea89390e09 | note | Check Item - Check Item
a5fc0fe4-55cf-554f-8701-5c12f513ab8a | note | Reference - MRTS14 CL 13.2
9067d7e3-a9d9-4c57-abfb-37fe29040069 | checkpoint | Other materials may be considered but evidence of the full approvalof the department will be provided to the administrator prior to their use.
9f83f2f4-513b-5bfb-86eb-4c4a7672ceea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cca1f599-5ddb-5da0-848c-54dfbf6ed12e | note | Check Item - Hold Point
315e3daf-3386-5090-830a-c89486dd445e | note | Reference - MRTS14 CL 13.3.1.1
8fa0940b-035d-4442-92e9-cb49b301ff0c | signoff | HOLD POINT
32939564-7afb-4886-b01e-ff4c37e2d708 | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3
33a9dcb6-a6e4-5547-aa16-97b342e369bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f6cbb5ae-d669-5e20-8477-8fa60a088044 | note | Check Item - Check Item
8067abed-69c0-5b00-a73f-6f02fb84b5b6 | note | Reference - MRTS14 Cl 13.3
4fc5106f-7073-404a-94f3-f5c5c49d5e4e | checkpoint | Sign faces are fabricated in accordance with the requirements of the Design Guide for Road signs to the size specified in the contract
e591e4e1-8216-5dd1-942c-d8f296b9ba9e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec753319-be28-53a6-a5e3-3a74d4431461 | note | Check Item - Check Item
d563c90f-a38c-5961-85d6-8b7a4ae2efc5 | note | Reference - MRTS14 Cl 13.4
bb1a57eb-1286-412e-80a6-25a5012a39f9 | checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
5f35c810-8457-55ff-b285-1ed06e06fb21 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f12bae13-df88-5b60-b83d-6a086d4d7167 | note | Check Item - Check Item
7eafb99f-e7d0-5415-95c4-24cf0db1b4f2 | note | Reference - MRTS14 Cl 14.2.3
96dddbfd-c616-4302-bcf8-b8ccded6728f | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required
4b91da36-773d-5ccf-837f-09e86a315707 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6ba6f9a4-1cb1-5a39-abe4-acb676d26492 | note | Check Item - Check Item
fbba0e61-2bce-5076-b2fa-6cf491d022ce | note | Reference - MRTS14 Cl 14.2.3
37fe30c7-c17c-4f16-bfa1-f5a4e9bf15bc | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
a7aa6046-c5d9-5591-bce2-43510df8f657 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
debda205-5f65-5ee9-b49d-13f02740529a | note | Check Item - Check Item
67b523b0-eec1-581a-b950-78677550a890 | note | Reference - MRTS14 Cl 14.3
649dbb8a-8956-4eed-94f1-4e18932d958c | checkpoint | Erection of Road Signs
d1dde016-cb62-58b1-b0b9-16f95ff258bc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fd4ee1c1-b9f6-5ccd-b4f4-00a23ffc492c | note | Check Item - Witness Point
64721980-3821-5945-87ad-dde84978107f | note | Reference - MRTS14 Cl 14.4
8d230574-ea2f-4b6d-9c91-4fac0ffed8b3 | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD
fa76e5d2-ffd2-5346-a3ba-f0509adcf5ee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
07a4046d-cc1e-5535-ab1b-d5645952b977 | note | Check Item - Check Item
b6d72b51-7afb-57f2-b498-30a6e41bfc9e | note | Reference - MRTS14 Cl 14.4.2
2e668619-763d-488f-a2fd-20959a552219 | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete
0c8c0fff-bb7e-5d5f-b1b0-37db9cbaf33f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7fbc6088-f581-5c71-8062-1330326718e2 | note | Check Item - Check Item
4d4e0a6e-2502-5e4e-873b-5bfd1ca3b310 | note | Reference - MRTS14 Cl14.4.5
0df8f9f2-60a7-4df8-a07b-f824d4485332 | checkpoint | Final Verification
ccfab167-d6e7-5c5a-b2fb-025090383e80 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
08137f8f-9cb3-5ea1-b32c-debfa28e6f36 | textbox | Print Name:
457cc457-8969-5c9c-ab35-8fcb1c2dff2a | date | Date:
364bd8e6-74f2-5457-b392-0e2bd3d99c86 | note | Project Manager Verify that the Above has been Constructed according to Specification
4c0e621d-d537-56e8-a3d3-553980b3a41c | textbox | Print Name:
b2718482-33c5-56f3-93ff-0ee811872e21 | date | Date:
f86c1890-a958-408a-9949-53e9bbabc892 | signoff | Signature
c0178210-1986-49cb-a14d-b1b417ff736a | checklist | 14.08 - Demolition of Road Furniture | itp | 14.08 - Demolition of Road Furniture
b6594451-6353-4f43-a119-d4e72c80749b | section | Details
6af5b19a-b7ff-40f7-9959-3a66aed7b862 | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
ab678434-7cfa-50f6-a445-c7c61c563e1f | note | Check Item - Check Item
ab62eda7-bb7e-5735-b56f-c605f1ad2caa | note | Reference - MRTS14.1
6ffb48cf-9bde-4d17-bf3b-fcfc274317f0 | checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
d53e2c28-7ec1-5489-9c80-e8b01fd6d1d0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2633a521-6198-5bf9-a02d-637eee292b0e | note | Check Item - Check Item
333daf3b-2ec8-5f3a-8943-37c0775020a9 | note | Reference - MRTS14 Cl.7.3
e60a6226-0b59-4af6-85f7-12eb53738957 | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
a8de4b5b-8e96-54f4-a5e0-685707319d00 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
73b48459-b859-5f2f-af1c-be592e036d76 | note | Check Item - Check Item
2213416b-d66b-5f4d-ae41-99f1a9adf2f1 | note | Reference - MRTS14 Cl.7.3
665cdad6-5473-4147-a998-00d3f64f1db8 | checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
8dd04a71-1060-50c5-92b8-be402ed48a03 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bedf2941-1adb-5091-b352-25648739df16 | note | Check Item - Milestone
2b875330-6bd5-5652-bd7f-aa32e2dc6ac1 | note | Reference - MRTS14 Cl.7.3
1e59b8c8-c525-4b82-816f-8ce78f7626ff | checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
f40b0f8c-da82-5419-9b4e-369a13f4402e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
052fdac3-0f28-52cf-b749-d7926a01f9f3 | note | Check Item - Hold Point 2
f288931b-eb51-5ca3-923d-4e280faa1332 | note | Reference - MRTS14 Cl.9
73f35288-be24-468e-93fd-742de7e2d45b | signoff | HOLD POINT
49e24629-4b1d-4943-bcca-3d83a31e105a | checkpoint | Final Verification
eb583129-8810-5049-97e4-dcf652dd97c5 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
cedb974b-22a1-529d-8fc6-3c6c4c704ed7 | textbox | Print Name:
1ab4ac4d-8344-510f-945a-55ad4d3d0b12 | date | Date:
2d834639-6242-5c12-a3f4-52cb425c3ec4 | note | Project Manager Verify that the Above has been Constructed according to Specification
c027f283-30c0-5d40-8906-e7d99973dc7f | textbox | Print Name:
f317a3bc-77ae-5435-a524-dcc0006b4b54 | date | Date:
98733344-b3e9-430e-8b00-cb1f08550d78 | signoff | Signature
103cd210-1660-47bc-9288-c050227b49dc | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
b79ed502-77a6-4296-871e-b3127b0f2f7f | section | Details
9f8d170f-d11e-4b1a-b142-3d9eff42176d | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
aefd12ac-1420-53b1-81a3-d21caa1fc4ea | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
fdb2f4c6-5e07-5a4a-b3b0-1d07b9df6969 | note | Check Item - Hold Point 1
6c7559b9-6cd6-56e8-a898-3eecd013c4bd | note | Reference - MRTS16 Cl 5.2.1
acb2cfd1-1cc1-4255-8224-076946304eb9 | signoff | HOLD POINT
703a86a5-eee1-498c-a95f-48c77a9c1fa0 | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
fb2e2ed5-00d0-5eac-90e7-18a8adf19f3a | note | Acceptance Criteria and Frequency (Project Specific) - Plan
ed374d3e-b45f-5c2d-8282-6a8729c46096 | note | Check Item - Hold Point 2
7a26db7c-6a45-5cd8-9886-6facfda750b9 | note | Reference - MRTS16 Cl 5.2.2
4ab84a5a-8286-4e21-a1d4-8640b0dcd134 | signoff | HOLD POINT
9756872d-7062-4d6b-84ed-92c0b59243ef | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
9c9e066a-2fe3-58b0-8198-b18fcdcce4df | note | Acceptance Criteria and Frequency (Project Specific) - Plan
2e6a2c8d-28e6-5035-bc2b-c23f35b2f572 | note | Check Item - Hold Point 3
3e0e3802-6101-5e5e-93c2-0e9220dda5d9 | note | Reference - MRTS16 Cl 5.3.1
7366d757-7b0c-461f-b573-64aa5e25ae03 | signoff | HOLD POINT
c2a16bfb-8568-4274-ace1-0b13ec2496a8 | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
56ac097a-495b-514d-852c-3c95aa848623 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
e5e6e168-40f1-54cc-b49b-d657a425b7fd | note | Check Item - Hold Point 5
e446abae-e9a5-5345-9d87-c4ba6dcdb8a6 | note | Reference - MRTS16 Cl 5.3.3
74724dbd-8808-40ca-b1cc-a401c7460c58 | signoff | HOLD POINT
2aaaea83-539b-451c-b009-0350916b11fa | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
f686c69d-4a10-58c5-8935-36699145972c | note | Acceptance Criteria and Frequency (Project Specific) - Plan
0134a4f2-835d-5fd0-ae32-2ba4ab34a1a6 | note | Check Item - Hold Point 6
2543ba9e-7a55-50b9-ab90-d8081aea388b | note | Reference - MRTS16 Cl 5.3.4
133c43f0-dfc9-4a58-a3d4-cfb7add63cb6 | signoff | HOLD POINT
61ad8410-4c32-45f5-9643-fd2021be936a | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
cedb41a6-ef31-5704-94b8-975decef948b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8505b19b-f6e1-5491-a9b9-a4ac6fff03f4 | note | Check Item - Check Item
5f9bece6-1f58-52a7-b493-98c8d8236198 | note | Reference - MRTS16 Cl 7
21fe7dd5-4aee-44d0-b9e3-4f2749df5fcf | checkpoint | Materials are stored to ensure no deterioration or contamination occurs
f66ab91b-892c-5bc5-9897-3310be892e68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
403e1361-9885-5b85-9251-751fd251e9e2 | note | Check Item - Check Item
e6a3d602-1e31-51b4-aa0a-9bb27dc169a4 | note | Reference - MRTS16 Cl 7
02309455-119a-4b10-8433-46951808005f | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
f393d498-2a1b-57a1-9b16-f8289976608a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cc1e9bf9-c075-5f06-aa5d-3844bd5ca76f | note | Check Item - Check Item
dd5d6c0f-a930-5e9d-8479-0bc5435f4d12 | note | Reference - MRTS16 Cl 7
218a1da3-f2e0-4e7c-a607-8a1ea87807c5 | checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
734fd9b7-d2f5-5262-b39b-8bfc8843c680 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2f904dda-35f7-5856-93bd-6ceeb76d85de | note | Check Item - Check Item
a3676382-9dee-5001-8198-7e71d55bdf88 | note | Reference - MRTS16 Cl 7.6.2
02b5fd92-6868-4fc3-b995-1d82c73891e7 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
6d5083ae-3de0-5928-8c20-245306c98867 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1ec58b6a-e2d2-576f-8168-2ed69895bc0c | note | Check Item - Check Item
cbc4ed9d-1a90-515e-b66f-09143728c08c | note | Reference - MRTS16 Cl 8
31173f60-591a-4ea9-8364-c5de23d02de0 | checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
29878104-ea03-5fe1-a49e-bf4654d55638 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b7c5ecfa-4bc2-5b9a-909a-4f64e90b3fec | note | Check Item - Check Item
e658341d-0853-503e-a248-d271b04c1dff | note | Reference - MRTS16 Cl 8.4 TMR SD 1644
c01a8b38-8d18-499c-bb9d-ec15f11df197 | checkpoint | Site is weed free prior to ground preparation operations
d9d612a3-ab29-5545-a637-42f4749eabab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9d933293-7364-5d4d-93b5-7b1e66bf932d | note | Check Item - Witness Point
1c0f4282-19a4-5899-b46c-72e19de29da8 | note | Reference - MRTS16 Cl 8.3
e82e6562-068c-4ec1-a875-253dd5fe7349 | checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
30883c29-eaa9-522e-b988-3e679e256c43 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
27904477-9281-5023-9942-710c09d094d6 | note | Check Item - Witness Point
f2839dd2-db06-5b0d-8461-64727660dacf | note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
706d6961-4cbe-4597-97d0-7fa058342caf | checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
94623ad5-f48a-5dd3-a5e6-baae377aff6e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ef32b5be-3e17-5da0-be6c-c3f441de17f3 | note | Check Item - Hold Point 7
cb295741-b2f4-58da-a980-ecf1c8c6d1c3 | note | Reference - MRTS16 Cl 8.2.1
80b594f8-59e3-477b-91f7-1e28457f5f5b | signoff | HOLD POINT
0f4a669e-bc24-44aa-a094-e70bf00a2c81 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
a183ee45-c4c8-5ac0-924e-d1d23598ead9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b34b5b3c-c386-523c-9ffa-84b0a17ca691 | note | Check Item - Hold Point 8
5644926c-3ff0-58e3-bdef-177cec478ad5 | note | Reference - Cl 8.4.1.1
ec53c245-502c-423c-bd74-e41ec823c8ab | signoff | HOLD POINT
d081e3f8-b933-4ac7-a097-393e614b8121 | checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
720d5f96-4194-51fc-a29a-0575d1b479bc | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
27a0ebc5-40fc-5c13-bb14-89ac5a1cdcbe | note | Check Item - HOLD POINT
18ddae47-7ee4-5e6d-8544-dcb749ca1fb5 | note | Reference - CTS16 Cl. 3.1.6
1c375bde-58cd-4dd8-8099-7b0e49329c6f | signoff | HOLD POINT
bbaccbe2-3b0f-4d63-9c88-bf5235730013 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
cd14f144-f31d-5a48-8400-585fced21c2f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d87bce89-b3e5-5148-8cb4-7e1b8c46cfa2 | note | Check Item - Witness Point
c2a3c65b-5602-5aa0-8da7-b40099461766 | note | Reference - MRTS16 Cl 8.4.2.1
9728719e-e4ad-4ff6-a621-da6aa3232685 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
88d60fe7-6b38-5603-91f4-0e7fae25c9e5 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
f51dfae7-6310-5bc8-a86c-ed04797a6a1a | note | c) on the day turf is delivered to site
d107dbb9-ecae-5bf6-a441-2b0815a4bf50 | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
86a8c730-7732-579b-aa6a-76052230587a | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
62d3f5a4-549f-563a-8c9f-b83cc1795fc7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1a40fbca-2d73-5929-aa4d-78b1a94286d0 | note | Check Item - Check Item
b95116e3-82c8-5861-9ef4-8378edf97e20 | note | Reference - MRTS16 Cl 8.5.2.
abe70589-f39b-4134-9acd-5d4df2e5a9a2 | checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
01d3c8c2-f437-51ec-bf9d-035bd760e1ab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57be027f-7dc8-5631-9321-1814d145eae3 | note | Check Item - Check Item
c531ff3c-67ea-5ef0-86ba-2b0486feac46 | note | Reference - MRTS16 Cl 8.5.1.3
38cead50-17f8-4d56-925c-3f299f12f6ae | checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
aa74d8c4-61c3-5af1-98e8-64cf702adda3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9bf5d86a-f44f-561d-8003-2827f27ecfce | note | Check Item - Check Item
b3246f94-58b1-55fc-bb2b-cdb9257a72c1 | note | Reference - MRTS16 Cl 8.2.1.4
0d95a25c-7d2e-4272-8773-1ca8e8402cdb | checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
b00d47cb-37c3-50f1-9872-0ffbe2f636ff | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8d722a1e-d2dd-536b-9341-9bdeaf60f0f7 | note | Check Item - Check Item
5fff0c2a-e3cb-528b-b274-b99c19739259 | note | Reference - MRTS16 Cl 8.5.1.3
e3438334-c026-4a8c-9970-638b88d9f440 | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
b04021ee-fda5-5a73-986d-965ce722273a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
399023b4-0c50-571c-9912-00d144eac83e | note | Check Item - Check Item
b8b5aed3-4028-53b2-b9df-85f6dec2b872 | note | Reference - MRTS16 Cl 8.5.2
484e5df1-83a7-41ae-891c-3869e42db856 | checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
3851bf24-6b02-5f59-bf07-5763cb6a994f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
869a36cf-810f-5cdb-b2b2-81722a321c9a | note | Check Item - Check Item
3b3f88e6-80cb-5189-8db4-fe5c2e3f0957 | note | Reference - MRTS16 Cl 7.6.3.1
d8c2b004-9709-4834-af35-97b238af0fe2 | checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
ff877bab-28c3-5f27-b67b-311a74aedaed | note | Acceptance Criteria and Frequency (Project Specific) - Visual
85000f47-a4ec-589b-a13d-41260ec56435 | note | Check Item - Check Item
c6a06e42-a1c0-55ac-afac-895c8dcdd2cf | note | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
e336a2eb-671e-433c-b153-3b00a01c9f8e | checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
e29257c2-a152-5dc2-b147-ba8cfa8c6c19 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
93ad729e-6cf4-5904-b6e3-a38c6c42179a | note | Check Item - Check Item
78cd3a2f-8ccd-5430-8e15-22859ebf0c3c | note | Reference - MRTS16 Cl 8.5.3.2
5581432c-d6e9-45c6-8cd8-d59ff9ddefb5 | checkpoint | Administrator notified of plant delivery to allow for inspections
5a7acb22-cb1b-567e-9557-82ad92bc3d9e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1ff80297-02fb-525d-a25e-c00c5505668a | note | Check Item - Witness Point
827d9a78-c32b-5e93-a84b-6b5d5e6eab7a | note | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
c3341e29-20df-4209-a5d3-4dea500425da | checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
23122f4c-6e41-5702-af76-fac9016ad82e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f54c4fef-57ef-5db9-8a1b-4ba35e21208b | note | Check Item - Hold Point 11
6bc6fbd5-8e90-59a5-adfa-22278b3a098d | note | Reference - MRTS16 Cl 8.5.3.3
d3897437-8d11-4056-90a8-30b394f314d8 | signoff | HOLD POINT
54de5034-6cb1-4aa1-992e-961661275680 | checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
c0b30898-6c13-51ae-bc07-b541b61747a6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2ae4dd28-d0ac-5fd4-bfcc-aa0a3830f4b1 | note | Check Item - Check Item
6add44df-8c41-51ea-bc85-312ff94179a1 | note | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
7765986a-4ba0-49e3-bdf1-cb8568068635 | checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
c5338fce-a88e-535b-922e-a9862e1ff49a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8c832279-beb7-59af-877c-4ad44697802e | note | Check Item - Check Item
696dc2ac-a1c9-5d9c-a95e-f75cdba5ae60 | note | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
28266a5f-80fa-4d90-91e2-88c4fcb78fdb | checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
9661eb1e-f871-5277-b6c1-ca752552f658 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
17acda9d-d326-58ce-a1c0-54f4a9946be0 | note | Check Item - Check Item
6aa6ab8e-21bf-5025-ba7f-f3c7c5f9671f | note | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
754c91e6-896c-4edc-8ecf-678f79530033 | checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
8bbfd5e9-060f-59d6-802e-9c5d46743d14 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3979e5c0-59a2-5fa4-9a2d-3e7a1deadbc1 | note | Check Item - Milestone
00089bac-0462-5617-a886-3a03c0cb1e20 | note | Reference - MRTS16 Cl 9.1
272b921d-5e19-4104-af88-963831aed7b9 | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
c44cd03e-5419-550a-97fd-dda3d9f4c188 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
749bf72b-19fe-5c1b-a6cf-e4c097f349d5 | note | Check Item - Check Item
ad5a1a0e-2b28-5c65-b7bb-83049564325d | note | Reference - MRTS16 Cl 9.1.1
f2ff6b9c-cb91-4913-9104-9f696d688e2c | checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
53c9f594-5a83-5544-9efc-072adfc639ac | note | Acceptance Criteria and Frequency (Project Specific) - Visual
819d0c13-14ce-5175-a6e0-e2076aa370c0 | note | Check Item - Hold Point 10
5291e554-eb5d-5f4b-8049-a4002bc2209c | note | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
1b92c30f-d90c-4f4e-8f71-d3d64b272b70 | signoff | HOLD POINT
98915f0f-2677-4998-bf07-262322845c1f | checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
9e003047-e2b7-5562-aa2e-eeaad1069d2b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ebea7fa0-ec26-5a85-a4a6-b64cab6b5a98 | note | Check Item - Milestone
ed28056e-b01c-58f0-b9b7-3dda0e1b578f | note | Reference - MRTS16 Cl 9.2
afcbe21c-67a6-4963-b973-0f06ab9ac64f | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
8d97ca02-7ecc-5c90-a568-da03f109a945 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
81bcd42a-e242-5994-9ce5-4464915c6a02 | note | Check Item - Check Item
3ad199a4-5bde-54bf-b437-09e5ff6d7539 | note | Reference - MRTS16 Cl 9.2.1
def66868-0be6-4bf2-a6cb-b0d3152521ef | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
d948b866-5b24-53db-b92c-e2fcaa9abf47 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
36d8d484-87e6-54e0-882b-43ba2ed6de0e | note | Check Item - Milestone
0be2f9d8-cddf-5813-9017-5a67b5685f57 | note | Reference - MRTS16 Cl 9.2
38b76a08-da97-416c-8d94-499c115053d1 | checkpoint | Final Verification
7c7a6791-6b38-5edd-a006-fcb81d1ff728 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
08d81fd2-4ec9-5cfd-81db-71d5fed1d359 | textbox | Print Name:
f879e650-ca9d-583d-a892-82dcca60d4ad | date | Date:
b684427d-5763-513f-a31c-a2dbfdf88fd1 | note | Project Manager Verify that the Above has been Constructed according to Specification
2d994a20-a232-5cb1-a256-ae8c1eba425d | textbox | Print Name:
64bb1fd8-1ff7-5a0a-8f72-22d3781574e3 | date | Date:
e9f94ad9-9148-437e-b550-2fcb305d8cc7 | signoff | Signature
8b2b1814-3d41-4470-ae40-0d49f42b2b46 | checklist | 16.02 - Installation of Turfed Areas | itp | 16.02 - Installation of Turfed Areas
3b710c09-5aa8-4461-ac39-299b0c765345 | section | Details
e2ce0127-ff7b-485c-bfe0-39f0807fb72b | checkpoint | Installation of Turf Shall Comply with Project specific Requirements listed in MRTS16 Annexure.
70a10c59-5c9c-52e4-a048-6153d07e5dc8 | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
ed1cb2d9-7c49-52f0-aa60-5c6c6d8fc7bb | note | Check Item - Hold Point
9c10cc0a-3956-5808-ab95-8a03860396bb | note | Reference - MRTS16.1 Cl 3.3.1
3c581991-0ecf-4e76-b67b-c8a2e45d8682 | signoff | HOLD POINT
a6225e07-5571-43fa-85d9-09cac72b5dd9 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
8a2dda10-5656-5c39-aa88-829693184891 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
2023cf70-ee64-5dcc-b03c-ce7269081c32 | note | Check Item - Hold Point 8
a6859352-6579-59d4-a093-2f461f31c945 | note | Reference - MRTS16 Cl 8.5.2 & MRTS16 CL 8.4.1.1
33ab83e1-6a65-4984-9cf3-6a0745ddc9d0 | signoff | HOLD POINT
49c15a69-a980-4b14-ae40-b69ad0fead33 | checkpoint | Topsoil shall be installed within three days from the completion of the subsoil operations. Topsoil shall be spread to the required depth. (75mm)
2c892ce6-d4d2-5905-8b09-8f30970421d0 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
ba898129-2847-54df-8f19-c1d6f6cc2cd2 | note | Check Item - Witness Point 6
219d8583-cb9c-5afd-9b2b-02759989f2e8 | note | Reference - MRTS16 Cl 8.5.2
928e1a3e-8bde-446c-a1b2-6d4ea6c29336 | checkpoint | Subsoil operations shall occur immediately after the application of amelioration agents. As per Table 8.5.2
b2d798d6-2fcb-5346-a491-7cdae682ab5f | note | Acceptance Criteria and Frequency (Project Specific) - Plan
9f26ed1b-4a4b-52e4-af04-5dc6f1b3cbca | note | Check Item - Witness Point 3,4, or 5
ff6626ad-2e4e-594c-880d-4b250c75fa32 | note | Reference - MRTS16 Cl 5.3.3
b06bfbbe-f019-4034-bf08-fca97a0b4203 | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
8e54f84e-87f9-5a09-90db-d03df4b93ef5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0044f5f8-4dc6-52c9-b057-c2188c101689 | note | Check Item - Check Item
fd87a2e2-5d7f-56a6-a0db-f44c71627f88 | note | Reference - MRTS16 Cl 7
feae54cb-97df-4b6d-9145-e837025d3b38 | checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
f7445099-f630-5492-b67b-046dc7c3335b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
013664b3-2622-525b-8de8-7b7cbfe7984b | note | Check Item - Hold Point 7
c7cb84c8-645d-5cd9-8071-cba916c9f314 | note | Reference - MRTS16 Cl 8.2.1
6517816d-57ea-4dcb-8c29-87a7a7fc1ad6 | signoff | HOLD POINT
f816035b-c81e-428d-aeca-4adfaf8e64b0 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
fae6aadf-507c-51ce-a5e8-cec67da59aff | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdcf0e4c-9df4-52f7-949c-33b86123c42a | note | Check Item - Witness Point
63a13494-a62c-5a3f-87c5-4cb356da96d6 | note | Reference - MRTS16 Cl 8.4.2.1
73616389-6c4f-4da9-8d87-a4ac564a77d2 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
4575c62d-b573-500b-809b-1ba118bfc0db | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
9d1c4aa8-4d84-5639-9ec6-76695cbf60db | note | c) on the day turf is delivered to site
3ef46ed7-61a9-5de4-a273-5e03885bb11f | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
9c7ca227-b879-5cf6-8a9c-573e4d9dd7ed | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
bb2c0ec4-2f27-5879-b393-ff8b7a39527d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
035ef475-73eb-5bf4-98a1-f03c8a200325 | note | Check Item - Check Item
e46bc3df-8081-53f1-9c46-a689c05d5ebe | note | Reference - MRTS16 Cl 8.5.2.
edeefe66-4d24-401c-8cd2-64dc712a2883 | checkpoint | Subsoil Testing Requirements Completed as per requirements of Form D & Form E
b191d965-0cd3-5c69-a4cd-a62b2cb30fd8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a38b37ce-c85c-55c1-ae0b-f64b00e17a75 | note | Check Item - Check Item
82059c1f-cd45-51bd-9bf0-e45e5f34d19f | note | Reference - MRTS16 CL 4.1
38508bee-207e-4347-ae76-8893e405f0ae | checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
ce021bd0-942a-5569-a84a-818b35a8a141 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
af9c4d48-ee01-52d2-984d-2ea1977429e7 | note | Check Item - Check Item
e858043c-c71b-5d87-8ae8-3f5aec985d8f | note | Reference - MRTS16 Cl 8.5.1.3
8ecb9c59-add4-47eb-b3cf-1312bb6aeb65 | checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
ef60a369-a3e2-52e4-8dd4-75340846e2a2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5c907b4d-0466-524c-9e7a-3f26465461eb | note | Check Item - Check Item
47257651-2765-5d88-a7c9-785bb7550dfa | note | Reference - MRTS16 Cl 8.2.1.4
27ee747e-5301-4f28-889b-69d7b56db9c5 | checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
5f3b1e25-1f21-5603-9bbc-e96cf4ed274d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e7cd82e1-684f-5a87-ae48-9ead4ea4e8d6 | note | Check Item - Check Item
458c860b-3af7-58dd-92c3-e652e00b14d1 | note | Reference - MRTS16 Cl 8.5.1.3
e92884f5-fafd-4e48-9b62-5f3144f6c57e | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
b65ce0f1-387d-5512-b4a2-1cdd4f9e3475 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
aaab8564-9ee1-5f89-a910-d63a581329aa | note | Check Item - Check Item
d4591a1d-39c3-59b7-b26a-9881cf8ddc96 | note | Reference - MRTS16 Cl 8.5.2
8da1c8ed-2f32-48e4-b4b2-e89912307bd6 | checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
d8061150-2207-5505-9183-82c6ec2b520a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0ad0b453-7d5e-523a-bcb5-4d9d7169dcab | note | Check Item - Milestone
3054fcd6-a169-5165-a7c7-802a51756c8e | note | Reference - MRTS16 Cl 9.1
b5895c80-b5ac-4f5e-8fa9-dbfcbc6de84a | checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
30cff65d-8574-5d85-aaef-63cb41ef5752 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fd936e6a-5b0e-564b-8970-9416257497a1 | note | Check Item - Milestone
3cec1163-31df-5589-8d22-8d5946f62565 | note | Reference - MRTS16 Cl 9.2
8e522f46-e777-4c44-a8ce-c6fffcee962c | checkpoint | Final Verification
41dc1f42-3581-5e1b-94d9-e393ec0d9874 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
5d60fcb7-bed8-589b-9f8d-032d73d7b13d | textbox | Print Name:
365df27f-1b61-5328-a301-4bf25c08981a | date | Date:
773275bb-a3b0-5e85-8b75-28a169e8598f | note | Project Manager Verify that the Above has been Constructed according to Specification
8e47c940-f185-5868-ab87-edc856bfae1c | textbox | Print Name:
0c14f938-9a60-5573-b9b7-fad992954d2b | date | Date:
05b896ec-28ee-439f-879b-b5b0128183b2 | signoff | Signature
c8ff68e1-d7c8-456e-8528-42fe6bbdf561 | checklist | 27.01 - Geotextile | itp | 27.01 - Geotextile
a8839e64-00db-4762-b6b0-6a2fe626f57a | section | Details
382883c1-c448-4d46-b9d5-d6b9dfb5ab46 | checkpoint | Geotextile strength and filtration classes as specified on drawings or within MRTS27
efe2d019-773a-5a16-9daa-61b7356e5655 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
43970e2b-62cf-55cd-9922-f8076a7df063 | note | Check Item - Check Item
65f41fbe-6bae-5922-a89c-26147e713b33 | note | Reference - MRTS27 Cl6
44fe2923-2801-4e58-8580-8f7156df052a | checkpoint | Geotextile stored on site under protective covers, off the ground and in a manner unaffected by heat. Rolls clearly marked with manufacturer, type and batch.
7c637226-34b6-5891-9df7-cc21c4246ea9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0a933a48-6510-5146-ba5f-87f136bc1967 | note | Check Item - Check Item
7eefde2a-1ab9-58c6-8080-37a0b0d638a6 | note | Reference - MRTS27 Cl7
0d96523d-4ab8-4a9a-b25a-d205a89d4df8 | checkpoint | Proposed Geotextile submitted to and accepted by Adminstrator for acceptability to Cl6.
35a03696-d46f-5511-b6d9-bfb3a8cd9a55 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8bc240a2-03c7-5c91-8364-7efeacd8432b | note | Check Item - Hold Point 1
3a7fd833-3435-53ff-ae26-a7706f9a4b7e | note | Reference - MRTS27 Cl8.1
25233533-c0a1-4fcf-94b8-34d6a873d4f1 | signoff | HOLD POINT
0647ff77-ba3e-4b29-90e1-c1a0fbc0a41f | checkpoint | Geotextiles installed as specified in the contract
0904f2c7-2804-5785-8346-3b72f44b6598 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2c9687b0-8d8c-5cda-9fe3-fa17afdff00b | note | Check Item - Check Item
7430a622-9e18-55a6-9526-54de7b4bfb27 | note | Reference - MRTS27 Cl9.1
34562822-dbf1-4663-b700-e0ef670b5b14 | checkpoint | Area cleared and graded with all sharp objects and large stones removed and covered within 48hours of being placed
5d3bfcec-fd34-5fe2-8313-4670ae2e86c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
90ab5725-259f-5385-8771-57cf74718248 | note | Check Item - Check Item
5c97169d-7af5-5148-a56f-02a188f5388c | note | Reference - MRTS27 Cl9.1
45e83f4b-a481-4737-b500-702218dae0b1 | checkpoint | Initial uncompacted layer thickness for fill material placed over the geotextile shall be not less than 200mm of D85 of the fill material, whichever is greater.
91d30958-3181-51fa-91cb-a4a9c284f10d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6b776b39-8735-51df-8a5f-dff8368ff530 | note | Check Item - Check Item
aa10a072-8a03-5f64-93db-922e991b9afc | note | Reference - MRTS27 Cl9.2
2ca49d34-dc6f-4149-aa66-fcee4e036840 | checkpoint | Jointing of geotextiles in accordance with clause 9.3. If overlap is not specified, it shall be a minimum of 500mm. If used to line subsoil drainage trenches, the geotextile shall fully envelop the drainage material with a minimum 300mm overlap at the top of the trench.
5b89e780-560a-5a8b-90c5-fb02253922f2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9e195308-4ae8-5315-9fbc-783a8af0079a | note | Check Item - Check Item
20141231-1429-55fb-a1bf-3fa1d8f92ad6 | note | Reference - MRTS27 Cl9.3
effb2ee8-1895-4890-a089-a3973b0102ad | checkpoint | Filling over installed geotextile shall be in accordance with clause 9.4. No construction equipment shall stand or travel directly on the laid geotextile. Rock placed directly on geotextile shall be placed with a drop height not exceeding 1.5m.
54d5b1c2-aa1a-5739-bb67-9f0f40ea8359 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
218d19cf-07f6-55a8-bc0b-468608228ac5 | note | Check Item - Check Item
5a0e5ef1-d37f-5c35-9e16-707bc29d975b | note | Reference - MRTS27 Cl9.4
20a9a4f8-6509-465d-8487-5ebae139516d | checkpoint | Where batch size is <5000m2, sampling and testing need not be undertaken, provided the nominal strength of the material supplied is 20% higher than the requirements and the filtration properties are 20% lower than the requirements stated.
f9120ed4-705c-578e-8029-faa9ad5d435f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4e21608c-f547-5d47-9ac9-ee22cb92083c | note | Check Item - Check Item
60002292-1516-5e7b-87d7-da412cc8c315 | note | Reference - MRTS27 Cl10.2
ba0a302b-2189-4ebe-851c-cb92ba145246 | checkpoint | Where directed, a testing sample shall be cut and provided to the administrator
2dfc9846-8d41-537d-99d3-83d5d4417b0e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
76a4024c-4a71-5f2e-84f4-dd90bfed40dc | note | Check Item - Witness Point
bde9bb5b-cbf8-52e4-b214-010a22ee5e2b | note | Reference - MRTS27 Cl10.2
4697099c-c97d-4fe9-b119-3a852dcc2ba4 | checkpoint | Sampled geotextile shall be tested by the Contractor for the range of properties specified in Table 6.2 and Table 6.3 in accordance with the requirements of Clause 10.3.
09fbee3a-2d2f-5b22-abc1-c4f854fab8fd | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5de8021a-010d-5bdb-8736-29a974b2a5f8 | note | Check Item - Check Item
f92ef9a4-7d0c-50ca-b267-cdedae09ff9c | note | Reference - MRTS27 Cl10.3
d1f96db0-8180-49b4-8e39-c7e1897d4c57 | checkpoint | Geotextile not placed until administrator accepts test results
dbabcddf-3c36-5915-84b2-4fffba387b8e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
50cbf376-5099-543a-9f71-d2b35fc019b3 | note | Check Item - Hold Point 2
6a86982e-d289-5c68-bf70-18962f46c67c | note | Reference - MRTS27 Cl10.4
e7aea854-8ef6-43ac-9a21-cb346aa9e916 | signoff | HOLD POINT
e7321b22-63b3-4a16-b451-aca8c88b02cc | checkpoint | The administrator may select samples from the site for audit testing.
eb14cd17-cf80-5db5-8ea6-ab024455469d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5cefb1c0-8e99-5a7d-a356-8495c36c370a | note | Check Item - Check Item
0f36aa79-44a4-5ed5-bb2e-d350ad8f57f8 | note | Reference - MRTS27 Cl10.5
e882d0b6-4145-45c1-9ca3-580097b4143e | checkpoint | Final Verification
ce21967d-1ee6-5d46-b83c-4dc87079be59 | note | Project Manager Verify that the Above has been Constructed according to Specification
b1b05529-fb34-5572-89ad-18dfd48794c5 | textbox | Print Name:
3e226d33-a365-5724-94f8-f43226300c16 | date | Date:
b952a616-8186-599f-ad7f-c24ee48ed23b | note | Client Verify that the Above has been Constructed according to Specification
05affcd8-d01b-5d09-bec2-241e649fceca | textbox | Print Name:
04f4e53f-99a0-5f9b-bf03-6a2777fd0e6e | date | Date:
cec92b25-b38b-4d1f-881c-4802ba07d4f7 | signoff | Sign ITP
db23a809-f5be-4f28-b2ed-7f23c78123db | checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities
ef911ec5-9083-48c5-ad16-0eb02b673e76 | section | Details
122acb6b-e155-472a-841b-51a2ede1aa63 | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
788cbe44-f065-5429-be31-a717a0c60548 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b62bc77-913a-5a37-ac68-e71641ecaf9f | note | Check Item - Check Item
ef990703-00ce-51ed-a483-8b43491d4538 | note | Reference - MRTS28 Cl. 4.2
f452b59f-9a24-4e52-8d62-14a2b2e825e1 | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
82f7ff43-1b82-5272-b634-ef4a53e7f65d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a464e4d0-666d-5e34-9725-a913da2f25cd | note | Check Item - Check Item
b9b53fce-ddd1-5076-874c-203fedffde4d | note | Reference - MRTS28 Cl. 4.3
cdc1f023-53e1-465f-b889-519873e54df4 | checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
5f6208ad-6be8-5915-b83e-5f6c09314fa0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9eec64ad-0dff-543b-9e79-63e3c0e67ab2 | note | Check Item - Check Item
ff479e27-f214-5468-bd8d-e700811682d9 | note | Reference - MRTS28 Cl. 4.4.2
c0a1fa17-92fd-4e61-888d-b1e8cad35b7a | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
d1a551b1-f28d-5e79-b452-4d319873bcae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c2dde83f-1918-5d5f-8469-9221b5dc63ce | note | Check Item - Check Item
40ac9320-f250-582f-a255-1ae1bc605d6e | note | Reference - MRTS28 Cl. 4.5.7
30ae036f-7940-4162-b01d-9bfaaebdb892 | checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
744c3987-fe71-52d7-96a3-8e53f66ac1a6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a25a9ff1-f951-54c5-bbf7-ce80ae8fdc83 | note | Check Item - Check Item
1269462b-ac22-5976-96be-3de565b1205a | note | Reference - MRTS28 Cl.4.5.1
536bf257-184c-49d3-9461-595a6f3245e6 | checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
5e827342-5a3b-5384-9dcc-d67d9026f05e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
05e8c563-9560-56b9-a932-c0724222a90e | note | Check Item - Check Item
fc8b6e5d-cbfc-5dde-8062-03fff089f2fc | note | Reference - MRTS28.1, C.l 3
9c6a8237-3257-4441-b544-712ae4d6e699 | checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
98cc444a-b1d3-5d61-9cd3-c32607bfa390 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc623e5b-316b-5251-a94d-6561121ebb47 | note | Check Item - Check Item
46e4cd2d-7958-56fb-b827-bc06009998be | note | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
3e328fab-c426-451a-96c4-53fd0bcd7c87 | checkpoint | Final Verification
7bd0eaf9-a2cf-58f8-ae0c-8105f46d3105 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
040f4e94-8775-5434-a8fe-dce77037c8b3 | textbox | Print Name:
ae1f91bf-7a4f-5b6f-bda4-7265d13b9c0b | date | Date:
74701139-c58f-598c-9a2e-74bb638498e6 | note | Project Manager Verify that the Above has been Constructed according to Specification
8a2b1bd4-6cce-549b-a81b-ab5925aec885 | textbox | Print Name:
07639ba8-d396-5d8b-a2e4-ff9b883882d9 | date | Date:
63c96cdc-cb84-4a53-9f17-5905e35df2ed | signoff | Signature
ba040a45-6498-4c3f-9351-3ade49a5075a | checklist | 51.00 - Environmental Management Systems | itp | 51.00 - Environmental Management Systems
ef4314d7-188d-461e-9e0d-d470c3b473eb | section | Details
5ee28d8f-39f2-4f47-b12a-c9d3a9ecdc6d | checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
c6d8b5b0-697c-5295-9c37-60d97b180b1a | note | Check Item - Milestone
c1dc6c96-acfa-5192-a612-a19304aa0391 | note | Reference - MRTS51 Cl. 6.3
e76bcb00-c716-4896-b7bd-9e185c053eb1 | checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
13853089-1944-5352-9f04-076429d6e43d | note | Check Item - Hold Point 1
d6ac5972-ff9b-5e97-8bdd-39a1d0337da9 | note | Reference - MRTS51 Cl. 6.3
abb8748b-f54c-40b7-b755-102dc46d50ce | signoff | HOLD POINT
314745b9-232e-49a2-a887-0a3bc31242c3 | checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
cf3431fb-bb31-5f72-a0de-31208d2a4092 | note | Check Item - Hold Point 2
915e96a1-fa39-5e18-a8c6-4f74803243b0 | note | Reference - MRTS51 Cl. 6.4
978fae16-23b5-4bac-815c-07f48a97630b | signoff | HOLD POINT
f2a2d320-4bab-4482-905c-e4d270f57d8a | checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
e860a031-e5ee-5b71-bed9-7c835863b402 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b807bd8b-1357-5bbd-9fd6-d076566147ea | note | Check Item - Check Item
b7c03857-b7ab-586a-96dc-7dc79de67812 | note | Reference - MRTS51 Cl. 7.1
6562404a-c3ff-4027-bb21-d6d67505ac32 | checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
81f2d39a-4486-53dc-a1a8-5a76edb788a7 | note | ○ Landfill Gas Requirements
580712e0-7525-5157-9491-af0c64bac548 | note | ○ Contaminated Land Requirements
be28d2a8-79e6-50bc-b5ef-ff0bb9286ff6 | note | ○ Water Quality Requirements
39046cd7-dc25-5a92-b1de-1c9ab028677b | note | ○ Bio Security Requirements
661702a9-a8ef-5674-a70b-2778cdfceeea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
258cf480-3d1f-5f23-b55a-e150a7646999 | note | Check Item - Check Item
f9709035-801f-54ee-856c-a1a984c8e53b | note | Reference - Contract Documents
ec51fada-4962-4306-a2fd-63d3d274e04e | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
ea5a4c23-433b-59fc-9365-5473b90897b2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15911f2b-8484-532b-9089-2f7b4eacd005 | note | Check Item - Check Item
1face5a0-5429-5f16-a697-1379fff72f37 | note | Reference - MRTS51 Cl. 8.4.1
2cda54fb-b602-4997-b9f1-189bb59dff9f | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
2b367b8d-654e-52eb-9f8c-92ab432b1ef0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3a407d3c-4501-55e0-90e5-b284a37bedf7 | note | Check Item - Check Item
65472ceb-9e0d-5b85-bfdf-08877aae03f3 | note | Reference - MRTS51 Cl. 8.5.2
57e40341-7e63-4738-9d15-447ed9f3f9a0 | checkpoint | Project records shall include all noise monitoring results if required
68427e48-1410-5fd0-adff-17b1354c1079 | note | Check Item - Check Item
fdbda6a4-6a20-5272-ba10-3cffed3d2855 | note | Reference - MRTS51 Cl. 8.6.3
34b0b884-3486-4add-87eb-4e26d004e986 | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
02aa5d8d-e82b-5f68-999b-964cc379f813 | note | Check Item - Check Item
0096b841-8cbf-5ab7-a15e-aefa9a182d48 | note | Reference - MRTS51 Cl. 8.6.2.3
b3791818-d9fd-429b-beeb-d4ef0589da3e | checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
6706b3ef-d17a-56f3-9d6b-cf0a1c23ad71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b5d9effe-787f-57fb-9569-d7aae45e3f92 | note | Check Item - Check Item
0b4d9c01-0861-5565-9d15-04567d8a0e84 | note | Reference - MRTS51.1 Cl. 8.6.1
169c1ea8-4925-4552-ae08-aa11c418da43 | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
74c0a7a8-ac6b-5c88-9ab1-e5bc60f35742 | note | Check Item - Check Item
41b8b27c-19bc-5ac5-9ac4-dcddbc7b282a | note | Reference - MRTS51.1 Cl. 8.6.2
ad59d316-03d0-4d4e-98fe-b78ec53edee2 | checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
983d9855-72d4-56c7-bea3-b32ac85e9197 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5a8701c8-aa30-57c5-8199-181cf195d734 | note | Check Item - Check Item
eb67a90e-2535-5f11-8192-9aa0e19b1a15 | note | Reference - MRTS51 Cl. 8.7.3
73a512fd-44c9-4d30-84a1-2c3816d80e94 | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
cbd2449f-add2-5526-a853-1cae1aafe2f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
83a57302-d80b-5bf3-9402-677f81e63a14 | note | Check Item - Check Item
2d4fc35e-438f-5eb2-b945-bc74959f3e65 | note | Reference - MRTS51 Cl. 8.8
77ee3e24-bc5b-4e4d-aed9-c93573d50400 | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
45f5c751-32b3-5284-be30-322d404719f4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5e2b3ee4-9432-598d-8fe6-1a0288be2954 | note | Check Item - Check Item
0910d2b7-20c6-5de0-a6e4-b2858f415ad6 | note | Reference - MRTS51 Cl. 8.9.1
fafb56c9-51b7-4c9f-8964-c0e0443cddf2 | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
8018a32a-b6e4-5796-a4e1-e8d220bd280d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15f7db6f-d0ec-5b72-9040-f81d0426ac86 | note | Check Item - Check Item
c84489a2-06bf-5996-9833-a87762f5ec09 | note | Reference - MRTS51 Cl. 8.10.1
c301c209-7a70-47ee-b4b9-2a66f4ad6223 | checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
450b7b7d-e0fe-5dad-a497-caf11a29251d | note | Check Item - Check Item
50f1fce6-acfe-50cb-aaa5-dadc47a9c10e | note | Reference - MRTS51.1 Cl. 8.10.3
ba30a520-7ec7-4e62-b3aa-d7821717cde9 | checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
a422fdc1-94ca-5903-8ba0-88bf7907c098 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
90a710c3-03e4-5e34-978e-9e5250883e56 | note | Check Item - Check Item
b286a774-383f-580f-b18f-31f08739e485 | note | Reference - MRTS51 Cl. 8.11.1
05095903-8395-4fbf-9358-a01d15dfd92e | checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
3957ce23-ef82-55b2-995d-d735ebd9839b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f0dab910-3bdb-5cbe-be59-cb3cba69d46a | note | Check Item - Check Item
9af9354d-4a3b-5660-b5ca-3b9eacce979f | note | Reference - MRTS51 Cl. 8.12.2
8ceb930f-38e1-475c-aa30-c27e6f0847be | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
5b478222-bfe3-5567-aac0-bc76fb8f0ae9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
368dd313-6da8-500e-9243-6e33bf71cb5d | note | Check Item - Check Item
57085187-06b1-5476-a3c4-33e02167983c | note | Reference - MRTS51 Cl. 8.13.2
fb2239f3-f4ba-421a-9092-44cab1e1a22f | checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
667bc6f1-6d75-514a-848a-b6ad32f5e007 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1f2bc45b-870f-57de-b046-f27232b604ab | note | Check Item - Check Item
b2a26438-11d0-578f-ab53-49448114b1e4 | note | Reference - BCC Supplied Certificate
39152fd6-facf-42f0-b941-ead3b73984e0 | checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
d0c541f0-122f-584e-9da5-1ca4e7e8a697 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d2831ae3-c1fe-53ae-8fa8-d641c4bcdb51 | note | Check Item - Check Item
ec72892d-3660-57a8-8d24-b9e514d71a9d | note | Reference - MRTS51.1 Cl4.2
9c3384bd-d23a-4ced-a29e-87520fc4d3ba | checkpoint | Maintan a animal tamping register inline with the SMP
8e1f97c3-07e6-55d0-a30e-6a1e74b1e4c1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec81d6f1-d117-56a6-a09a-3d0537167f9c | note | Check Item - Check Item
93718b07-231b-556e-8b80-8a2f1f8a8d13 | note | Reference - SMP requirement
6d61fecf-b4a6-4c66-8a48-5d6af0e2553a | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
8e470aaf-9aee-5f29-a495-33fd1047df91 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8316eac8-4d05-50a3-9fcb-edd4146561ce | note | Check Item - Check Item
c9080970-aa38-56da-879a-c6c2344e09b2 | note | Reference - MRTS51 Cl. 8.14.1
fb04d28b-62a5-46eb-b175-b67b5800baa9 | checkpoint | Final Verification
d6ac6396-b335-583a-8052-40c5fa60ddba | note | Project Manager Verify that the Above has been Constructed according to Specification
1156846a-92d0-5e68-ad12-39ef067db2b7 | textbox | Print Name:
0d167df9-04fc-5072-b3f2-c1972f54bea4 | date | Date:
35400b9b-f8e9-550f-b600-e9dc5482109c | note | Client Verify that the Above has been Constructed according to Specification
a1f27e46-9c39-5623-9442-697c43f759e6 | textbox | Print Name:
f5ccc37c-efa5-5df6-9a4b-1de1f00ee489 | date | Date:
96a914f9-9260-4ae1-af68-9c1ba3f873dd | signoff | Signature
efaa4d9c-5fe2-482a-ac84-6995868b07c6 | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
6fc58a41-8473-4ba9-9569-da67516e9cb7 | section | Details
9611d4fe-d759-49ba-a399-fb585e383026 | checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
b8bc53df-c83f-5b6f-99ba-0f6ca63e22d8 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
43d0c29b-8edc-500b-8a42-e30a5645e3bd | note | Check Item - Hold Point 1
702a8804-f4b1-5a86-849f-62ce4eafd204 | note | Reference - MRTS52 Cl. 6.1
ff8af644-2bbd-4c08-8771-92537e474f38 | signoff | HOLD POINT
cd37f7ab-9814-4bc2-b6ad-3b19282a720d | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
71d79644-7964-5523-b91c-b2cb189db5a6 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
dcf2a9c6-b530-560c-bbd6-5e98aa7b6fdc | note | Check Item - Hold Point 2
5bd743bc-f336-514a-8a53-b4abd925975e | note | Reference - MRTS52 Cl. 7.1
44f2d179-05a8-47cb-95a5-b56db5247671 | signoff | HOLD POINT
497f2cac-420e-4ec6-a1d4-4ba17296f95a | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
313fe1bc-01e7-5315-a406-90c317aa6e47 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
89b18faa-b61c-5a6b-bf93-28d2b602626e | note | Check Item - Records
84a0dc7f-ff7b-5033-b74f-e149a9f825d9 | note | Reference - MRTS52 Cl. 8.1
d8a508a2-ee57-43ce-b4d7-73723e466cf3 | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
7727f1fe-6dd7-5759-b635-8be0f81662d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8ba4933c-9869-5e23-9fbd-61c27f8baaae | note | Check Item - Records
33181779-0e8b-5828-bf25-4694226a0ed6 | note | Reference - MRTS51 Cl. 8.2.3.2.1
41d88670-f01a-4df3-9543-714cb00d8550 | checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
c6fa6c47-7d7a-5dfa-994a-e2237577df4c | note | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
088aa021-25fc-5d4e-b4a3-5564b9f9df02 | note | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
94662e8e-558d-50f7-8cce-256ed7900a8e | note | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
ebf49e16-d959-5900-aaa3-c0ccdc820f7f | note | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
531f42fe-2e14-52a7-b36f-d0a8180eac33 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
429d9398-f4fe-5503-b367-8f0758d3fdd7 | note | Check Item - Check Item
85a096bc-53c9-5641-a193-fbd8804a1d17 | note | Reference - MRTS51 Cl. 7.2
786f306b-3ef4-4127-82ac-7739882e0255 | checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
dd032a14-11cb-5609-9fee-f97f8b5ce150 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f8d34f72-a624-5457-a9a3-c96fff9e2cce | note | Check Item - Check Item
c61dcd01-32cd-5a5e-bf2a-f7ef3d5aedfa | note | Reference - MRTS51 Cl. 7.3
3a2f269e-670b-4a7b-ad89-298b19560220 | checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
c6a702cb-f760-5cf4-8489-8af5bdcb9b02 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
69157357-d194-5141-b929-b1a1bc21bd30 | note | Check Item - Records
313b25da-d7d4-5746-99a6-beeb33318875 | note | Reference - MRTS51 .1 Cl. 4.1.1
2a138cbd-bb45-4340-89ed-60a3d6c0914a | checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
49454f8e-5620-503a-af69-b9c86b3c19c0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e642aa27-faca-58fe-9853-9a53e1672f98 | note | Check Item - Records
ed1161c8-f000-505a-b97c-4f62620bfa3b | note | Reference - MRTS51.1 Cl. 4.1.3
ace91118-b86b-49fd-b593-6143cabfa380 | checkpoint | Final Verification
43d69d5d-0817-574a-8efd-77ae9aaa88b7 | note | Project Manager Verify that the Above has been Constructed according to Specification
c487f288-aad1-5594-ba64-0ab0bb129b52 | textbox | Print Name:
d46310c0-1a55-5f78-ad8d-7219393071f8 | date | Date:
ddf9c4f3-c02f-5907-a59a-9f80527ca43f | note | Client Verify that the Above has been Constructed according to Specification
fbc0d397-f8e2-5f6f-a0bb-5359d4abbc00 | textbox | Print Name:
ddf60681-d393-5eeb-9078-025d045a7503 | date | Date:
10b1faf1-b317-4fa2-93d9-4f2a298d45f8 | signoff | Signature
b43bf496-01e5-4311-b7a1-d58a3010c836 | checklist | 70.01 - Placement of Concrete | itp | 70.01 - Placement of Concrete
e6a53a36-2548-425b-92f8-83b95c9b7ef9 | section | Details
fed91389-8b19-4204-939f-021347ffe4e5 | checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
973479be-d932-56de-8f09-fbeb4886bd78 | note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
f6721eb7-5e3d-5507-9f1b-341fff713ac1 | note | Check Item - Check Item
13694148-9fd7-5402-a75a-f8656832d74e | note | Reference - MRTS70 Cl 13.1
d3e87815-aa6d-433b-84ec-3cfeeec33828 | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
03f247b4-ca76-5dbd-a238-4c2d9add91a5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b53d9724-9f5c-54c6-9275-6f49a21fa002 | note | Check Item - Milestone
3a52748c-2a80-5591-9164-306b3def998f | note | Reference - MRTS70 Cl 15.3
9f06867e-48a7-48ae-b4b1-fdfd2e44b0a0 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
8c550e4e-1300-56e0-b1a4-2287d0e3b5a1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
46b82606-8ab0-5eb6-b361-aa1aa557c543 | note | Check Item - Hold Point 2
928ef50d-a0d8-5926-b47b-c053f3945a8f | note | Reference - MRTS70 Cl 15.3
a0e7d635-9161-45fb-a5e3-f6c075d5bf30 | signoff | HOLD POINT
1fffeb17-11b8-4399-a7fc-6ec87da2bd9b | checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
f1e7c82d-8fd7-5c7b-9165-3bbdd961c232 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3a8ce0d3-7978-5d57-83b7-6b666be3876c | note | Check Item - Hold Point 3
762c8353-6936-58f6-9722-345aff8d781e | note | Reference - MRTS70 Cl 15.4.1
bf6f3335-4f9e-4b2d-bd3d-9eab69160691 | signoff | HOLD POINT
68a10382-a09c-4890-a03c-65509ddfb4ce | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
39fb46f5-67b3-5030-9ad1-fc63fb2b2f71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a012b314-44ed-5341-bf4c-352b7fe3f031 | note | Check Item - Hold Point 4
bdefcc88-f31a-54a2-82d4-97e14ffb641f | note | Reference - MRTS70 Cl 15.6
81e0c6dc-df28-49e9-96ce-1106a3dbf352 | signoff | HOLD POINT
3e5ee2d1-e7c5-44f3-9a72-d4a48f80681b | checkpoint | No concrete shall be placed in the Works until:
4cca99e3-2d8f-5747-9e32-37d9dfafeb07 | note | a) the formwork and reinforcement have been inspected
70bbe150-928a-5b18-99ff-7410ee5f0f79 | note | b) all foreign material has been completely removed from the forms
c29de313-2c93-5bdd-aba5-a03bb55d44c2 | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
3a6483a6-5c60-5abe-8a03-9254dc2a94da | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cd5eb428-391d-54f1-a063-5a1f5ae3f0bd | note | Check Item - Hold Point 5
ce18c9c4-0fed-56fa-a0c3-1123e48f244b | note | Reference - MRTS70 Cl 15.6.1
931f6e16-0fbf-40f2-8aae-e7fd45887aa7 | signoff | HOLD POINT
fe740d9a-ca5e-4543-9864-9434ea72fc48 | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
95173b36-1892-5413-b8fd-ed3f10891da2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
288ae8d0-777b-5f11-8680-cc4bc84fa83d | note | Check Item - Witness Point
52e07e07-f67f-5b89-8dc7-b2220097f2b7 | note | Reference - MRTS70 Cl 15.6.1
2e9c3165-f415-4d87-afc9-ecfe125a3bf4 | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
531eafb3-17d1-5306-a081-44fa0400c497 | note | Acceptance Criteria and Frequency (Project Specific) -
41a7a5d3-9db7-527f-be7e-701fc3e74d88 | note | Slump Test: ¦¦ Spread Test:
5f10864c-541b-5ae0-8dd2-d9345e5979c6 | note | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
b7efde9c-0937-5fb2-888b-8f3b86a44c41 | note | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
36e336a3-aee9-5c5a-8fd8-982165b23953 | note | 80<110 - ±20
023d366c-415b-5d2d-9005-876c852b4f09 | note | 110<150 - ±30
35eacc27-25cd-56a4-9746-3b2cd14cdb2f | note | 150< 200 - ±40
a3d6923f-136b-5520-ba1f-a2c0be624556 | note | Every Load
70a1a9c0-c775-5dae-b8b9-a10f8da25355 | note | Check Item - Check Item
fbcb68b0-c1a4-506c-b7da-8157aadef975 | note | Reference - MRTS70 AS 1379 Table 6
234a3601-951a-4444-9e49-ab804d747945 | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
a86e4ea0-b351-570e-aa36-194e713bf2bb | note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
12fd9e83-8294-50c4-a93e-f8703efd6e10 | note | ○ 4-10 Loads - 4 Samples
8a498961-88a4-5200-a540-d3763102187c | note | ○ 11-23 Loads - 5 Samples
84d2802a-c3c7-5c09-b801-49bbf7a8dc53 | note | ○ >24 Loads - n/4
7e6a070d-7b14-5937-8e58-a6385f98b957 | note | Check Item - Test Results
0497db6b-c086-51fe-a236-5a990ee539a1 | note | Reference - MRTS70 Cl 15.2
526bb768-0f13-4461-af13-dc65d2ee3e02 | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
5adb5a5d-4ae1-5792-ad8d-5d0395362dbb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2ec6f555-6a3c-557e-96f0-d2ce378cc39b | note | Check Item - Check Item
e936be9d-ba6b-5f05-9cfd-5310933f81a4 | note | Reference - MRTS70 Cl 16.5.2
bdfc7736-27c8-4cf7-81ec-c3d5b2b2f380 | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
3ade8744-a735-5254-936c-f73f0e752538 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bdd9b0f5-bdff-5408-8a1c-643732b1efc1 | note | Check Item - Check Item
b2b889ee-14a6-5cc7-8ffa-ff8462963942 | note | Reference - MRTS70 Cl.16.5.1
a4493eeb-159b-4fcc-abb1-59e0a7a57ab7 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
387bdd83-c6d2-5f90-ae87-c6d15f386b0a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ca40158b-dc80-51f3-a537-4022eadbaa57 | note | Check Item - Hold Point 7
e618a3fc-ce21-51f8-a725-abf66ca1aea7 | note | Reference - MRTS70 Cl 15.13
30a64644-65e8-4a85-9310-23813d2ee878 | signoff | HOLD POINT
635200c9-80a7-4631-a33f-5079f8277911 | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
a41099f1-308a-5dce-9f45-4b3de09553f4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f438193b-18d8-5a77-96b1-45c77142cdf5 | note | Check Item - Hold Point 6
51899ff6-2c8d-5149-ba3e-a6b358de8d6a | note | Reference - MRTS70 Cl 15.8
3f67614f-1437-4280-b78a-ef26b14c1f5a | signoff | HOLD POINT
c0b1c785-ec5e-4783-bc77-77c30df15123 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
e58c8bfd-910a-5f0e-a301-e5232409b2d0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
28bc3cdc-3f61-56c2-b37d-c32e9a8bfe4f | note | Check Item - Witness Point
49767274-595b-5425-b9ac-5d7c18aec4e3 | note | Reference - MRTS70 Cl 15.8
52587b4c-16a5-4f8c-87d9-f806f9161210 | checkpoint | Following removal of forms
54279157-e3f9-5173-a3b4-83b2107ea7de | note | ○ Fins and unwanted projections are ground off
cf0c84cf-c07f-53c6-80b3-3b89538008ce | note | ○ Pockets and honeycombed areas repaired using approved methods
e8feded8-8c22-570e-bb08-e544bb51f515 | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
a913719e-1a0f-5709-ad64-df858596092c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8d376e0b-9376-50bd-a009-bd84a58bf93a | note | Check Item - Check Item
c1cdaeaa-c77b-5f44-90c2-1297f9d19531 | note | Reference - MRTS70 Cl 16.8.1
2ae0091f-cc27-4ad6-b969-f98f46445442 | checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
d715eb3d-2dfb-56ec-b199-89aff7d3e9ba | note | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
154d4e73-37d3-576d-b4ab-babbb5e733f0 | note | Check Item - Check Item
49b3a88c-4073-5034-a4c3-160d0a96e644 | note | Reference - MRTS70 Cl 15.7.3
a2743cf3-f3e7-45a9-8840-466068aefd2f | checkpoint | Acceptance or Rejection of Hardened Concrete
e36381c7-0eb4-5eda-a60d-5868f4a3d0af | note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
38ec00c1-39a9-5803-8840-619c75266326 | note | b) < Fc (Ave 3 consective samples from Lot)
82962978-464b-5f7f-89a9-70d450addba0 | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
c33cdc0c-29cd-57e4-bce0-7f1118a467bf | note | In addition
b4891086-f984-580f-a9b6-25afec565c52 | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
890bb00b-e670-5864-9977-e805debb1183 | note | Check Item - Test Results
ab231f18-84a5-5e10-834d-ba9503a157d6 | note | Reference - MRTS70 Cl 12.5
b4a722d4-39b8-4e90-97e9-9e0c3ce9839f | checkpoint | Final Verification
f60e450a-6cbf-5161-b966-b2218b29ec8a | note | Project Manager Verify that the Above has been Constructed according to Specification
470c77fc-4628-5bbc-b547-764be7ce3196 | textbox | Print Name:
402f33b7-3a20-5635-9693-a08bf02816dc | date | Date:
d5d7395e-cf35-5dc9-a160-f917d0c94041 | note | Client Verify that the Above has been Constructed according to Specification
8fcbec3d-b31a-51ea-b3ff-14bd94886dca | textbox | Print Name:
44f2153a-ad0e-5111-9c27-48cae17d45c8 | date | Date:
01446448-51a7-4354-b586-4909c28e0e2f | signoff | Signature
fde99772-10e3-4e42-bb69-3f82371d20f5 | section | Details: Concrete Record
9d78b9df-7d12-4119-98c4-c1c280b43f80 | checkpoint | 1 - Date
3bb65070-6783-55d9-be27-076d3b77bdc4 | date | Truck 1:
91a64893-0095-5ccb-9ad4-a5b9bdd3aa1d | date | Truck 2:
b3de8e47-888e-511e-a500-0fb2c61176c7 | date | Truck 3:
8157b841-7e74-53e9-a04c-6c7e4b896d44 | date | Truck 4:
8a246b26-55a8-427a-a297-d0f9cbc0e137 | checkpoint | 2 - Docket
b6775d07-bd1a-5cb8-9b39-47d6b1c54385 | textbox | Truck 1:
77749201-e5ef-58f8-be39-a76edebaa735 | textbox | Truck 2:
e6e42200-1346-5b94-aae8-6cf9f9aaaadf | textbox | Truck 3:
031371f0-2b38-58a1-93ee-32738c51de15 | textbox | Truck 4:
6c0ad0c6-7c41-4e7e-8c00-482bbfc41032 | checkpoint | 3 - Time Batched
3f8c2c2b-e1fc-5979-8434-fb4596dcfb40 | textbox | Truck 1:
c2fe0dc8-11db-5775-8927-d1b4d3c8aca6 | textbox | Truck 2:
d7a0f941-c55f-53bf-9c36-92274f2e1be0 | textbox | Truck 3:
f58717cb-9000-5f04-aa4f-236850174ead | textbox | Truck 4:
598e2992-7195-49c4-b925-9b310f00294e | checkpoint | 4 - Truck Arrival Time
dc11f4fc-9940-56cf-a153-fe43c328bb3c | textbox | Truck 1:
b004a51e-fb07-5ddf-8e26-782ddd875f78 | textbox | Truck 2:
2fd856b0-3f02-5ccd-bd6b-9ac32b308e3d | textbox | Truck 3:
9fe968fc-36b6-5b88-9e77-1354fc064908 | textbox | Truck 4:
7fc0dfad-f76c-47dc-b50c-f3b667ff353e | checkpoint | 5 - Load Size (m3)
dbf0f233-d548-58fc-a477-e63e54fc7692 | textbox | Truck 1:
f701b32c-9f98-5a37-b437-1828081f2a6a | textbox | Truck 2:
fe01080b-0382-5b6c-89b4-5f494c4eb848 | textbox | Truck 3:
b15cfe34-9d88-5d7a-a244-be22ff08fd2b | textbox | Truck 4:
8b6f379e-40e6-4290-bf12-d2ad8cfc2a10 | checkpoint | 6 - Mix
8ae215c8-f20c-4dbc-88f4-027676de0aef | checkpoint | 7 - Slump (mm)
17ad703d-418a-5c48-ad74-6505adc06139 | textbox | Truck 1:
e90471b5-9c89-55e7-936c-7f5dcb83fe6b | textbox | Truck 2:
ee6a36f2-4a9d-5e7a-b466-06bdd81e73a0 | textbox | Truck 3:
4e8b82d9-34d0-581d-9f8b-757e8b68cafb | textbox | Truck 4:
d2ff6899-f59e-4d70-abbc-af44be81a915 | checkpoint | 8 - Slump Time
ce91a2da-bb99-5500-bb0b-bb9f7741c954 | textbox | Truck 1:
eb5594c0-2089-5990-9259-3b0500470d47 | textbox | Truck 2:
e0110d96-acd1-5545-b74f-ffce69e5c953 | textbox | Truck 3:
964725ce-0ad4-5a6f-973d-b8b797207005 | textbox | Truck 4:
317e0b30-c671-43a0-ae08-73c279ddff68 | checkpoint | 9 - Concrete Arrival Temperature (˚C)
5f1662c5-fdf0-5695-8935-763f17e693fd | textbox | Truck 1:
f5560435-a94e-5610-bce5-4202bfa18a8b | textbox | Truck 2:
859cc70e-d53b-5ec4-bed2-91bacafd96d9 | textbox | Truck 3:
642fc01d-4dce-5408-b943-ea44ca987dfa | textbox | Truck 4:
c2f6f9f5-8c43-45a6-9664-755bc338d178 | checkpoint | 10 - Ambient Temperature at time of slump (˚C)
04696778-aa99-576c-accc-b5ed4ed983ad | textbox | Truck 1:
7de37d37-291f-5ad1-b7dd-d0a669c27525 | textbox | Truck 2:
a727c49a-10ce-5f99-ae34-24db5b972b5b | textbox | Truck 3:
6cc6f6e1-e1ee-5ff3-8468-aa03a5b4d243 | textbox | Truck 4:
335df902-d647-4bf4-b78b-21fc8002cfaa | checkpoint | 11 - Time Start delivery
7573bfe3-6596-5e41-9475-19d3536d7411 | textbox | Truck 1:
99fdc344-11e4-5e16-8ffe-bf96af3cdb2c | textbox | Truck 2:
ea7f459f-a179-5a21-bc9d-1e6c4e85640b | textbox | Truck 3:
958a2528-a593-54ed-bce8-e01c684def9a | textbox | Truck 4:
a3340414-c26a-4644-85c3-e138f7654140 | checkpoint | 12 - Time Finish Delivery
ac0f8ab9-3b6e-5082-b100-4e1a8d74950d | textbox | Truck 1:
109bcf6b-cbd5-5f54-ae56-070d96a7c3c5 | textbox | Truck 2:
92bffe96-2e35-58f5-9ecc-fc4e47448771 | textbox | Truck 3:
ea5bd944-1fdd-54f5-bad8-8bd810c497b2 | textbox | Truck 4:
9a763c70-e66a-45df-80ba-2f5bfffc715e | checklist | 70.03 - Supply of Concrete | itp | 70.03 - Supply of Concrete
1a5db68b-f045-4fb6-8113-0f91bf4053e6 | section | Details
32b580fd-ec14-43a9-9205-8448dc02e22d | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
490c5d85-370e-5c1e-9516-c1bd50cac3e7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
800e02ea-c34c-5074-a885-e74253b52c5c | note | Check Item - Milestone
d7ca7f20-0243-5fc2-bcb0-95115736f59d | note | Reference - MRTS70 Cl 9.2
f34b1440-83cb-4e5e-81a0-9322435176e2 | checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
1d326cc9-5251-5e1f-8719-6ffa3bd08f46 | note | Check Item - Milestone
5576398c-404c-54c6-b7ad-6a4b7998d07c | note | Reference - MRTS70 Cl 17.6.1
b060d02f-2cc5-410f-aa10-66a9a7a07b73 | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
ac6ac6ef-464a-5c78-82d1-fb7611ebabfd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
91c6e6bf-e0b8-5804-8d09-6a14cfeaa8b7 | note | Check Item - Milestone
1a7e5020-20ea-5ba7-986c-9d62fb6099f4 | note | Reference - MRTS70 Cl 13.1
3b8af8dc-c48d-47fb-8f3c-2f2f1f145711 | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
f73ffbd0-94e6-5c80-8a7e-f77716faa575 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d0f1d01a-9189-51d4-a035-a9a8b1778229 | note | Check Item - Milestone
aed98f4d-bb17-58a8-aa30-17ac999efd79 | note | Reference - MRTS70 Cl 15.11.1
7b86e539-46e7-422f-b262-0df37cc01a2b | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
ccf56432-459d-5aed-b7b7-425c449546d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9f09088d-3e8f-5f92-932b-289b018ccab2 | note | Check Item - Milestone
45c33632-6496-578c-b8af-a2e4d21d0b00 | note | Reference - MRTS70 Cl15.5
1c884f48-94a7-43c2-82d3-173f325a502f | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
ccc0d4e3-d9dc-503b-9537-ada32663e195 | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
1e982431-6c1c-5569-8531-51790c83f0fb | note | Check Item - Witness Point
f5069bc2-87e5-57c6-a91e-f653cccc1758 | note | Reference - MRTS70 Cl 15.1.1
5b4498c8-1428-479d-870a-58ad6bd7c8b7 | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
dd4d27c0-a930-587d-b70d-29f743a6b64c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e7d790de-3a79-5ab8-944a-6be3f9469c11 | note | Check Item - Hold Point 1
b17a998c-e059-587e-8889-6c33827fb668 | note | Reference - MRTS70 Cl 15.1
ac73df4c-76d4-44de-b1dd-74890ad6766a | signoff | HOLD POINT
f68f830e-13aa-4dca-bcfd-87c95d90e54e | checkpoint | Final Verification
61839899-feab-5e3a-8d4c-bf0de27e55ad | note | Project Manager Verify that the Above has been Constructed according to Specification
0d1a786e-8032-587f-b508-a1c7bacc13ec | textbox | Print Name:
10998312-0da5-5afe-ad73-5369e9861a6e | date | Date:
7c075c96-0a47-5f98-bc91-e3183e882d33 | note | Client Verify that the Above has been Constructed according to Specification
2bd90da5-884d-5a5d-b086-89cd4b11e5ed | textbox | Print Name:
2d9800e4-4020-5ca9-8024-8db70461a65a | date | Date:
db3475da-87aa-4a21-9e45-7d3a242546ad | signoff | Sign ITP
3ab5fba2-9dee-4224-94f8-87367b356a52 | checklist | 71.01 - Reinforcing Steel | itp | 71.01 - Reinforcing Steel
de53435b-6fa5-4362-aa8a-c92275b785d3 | section | Details
260aacff-ecf0-4272-97a6-6535c8fe8709 | checkpoint | Submission of proposed supplier of reinforcement with three days notice prior to supply.
b3f5db90-0fe7-5f69-800c-20514f9764fa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f6e40bcc-b6fd-542e-bab9-997db8d098dc | note | Check Item - Milestone
70af5ea6-1d3e-5732-a3a9-e75de3a7505d | note | Reference - MRTS71 Cl 6.1
5f56564e-5039-4edf-bb58-024a7d95d3d2 | checkpoint | Acceptance of supplier from Administrator
752dd03d-d7f8-59d6-9938-240f742d43eb | note | Check Item - Hold Point 1
f2e2dbc6-63b3-5cff-9ae1-65ea427dfab8 | note | Reference - MRTS71 Cl 6.1
0c5f5e46-a3ce-45cd-997c-ed0268d17043 | signoff | HOLD POINT
7585f8ac-65e9-4e02-b9f7-6e7c70886189 | checkpoint | Inspection of steel reinforcement before placement of concrete.
88860514-0831-5925-a004-f4ead83de55d | note | Check Item - Hold Point 3
927d992e-6860-554f-9d92-e0596aa646c6 | note | Reference - MRTS71 Cl 10
df46adf0-ae22-49e5-a0a6-c1010ccbbc63 | signoff | HOLD POINT
2b10a7c3-82d8-4c8c-b723-b9156ce2da7e | checkpoint | The min. clear distance between parallel bars other than lapped bars shall be the greater of: 1.5 x the diameter of the larger bar, 1.5 x max nominal size of aggregate, or 40mm
26c13691-8793-54fb-80fa-3682977e9e76 | note | Check Item - Witness Point
61845e39-76e4-589d-a6fe-3fa2b1871771 | note | Reference - MRTS71 Cl 10
9012437a-2301-4b95-bc70-c93db784397b | signoff | WITNESS POINT
ce2a068c-4d12-4d53-bb86-8726449548ca | checkpoint | Permitted mechanical reinforcing bar splices listed in Clause 1 of MRTS71.1.
c4355047-9567-5fe3-a5b0-b88ee7e0108e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
40eeb640-dee6-5ffd-b7f9-b15d1a505e53 | note | Check Item - Hold Point 4
04c6cb20-8e56-5616-8c3f-9f63d349cc99 | note | Reference - MRTS71 Cl 11.3
7929c9af-011a-47df-9728-147697f6f794 | signoff | HOLD POINT
1b1ae11a-fe27-45e2-a05a-f7b181c4e499 | checkpoint | Installation of mechanical reinforcing bar splices as per provisions in Clause 11.3.2
a2f24759-44e7-59e9-a82e-457de4f28128 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
51762522-113a-5587-a360-95540b81ff1e | note | Check Item - Witness Point
01aca331-2239-5fa8-bbec-46818e251ff7 | note | Reference - MRTS71 Cl 11.3.2
68b548b9-1c1c-4418-a7bf-8422cc712446 | signoff | WITNESS POINT
b435ee8d-fc16-442b-a159-8bf34a48dd3c | checkpoint | No substitution of different size, grade or ductility class of steel reinforcement shall be placed unless approved by the Administrator.
604571b4-6e47-509c-a473-e3d4b8d66593 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
946f2788-0e0b-5d3e-976e-a9109f0e262f | note | Check Item - Hold Point 5
ecac97c0-4d8e-5b9d-9694-80fc70e8a92a | note | Reference - MRTS71 Cl 13
492b5261-2880-4d88-83ca-8783caf285af | signoff | HOLD POINT
e25712b4-4ce8-4b1e-a04e-145eb1cfe456 | checkpoint | Application for substitution of reinforcement forwarded to Administrator 3 weeks prior to supply
3f48a051-a0eb-5e15-b7c9-368ef187346f | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
dab7a34a-3f80-52dc-aa17-d27e1f0f629f | note | Check Item - Milestone
70239bbf-aa9a-5a55-a7c9-aaf964fca872 | note | Reference - MRTS71 Cl 13
993d1d0a-19bd-49a1-b06c-57b07edce8eb | checkpoint | Final Verification
5bb644b3-e145-5826-918c-c519db173b70 | note | Project Manager Verify that the Above has been Constructed according to Specification
7535fbd2-d3c7-5e0e-9432-dddc053628bb | textbox | Print Name:
0e5c86f4-35ec-54df-bdae-d243da9b8d32 | date | Date:
071e80b4-337f-5a1a-b33f-0a122397f147 | note | Client Verify that the Above has been Constructed according to Specification
579251b4-9307-5f5e-9fc1-7914656548b6 | textbox | Print Name:
2c00dee8-44ad-5003-9a19-188dbb5cf41f | date | Date:
26feeece-b9f0-45d3-8632-6a2854e2ae55 | signoff | Sign ITP
867db1cf-7ff2-42c8-b7c6-511d4b5a55e7 | checklist | Horizontal Drains |  | Horizontal Drains
85ab2f10-1004-4408-bd26-3845d1a680a9 | section | Details
7efd8f23-e296-4977-acee-8510a178b533 | checkpoint | Horizontal drain construction procedure shall be submitted 10 days prior to the start of works, construction procedure shall nominate the proposed geotextile filter fabric, procedures for drilling and procedure for installation of drain pipes.
a76b9966-09da-5437-a669-2b655005d49e | note | Acceptance Criteria and Frequency (Project Specific) - Written
aa76c217-9946-515f-adf7-d1a793e0371d | note | Check Item - Hold Point 1, Milestone
457e667e-0741-5e9f-b293-dada940952ad | note | Reference - ATS 2280 Clause 4.1
dd3f1f70-618b-47a7-b248-03f2ce237ebd | signoff | HOLD POINT
6ba41657-174b-4af7-8d6d-0dcb79e76268 | checkpoint | Materials shall be as per nominated drawings the UPVC pipe shall be class 18 and comply with AS 1477.1, Filter fabric shall be non-woven geotextile conforming to MRST27 and be abrasion resistant to resist damage on installation.
a5c076ff-0000-509e-8ea8-044711da178c | note | Acceptance Criteria - Internal
9b477801-92a1-5748-9369-e4fa134515ae | note | Reference - ATS 2280 Clause 5
ce5bf6f7-b959-58a4-bd84-8b3beaa48ddc | note | Internal Check
b2820a3d-2ead-4b37-9687-c1cb8eabd830 | checkpoint | Location of drillign holes shall be as per the contract drawings and comply with the location orientation and length specified.The position of each drill hole shall be marked on the surface of the slop prior to commencemet of drilling, and notice sent to the administrator prior to the start of drilling.
7b836593-c2df-5500-9722-eba8bb888f5c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
58392c27-dc80-52d7-9b4c-106db0d65e3b | note | Check Item - Hold Point 2
6558ed52-a1a0-5c42-be5b-d7e2c0c9fd5c | note | Reference - Project Drawings
328f4d77-0554-4647-99d5-9bc7da502a1b | signoff | HOLD POINT
c39fb428-4bb4-4cbb-901d-d18f62cb6d6b | checkpoint | Positional tolerance must be within 100mm + - vertically and 300mm + - horizontally from the specified position. Holes shall be drilled ina straight line and shall not deviate past the straight by more than 25mm over any 2m length of hole.
e4a80568-57ae-5800-a4fd-5fe310ebd497 | note | Acceptance Criteria - Internal
bb68df03-2802-5e3f-b5d0-816fa0961a09 | note | Reference - ATS 2280 Clause 6.3 & 6.9
ceea98dc-18b6-4233-82ed-db06c5271d53 | signoff | Internal Check
6e3ecee1-088f-492f-9ae2-450e9e4f3bd5 | checkpoint | Holes for horizontal drians mmust be drilled on an inclination of 5 degrees dipping towards the exposed slope face with an acceptable range of 3-7 degrees, drill holes shall be 150mm diameter and drilled 100mm longer than specified depth to avoid excess material at the end of the bore shortening the hole.
35369250-5296-5a28-a121-ff38efc53a21 | note | Acceptance Criteria - Internal
cb2e42a2-18cc-5930-8758-d3eb2d510709 | note | Reference - ATS 2280 Clause 6.10 and project drawings
cd29571b-d158-549f-ae70-2bd1ea2094f2 | note | Internal Check
754676f8-7652-47a7-b7c4-af81c7f29cf5 | checkpoint | Installation of drian pipes shall be in accordance with project drawings, an outer and inner drain pipe is to be installed in each drill hole with the unslotted 120 degree section of the pipe at the bottom after installation of outer pipe the annular space between pipe and drill hole will be tightly plugged with cement mortar of atleast 0.5m from the end of hole.
c2452e02-5905-568d-b5a1-3b316a892368 | note | Acceptance Criteria - Internal
b997b152-c998-56b0-af74-47324429009b | note | Reference - ATS 2280 Clause 7
925b5389-9270-5007-9b19-7323259ca9c5 | note | Internal Check
3e9f317d-22fd-4e64-8f6c-71356a450373 | checkpoint | A drilling report shall be completed for all horizontal drains holes completed in a days production and will be provided to the administrator within 5 working days from completion of holes.
4bdf2118-af6c-5397-8ce6-1a5892ab5f80 | note | Acceptance Criteria - Written
454b62d4-26bf-50c7-adf6-37ce0f22cf39 | note | Reference - ATS 2280 Clause 6.16
6121f8e0-3ec7-5346-8520-9c097be64452 | note | Milestone Submission
ac997a2f-517a-4b06-a9f5-92efaa167614 | checkpoint | Final Verification
9a9242f5-d58c-58d7-8713-3c2df5ba8a14 | note | Project Manager Verify that the Above has been Constructed according to Specification
6c732c8a-75a4-51ee-9a23-d4fa50cbb1dc | textbox | Print Name:
94d12959-4fcd-5cc6-8e75-2cbc090dd9cc | date | Date:
e4410202-4a8c-5f0b-b4cf-23cdcf1762b4 | note | Client Verify that the Above has been Constructed according to Specification
d86a48d5-cd61-5ff8-b0a4-53f59fda460b | textbox | Print Name:
c27beb2f-9625-50ca-949d-99f6fe4c167c | date | Date:
b4b8bf26-eb85-44ba-9729-b433ebdd2b65 | signoff | Sign ITP
3d73c631-fc0e-43f3-a04f-f5f37a323da1 | checklist | Mac Mat R |  | Mac Mat R
af28b354-ed22-4bf4-9269-bff625c1dcb9 | section | Details
aa701e8d-a948-4ecb-af76-f6547c3fdaa0 | checkpoint | At least 7 days prior to works commencing the construction procedure for the MacMat - R installation will be submitted to the Administrator for review and acceptance.
e3e25a6e-69a7-589b-b726-7797f37219fc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f9af5a3c-7533-5f58-90d8-34864dacbdb4 | note | Check Item - Check Item
86fa008d-5383-4174-b128-d5ecfa00eb63 | signoff | HOLD POINT
a8011d25-9064-40d2-b888-cff913253c4e | checkpoint | Product shall be Maccaferri MacMat R or an alternative that has been approved by the administrator
e62f933d-f4fe-5b28-9300-c3e0285cb2f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6d2f48b7-2441-5a97-b774-74efc1308792 | note | Check Item - Check Item
06afb999-1a11-5bbc-9bf1-3cbbd38b5d8a | note | Project Drawings
6fa987df-5a95-47da-9c88-20e0c6e9e600 | checkpoint | Has the section of works been clearly identified and is there a lot map attached to this ITP
96e6aac5-35fd-572b-bdfd-364569017e68 | note | Acceptance Criteria and Frequency (Project Specific) - Internal Check
932db517-db2a-5573-b513-22a9cd7315f1 | note | Check Item - Check Item
593e38cf-d535-58dc-a724-b59b541d0a75 | note | Project Drawings
6b042474-f2b8-40fd-bdb2-54246623b13c | checkpoint | Macmat shall be anchored and pinned into top of slope with a 300mm deep trench 500mm wide, and then backfilled and hydroseeded over. The trench shall sit 500mm back from the top of batter.
36dc6e4e-33ab-50e3-88db-a7dd170e45e6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
882182e9-3fba-5ed2-963b-c4775a29af9d | note | Check Item - Check Item
a23ac53b-4528-52ff-9a6a-b19067b6d5b3 | note | Project Drawings
70ad2db9-8c07-462f-9884-5163ea2eac27 | checkpoint | MacMat R shall be placed in one continuous strip runnign down the batter without breaks, adjacent runs of MacMat R are to have a minimum 100mm overlap and be pinned in a direction perpendicalr to the angle of the slope along the over lap
6473d6f6-15a9-5436-b1cf-aefd45426bef | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2be80d79-e94a-5775-a140-02a601d455ea | note | Check Item - Check Item
55fe4846-018d-4ab5-8439-0d2dcafb990a | signoff | Manufacturer Specification
a2bbf7f1-3f73-4211-8fa6-16dcc3103331 | checkpoint | Final Verification
ce09a765-1267-5aac-97f0-1a2a5b8bae6b | note | Project Manager Verify that the Above has been Constructed according to Specification
568eba62-a422-5149-93eb-139af8df348f | textbox | Print Name:
6e945c59-88c7-5eda-8a21-e94c9390f67a | date | Date:
b55e2465-8348-5602-ba77-00fd59453edb | note | Client Verify that the Above has been Constructed according to Specification
1ed34b0e-cf9d-5bae-8762-bf83174616fe | textbox | Print Name:
de6c1f46-d18d-5baa-bc17-073c73643d24 | date | Date:
e8268a68-8e9c-456d-8183-eca11b5dff12 | signoff | Sign ITP