## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
867db1cf-7ff2-42c8-b7c6-511d4b5a55e7 | checklist | 3.HD - Horizontal Drains |  | 3.HD - Horizontal Drains
85ab2f10-1004-4408-bd26-3845d1a680a9 | section | Details
7efd8f23-e296-4977-acee-8510a178b533 | checkpoint | Horizontal drain construction procedure shall be submitted 10 days prior to the start of works, construction procedure shall nominate the proposed geotextile filter fabric, procedures for drilling and procedure for installation of drain pipes.
a76b9966-09da-5437-a669-2b655005d49e | note | Acceptance Criteria and Frequency (Project Specific) - Written
aa76c217-9946-515f-adf7-d1a793e0371d | note | Check Item - Hold Point 1, Milestone
457e667e-0741-5e9f-b293-dada940952ad | note | Reference - ATS 2280 Clause 4.1
dd3f1f70-618b-47a7-b248-03f2ce237ebd | signoff | HOLD POINT
6ba41657-174b-4af7-8d6d-0dcb79e76268 | checkpoint | Materials shall be as per nominated drawings the UPVC pipe shall be class 18 and comply with AS 1477.1, Filter fabric shall be non-woven geotextile conforming to MRST27 and be abrasion resistant to resist damage on installation.
a5c076ff-0000-509e-8ea8-044711da178c | note | Acceptance Criteria - Internal
9b477801-92a1-5748-9369-e4fa134515ae | note | Reference - ATS 2280 Clause 5
ce5bf6f7-b959-58a4-bd84-8b3beaa48ddc | note | Internal Check
b2820a3d-2ead-4b37-9687-c1cb8eabd830 | checkpoint | Location of drillign holes shall be as per the contract drawings and comply with the location orientation and length specified.The position of each drill hole shall be marked on the surface of the slop prior to commencemet of drilling, and notice sent to the administrator prior to the start of drilling.
7b836593-c2df-5500-9722-eba8bb888f5c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
58392c27-dc80-52d7-9b4c-106db0d65e3b | note | Check Item - Hold Point 2
6558ed52-a1a0-5c42-be5b-d7e2c0c9fd5c | note | Reference - Project Drawings
328f4d77-0554-4647-99d5-9bc7da502a1b | signoff | HOLD POINT
c39fb428-4bb4-4cbb-901d-d18f62cb6d6b | checkpoint | Positional tolerance must be within 100mm + - vertically and 300mm + - horizontally from the specified position. Holes shall be drilled ina straight line and shall not deviate past the straight by more than 25mm over any 2m length of hole.
e4a80568-57ae-5800-a4fd-5fe310ebd497 | note | Acceptance Criteria - Internal
bb68df03-2802-5e3f-b5d0-816fa0961a09 | note | Reference - ATS 2280 Clause 6.3 & 6.9
ceea98dc-18b6-4233-82ed-db06c5271d53 | signoff | Internal Check
6e3ecee1-088f-492f-9ae2-450e9e4f3bd5 | checkpoint | Holes for horizontal drians mmust be drilled on an inclination of 5 degrees dipping towards the exposed slope face with an acceptable range of 3-7 degrees, drill holes shall be 150mm diameter and drilled 100mm longer than specified depth to avoid excess material at the end of the bore shortening the hole.
35369250-5296-5a28-a121-ff38efc53a21 | note | Acceptance Criteria - Internal
cb2e42a2-18cc-5930-8758-d3eb2d510709 | note | Reference - ATS 2280 Clause 6.10 and project drawings
cd29571b-d158-549f-ae70-2bd1ea2094f2 | note | Internal Check
754676f8-7652-47a7-b7c4-af81c7f29cf5 | checkpoint | Installation of drian pipes shall be in accordance with project drawings, an outer and inner drain pipe is to be installed in each drill hole with the unslotted 120 degree section of the pipe at the bottom after installation of outer pipe the annular space between pipe and drill hole will be tightly plugged with cement mortar of atleast 0.5m from the end of hole.
c2452e02-5905-568d-b5a1-3b316a892368 | note | Acceptance Criteria - Internal
b997b152-c998-56b0-af74-47324429009b | note | Reference - ATS 2280 Clause 7
925b5389-9270-5007-9b19-7323259ca9c5 | note | Internal Check
3e9f317d-22fd-4e64-8f6c-71356a450373 | checkpoint | A drilling report shall be completed for all horizontal drains holes completed in a days production and will be provided to the administrator within 5 working days from completion of holes.
4bdf2118-af6c-5397-8ce6-1a5892ab5f80 | note | Acceptance Criteria - Written
454b62d4-26bf-50c7-adf6-37ce0f22cf39 | note | Reference - ATS 2280 Clause 6.16
6121f8e0-3ec7-5346-8520-9c097be64452 | note | Milestone Submission
ac997a2f-517a-4b06-a9f5-92efaa167614 | checkpoint | Final Verification
9a9242f5-d58c-58d7-8713-3c2df5ba8a14 | note | Project Manager Verify that the Above has been Constructed according to Specification
6c732c8a-75a4-51ee-9a23-d4fa50cbb1dc | textbox | Print Name:
94d12959-4fcd-5cc6-8e75-2cbc090dd9cc | date | Date:
e4410202-4a8c-5f0b-b4cf-23cdcf1762b4 | note | Client Verify that the Above has been Constructed according to Specification
d86a48d5-cd61-5ff8-b0a4-53f59fda460b | textbox | Print Name:
c27beb2f-9625-50ca-949d-99f6fe4c167c | date | Date:
b4b8bf26-eb85-44ba-9729-b433ebdd2b65 | signoff | Sign ITP
3d73c631-fc0e-43f3-a04f-f5f37a323da1 | checklist | 3.MM - Mac Mat R |  | 3.MM - Mac Mat R
af28b354-ed22-4bf4-9269-bff625c1dcb9 | section | Details
aa701e8d-a948-4ecb-af76-f6547c3fdaa0 | checkpoint | At least 7 days prior to works commencing the construction procedure for the MacMat - R installation will be submitted to the Administrator for review and acceptance.
e3e25a6e-69a7-589b-b726-7797f37219fc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f9af5a3c-7533-5f58-90d8-34864dacbdb4 | note | Check Item - Check Item
86fa008d-5383-4174-b128-d5ecfa00eb63 | signoff | HOLD POINT
a8011d25-9064-40d2-b888-cff913253c4e | checkpoint | Product shall be Maccaferri MacMat R or an alternative that has been approved by the administrator
e62f933d-f4fe-5b28-9300-c3e0285cb2f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6d2f48b7-2441-5a97-b774-74efc1308792 | note | Check Item - Check Item
06afb999-1a11-5bbc-9bf1-3cbbd38b5d8a | note | Project Drawings
6fa987df-5a95-47da-9c88-20e0c6e9e600 | checkpoint | Has the section of works been clearly identified and is there a lot map attached to this ITP
96e6aac5-35fd-572b-bdfd-364569017e68 | note | Acceptance Criteria and Frequency (Project Specific) - Internal Check
932db517-db2a-5573-b513-22a9cd7315f1 | note | Check Item - Check Item
593e38cf-d535-58dc-a724-b59b541d0a75 | note | Project Drawings
6b042474-f2b8-40fd-bdb2-54246623b13c | checkpoint | Macmat shall be anchored and pinned into top of slope with a 300mm deep trench 500mm wide, and then backfilled and hydroseeded over. The trench shall sit 500mm back from the top of batter.
36dc6e4e-33ab-50e3-88db-a7dd170e45e6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
882182e9-3fba-5ed2-963b-c4775a29af9d | note | Check Item - Check Item
a23ac53b-4528-52ff-9a6a-b19067b6d5b3 | note | Project Drawings
70ad2db9-8c07-462f-9884-5163ea2eac27 | checkpoint | MacMat R shall be placed in one continuous strip runnign down the batter without breaks, adjacent runs of MacMat R are to have a minimum 100mm overlap and be pinned in a direction perpendicalr to the angle of the slope along the over lap
6473d6f6-15a9-5436-b1cf-aefd45426bef | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2be80d79-e94a-5775-a140-02a601d455ea | note | Check Item - Check Item
55fe4846-018d-4ab5-8439-0d2dcafb990a | signoff | Manufacturer Specification
a2bbf7f1-3f73-4211-8fa6-16dcc3103331 | checkpoint | Final Verification
ce09a765-1267-5aac-97f0-1a2a5b8bae6b | note | Project Manager Verify that the Above has been Constructed according to Specification
568eba62-a422-5149-93eb-139af8df348f | textbox | Print Name:
6e945c59-88c7-5eda-8a21-e94c9390f67a | date | Date:
b55e2465-8348-5602-ba77-00fd59453edb | note | Client Verify that the Above has been Constructed according to Specification
1ed34b0e-cf9d-5bae-8762-bf83174616fe | textbox | Print Name:
de6c1f46-d18d-5baa-bc17-073c73643d24 | date | Date:
e8268a68-8e9c-456d-8183-eca11b5dff12 | signoff | Sign ITP