## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DOT-31608-FUL-QAC-ITP-001 - Preconstruction | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-001 - Preconstruction Rev 0
section | 1 - Pre-construction Checklist
checkpoint | 1.1 - Communication
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Community and emergency services
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.2 - Communication (2)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Emergency response plan
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.3 - Approved Construction Documentation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: IFC drawings (PDF, hardcopy)
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.4 - Approved Construction Documentation (2)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Digital (CAD) files for surveyor
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.5 - Approved Construction Documentation (3)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Budget / Resource arrangement POs (incl. sub-contract agreements)
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.6 - Approved Construction Documentation (4)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Quantities / Specifications
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.7 - Dilapidation Report (1)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Residential (ie: structures, access/gate, letterbox, fence)
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.8 - Dilapidation Report (2)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Business (ie: structures, access/fence/gate, signs/letterbox)
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.9 - Heritage / Cultural listed areas
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: No go zones established
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.10 - Protected Environment
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Protected environment flora & fauna identified and workshopped
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.11 - Underground services - DBYD
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: DBYD up to date and stored in file
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.12 - Underground services - Service location
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Assess and arrange for Service location
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.13 - Underground services - Excavation permit
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Excavation permit implemented and all personnel signed on
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
section | 2 - Precommencement Checklist
checkpoint | 2.1 - Traffic Management - VMS Boards
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: VMS boards implemented
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Engineer / Foreman
date | Date Completed:
checkpoint | 2.2 - Traffic Management - TMP
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: TGS, TMP and MOA approved
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Engineer / GPP Coordinator
date | Date Completed:
checkpoint | 2.3 - Site Demarcation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Litmit of works and control points implemented
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.4 - Utilites clash assesment
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Clash assessment of all services with construction activities
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.5 - Review of SWMS
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: SWMS reviewed and communicated with personnel
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.6 - Site Access
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Vehicle movement plan implemented
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.7 - Site establishment
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Site compound, site parking, material stockpile areas established
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-001A - Installation of Traffic Bariers | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-001A - Installation of Traffic Bariers Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Melton Hwy/Leakes Rd site
label | REFERENCE DOCUMENTS: Site Induction Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Work pack briefing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Work pack signed.
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP.
label | REFERENCE DOCUMENTS: CEMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Traffic Management
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved TMP and MOA in place. Traffic management implentation is inpected and verified to be fit for purpose
label | REFERENCE DOCUMENTS: Approved MOA
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved MOA / Superintendents Correspondence
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.6 - Lift plan
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that a lift plan has been prepared for the works and covers the lifting capacity required for the barriers
label | REFERENCE DOCUMENTS: Lift Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.6 - Light towers
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure light towers have been procured and set up to adequately light up the work site at night
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.7 - Availability of water
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that a watercart or connection to water has been sourced, so that the crash cushions can be filled with water
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.8 - Procurement of barriers
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that all required concete barriers have been delivered to site and inspected to be in adequate condition
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.9 - Procurement of end treatments
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that adequate end treatment cushions have been procured, as well as all required fixings and connections
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendents Correspondence
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.10 - Certificate of Compliance
label | FREQUENCY: Prior to Fabrication
label | ACCEPTANCE CRITERIA: Manufacturers Certificate of compliance for all precast concrete barriers demonstrating structural adequacy for the specified MASH level and compliance to project specification design requirements by a suitably qualified structural engineer.
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Certificate of Compliance
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Installation
checkpoint | 2.1 - Prelifting Check
label | FREQUENCY: Prior to Work Commencement
label | ACCEPTANCE CRITERIA: Before lifting barriers, inspect that the lifing points for wear, corrosion or cracking
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Set out of Barriers
label | FREQUENCY: Prior to Work Commencement
label | ACCEPTANCE CRITERIA: Ensure that the location of the barriers has been marked on site in accordance with the traffic barrier detailed installation design
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Placing barriers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Barrier are placed in correct alignment in position shown on installation drawings.
label | ○ Check the end of each barrier to ensure that they are correctly orientated and secured so that they lock in to place. The coupling on the end of the barriers must already be inserted prior to lowering the abutting barrier
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey Markups, This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Confirmation of line and level
label | FREQUENCY: Each Barrier
label | ACCEPTANCE CRITERIA: Alignment should be adjusted where necessary to provide a smooth and even vertical and horizontal alignment.
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Survey Check
label | RECORD OF CONFORMITY: Survey Conformance Report
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Installation of end treatments
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that the end treatment crash cushions are installed as per the manufacturers specification, and filled with water
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-002 - Underground Stormwater Drainage | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-002 - Underground Stormwater Drainage Rev 0
section | 1 - Stormwater Products and Materials
checkpoint | 1.1 - Drainage Pipes
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058.
label | ○ Documentation as per 701.05 is available in Teambinder Material Approval form
label | REFERENCE DOCUMENTS: 701.04, 701.05
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.2 - Drainage Pits
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: - Drainage Pits are supplied in accordance with 705.07.
label | ○ Pits deeper than 1m to be fitted with step irons as shown on the drawings. Step irons to be compliant with AS4680.
label | ○ Suppliers documentation has been submitted via Teambinder Material Approval form
label | REFERENCE DOCUMENTS: 705.07
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.3 - Drainage Bedding Material
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Bedding Materials comply with Table 701.081 and 701.082.
label | ○ Material Approved via Teambinder Material Approval Form.
label | REFERENCE DOCUMENTS: Table 701.081, Table 701.082
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.4 - Drainage Backfill Material
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082
label | ○ Material Approved via Teambinder Material Approval form.
label | REFERENCE DOCUMENTS: Table 701.081, Table 701.082
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding & Backfill Material Testing
label | FREQUENCY: 1 per 1,000 tonnes or part thereof
label | ACCEPTANCE CRITERIA: Bedding and backfill material tested at to ensure materials comply with the following:
label | REFERENCE DOCUMENTS: Table 701.091, Table 701.092, Cl. 701.29, Table 701.291
label | INSPECTION / TEST METHOD: Grading and Plasticity Index
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.6 - Material Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Material inspection to be completed for all precast pits, pipes and culverts.
label | REFERENCE DOCUMENTS: Order Acceptance Form
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
section | 2 - Preliminary Works
checkpoint | 2.1 - Work pack briefing
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been briefed on the relevant work park to scope of works.
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Work pack signed.
label | HP*
label | RESPONSIBILITY: Engineer / Foreman
date | Date Completed:
checkpoint | 2.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available design revision in use.
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision IFC drawings
label | HP*
label | RESPONSIBILITY: Engineer / Foreman
date | Date Completed:
checkpoint | 2.3 - Ground Penetration Permit (GPP) issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Engineer / GPP Coordinator
date | Date Completed:
checkpoint | 2.4 - Usage of HDPE Pipes
label | FREQUENCY: Pre Process Approval
label | ACCEPTANCE CRITERIA: HDPE (Stormpro/Blackmax) pipes to be used only under non-paved areas inlin with the latest design.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
label | INSPECTION / TEST METHOD: Teambinder Material Approval
label | RECORD OF CONFORMITY: Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.5 - Backfilling with cement stabilised sand (If required)
label | FREQUENCY: Each drainage line
label | ACCEPTANCE CRITERIA: Subject to superintendent approval, underground stormwater drains may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand.
label | ○ Mixture to have a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Superintendents Correspondence, ITP signed
label | AP
label | RESPONSIBILITY: Engineer / Superintendent
date | Date Completed:
section | 3 - Installation of Drainage
checkpoint | 3.1 - Confirm position of culverts
label | FREQUENCY: Prior to commencing drainage line
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts and stormwater drainage, confirm the position with the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.10 IFC Drawing
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Design and survey setout postion confirmed with Superintendent.
label | HP*
label | RESPONSIBILITY: Engineer / Foreman
date | Date Completed:
checkpoint | 3.2 - Excavation
label | FREQUENCY: Each trench
label | ACCEPTANCE CRITERIA: Ensure trench is excavated to prepare culvert foundation and specified depth of bedding.
label | ○ Box culverts: distance between culvert wall and trench wall is between 0.5 - 1.0 x the overall height of the culvert.
label | ○ Pipe culverts: the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm.
label | ○ Pits: Clearance from external faces of the pit to each face of the excavation to be not less than 400mm
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.15 Table 701.151, Cl. 705.05(b)
label | INSPECTION / TEST METHOD: Site Inspection, Measurements of trench
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.3 - Bedding
label | FREQUENCY: Each trench
label | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be:
label | — minimum 100mm for pipes of D< 1500mm
label | — minimum 200mm for pipes with D ≥ 1500 mm
label | ○ 'D' is the nominal pipe diameter or culvert width.
label | ○ Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | ○ Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height.
label | ○ Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.16, Cl. 701.20(a)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Report
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.4 - Laying - Circular Pipe
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream)
label | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | ○ Where applicable, the top of the pipe as marked shall be within five degrees of the vertical axis of the culvert.
label | ○ Spacing of multiple rows of culverts to reflect Table 701.171.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.17(b)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.5 - Laying - Box Culverts
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Consecutive sections of box culverts are firmly placed butted together. The top section matched to the bottom section and no lips over adjoining bottom sections.
label | ○ Contact areas between the top and bottom sections mortared.
label | ○ Multi‑row box culverts laid with sections in each row in contact with the sections in the adjacent rows.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.17(c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.6 - Laying - Cutting of Culverts (If applicable)
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: When cutting culvert section to length or to create a penetration, cuts to be done by machine to achieve a clean vertical face.
label | ○ Any exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.17(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.7 - Jointing
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Rubber Ring Joints (RRJs) jointed with rubber rings which have been kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
label | ○ RRJs assembled and prepared in accordance with the manufacturer’s recommendations.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.18
label | INSPECTION / TEST METHOD: Document review/ Site Inspection
label | RECORD OF CONFORMITY: Manufacturer’s recommendations, ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.8 - Survey
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The location of each run of underground drainage has been verified by a survey pickup prior to backfill and form the as constructed survey.
label | Tolerances that apply:
label | (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm
label | (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm
label | (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade.
label | (d) Departure from design grade of pipe runs +/-10mm in 10m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.701.10
label | INSPECTION / TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey Report
label | SCP
label | RESPONSIBILITY: Engineer / Surveyor
date | Date Completed:
checkpoint | 3.9 - Backfilling
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Culvert Under Area to be Paved:
label | ○ Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | ○ Where the trench is excavated from below design subgrade level the trench is filled with selected backfill material.
label | Culvert Under Area not to be Paved:
label | ○ The trench is backfilled with selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.10 - Inlet/Outlet Structures
label | FREQUENCY: Each headwall
label | ACCEPTANCE CRITERIA: Inlet and outlet structures constructed in accordance with the drawings and specification. Concrete used for the construction of inlet and outlet structures shall comply with the requirements of Section 610.
label | ○ Footings extended to the depths shown on the drawings or as necessary to achieve a satisfactory foundation.
label | ○ If backfilling to the required level, select backfill material is used.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.25, Cl.610
label | INSPECTION / TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Latest IFC Drawing, ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
section | 4 - Testing and Inspection
checkpoint | 4.1 - Inspection of drainage lines
label | FREQUENCY: Each culvert prior to construction of pavement layers
label | ACCEPTANCE CRITERIA: All drainage lines beneath pavement inspected with CCTV cameras, after completion of earthworks to subgrade level and prior to construction of pavement layers.
label | ○ Inspections shall be conducted by an independent testing organisation using CCTV and reporting in accordance with WSA 05-2013 (Conduit Inspection Reporting Code of Australia).
label | ○ Reports provided to the Superintendent, with a copy of the CCTV and a summary of the loation of any defects detected.
label | ○ Any section of damaged pipe or box culvert which does not comply with Cl 701.31 is to be removed and where approved by the Superintendent, defects are to be reapirs inline with the previous.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.06 (k), VicRoads Spec. Cl. 701.30 and 701.31
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Inspection Organisation Inspection report, ITP signed
label | HP
label | RESPONSIBILITY: Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Bedding Compaction Requirements
label | FREQUENCY: 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls)
label | ○ Min. 20% of all lots for each culvert shall be tested.
label | ACCEPTANCE CRITERIA: Bedding assessed for compaction and /or moisture in lots.
label | ○ Bedding compacted to refusal with handheld mechanical equipment with a mean moisture ratio of 92%.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.20 (a)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction and moisture Test Records, ITP signed
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 4.3 - Backfill Compaction and Moisture requirements
label | FREQUENCY: 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls)
label | ○ Min. 20% of all lots for each culvert shall be tested.
label | ACCEPTANCE CRITERIA: Backfill assessed for compaction and or moisture in lots.
label | ○ Backfill material which will have a nominal size after compaction of 40mm or < less compacted to a mean value of density ratio of not less than 97%.
label | ○ Backfill material which has a swell equal to or greater > than 2.5% maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: VicRoads Spec. 701.20 (b)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction and moisture Test Records, ITP signed
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 4.4 - Flushing System
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Each culvert flushed clean from end to end on completion and maintained in proper working order.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.28
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-003 - Stripping Topsoil Clearing and Grubbing | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-003 - Stripping Topsoil Clearing and Grubbing Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG site
label | REFERENCE DOCUMENTS: PMP Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Coordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer, Site Foreman
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Refer to latest drawings and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, induction register Project Spec. Cl.1200.03
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Site induction signed, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Ground Penetration Permit (GPP) issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current GPP signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: GPP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: GPP no.
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: TMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.8 - Extent of Clearing and Grubbing
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Extent of Clearing and Grubbing shall be within the limit of works and not more than the width required for completion of work under the contract
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Extent of Clearing and Grubbing reviewed by Superintendent
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Identification of Cultural Heritage sites and areas of Cultural Significance
label | FREQUENCY: Prior to Excavation
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Immediately stop work and notify the Superintendent if any Cultural Heritage is discovered or identified during construction.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | REFERENCE DOCUMENTS: Relevant EMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Cultural Heitage approval (when required), Signed ITP
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Stripping of topsoil and grubbing of vegetation
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | ○ In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Removal of abandoned services
label | FREQUENCY: Prior to commencing this work
label | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done.
label | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | ○ Decommissioned services to be disposed of in a suitable manner.
label | ○ Decommissioned pits have been broken back to 0.3 metres below subgrade level.
label | ○ Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Clearing of Trees and Vegetation
label | FREQUENCY: During clearing works
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed by a suitably qualified arborist to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Disposal of vegetation
label | FREQUENCY: At completion of works
label | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from the site.
label | ○ Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.07
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Delivery docket
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-004 - Excavation, Fill with Type B & Subgrade Prep | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-004 - Excavation, Fill with Type B & Subgrade Prep Rev 0
section | 1 - Preliminaries
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Re-Use of insitu material
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
label | ○ Type B Material shall meet the following requirements:
label | — CBR ≥ 1.5%
label | — Swell < 2.5%.
label | ○ Attach: Test Certificates
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.04, Cl. 204.06
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results, Material Category agreed with Superintendent
label | HP*
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.4 - Type B Material Approval
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to the import of Type B material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type B material complies with section 204 of the VicRoads Spec.
label | ○ Type B Material shall meet the following requirements:
label | — CBR ≥ 2%
label | — Swell < 2.5%.
label | ○ If parameters are not met, remove 400mm of material mm below Cut Floor Level and replace with conforming Type B material.
label | ○ If removal and replacement of material below the Cut Floor Level is not required, surface shall be loosened to a depth of 150mm and re-compacted to meet the specified requirements.
label | ○ Attach: Test Certificates, Sample Delivery Dockets
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.04(c), Cl. 204.06(e)
label | INSPECTION / TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Geotechnical Report
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Cut Activities - 400mm below
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | ○ The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | REFERENCE DOCUMENTS: 204.03
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Ground water
label | FREQUENCY: Prior to Commencing (if required)
label | ACCEPTANCE CRITERIA: Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.06(h)
label | INSPECTION / TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior to construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION / TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Proof Roll - Cut Floor
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
label | ○ Superintendent to be present during all test rolling.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | ○ No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | ○ Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | ○ Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03, Cl. 204.10(b), Cl. 204.07(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area visually reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Compaction Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Frequency = 6 tests per lot
label | ○ Min Frequency (subject to approval) = every second lot
label | ○ Lot = One day's production or 4,000m2, whichever is the lesser
label | ○ Characteristic Density Ratio =
label | 97% minimum when more than 400mm below top of Type B Fill
label | 99% minimum when within 400mm of top of Type B Fill
label | ○ Attach: NATA Compaction Test Report
label | REFERENCE DOCUMENTS: Table 204.131, Section 204.13, 204.14
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Sign ITP, NATA Compaction Test Report
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Survey Pickup
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Ensure the Cut Floor Level is recorded by survey
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Survey As-Built
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
section | 3 - Fill Activities
checkpoint | 3.1 - Placement of Fill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
label | ○ Each layer shall be keyed in to the layer above by means of a textured surface
label | ○ Any rocky material present must be uniform throughout the layer.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Preparation of final surface - Subgrade
label | FREQUENCY: Prior to construction of subgrade layer
label | ACCEPTANCE CRITERIA: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Trimming and level conformity
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping does not differ by the mean values of more than 5 mm above or 15 mm below the specified level.
label | ○ The level at any point of the sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION / TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 3.4 - Proof Roll - Top of fill layer
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
label | ○ Superintendent to be present during all test rolling.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | ○ No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | ○ Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | ○ Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03, Cl. 204.10(b), Cl. 204.07(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area visually reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Post-compaction Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Post compaction testing shall meet the following requirements:
label | — CBR ≥ 1.5%
label | — Swell ≤ 2.5%
label | — Characteristic Density Ratio ≥ 99%
label | — Moisture Ratio ≥ 70%
label | ○ Subject to approval min frequency testing as follows:
label | — Compaction & Moisture: 1 test per 2 lots
label | — CBR & Swell: 1 test per 8 lots
label | ○ Attach: NATA Compaction Test Report
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Survey Pickup - Top of subgrade
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: Ensure the Top of subgrade is recorded by survey
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Survey As-Built
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
section | 4 - LOT Closeout
checkpoint | 4.1 - Survey As-Built
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Scale A:
label | — Min. No. of Measurements Per Lot: 80
label | — Range x (mean) = +5, -15mm
label | — Max S (Standard Deviation) = 12 mm
label | ○ Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS: Section 204.03 (h), 204.16
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: Attach As-Built Report
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 4.2 - Non-conformance Closure
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure All related Non-conformances are recorded and closed out.
textbox | Enter: CAMS Case Number(s)
label | ○ Attach: Closed NCR Report
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.3 - Red Line Markups
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure any changes from design are captured in red-line markup drawings
textbox | Enter: RFI References
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.4 - Final Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Quality Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-005 - Fill with Material Type A | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-005 - Fill with Material Type A Rev 0
section | 1 - Preliminaries
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Type A Material Approval
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to the import of Type A material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type A material complies with section 204 of the VicRoads Spec.
label | ○ Type A Material shall meet the following requirements:
label | — CBR ≥ 6%
label | — Swell ≤ 1.5%
label | — Permeability ≤ 5e-9
label | — PI (LL) = 6 - 25
label | — PI x 0.425 passing ≤ 1000
label | ○ Grading:
label | — % passing 75.0mm sieve = 100
label | — % passing 4.75mm sieve = 40 - 80
label | — % passing 0.075mm = 10 - 40
label | ○ Attach: Test Certificates, Delivery Dockets
textbox | Enter: Teambinder Approval number
label | REFERENCE DOCUMENTS: Project Specification Cl. 3020.05, VicRoads Specification Cl. 204.04(b), Cl. 204.06(c) Table 204.041
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Approval #
label | HP*
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.4 - Review of Subgrade Test Roll
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
textbox | Enter: Subgrade ITP Number
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03, Cl. 204.10(b), Cl. 204.07(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP visually reviewed by Engineer, Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 2 - Fill Activities
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Fill
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | ○ The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | REFERENCE DOCUMENTS: Project General Specification Cl.1190.06, Latest IFC Drawings
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Placement of Fill
label | FREQUENCY: Prior to Fill
label | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Layers with a compacted thickness >200mm may be placed subject to approval from the Superintendent.
label | ○ Each layer shall be keyed in to the layer above by means of a textured surface
label | ○ Any rocky material present must be uniform throughout the layer.
textbox | Enter: RFI Number
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Preparation of final surface
label | FREQUENCY: Prior to placement of next layer
label | ACCEPTANCE CRITERIA: The level tolerances at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.15, Cl. 204.03(g), Cl. 173, VicRoads Specification Table 204.03(f)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll - Top of placed layer
label | FREQUENCY: Each Test Lot
label | ACCEPTANCE CRITERIA: Superintendent to be present during all test rolling.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling.
label | ○ No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | ○ Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | ○ Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.12, Cl.173.03
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Roll Form signed.
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Post-compaction Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Type A Material shall be tested for the following:
label | — Characteristic Density Ratio ≥ 99%
label | — CBR ≥ 6%
label | — Swell ≤ 1.5%
label | — Permeability ≤ 5e-9
label | — PI (LL) = 6 - 25
label | — PI x 0.425 passing ≤ 1000
label | ○ Grading:
label | — % passing 75.0mm sieve = 100
label | — % passing 4.75mm sieve = 40 - 80
label | — % passing 0.075mm = 10 - 40
label | ○ Subject to approval min frequency testing as follows:
label | — Compaction & Moisture: 1 test per 2 lots
label | — CBR & Swell: 1 test per 2 lots
label | — Grading: 1 test for every second lot tested for compaction
label | — PI (LL): 1 test every 4 lots
label | — Permeability: 1 test every 4 lots
label | ○ Attach: Test Reports
label | REFERENCE DOCUMENTS: Table 204.131, Section 204.13, 204.14
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Attach Test Results
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - LOT Closeout
checkpoint | 3.1 - Survey As-Built
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Scale A:
label | — Min. No. of Measurements Per Lot: 80
label | — Range x (mean) = +5, -15mm
label | — Max S (Standard Deviation) = 12 mm
label | ○ Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS: Section 204.03 (h), 204.16
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: Attach As-Built Report
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 3.2 - Non-conformance Closure
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure All related Non-conformances are recorded and closed out.
textbox | Enter: CAMS Case Number(s)
label | ○ Attach: Closed NCR Report
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Red Line Markups
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure any changes from design are captured in red-line markup drawings
textbox | Enter: RFI References
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Final Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Review Document
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Quality Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-006 - Unbound Pavements | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-006 - Unbound Pavements Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRU site
label | REFERENCE DOCUMENTS: PMP Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, Site induction, Project Specification Cl. 1200.03
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Project General Specification Cl.1125.07, Health and Safety Coordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Crushed Rock Mix design
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.812.04
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.7 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: TMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints.
label | ○ Transverse joints shall be offset from one layer to next by not less than 2 metres
label | ○ Transverse joints shall be offset from one layer to the next by not less than 2 m.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.304.07 (a, b & c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints.
label | ○ longitudinal joints shall be offset from one layer to the next by not less than 150 mm.
label | ○ longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.304.07 (a, d & e)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser.
label | ○ For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: After placing material
label | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.304.08(b)(iv), Cl. 173
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing and Inspection
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Specification Table 204.161, VicRoads Specification Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
label | INSPECTION / TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Modified Compactive Effort
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B.
label | ○ For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Permeability Testing
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec
label | ○ Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
label | REFERENCE DOCUMENTS: Project Specification Cl.3040.05(a) Table 3040.051
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Post-compaction Plasticity Index
label | FREQUENCY: After compaction
label | ACCEPTANCE CRITERIA: Post- compaction Plasticity Index must comply with the requirement of table 3040.053. Calss 3: 0 < PI < 10.
label | REFERENCE DOCUMENTS: Project Specification Cl.3040.05(a) Table 3040.053
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Post- compaction Grading
label | FREQUENCY: After compaction
label | ACCEPTANCE CRITERIA: The post compaction grading shall comply with the requirements of table 304.101
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 304.10 Table 304.101
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.7 - Survey Level
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Scale A:
label | ○ Minimum number of measurements per lot: 80 For Upper
label | ○ Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm
label | ○ Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm.
label | ○ Base: Mean ± 5 with a maximum Standard Deviation of 8mm.
label | REFERENCE DOCUMENTS: VicRoads Specification Table 304.061, Table 304.062
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-007 - Subsoil Drainage | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-007 - Subsoil Drainage Rev 0
section | 1 - Material & Methodology Approvals
checkpoint | 1.1 - Subsurface Drainage Pipes
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure all subsurface drainage pipes ordered are Category 1: peroforated plastics Class 1000 and Precast concrete Class 2.
label | ○ All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.04
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.2 - Drainage Geotextile
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Type 2 drainage (NFC) Geotextile filter to meet requirements of a First Stage filter as per Table 702.061
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.061
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.3 - SSD Backfill Material
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Type 2 and 3 backfill material types to be reviewed aginast specifcation and approved prior to ordering and use.
label | ○ Minimum testing requirements are reflected inline with 702.13.
label | ○ Type 2 NFC Grade B4 Filter Material
label | ○ Type 3 Sand Filter Grade A4 to A6 Filter Material.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a) Table 702.131
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.4 - Terminals & Pits
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Terminals and Pits
label | ○ Flushout Risers SD 1631 and Type S1 Pits reflect VR SD 1611.
label | REFERENCE DOCUMENTS: SD 1611 Issue D, SD 1631 Issue E
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 1.5 - Compaction Methodology
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure compaction methodology of No Fines Backfill developed and submited for review prior.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Superintendent / Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Preliminary Works
checkpoint | 2.1 - Check current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
checkpoint | 2.2 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | ○ Ensure DYBD Plans and Drawings relating to the particular area are available, current and where applicable higlights temporary services installed by Contractor
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Subsurface Drainage Works
checkpoint | 3.1 - Suitability of Materials
label | FREQUENCY: Prior to placing drainage
label | ACCEPTANCE CRITERIA: Ensure subsurface drainage is not in contact with expansive materials (swell > 2.5%).
label | ○ For installation in expansive material, min. 100mm of compacted capping material is provided below the floor of the drainage trench.
label | ○ Ensure an adequate outlet is provided for existing drains.
label | ○ Drains that become redundant must be removed to ensure that water is not trapped. Refer below step.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.07(b)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Managing Existing Drainage
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Ensure removal and disposal of all reduntant pre-existing subsurface drainage assets.
label | ○ The area is backfilled with Type A material to subgrade or surface level.
label | ○ Where backfill is required above subgrade level, backfilling must be with pavement material that matches the pavement design for that pavement.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.07(c)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Excavation of Trench
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
label | ○ The top of any subsurface drainage pipe shall be at least 300 mm below the subbase and setuptfor the subsurface drain type.
label | ○ Grade of trench to be not flatter than 1 in 250 gradient.
label | ○ Base of the trench shall be inspected to verify compliance with the requirements prior to placing bedding in completed excavations.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08, VicRoads Spec. Cl.702.09(a)(b)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Use of Geotextile
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when granular material is placed.
label | ○ The appropriate Subsurface Drainage Type 2 (B4 NFC filter) or Type 3 (Grade A4 to A6 filter) has been setup prior to backfill.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Installation of Subsoil Drainage
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
label | ○ Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe.
label | ○ Flushout Risers, S1 Type Pits and Outlets are appropriate positioned to reflect the subsurface drainage design.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Placing of Granular Filter Material
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Filter socks must not be installed on subsurface drains backfilled with no fines concrete (Type 2). (HP)
label | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The loose thickness of layers shall not exceed 300 mm.
label | ○ For Type 2 (NFC) No-fines concrete shall be placed and compacted within 1 hour of mixing.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g), Project Spec. Cl.3030.05(b)
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.7 - Installation of Subsurface Outlet marker posts (If required)
label | FREQUENCY: After drainage is placed
label | ACCEPTANCE CRITERIA: Marker posts installed at all subsurface outlets, and must be 75 mm diameter x 1500mm treated pine inserted 600mm into the ground.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.07(b)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Site Engineer / Foreman
date | Date Completed:
checkpoint | 3.8 - Flushing Test
label | FREQUENCY: After drainage is placed
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.9 - Inspection and Completion
label | FREQUENCY: After drainage is placed
label | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV),
label | ○ Verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | ○ Placement of apshalt cannot proceed until after this inspection. CCTV is completed, damaged or deformed drainage pipe removed and replaced. Along with waste and defect free condition of lines verified by the Superintended.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-008 - Kerb and Channel | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-008 - Kerb and Channel Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Mix design
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
label | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | REFERENCE DOCUMENTS: SD2001, AS1379 Section 703.05, 703.06, 703.07
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP signed/Mix Design Certificate
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Bedding Material
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | REFERENCE DOCUMENTS: Section 703.21 IFC Drawings
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Material Conformance Certificate
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Curing Compound
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
label | REFERENCE DOCUMENTS: Section 703.10
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Material Conformance Certificate
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Temporary drainage provisions
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | REFERENCE DOCUMENTS: Section 703.18
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction / Installation Activities
checkpoint | 2.1 - Setting out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Section 703.17
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS: Section 703.21
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 2.3 - Formwork
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | REFERENCE DOCUMENTS: Section 703.12 AS3610
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre Pour Check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | REFERENCE DOCUMENTS: Section 703.09, Section 703.21, Section 610.17a), b) & c)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
textbox | Ambient temperature |  |  | °C
label | HP*/WP
label | RESPONSIBILITY: Site Engineer/Site superintendent
date | Date Completed:
checkpoint | 2.5 - Concrete placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | REFERENCE DOCUMENTS: Section 703.08, Section 703.23
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
textbox | Concrete Temperature |  |  | °C
label | IP
label | RESPONSIBILITY: Site engineer
date | Date Completed:
checkpoint | 2.6 - Transitions
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | REFERENCE DOCUMENTS: Section 703.24
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site engineer
date | Date Completed:
checkpoint | 2.7 - Surface Finish
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | REFERENCE DOCUMENTS: Section 703.25
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Forman
date | Date Completed:
checkpoint | 2.8 - Formwork Stripping
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | ○ External faces 2 days
label | ○ Permanently hidden faces 1 day
label | REFERENCE DOCUMENTS: Section 703.12 AS3610
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Forman
date | Date Completed:
checkpoint | 2.9 - Tolerance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width, for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | REFERENCE DOCUMENTS: Section 703.15
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: SITE Engineer/surveyor
date | Date Completed:
checkpoint | 2.10 - Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | REFERENCE DOCUMENTS: Section 703.10
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
checkpoint | 2.11 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | REFERENCE DOCUMENTS: Section 703.26
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Forman
date | Date Completed:
checkpoint | 2.12 - Backfilling
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | REFERENCE DOCUMENTS: Vic Road spec 703.29
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.13 - Protection of Concrete
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | REFERENCE DOCUMENTS: Section 703.27
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.14 - Cracking of Concrete
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | REFERENCE DOCUMENTS: Section 703.30
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Post-construction / Post-installation Activities
checkpoint | 3.1 - Survey Conformance
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | REFERENCE DOCUMENTS: Section 703.15
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: As-built survey records
label | WP
label | RESPONSIBILITY: Project Engineer/ Surveyor
date | Date Completed:
checkpoint | 3.2 - Non-conformance Report (NCR) Closure
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: SE/PE/SPE
date | Date Completed:
checkpoint | 3.3 - Red lines
label | FREQUENCY: Once, prior to closure of this lot
label | ACCEPTANCE CRITERIA: All RFI's and deviations from drawing to be marked in accordance with CRU red line markup procedure
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: SE/PE/SPE
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-009 - Asphalt Placement | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-009 - Asphalt Placement Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION / TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Ensure underlying lot conforms
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved.
label | REFERENCE DOCUMENTS: Relevant ITP for underlying lot
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Inspection and Test Plan
label | HP*
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 1.3 - Visual Inspection of underlying lot
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate
label | Contractor's work for matters including the following:
label | (i) Homogeneous surface and pavement material
label | (ii) Uniform in texture
label | (iii) Free from tearing and scabbing
label | (iv) Free from laminations
label | (v) Free from loose and foreign materials and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract.
label | REFERENCE DOCUMENTS: Relevant ITP for underlying lot
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Inspection and Test Plan, ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: 407.13
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer / gauage
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV):
label | (i) Transverse Joints Offset from layer to layer by at least 2m
label | (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane.
label | (iii) Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | INSPECTION / TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor, Superintendent
date | Date Completed:
checkpoint | 1.6 - Longitudinal Joints with existing Pavement
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | ○ Depth of step to be cut to the full depth of each indiviual layer.
label | REFERENCE DOCUMENTS: 407.16 (c), Project Specs. Section 3040.06 (d)(vii)
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement
checkpoint | 2.1 - Commencement of placement
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement.
label | REFERENCE DOCUMENTS: 404.13, 405.07, 407.18
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Inspection and Test Plan
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Cold Weather Placement Management Plan
label | FREQUENCY: Prior to commencing Paving (Seasonal)
label | ACCEPTANCE CRITERIA: Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
label | REFERENCE DOCUMENTS: 407.17C
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Inspection and Test Plan
label | HP*
label | RESPONSIBILITY: Project Engineer/ Asphalt Project Manager or Engineer
date | Date Completed:
checkpoint | 2.3 - Mix Design Confirmation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION / TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Delivery docket, Completed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Running traffic on Placed Asphalt
label | FREQUENCY: During Construction
label | ACCEPTANCE CRITERIA: Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic.
label | REFERENCE DOCUMENTS: 404.14
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Inspection and Test Plan, ITP Signed, Thermometer / gauage
label | HP*
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Placing Material
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: 407.21 - DGA as per 407.22
label | ○ 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C.
label | REFERENCE DOCUMENTS: 407.21, 405.08, 404.14, 417.12
label | INSPECTION / TEST METHOD: Material Sampling & testing
label | RECORD OF CONFORMITY: Visual Inspection/Compaction test results, Visual Inspection/Visual Inspection/Field Report
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor, Superintendent
date | Date Completed:
checkpoint | 3.2 - Survey Level Conformance
label | FREQUENCY: Per 4,000m2 at completion of work
label | ACCEPTANCE CRITERIA: 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
label | Scale of Surface Level Measurement -
label | Granular or CT Subbase ¦¦ Asphalt Layers
label | Range (mm) ¦ Max S. (mm) ¦¦ Range (mm) ¦ Max S. (mm)
label | Scale A - +4 to -8 ¦ 8 ¦¦ +/- 5 ¦ 8
label | Scale B - +6 to -12 ¦ 13 ¦¦ +/- 8 ¦ 10
label | REFERENCE DOCUMENTS: VicRoads Sec 407.293, Surface Level Tolerances for Sub-base and Pavement Courses
label | INSPECTION / TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Survey Conformance Report
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor / Survey Manager
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-010 - Guardrail Installation | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-010 - Guardrail Installation Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Work pack briefing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | REFERENCE DOCUMENTS: WP
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Work pack signed.
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Procurement
checkpoint | 2.1 - Steel Test Certificates
label | FREQUENCY: Min 14 days prior to commencing
label | ACCEPTANCE CRITERIA: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | ○ All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (b)
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Data Sheets, Material Test Certificates
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Steel Material Properties & Protection
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (c), (d)
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Data Sheets, Visual Inspection
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Identification of guard fence components
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(a)
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: Completed Receival & Inspection Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - W-Beam Barrier with non standard requirements or other special measures
label | FREQUENCY: Prior to Installation
label | ACCEPTANCE CRITERIA: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(a)
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This signed ITP
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Concrete mix design (As Applicable)
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | (i) Portland cement-based concrete, N20 strength grade, or
label | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.703, Cl.708.05(g) AS1379
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix design approval
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Guard Fence Installation
checkpoint | 3.1 - Approval of location and length
label | FREQUENCY: Prior to Installation
label | ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This signed ITP
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Survey set-out
label | FREQUENCY: Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Project Spec. Cl.1190.06, Latest IFC Drawings
label | INSPECTION / TEST METHOD: Testing
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 3.3 - Post Installation
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness.
label | ○ If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(a)
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - W-Beams
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.08(b)
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Guard Fence Tolerances
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(d)
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: Survey Records
label | SCP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 4 - Concrete Maintenance Strip
checkpoint | 4.1 - Dimensions and set-out
label | FREQUENCY: After installation of guardrail
label | ACCEPTANCE CRITERIA: The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.2 - Bedding and concrete
label | FREQUENCY: After installation of guardrail
label | ACCEPTANCE CRITERIA: The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.3 - Separation from Kerb
label | FREQUENCY: After installation of guardrail
label | ACCEPTANCE CRITERIA: Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 5 - Audit
checkpoint | 5.1 - Compliance Audit of Barrier System Installation
label | FREQUENCY: Prior the issue of the Certificate of Practical Completion
label | ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed.
label | ○ A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.10, Project Specific Specification PS3090.07(f)
label | INSPECTION / TEST METHOD: Safety Audit
label | RECORD OF CONFORMITY: Certificate of Compliance for each treatment installed, Product and Installation Manual
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Completion
checkpoint | 6.1 - Delineators
label | FREQUENCY: Once installation of assets completed.
label | ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
label | ○ The delineators shall be arranged so that vehicles approaching from either direction at night will only see:
label | — Red delineators on the left side of one-way and two-way roadways
label | — White delineators on the right side of two-way roadways
label | — yellow delineators on the right side of one- way roadways
label | ○ Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.11
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Site Photos
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 6.2 - Grassing of disturbed areas
label | FREQUENCY: Once installation of assets completed
label | ACCEPTANCE CRITERIA: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser.
label | ○ A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.20
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Site Photos
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Quality Assurance
label | FREQUENCY: Completion of works
label | ACCEPTANCE CRITERIA: Submit all quality assurance documents to the superintendent including the following items:
label | (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection.
label | (ii) Time and date of when traffic barriers were installed
label | (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification.
label | REFERENCE DOCUMENTS: IFC Drawings, Project Specific Specification PS3090.04
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: As built Records and Certificate of compliance
label | SCP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP