## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DOT-31608-FUL-QAC-ITP-011 - Topsoil Placement and Landscaping | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-011 - Topsoil Placement and Landscaping Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Refer to latest drawings and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Submissions and records
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
label | Following information shall be provided to the superintendent:
label | ○ Inspections:
label | — Plant stock for all plant species
label | ○ Samples:
label | — Mulch
label | — Imported topsoil
label | ○ Records:
label | — Evidence of origin of indigenous provenance plant material
label | — Analysis certificates for grass seed
label | — Details of suppliers
label | — Soil tests on imported topsoil
label | — Copies of fertiliser labels
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.03
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Records & Certificates
label | AP
label | RESPONSIBILITY: Site Engineer / VicRoads Superintendent
date | Date Completed:
checkpoint | 1.3 - Supply of mulch
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible.
label | ○ All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454, and shall comply with Table 720.044
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.04, VicRoads Standard Table 720.044 AS4454
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Supply of topsoil
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil.
label | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.04, VicRoads Standard Table 720.042
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting out planting areas
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
label | ○ Plant density requirements and planting offsets established in the plant schedule are to be adhered to.
label | ○ Plants shall be placed as shown on the drawings.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.06
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Site Preparation
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Soil preparation shall be in accordance with Table 720.071
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.07, VicRoads Standard Table 720.071
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Ripping of subsoil
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: All ripping works shall conform to the requirements of Cl 720.07 (b).
label | ○ Ripped areas of planting, individual tree planting and grassing are to be made available for inspection prior to mulching, planting or grassing, and shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.07(b)
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer / VicRoads Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Topsoil Placement
label | FREQUENCY: At completion of works
label | ACCEPTANCE CRITERIA: All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths:
label | — Batter slopes > 2:1 = 50mm
label | — Tree and shrub plantation bed areas = 100mm
label | — Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment
label | — All other areas - 75mm
label | ○ Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas. Topsoil shall not be compacted.
label | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(k), VicRoads Standard Section 204.17, VicRoads Standard Section 720.07
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Cultivation
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Cultivation shall be undertaken to break soil down to a tilth with 80% of the volume composed of clods less than 50 mm in diameter
label | ○ Prior to mulching, planting or grassing, area to be presented to Superintendent for approval.
label | ○ In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.07
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer / VicRoads Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bulk density of soils for planting and grassing
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
label | ○ Vibrating plates shall not be used. Ensure the dry bulk density does not exceed the limits in Table 720.072
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.07
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Topsoil finished surface levels
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: The finished level of grassed areas shall be:
label | (i) not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
label | (ii) level with the bottom of fence plinths;
label | (iii) level with adjacent pavements, kerbs, pits and other structures.
label | ○ The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
label | REFERENCE DOCUMENTS: VicRoads Spec. Section 720.07
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Planting
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Holes in heavy soils or on batters shall be prepared so as to ensure adequate drainage.
label | ○ Planting holes shall be backfilled with friable topsoil free of debris, rocks and clods greater than 50 mm in diameter.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.09
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Mulching
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Install wood mulch to all Planting Areas unless otherwise specified.
label | ○ Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all Planting Areas. If space does not permit this in median, separator or splitter-island planting, mulching shall extend to the back of kerb.
label | ○ The Contractor shall install 2 metre diameter mulch rings around all Individual Tree Plantings.
label | ○ Mulch depths in all situations shall be a minimum 75 mm and maximum 125 mm.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.08
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Grassing of disturbed areas
label | FREQUENCY: Once installation of assets completed
label | ACCEPTANCE CRITERIA: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser.
label | ○ A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.20
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Site Photos
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Grassing
label | FREQUENCY: Each applicable lot
label | ACCEPTANCE CRITERIA: Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
label | ○ Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 720.10
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-012 - Traffic Island, Median Island & Driveways | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-012 - Traffic Island, Median Island & Driveways Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Bedding Material / Base Layer
label | FREQUENCY: Once, for each mix design, prior to placement of material
label | ACCEPTANCE CRITERIA: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
label | REFERENCE DOCUMENTS: IFC Drawings 703.21, 812.04
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Material Certification
label | IP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
checkpoint | 1.3 - Concrete Mix
label | FREQUENCY: Once, for each mix design, prior to placement of concrete
label | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | ○ Paving concrete mix conforms to AS1379.
label | ○ SUP concrete mix is registered with VicRoads.
label | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
label | ○ Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
label | REFERENCE DOCUMENTS: IFC Drawings 703.05 (a), 703.07
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Concrete Mix Design
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Evaporative Retardant
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
label | REFERENCE DOCUMENTS: 703.09
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Material Submission
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Curing Compound
label | FREQUENCY: Once, for each product, prior to placement of concrete
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | REFERENCE DOCUMENTS: 703.10 (a)
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Curing compound submission
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.17
label | INSPECTION / TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: CONQA Hold Point
label | HP
label | RESPONSIBILITY: Project Engineer, Superintendent & Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions (if required)
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority. The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec Cl.703.18
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Written approval from relevant waterway authority, ITP Signed
label | AP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Pavement Thickness Increases for Crossings
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
label | i. Pram crossings
label | ii. Vehicle crossings (residential and/or commercial)
label | iii. Established / existing mature trees
label | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec 703.16, 703.24, Relevant Council Drawings
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Superintendent/ Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding Preparation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All bedding material shall be as specified on design drawings. Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.21, 812, 820 IFC Drawings
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Formwork
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.12
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.6 - Steel Reinforcement
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
label | ○ The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
label | ○ Reinforcement shall be supported using either concrete or plastic chairs.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.13 & Cl.703.13, AS/NZS 4671
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.7 - Pre-pour inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b) (c)(d), AS 1379
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer, Superintendent & Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Concrete Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete Testing Frequency: 0m³ to 50m³ = 1 sample
label | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 2 no. 28 day strength.
label | ○ Slump Testing Tolerances:
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | REFERENCE DOCUMENTS: VicRoads Spec 703.11
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Concrete Pour Record, ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.12 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete
label | ○ Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
label | REFERENCE DOCUMENTS: VicRoads Spec Cl. 703.10
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.13 - Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas. Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.15
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.16 - Joints
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Expansion Joints: shall be placed at intervals as specified by the drawings.
label | ○ Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
label | ○ Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
label | REFERENCE DOCUMENTS: VicRoads Spec Cl. 703.26 (b)
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.17 - Stripping Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | i. 2 days for vertical formwork on external surfaces; and
label | ii. 1 day for vertical forms on permanently hidden surfaces
label | REFERENCE DOCUMENTS: VicRoads Spec 703.12, AS3610 Table C2
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.18 - Protection of Newly Poured Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | REFERENCE DOCUMENTS: VicRoads Spec 703.27
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
section | 3 - Post-Construction
checkpoint | 3.1 - Survey data captured for as-built purposes
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings / survey records
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: As-built survey records
label | SCP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Cracking of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 703.30, 687
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Compressive Strength Test Results
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | REFERENCE DOCUMENTS: IFC Drawings, Relevant Council Drawings 703.11 Table 703.111
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Attach: Compressive Strength Test Results
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Backfilling
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.29
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
section | 4 - Completion
checkpoint | 4.1 - As-built Survey
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from alignment = ±10mm
label | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | ○ Irregularities in alignment = 5mm in 3m
label | ○ Section dimensions = ±5mm
label | ○ Section dimensions (less than 25mm) = ±3mm
label | ○ Width of pavement = -5mm, +15mm
label | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | ○ Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec 703.15
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.2 - Red-Line Markup
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Capture any changes in design or RFI's as per approved red-line markup procedure
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 4.3 - Non-conformance Report (NCR) Closure
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | REFERENCE DOCUMENTS: Quality Management Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-013 - Permanent Line Marking | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-013 - Permanent Line Marking Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Inductions
label | FREQUENCY: Prior to Commencing linemarking works
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRU Site.
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: ITP signed, Site induction signed.
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to Commencing linemarking works
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP signed, SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing linemarking works
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) drawings, & latest available revision used.
label | REFERENCE DOCUMENTS: IFC Project Drawings,
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: ITP signed, Latest revision IFC drawings
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing linemarking works
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per construction environmental management plan
label | REFERENCE DOCUMENTS: CEMP, Site induction
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing linemarking works
label | ACCEPTANCE CRITERIA: Approved TMP and MOA in use
label | REFERENCE DOCUMENTS: Applicable TMP
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed, Approved TMP & MOA
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Linemarking Works
checkpoint | 2.1 - Verification of line marking material
label | FREQUENCY: Prior to commencing site preparation
label | ACCEPTANCE CRITERIA: Line marking material to comply with minimum requirements as specified in VicRoads Spec 721.A05, VR721.A13, VR721.A14, & PS3070.05
label | REFERENCE DOCUMENTS: VR721.A05
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: ITP signed, Material compliance
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Site preparation
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Site to be prepared by removing any foreign materials and debris within reasonable limits.
label | REFERENCE DOCUMENTS: VR721.A06, VR721.A08
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Removal of unsuitable/redundant markings (If required)
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: If redundant/unsuitable pavement markings to be removed, removal methodology to be approved by superintendent
label | REFERENCE DOCUMENTS: VR721.A06, VR721.A08, VR721.A12
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Set out of line markings; dimensions and spacings
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the setout and installation timeframes are adherred to.
label | REFERENCE DOCUMENTS: IFC Drawings VR721.A09, VR721.B05, VR721.B04
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed Consent to proceed by Superintendent OR written exemption granted
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Painted pavement marking application (if required)
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: If required, Council approved painted pavement marking is to be applied by a self propelled machine, with the minimum requirements for paint, glass, and skid resistance to be as per Material TDS
label | REFERENCE DOCUMENTS: Material TDS
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Long life pavement marking application
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: all line marking shall be applied using a self propelled ride-on machine including statcon marking unless otherwise approved, with the minimum requirements for long life materials and glass beads to be as per table 721.E021 & Material TDS
label | REFERENCE DOCUMENTS: VR721.E01, VR721.E02, Material TDS
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Protection of works
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Work to be protected by appropriate means until it is trafficable.
label | REFERENCE DOCUMENTS: VR721.A11
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Acceptance of retroflectivity
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Contractor to measure level of retroflectivity, with the average of six test site retroflectivity values for each lot.
label | REFERENCE DOCUMENTS: VR721.A13
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed, Test report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Acceptance of colour
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Colour match tests for white & yellow markings to be conducted as per 721.A14, with results forwarded to the superintendent no later than 5 days from testing.
label | REFERENCE DOCUMENTS: VR721.A14
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed, Test report
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Acceptance of tolerances
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Survey conformance report to show line marking applied as per tolerances shown in table 721.A101.
label | REFERENCE DOCUMENTS: VR721.A10, VR721.A101
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed, Survey report
label | SCP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Acceptance of work
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: Work to comply with specified requirements as detailed in VR721.A12
label | REFERENCE DOCUMENTS: VR721.A12
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Records & reporting
label | FREQUENCY: Per lot
label | ACCEPTANCE CRITERIA: All new markings to have job completion report forwarded to the superintendent, with a retroflectivity report completed and forwarded to the superintendent showing the retroflectivity for each test lot.
label | REFERENCE DOCUMENTS: VR721.B06
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed, Reports
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-014 - Permanent Roadside Signage | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-014 - Permanent Roadside Signage Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Inductions
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG Site.
label | REFERENCE DOCUMENTS: PMP Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction card
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision IFC drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, Site induction
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: Applicable TMP no.:
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Roadside Signage Install
checkpoint | 2.1 - Set out posts and foundations
label | FREQUENCY: Prior to commencing install
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.714.06
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Consent to proceed by Superintendent OR written exemption granted, This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material compliance
label | FREQUENCY: Prior to commencing install
label | ACCEPTANCE CRITERIA: All road Signing must comply with the Technical References including the requirements of section 860 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
label | REFERENCE DOCUMENTS: VicRoads Specification 860
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Material compliance, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Installation method
label | FREQUENCY: Once per lot
label | ACCEPTANCE CRITERIA: The sign installation shall be as described in the sign schedule and as shown on the contract drawings.
label | REFERENCE DOCUMENTS: VicRoads Specification 714.04 & 07
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Installation tolerances
label | FREQUENCY: After completion of works
label | ACCEPTANCE CRITERIA: Verify signs were installed to tolerances stated in VicRoads Sec. 714.05
label | REFERENCE DOCUMENTS: VicRoads Specification 714.05
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Photos, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-015 - Electrical and Communications Conduit Installation | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-015 - Electrical and Communications Conduit Installation Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - IFC / Shop Drawings Submission & Approval.
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: IFC Construction Drawings & Most Current Revision.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: IFC Dwgs
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.2 - Survey Set-Out
label | FREQUENCY: Where Required
label | ACCEPTANCE CRITERIA: Qualified Surveyor to set out extent of works on ground
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION / TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey Calibration Certificates
label | WP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit/ Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Identify underground services NDD/hand dig as necessary.
label | ○ DYBD documents
label | REFERENCE DOCUMENTS: Dial Before You Dig
label | INSPECTION / TEST METHOD: Survey
label | RECORD OF CONFORMITY: Excavation Permit
label | HP*
label | RESPONSIBILITY: Foreman
date | Date Completed:
section | 2 - Materials
checkpoint | 2.1 - Conduit Sizing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Conduit sizing to comply with VR table 733.021
label | ○ Excludes utility providers designs and requirements
label | REFERENCE DOCUMENTS: VR SS, Table 733.021
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This Checklist
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 2.2 - Material Backfill
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Unless otherwise specified, materials used for bedding and backfilling shall be uniform in composition and free from perishable matter and shall comply with the requirements specified in Table 706.061.
label | REFERENCE DOCUMENTS: VRSS 706.03
label | INSPECTION / TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This Checklist
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
section | 3 - Excavation
checkpoint | 3.1 - Entry/ Exit Points
label | FREQUENCY: Prior to Excavation
label | ACCEPTANCE CRITERIA: Entry/Exit points to be established
label | REFERENCE DOCUMENTS:
label | INSPECTION / TEST METHOD: Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.2 - Minimum Cover
label | FREQUENCY: Ongoing
label | ACCEPTANCE CRITERIA: Minimum conduit cover shall apply as per table 733.031
label | ○ Under Freeway Pavement – 1200mm
label | ○ Under Arterial Road Pavement – 1200mm
label | ○ Under Local Road Pavement –600mm-800mm
label | ○ Under Open Drains – 750mm
label | ○ Under footpath or unpaved areas (LV Circuits only) – 600mm
label | ○ Under footpath or unpaved areas (Extra LV or Comms conduits only) – 300mm
label | REFERENCE DOCUMENTS: VR SS 733.031, Refer Individual asset owners specifications
label | INSPECTION / TEST METHOD: Survey
label | RECORD OF CONFORMITY: AS Builts
label | SCP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.3 - Backfilling
label | FREQUENCY: Prior to backfilling conduits
label | ACCEPTANCE CRITERIA: Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
label | ○ For Vicroads assets only. Not applicable to Utility providers
label | REFERENCE DOCUMENTS: VR 733.06
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP
label | HP
label | RESPONSIBILITY: Superintendent or Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Compaction Requirements
label | FREQUENCY: During excavation
label | ACCEPTANCE CRITERIA: Under Paved Areas - 98% Modified Compaction
label | ○ Unless otherwise specified, pavement material shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified compactive effort.
label | ○ Bedding and Backfill (except pavement)
label | ○ Backfilling beneath areas to be paved shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%. The calculation of density ratio shall be based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
label | REFERENCE DOCUMENTS: Test Results
label | INSPECTION / TEST METHOD: Compaction Test
label | RECORD OF CONFORMITY: Test Result
label | TP
date | Date Completed:
checkpoint | 3.5 - Survey pick up / Bore Mark Out
label | FREQUENCY: During Bore
label | ACCEPTANCE CRITERIA: Survey to pick up as record of conformity on top of laid conduit prior to backfill.
label | REFERENCE DOCUMENTS: Survey
label | INSPECTION / TEST METHOD: Survey
label | RECORD OF CONFORMITY: AS Builts.
label | SCP
label | RESPONSIBILITY: Foreman
date | Date Completed:
section | 4 - Completion
checkpoint | 4.1 - Entry/ Exit Points
label | FREQUENCY: On Completion
label | ACCEPTANCE CRITERIA: Ensure clean fills is used to fill in Entry/ Exit points
label | REFERENCE DOCUMENTS:
label | INSPECTION / TEST METHOD: Review
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 4.2 - Conduit Layout
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Conduit arrangement to suit trench detail;
label | ○ Conduit to slope towards pit for drainage purposes;
label | ○ Quantity of conduits to be confirmed and entered w/ each lot.
label | REFERENCE DOCUMENTS: Utility Provider Drawings/ Project Plans
label | INSPECTION / TEST METHOD: Project Engineer
label | RECORD OF CONFORMITY: Inspection
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 4.3 - Draw Cord
label | FREQUENCY: On Completion
label | ACCEPTANCE CRITERIA: Each conduit for electrical wiring an communications cables shall be provided one synthetic draw cord not less than 3mm diameter and a minimum breaking strain of 1.6kN
label | REFERENCE DOCUMENTS: VR SS, 733.05
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 4.4 - Site clean up
label | FREQUENCY: On Completion
label | ACCEPTANCE CRITERIA: Ensure site is clean and all garbage has been removed
label | REFERENCE DOCUMENTS: VR 733.09
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 4.5 - Maintenance of Pavement
label | FREQUENCY: On Completion
label | ACCEPTANCE CRITERIA: The reinstated surface shall be maintained in a trafficable condition after the completion of backfilling. Additional pavement material shall be placed in the trench and compacted as specified where in paved areas settlement or loss of material from the surface exceeds 20 mm measured from a straight edge laid across the top of the trench.
label | REFERENCE DOCUMENTS: VR 706.11
label | INSPECTION / TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Foreman
date | Date Completed:
checkpoint | 4.6 - Records
label | FREQUENCY: On Completion
label | ACCEPTANCE CRITERIA: Bore Logs of the works to be supplied from subcontractor
label | REFERENCE DOCUMENTS: Bore Logs
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP
checklist | DOT-31608-FUL-QAC-ITP-016 - Installation of Traffic Signals | itp |  |  |  |  | DOT-31608-FUL-QAC-ITP-016 - Installation of Traffic Signals Rev 0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG site
label | REFERENCE DOCUMENTS: PMP Inductions Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION / TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, Site induction, Project Specification Cl. 1200.03
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION / TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer & /Site Foreman
date | Date Completed:
checkpoint | 1.5 - Ground Penotration Permit issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current Ground Penotration Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION / TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Installing Traffic Signals
checkpoint | 2.1 - Civil Works
label | FREQUENCY: Following Preliminary Works
label | ACCEPTANCE CRITERIA: Works completed and subcontractor DoT Report completed in accordance with Section 730 & 733 of the Department of Transport Specification
label | ○ Pre-installation meeting conducted
label | — HP Sec 730.08 c -DoT Pre-Installation Report
label | ○ Alternative foundations noted in Pre-Installation Report
label | — HP Sec 730.11-DoT Pre-Installation Report
label | ○ Proposed boring to be discussed, agreed and noted on Pre-installation report
label | — HP Sec 733.03 - DoT Pre-Installation Report
label | ○ Pre backfill inspections (conduit / foundation) carried out and signed off
label | — HP Sec 730.11, HP Sec 733.03, HP Sec 733.06
label | ○ Pit lid Surround prepour inspection
label | — HP Sec 733.07 (c)
label | ○ Grouting of bores to be inspected
label | — HP Section 733.03
label | — Concrete testing completed (Slump and Compressive Strength) In accordance with Section 610.16
label | REFERENCE DOCUMENTS: (DoT) Pre-Instalation Report
label | INSPECTION / TEST METHOD: Document review & Site Inspection
label | RECORD OF CONFORMITY: Signed Pre-Installation Report, Completed Healey's ITP FO41 Pit, Conduit, Foundation Installation, Concrete test reports
label | HP*
label | RESPONSIBILITY: Site Engineer & Sub-contractor
date | Date Completed:
checkpoint | 2.2 - Electrical Works
label | FREQUENCY: Following Civil Works
label | ACCEPTANCE CRITERIA: Works completed and subcontractor DoT Report completed in accordance with Section 730 of the Department of Transport Specification
label | 1) Traffic hardware inspected HP Sec 730 14
label | — DoT Pre Comissioning Report.
label | 2) Cabling Scheme agreed HP Sec 730.17
label | — DoT Pre Comissioning Report.
label | 3) Electiral Tests & Flash Test performed HP Sec 730.17
label | — DoT Continuity, Insulation, Pre-comissioning Reports,
label | — HEALEYS - FO83 TSIR Electrical Checklist Inspection & Test Plan
label | REFERENCE DOCUMENTS: (DoT) Continuity Report, (DoT) Insulation Resisitance Report , (DoT) Pre-commissioning Report
label | INSPECTION / TEST METHOD: Document review & Site Inspection
label | RECORD OF CONFORMITY: Signed & DoT Reports, Concrete test reports.
label | HP*
label | RESPONSIBILITY: Site Engineer & Sub-contractor
date | Date Completed:
section | 3 - Completion of Works
checkpoint | 3.1 - Completion of Traffic Signal Works
label | FREQUENCY: Upon Completion of all Works
label | ACCEPTANCE CRITERIA: Works completed and subcontractor ITP completed in accorandance with Section 730 of the Department of Transport Specification
label | REFERENCE DOCUMENTS: (DoT) Comissioning Report , (DoT) Power Consumtion Report
label | INSPECTION / TEST METHOD: Document review & Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
signoff | Sign ITP