## Sheet1
1.1 | Work pack briefing | Prior to Commencing | All personnel on site have been briefed on the relevant work park relating to scope of works. | WP | Document Review | Work pack signed. | HP* | Site Engineer / Site Foreman | 1.1 - Work pack briefing | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: All personnel on site have been briefed on the relevant work park relating to scope of works. | REFERENCE DOCUMENTS: WP | INSPECTION / TEST METHOD: Document Review | RECORD OF CONFORMITY: Work pack signed. | HP* | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | 1.1 - Work pack briefing
1.2 | Check that current revision drawings are being used | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | HP* | Site Engineer / Site Foreman | 1.2 - Check that current revision drawings are being used | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used | REFERENCE DOCUMENTS: Project Drawings / Drawing Register | INSPECTION / TEST METHOD: Document review | RECORD OF CONFORMITY: Latest Revision Drawings | HP* | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | FREQUENCY: Prior to Commencing
2.1 | Steel Test Certificates | Min 14 days prior to commencing | Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation. | VicRoads Spec. Cl.708.05 (b) | Document review | Data Sheets Material Test Certificates | HP | Project Engineer/ Superintendent | 2.1 - Steel Test Certificates | FREQUENCY: Min 14 days prior to commencing | ACCEPTANCE CRITERIA: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (b) | INSPECTION / TEST METHOD: Document review | RECORD OF CONFORMITY: Data Sheets Material Test Certificates | HP | RESPONSIBILITY: Project Engineer/ Superintendent | Date Completed: | ACCEPTANCE CRITERIA: All personnel on site have been briefed on the relevant work park relating to scope of works.
2.2 | Steel Material Properties CHAR(AMP) Protection | Prior to Commencing | Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5. | VicRoads Spec. Cl.708.05 (c), (d) | Document review | Data Sheets, Visual Inspection | IP | Site Engineer | 2.2 - Steel Material Properties CHAR(AMP) Protection | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (c), (d) | INSPECTION / TEST METHOD: Document review | RECORD OF CONFORMITY: Data Sheets, Visual Inspection | IP | RESPONSIBILITY: Site Engineer | Date Completed: | REFERENCE DOCUMENTS: WP
2.3 | Identification of guard fence components | Prior to Commencing | w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams | VicRoads Spec. Cl.708.05(a) | Inspection | Completed Receival CHAR(AMP) Inspection Checklist | IP | Site Engineer | 2.3 - Identification of guard fence components | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(a) | INSPECTION / TEST METHOD: Inspection | RECORD OF CONFORMITY: Completed Receival CHAR(AMP) Inspection Checklist | IP | RESPONSIBILITY: Site Engineer | Date Completed: | INSPECTION / TEST METHOD: Document Review
2.4 | W-Beam Barrier with non standard requirements or other special measures | Prior to Installation | Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant. | VicRoads Spec. Cl.708.08(a) | Document Review | This signed ITP | HP | Project Engineer/ Superintendent | 2.4 - W-Beam Barrier with non standard requirements or other special measures | FREQUENCY: Prior to Installation | ACCEPTANCE CRITERIA: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(a) | INSPECTION / TEST METHOD: Document Review | RECORD OF CONFORMITY: This signed ITP | HP | RESPONSIBILITY: Project Engineer/ Superintendent | Date Completed: | RECORD OF CONFORMITY: Work pack signed.
2.5 | Concrete mix design (As Applicable) | Prior to Commencing | Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade. | VicRoads Spec. Cl.703 Cl.708.05(g) AS1379 | Document Review | Mix design approval | IP | Site Engineer | 2.5 - Concrete mix design (As Applicable) | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.703 Cl.708.05(g) AS1379 | INSPECTION / TEST METHOD: Document Review | RECORD OF CONFORMITY: Mix design approval | IP | RESPONSIBILITY: Site Engineer | Date Completed: | HP*
3.1 | Approval of location and length | Prior to Installation | The required location and length of all guard fence shall be confirmed with the Superintendent. | VicRoads Spec. Cl.708.08 | Document Review | This signed ITP | HP | Project Engineer/ Superintendent | 3.1 - Approval of location and length | FREQUENCY: Prior to Installation | ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08 | INSPECTION / TEST METHOD: Document Review | RECORD OF CONFORMITY: This signed ITP | HP | RESPONSIBILITY: Project Engineer/ Superintendent | Date Completed: | RESPONSIBILITY: Site Engineer / Site Foreman
3.2 | Survey set-out | Prior to Commencing Excavation | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used | Project Spec. Cl.1190.06 Latest IFC Drawings | Testing | Survey records CHAR(AMP) pegs on the ground | SCP | Site Engineer CHAR(AMP) Surveyor | 3.2 - Survey set-out | FREQUENCY: Prior to Commencing Excavation | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used | REFERENCE DOCUMENTS: Project Spec. Cl.1190.06 Latest IFC Drawings | INSPECTION / TEST METHOD: Testing | RECORD OF CONFORMITY: Survey records CHAR(AMP) pegs on the ground | SCP | RESPONSIBILITY: Site Engineer CHAR(AMP) Surveyor | Date Completed: | Date Completed:
3.3 | Post Installation | During construction. | Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness. If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil | IFC Drawings VicRoads Spec. Cl.708.08(a) | Visual Inspection | This signed ITP | IP | Site Engineer | 3.3 - Post Installation | FREQUENCY: During construction. | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness. If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(a) | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | 1.2 - Check that current revision drawings are being used
3.4 | W-Beams | During construction. | The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened. | VicRoads Spec Cl.708.08(b) | Visual Inspection | This signed ITP | IP | Site Engineer | 3.4 - W-Beams | FREQUENCY: During construction. | ACCEPTANCE CRITERIA: The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened. | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.08(b) | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | FREQUENCY: Prior to Commencing
3.5 | Guard Fence Tolerances | During construction. | Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length. | IFC Drawings VicRoads Spec. Cl.708.08(d) | Verify | Survey Records | SCP | Site Engineer | 3.5 - Guard Fence Tolerances | FREQUENCY: During construction. | ACCEPTANCE CRITERIA: Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length. | REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(d) | INSPECTION / TEST METHOD: Verify | RECORD OF CONFORMITY: Survey Records | SCP | RESPONSIBILITY: Site Engineer | Date Completed: | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
4.1 | Dimensions and set-out | After installation of guardrail | The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff. | VicRoads Spec Cl.708.12 | Visual Inspection | This signed ITP | IP | Site Engineer | 4.1 - Dimensions and set-out | FREQUENCY: After installation of guardrail | ACCEPTANCE CRITERIA: The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff. | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12 | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
4.2 | Bedding and concrete | After installation of guardrail | The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock. | VicRoads Spec Cl.708.12 | Visual Inspection | This signed ITP | IP | Site Engineer | 4.2 - Bedding and concrete | FREQUENCY: After installation of guardrail | ACCEPTANCE CRITERIA: The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock. | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12 | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | INSPECTION / TEST METHOD: Document review
4.3 | Separation from Kerb | After installation of guardrail | Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post. | VicRoads Spec Cl.708.12 | Visual Inspection | This signed ITP | IP | Site Engineer | 4.3 - Separation from Kerb | FREQUENCY: After installation of guardrail | ACCEPTANCE CRITERIA: Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post. | REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12 | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This signed ITP | IP | RESPONSIBILITY: Site Engineer | Date Completed: | RECORD OF CONFORMITY: Latest Revision Drawings
5.1 | Compliance Audit of Barrier System Installation | Prior the issue of the Certificate of Practical Completion | A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent.. | VicRoads Spec. Cl.708.10 Project Specific Specification PS3090.07(f) | Safety Audit | Certificate of Compliance for each treatment installed Product and Installation Manual | HP | Project Engineer/ Superintendent | 5.1 - Compliance Audit of Barrier System Installation | FREQUENCY: Prior the issue of the Certificate of Practical Completion | ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent.. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.10 Project Specific Specification PS3090.07(f) | INSPECTION / TEST METHOD: Safety Audit | RECORD OF CONFORMITY: Certificate of Compliance for each treatment installed Product and Installation Manual | HP | RESPONSIBILITY: Project Engineer/ Superintendent | Date Completed: | HP*
6.1 | Delineators | Once installation of assets completed. | Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 The delineators shall be arranged so that vehicles approaching from either direction at night will only see: - Red delineators on the left side of one-way and two-way roadways - White delineators on the right side of two-way roadways - yellow delineators on the right side of one- way roadways Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane. | VicRoads Spec. Cl.708.11 | Visual Inspection | Site Photos | IP | Site Engineer | 6.1 - Delineators | FREQUENCY: Once installation of assets completed. | ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 The delineators shall be arranged so that vehicles approaching from either direction at night will only see: - Red delineators on the left side of one-way and two-way roadways - White delineators on the right side of two-way roadways - yellow delineators on the right side of one- way roadways Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.11 | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Site Photos | IP | RESPONSIBILITY: Site Engineer | Date Completed: | RESPONSIBILITY: Site Engineer / Site Foreman
6.2 | Grassing of disturbed areas | Once installation of assets completed | All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place. | VicRoads Spec. Cl.708.20 | Visual Inspection | Site Photos | HP | Site Engineer / Superintendent | 6.2 - Grassing of disturbed areas | FREQUENCY: Once installation of assets completed | ACCEPTANCE CRITERIA: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.20 | INSPECTION / TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Site Photos | HP | RESPONSIBILITY: Site Engineer / Superintendent | Date Completed: | Date Completed:
6.3 | Quality Assurance | Completion of works | Submit all quality assurance documents to the superintendent including the following items: (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection. (ii) Time and date of when traffic barriers were installed (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification. | IFC Drawings Project Specific Specification PS3090.04 | Document review | As built Records and Certificate of compliance | SCP | Project Engineer | 6.3 - Quality Assurance | FREQUENCY: Completion of works | ACCEPTANCE CRITERIA: Submit all quality assurance documents to the superintendent including the following items: (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection. (ii) Time and date of when traffic barriers were installed (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification. | REFERENCE DOCUMENTS: IFC Drawings Project Specific Specification PS3090.04 | INSPECTION / TEST METHOD: Document review | RECORD OF CONFORMITY: As built Records and Certificate of compliance | SCP | RESPONSIBILITY: Project Engineer | Date Completed: | 2.1 - Steel Test Certificates
FREQUENCY: Min 14 days prior to commencing
ACCEPTANCE CRITERIA: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (b)
INSPECTION / TEST METHOD: Document review
RECORD OF CONFORMITY: Data Sheets Material Test Certificates
HP
RESPONSIBILITY: Project Engineer/ Superintendent
Date Completed:
2.2 - Steel Material Properties CHAR(AMP) Protection
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05 (c), (d)
INSPECTION / TEST METHOD: Document review
RECORD OF CONFORMITY: Data Sheets, Visual Inspection
IP
RESPONSIBILITY: Site Engineer
Date Completed:
2.3 - Identification of guard fence components
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(a)
INSPECTION / TEST METHOD: Inspection
RECORD OF CONFORMITY: Completed Receival CHAR(AMP) Inspection Checklist
IP
RESPONSIBILITY: Site Engineer
Date Completed:
2.4 - W-Beam Barrier with non standard requirements or other special measures
FREQUENCY: Prior to Installation
ACCEPTANCE CRITERIA: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(a)
INSPECTION / TEST METHOD: Document Review
RECORD OF CONFORMITY: This signed ITP
HP
RESPONSIBILITY: Project Engineer/ Superintendent
Date Completed:
2.5 - Concrete mix design (As Applicable)
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.703 Cl.708.05(g) AS1379
INSPECTION / TEST METHOD: Document Review
RECORD OF CONFORMITY: Mix design approval
IP
RESPONSIBILITY: Site Engineer
Date Completed:
3.1 - Approval of location and length
FREQUENCY: Prior to Installation
ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
INSPECTION / TEST METHOD: Document Review
RECORD OF CONFORMITY: This signed ITP
HP
RESPONSIBILITY: Project Engineer/ Superintendent
Date Completed:
3.2 - Survey set-out
FREQUENCY: Prior to Commencing Excavation
ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
REFERENCE DOCUMENTS: Project Spec. Cl.1190.06 Latest IFC Drawings
INSPECTION / TEST METHOD: Testing
RECORD OF CONFORMITY: Survey records CHAR(AMP) pegs on the ground
SCP
RESPONSIBILITY: Site Engineer CHAR(AMP) Surveyor
Date Completed:
3.3 - Post Installation
FREQUENCY: During construction.
ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness. If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil
REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(a)
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
3.4 - W-Beams
FREQUENCY: During construction.
ACCEPTANCE CRITERIA: The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
REFERENCE DOCUMENTS: VicRoads Spec Cl.708.08(b)
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
3.5 - Guard Fence Tolerances
FREQUENCY: During construction.
ACCEPTANCE CRITERIA: Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
REFERENCE DOCUMENTS: IFC Drawings VicRoads Spec. Cl.708.08(d)
INSPECTION / TEST METHOD: Verify
RECORD OF CONFORMITY: Survey Records
SCP
RESPONSIBILITY: Site Engineer
Date Completed:
4.1 - Dimensions and set-out
FREQUENCY: After installation of guardrail
ACCEPTANCE CRITERIA: The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
4.2 - Bedding and concrete
FREQUENCY: After installation of guardrail
ACCEPTANCE CRITERIA: The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
4.3 - Separation from Kerb
FREQUENCY: After installation of guardrail
ACCEPTANCE CRITERIA: Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
REFERENCE DOCUMENTS: VicRoads Spec Cl.708.12
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This signed ITP
IP
RESPONSIBILITY: Site Engineer
Date Completed:
5.1 - Compliance Audit of Barrier System Installation
FREQUENCY: Prior the issue of the Certificate of Practical Completion
ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.10 Project Specific Specification PS3090.07(f)
INSPECTION / TEST METHOD: Safety Audit
RECORD OF CONFORMITY: Certificate of Compliance for each treatment installed Product and Installation Manual
HP
RESPONSIBILITY: Project Engineer/ Superintendent
Date Completed:
6.1 - Delineators
FREQUENCY: Once installation of assets completed.
ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 The delineators shall be arranged so that vehicles approaching from either direction at night will only see: - Red delineators on the left side of one-way and two-way roadways - White delineators on the right side of two-way roadways - yellow delineators on the right side of one- way roadways Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.11
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Site Photos
IP
RESPONSIBILITY: Site Engineer
Date Completed:
6.2 - Grassing of disturbed areas
FREQUENCY: Once installation of assets completed
ACCEPTANCE CRITERIA: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.20
INSPECTION / TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Site Photos
HP
RESPONSIBILITY: Site Engineer / Superintendent
Date Completed:
6.3 - Quality Assurance
FREQUENCY: Completion of works
ACCEPTANCE CRITERIA: Submit all quality assurance documents to the superintendent including the following items: (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection. (ii) Time and date of when traffic barriers were installed (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification.
REFERENCE DOCUMENTS: IFC Drawings Project Specific Specification PS3090.04
INSPECTION / TEST METHOD: Document review
RECORD OF CONFORMITY: As built Records and Certificate of compliance
SCP
RESPONSIBILITY: Project Engineer
Date Completed: