## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6be434df-5184-4ec7-95ad-f31c432e9bd4 | checklist | Prototype Floor/Wall (ITC) |  | Prototype Floor/Wall (ITC) |  | 8ace87a4-8bbe-4780-a545-a1d7d803fdb9
ee8b7728-b9f9-4da8-a294-e0642501f21a | section | Review
c08be939-9789-4da1-a14d-82d9048b3c3c | checkpoint | Review section detail and 3D illustration from specification.
56fcdfc5-a147-4d43-9b44-25b24e6bca27 | section | Sopradrain 20
d5da2ce2-cd6c-46ec-99dc-377a71ec89ff | checkpoint | Substrate: The substrate must be clean and free from loose materials or any construction debris prior to installing Sopradrain 20. Commencement of installation shall be taken as acceptance of the substrate by the applicator.
e0b4bdc8-df3f-4fea-abb7-202778138eb8 | checkpoint | Sopradrain 20 must be installed vertically on the wall with nail fasterners from top edge to the bottom fillet.
435bcd4e-b485-4928-ba6a-2ab99cb15459 | section | Colphene BSW V
8578c07c-ede1-42fc-89cc-443b1b3751cc | checkpoint | Substrate: The substarte must be smooth, dry and free of ice, snow or any other substance that may prevent the membrane from adhering effectively. Commencement of installation shall be taken as acceptance of the substrate by the applicator.
9b5276fe-d8a5-4bd7-abd1-6b0b1d02d838 | checkpoint | Colphene BSW V is installed in vertical strips of 5 m maximum onto acceptable substrate.
e74abb1d-970a-4e4f-9e18-999e82f111ee | checkpoint | Colphene BSW V membrane is adhered to substrate by peeling off the silicone release film
66856d02-1f6d-4dae-a3db-38a90843364c | checkpoint | Prime Colphene BSW V with Elastostic primer to increase the Colphene BSW V Adhesion. ELASTOCOL STICK can be applied with a brush, a roll or a spray can. The application surface must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity.
f9df1b75-12d5-4b7b-8f60-86f3e4e43a8e | checkpoint | Install Colphene BSW V along floor/wall joint. 200mm lap onto prepared substrate/blinding.
78bb024a-9667-4cbd-86fd-d978f029f0c0 | checkpoint | Once installed, a pressure must be applied over the whole surface using a membrane roller to ensure good contact.
8f3660d0-bf52-4901-9905-e3a70728297d | checkpoint | Install Colphene BSW V to wall, lap onto previously installed membrane with a lap of 150mm.
203a19c5-4e69-49a2-b310-4a9c67a7231c | checkpoint | Membranes overlaps are sealed, by heat-welding, with a propane torch or using an electric hot-air welder.
5a15cddc-28aa-4908-856b-cac08311eafe | checkpoint | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm continuous bleed not smeared.
dfa8991e-0383-455a-bf77-f3adf36ac394 | checkpoint | Side lap joints must be a minimum of 100 mm and end lap joints must be a minimum of 150 mm
bb2cb2db-3a44-47d3-b751-ea5a36092e8c | section | Colphene BSW UNI NG
f4920e72-9f4f-4ee2-b5ca-bc59edcb5431 | checkpoint | Substrate: The substrate must be smooth, dry and free of ice, snow or any other substance that may prevent the membrane from adhering effectively. Commencement of installation shall be taken as acceptance of the substrate by the applicator.
4e3ce604-5776-4c0a-b53e-bdb1f321b40d | checkpoint | Ensure COLPHENE BSW UNI NG thickness is 4mm before the installation.
b16a6687-c27e-4c2b-ba27-fa59aafb13c0 | checkpoint | Lay CLOPHENE BSW UNIG NG loose on the prepared blinding floor using a roller for correct installation.
c79e5abd-24a5-443d-aed7-054a8bba3fb0 | checkpoint | Install Colphene BSW UNI NG to floor butting up to floor and wall junction and to be lapped with existing COLPHENE BSW V to achieve 200mm lap.
9a601057-8b95-470f-8628-f854c13e81b6 | checkpoint | Install Colphene BSW UNI NG reinforcing strip across floor/wall joint 150mm lap on wall, 250mm lap onto COLPHENE UNI NG on the floor. Ensure the COLPHENE UNI NG Reinfircement strip has smooth rounded edges at the floor/wall junction.
190c7ebc-7448-4329-b294-62d608cb6343 | checkpoint | Stagger the end laps by a minimum of 300mm to avoid excessive membrane layering.
d50f6c13-b8b7-49ed-9f40-4c552cfaca95 | checkpoint | Install Colphene BSW UNI NG to reinforcing strip across wall membrane horizontal joint - 300mm lap over the the COLPHENE BSW V joint. Ensure the COLPHENE UNI NG Reinfircement strip has smooth rounded edges at the wall membrane horizontal joint.
6aa9bea7-a0e2-4f01-a3e3-b37f8794846b | checkpoint | Visual inspection of joint welds at cross laps.
28933dec-1e1a-4fa4-b6f4-9b5a31b684c0 | checkpoint | Confirm no laps at capping beam construction joint
c9fc5fae-9bd8-4056-ac8f-909b7946b5fe | checkpoint | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm continuous bleed not smeared.
f72953f8-1162-4c70-a175-d873d7eaf2c2 | checkpoint | HOLD POINT - Bravada installer to conduct final review of membrane system installation and confirm compliance with shop drawing/specification.
b12392bd-ca86-4849-a38d-be2d35d50e36 | checkpoint | HOLD POINT - Bravada Supervisor to conduct final review of membrane system installation and confirm compliance with shop drawing/specification.
822dc37e-f144-4b2c-abb5-694321ca7d3e | checkpoint | HOLD POINT - Delta Group Project Manager, I have reviewed the Floor/Wall Prototype with Bravada, reviewed Bravad's ITC. I acknowledge handover of the works package to Delta Group and accept all responsibility for protecting the works package.
| checkpoint | Pressure Seal
| checkpoint | Pressure seal conecting new membrane with existing - By Delta
| checkpoint | Confirm Pressure seal steel plate width: 75mm
| checkpoint | Confirm Pressure seal steel plate thickness: 3mm
| checkpoint | Bolts sealed galvanised paint - By Delta
| checkpoint | Bolts: 12mm wide Excalibur bolts with washers installed at 100mm spacing c/c
098af7db-5f4c-4fee-833d-96323bce31ab | checkpoint | CHECKLIST COMPLETE AND SIGNED
0c9fcc2e-21b4-462a-b84e-cf8c1c862712 | checkpoint | ITC completed
25c7d0df-768a-4c30-ada3-8a6512238771 | checklist | Prototypes ITP | itp | Prototypes ITP |  | 32e4ff8f-ee6c-48e0-9405-fab1dfd66c74
feaa40df-85ea-4433-bd32-5e744cb4878c | section | 1
224933f3-ec3b-466a-9716-0b62f3c6d8ac | checkpoint | Sample Submissions Approved
f131f574-6a91-4489-842a-5de8162753ef | checkpoint | Shop Drawings Approved
5f24083d-fb96-4023-a529-9ef4d1679bcf | checkpoint | Prototype Injectable Hose installed
990feb80-5c28-4d6e-b6ae-4f8a2e79aa2b | checkpoint | ITC Pre-Pour Complete & Signed
83d60552-938d-4408-813e-b9b158abcb15 | checkpoint | Client Inspections Completed & Report Closed Out
6b40f0e1-bf0d-4714-b3af-9cd027dbd946 | section | 2
192da530-c95f-476e-bb13-b627f6de365a | checkpoint | Sample Submissions Approved
d1000e71-dff3-4ea5-b5ab-c2bb3c0ba9cf | checkpoint | Shop Drawings Approved
4179875f-3240-4c3b-872d-590491825ae1 | checkpoint | Prototype floor / Wall
8dce28a2-f71d-4e24-b59a-a5328ee6bc1c | checkpoint | Colphene BSW V - Installed to wall
94280a8d-fef1-4e20-860c-41eb3c428205 | checkpoint | Colphene BSW UNI NG - Installed to Floor
6c853060-6d08-4e92-9541-78e278710192 | checkpoint | Colphene BSW UNI NG - Reinforcement strips Installed
| checkpoint | Pressure Seal Installed
494b44d1-06cb-4e50-9ade-559c53090674 | checkpoint | ITC Pre-Pour Complete & Signed
11e29b43-68b1-4235-8613-539216746f9c | checkpoint | Client Inspections Completed & Report Closed Out
93e1fc53-1495-4d2d-90ac-882904ccae7d | section | 3
85c0dd42-3b73-4359-a3df-57c3b9fb8128 | checkpoint | Sample Submissions Approved
8ab0e8aa-acf9-48b7-985d-98814fc0ee3d | checkpoint | Shop Drawings Approved
9945d6d5-f189-4945-b088-7bfbdfe84504 | checkpoint | Prototype Pile cap
8808cfcd-e05c-4d52-9f95-f2f4c888e59e | checkpoint | Colphene BSW UNI NG Installed - To Pile Base
5ee16a42-30d6-4525-975d-261cfbc5593f | checkpoint | Alsan EP CAP Installed - To Pile Base
0e09a9e9-a448-4c45-9d02-1ecd99b8b86a | checkpoint | Alsan EP M Installed - Fillet
1625cd14-4ab4-47f4-84f3-960b3092568a | checkpoint | ITC Pre-Pour Complete & Signed
badde716-989f-44dc-9cae-d34fc312814e | checkpoint | Client Inspections Completed & Report Closed Out