## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
14185836-1b06-5f86-9ad7-c6daeb2a4eaa | checklist | SYS - ITP - Retaining Walls |  | ITP - Retaining Walls
8c9335a7-3af5-5e47-a887-39a89ff08c27 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9ce14095-414c-5d6d-8ec4-d9fde1bdc783 | checkpoint | 3.01.01 - Construction Pack
dfb723bb-584a-5713-be6d-07b0f19feadc | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
e2830cdf-362b-5f0e-8d22-f68f1a98219d | note | Standard / Specification - Downer
14282032-c33f-55dc-9ae6-ba093f01c0fa | note | Verifying Document - Construction Pack
9e7ee91d-d82a-5694-af12-0f67083b3c87 | note | Frequency - Submit 10 days prior to commencement of works
2a4ab9d4-071d-53fa-ac91-77f26febe2a2 | note | Activity - HP
d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c | note | By - ENG
ca255811-cbe5-57f5-8b49-d49ad30655f3 | signoff | AUTHORITY HOLDPOINT
0bf24461-d91f-58f3-b929-a737290bf896 | checkpoint | 3.01.02 - Survey Setout
dc572b14-0ed6-54c7-bc8f-85ed00c03dfe | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3e946a9d-b5c8-50e7-96e0-0400e8f6e89c | note | Standard / Specification - Downer
34bb53e5-aed2-52e3-a5c2-9f81d0a823ca | note | Verifying Document - Survey Records
61d76f5d-0ad9-583f-ac76-86ad184fa739 | note | Frequency - Prior to Works
376f33df-3b2b-5b0c-ab68-eb1a544a497d | note | Activity - H
c900da17-59f9-5691-b9d1-3bcd5996d491 | note | By - SV
a24a2c58-bf6f-5474-883c-40044bad1fc7 | checkpoint | 3.01.03 - Service Location
b9f21eeb-7675-5741-9a79-4af249ac51cd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
434102cd-5777-54cc-b4b5-32744d498024 | note | Standard / Specification - Downer
07a728fa-eece-56e9-af95-f512783809d3 | note | Verifying Document - Excavation Permit
077eeafa-3bad-5034-9687-5e46d0d70d1b | note | Frequency - Prior to Excavation
f621f899-2387-5113-900d-6bf9fc014ca0 | note | Activity - H
765fd8e2-b34a-5911-8b80-bd9e215f5033 | note | By - SE
0a214a7a-124a-5898-a837-e29e83751df0 | checkpoint | 3.01.04 - Internal Permits
b356337b-ff8b-5218-b916-0250a1283683 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 | note | Standard / Specification - Downer
62309b3c-27a8-5c74-8629-890633f13944 | note | Verifying Document - Internal Permits
83e97ed8-8c87-565f-9e65-f307d506c6a2 | note | Frequency - Prior to Excavation
d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 | note | Activity - H
3d563ef1-3b79-577d-b94f-308e34e1ca4e | note | By - SE
917e2881-0901-542f-ae25-686bf9c47009 | checkpoint | 3.01.05 - External Permits
b3b0e978-a810-584e-aa53-c42ce3c97641 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 | note | Standard / Specification - Downer
9637f9ab-b7c6-54c8-8436-24c62804f0c4 | note | Verifying Document - External Permits
86a70157-a919-5dd5-aa32-c8681501a34c | note | Frequency - Prior to Excavation
bdcdc434-1b5d-5073-8411-b8512f1171ba | note | Activity - H
9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 | note | By - PE
a1302970-0389-558d-b43c-67b14bbfc27a | checkpoint | 3.01.06 - Approved Construction Drawings
9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
35f67329-e2c7-5487-a6d4-58b982b7c249 | note | Standard / Specification - Downer
3dfe5430-9c4a-5998-aade-3c0355af63af | note | Verifying Document - IFC Drawings
2b7e4a6a-c00a-5a00-ac72-61e46e5f805a | note | Frequency - Prior to works start
64beb55c-164d-586e-993a-71bf994ecd03 | note | Activity - H
16b491c1-6520-5184-a1cd-e89a84b6dddc | note | By - PE
34b3d838-f63d-5499-aad4-14b7c1eb24ae | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
1437ac3f-e25b-5932-8866-3f1e2bab518b | checkpoint | 4.01.01 - Stone Strong Block Molds
24a4862f-20e9-5858-9e47-682e8ebdcd0f | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
b7e1ac9b-4fd0-5aed-91f1-207545543544 | note | Standard / Specification - PS - 12
4fbb56e2-610f-5ab3-b571-8d5a95c19942 | note | Verifying Document - Conforming Molds Post Carving
4ea6de2e-aec5-50b2-a438-bd4bd870e686 | note | Frequency - Before Installation
d4a2256c-c353-57e5-9fce-3979c4f41a52 | note | Activity - H
1c7d0313-833b-5b02-8452-76e926b94d30 | note | By - PE
a3cd3258-fb54-5b31-83f8-74d9198b64d1 | checkpoint | 4.01.02 - MSE retaining wall backfill Material
cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
22721888-49d4-5ebd-a823-b786fde9c2dd | note | Standard / Specification - GWS - 5.3.3
f760ee7e-3e30-5748-ac8d-dd6f4cff2189 | note | Verifying Document - Lab Results
ac1f5c71-71b7-5418-a6b3-d83649055b3c | note | Frequency - Prior to works
951e9d5f-bd61-5982-b242-bf9f0c0caffb | note | Activity - H
8ebf4f1b-07e1-53f7-b331-bcd4af254b27 | note | By - PE
05bce6c9-76c8-5aeb-94f0-6addb618072e | checkpoint | 4.01.03 - Geogrid
a5ac5972-5125-5559-af6d-1c6c4e7dedcc | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 | note | Standard / Specification - GWS - 5.3.1
0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 | note | Verifying Document - Datasheet
8616060a-d369-50b8-aaba-ef3009718c94 | note | Frequency - Before Installation
a58b35f4-bec7-526e-a186-cb8cfac7ff0c | note | Activity - H
96867ef7-72bf-5c39-9276-a8fa57a392dc | note | By - PE
6e039cf8-38d9-583d-81da-a16916cec0db | checkpoint | 4.01.04 - Para web
1caebfdf-02c1-5487-a1c2-99494d3a7d32 | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
fc6b5ecc-9ae5-5429-b362-4e4e740b858a | note | Standard / Specification - GWS - 5.3.2
c6a61179-13b0-5cce-86df-0b2aee73ba18 | note | Verifying Document - Datasheet
d6d44771-ac67-536d-add9-852624175da7 | note | Frequency - Before Installation
9d9aac6a-b187-50c7-bcbc-e7f671b406f3 | note | Activity - H
55508e0c-9e1b-52b3-a5d1-64da039c0ec6 | note | By - PE
e132fae1-e9b4-511f-a4c3-4d0a9e983806 | checkpoint | 4.01.05 - Drainage Pipes
7a5b659a-8903-53d2-923a-b6d92a4b1645 | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
7794d7ea-668a-5c32-bb0f-3680b36f6de3 | note | Standard / Specification - GWS - 5.3.4
ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 | note | Verifying Document - Datasheet
d56eee96-b50c-5a01-acdc-8056d052ceaa | note | Frequency - Before Installation
395116fd-81ab-5fbc-8151-6255ffeb4a71 | note | Activity - H
8fb5b411-f437-5583-8180-b42cdf2a2a99 | note | By - PE
e7adda1d-89e3-5dee-b757-9e3f5f015cac | checkpoint | 4.01.06 - Geocomposite drainage board
cd6be02c-c749-5f25-acc3-4ffb2cefa944 | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
ebf65b67-521d-5975-ac96-0b04a5a626cd | note | Standard / Specification - PS - 12
1de52d81-e41e-553d-9c21-f0f6340ab64c | note | Verifying Document - Datasheet
0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 | note | Frequency - Before Installation
f2e98e9e-bba5-51b9-b10c-728c27a797b5 | note | Activity - H
29b83dfe-e46e-5abc-a914-d0df434d4e6f | note | By - PE
7d04c6ae-3cb1-5c0a-9796-1cc24d0858ea | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
838e6cd4-76c0-5235-b72d-9a0f1a44ed66 | checkpoint | 5.01.01 - Excavation to subgrade
a44eca19-0903-53b8-b909-f430fbf6b9bf | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
5722bcfc-454b-577a-9ad1-d3e3205134b4 | note | Standard / Specification - GWS - 5.2
915e6908-c8fe-5ac1-9db4-a947962d0041 | note | Verifying Document - Scala Results
a490c5fe-167a-5b44-ab44-b30841d751aa | note | Frequency - Every 10m
6289dc62-ab20-571f-9d3e-14f5140d96a5 | note | Activity - H
b7a8ce23-7996-5bcd-af78-3797ae943025 | note | By - SE
c4674b26-69c0-5262-a38b-746e46d5825b | checkpoint | 5.01.02 - Foundation Approval
88bbf40b-3a7e-5106-a1eb-b04cac8b3276 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
87cf84f3-b265-54c8-91f4-8fe99cf580ac | note | Standard / Specification - GWS - 5.2
1686d54b-8287-51df-86cf-43bc7127c4b6 | note | Verifying Document - Approval
92f82e7a-8f29-5590-9360-08dca36f2305 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
75d2a1b0-4525-5583-9519-6b0bab956b25 | note | Activity - HP
13ca0be8-8086-5cfa-835c-649526f18337 | note | By - ENG
2ddb755a-f329-5467-ab5f-6a7fca5b3f95 | signoff | AUTHORITY HOLDPOINT
19ca66fa-e5a2-5cfc-b467-61317531b98d | checkpoint | 5.01.03 - Undercut subgrade
3a1426c3-4a4b-50d6-8c92-de9a0f129814 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 | note | Standard / Specification - GWS - 5.2
f1f6c15f-6596-5cfe-9cd1-5734db4e100b | note | Verifying Document - Survey Record/ Photo record
37cd6678-71f7-5b8a-aaae-7266b0c53b90 | note | Frequency - If required
09fca302-cdb5-5d57-a109-7acf55153583 | note | Activity - I
839acd88-9afc-5d25-87e1-5dc15047bc55 | note | By - SE
11e626b6-30f1-58a8-84fd-9bad3add61ff | checkpoint | 5.01.04 - Undercut backfill compaction
686827fe-56ed-5bab-9d64-495ebf6340bf | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
e5515d9a-8cc8-5f73-9ca8-e055c4cc041f | note | Standard / Specification - GWS - Table 3
08c502fa-14b9-5b61-b1a0-0533d2b91f20 | note | Verifying Document - NDM Results
49be031b-95ea-5b55-97e3-3536950c4134 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
14a27680-1a25-52b8-bd00-1fab40f44075 | note | Activity - H
c95dd2e2-6397-5c53-ba34-465a08f15a20 | note | By - SE
429c469f-d0be-5299-88a0-616d51d283a0 | checkpoint | 5.01.05 - Geogrid Installation
7c06f150-6a83-5a7f-bf9e-26add933060a | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
8150c2df-f463-5e1e-9900-9baeb8241b95 | note | Standard / Specification - GWS - 4.1
502aec9f-4e98-5c7b-ade9-d8d49f08c81f | note | Verifying Document - Photo record
956b32f9-ff13-55e8-a916-4c3f79f7faac | note | Frequency - Each layer - 1 layer per abutment to be inspected
1f4aba03-43ec-52d8-9410-bef8fd128ad6 | note | Activity - HP
2ce0bc49-bf59-54a7-a221-56df0205defd | note | By - ENG
80a3b809-4a16-5781-8b97-a04ae2c7abfa | signoff | AUTHORITY HOLDPOINT
bd17909b-24fc-567d-8e74-41ab189fc4b3 | checkpoint | 5.01.06 - Backfill Installation
c7c2d1b0-c2f8-5768-8d67-067103ab63da | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
523bffe5-aaee-5a9b-8e89-14e05f013cba | note | Standard / Specification - GWS - 5.3.3
11658044-8281-56e6-9f67-20faad0299fb | note | Verifying Document - Photo record
ac859c0c-278d-5b8e-a292-46ad56fb0962 | note | Frequency - Each layer
ef9db130-4c9f-5391-867a-972b372090fa | note | Activity - I
a3687b6e-7c6b-53f0-b274-e31e41cd696f | note | By - SUP
a62858e4-ea20-5ed9-923e-9ca82c01b7a0 | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
ad7fa407-e378-5634-ab93-1828e1f82e34 | note | Standard / Specification - GWS - Table 3
84067f73-90f3-5c9f-bcc9-3412062ae46f | note | Verifying Document - NDM Results
215fd151-1567-5313-ab16-40cc8c973c76 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
b1904192-86c4-5dc0-983d-0c4625692197 | note | Activity - H
1759d2ab-8aaf-5e44-8271-0bca9708cfa4 | note | By - SE
8ecddfdf-b738-562d-924c-6d9e94ab9029 | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
98614c55-f750-506f-9503-10c3e30e1881 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f9fe1ac-2fbc-57be-ac76-85de65fe652e | note | Standard / Specification - GWS - Table 3
4e604154-4a81-55e9-b377-2b88c923b018 | note | Verifying Document - Clegg Result sheet
bd438c47-31e5-566a-944c-a5b5c76088c7 | note | Frequency - Each layer - final layer to be inspected
774d86f1-ba7c-50b6-94d6-30bf5a948c3f | note | Activity - HP
7364a921-2ff7-5c35-9159-3054bb9afa4c | note | By - ENG
bb7a1071-2609-5dff-a667-8d15d7b69bbd | signoff | AUTHORITY HOLDPOINT
79e53a18-7c06-522e-b64b-df9faebbb82e | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
0de6b358-0f29-58af-ad62-e6befe37e01e | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
723574f2-3e35-56ba-972d-31c4f942de55 | note | Standard / Specification - GWS - Table 3
950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 | note | Verifying Document - Scala Results
1f645c31-308b-548f-8dde-196580b6b892 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
6720fe90-9a00-56ad-8968-01ae35b290ac | note | Activity - H
714be469-f8be-5424-9050-e3ecf0a94400 | note | By - SE
1fa40bf2-514b-5091-af6a-f9081489cccb | checkpoint | 5.02.01 - Level founding platform
9c8eb987-df2c-50a7-95ae-edac73b9c3d4 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
ca1e2ed9-2c2b-5b18-a741-e994b2b723df | note | Standard / Specification - PS - 12
43ce2579-fec0-5318-87c6-4a8e9b3a20bb | note | Verifying Document - Site Photo / Checksheet
1b680dd9-e479-578f-bbde-69c1729e3ee9 | note | Frequency - Prior to Stone Strong block installation
a9c7ed43-8613-5ebc-857e-690eca1a5585 | note | Activity - I
b5fbdddf-aa08-5620-83bd-7340b7acd380 | note | By - SUP
70fcc93e-5f6b-523c-8390-a613fc5c0dd4 | checkpoint | 5.02.02 - Installation of blocks
90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b12d3329-7987-5247-b922-ec1c92c9ed00 | note | Table 4: MSE Tolerances
dfcb71bb-f02b-56d1-bd66-3ef672ac4eab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
c9b8de3b-7e7d-54be-a648-be447dff7dc0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
18339fca-9026-508b-96e4-2fb4655e0c6a | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
7e0bf557-a381-509d-8795-4822c3e0c715 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
a3fbd331-d3ef-513a-8a89-9470f7fdb303 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
07037d56-3fae-5229-bb84-bcd2d797e781 | note | Standard / Specification - GWS - 5.4
48c1e9a8-8b89-527a-91c8-f72b261b72e0 | note | Verifying Document - Site Photo / Checksheet
54fda68a-448a-5dcd-8ed6-0a86c20b0e5a | note | Frequency - Each layer
913f0a58-b1ca-5bfb-8468-b952a9389447 | note | Activity - I
2396be86-4697-57ce-b7b9-b3a1d1c2257a | note | By - SUP
0738a9e4-1da3-543c-acc0-e874f185dfd9 | checkpoint | 5.02.03 - Paraweb Installation
0bef5334-c77a-5d85-8b74-f29c3c8ca7fc | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
622c6a80-827b-564b-a1b0-826cc8553560 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
50d68f77-c004-52f2-a57e-49698bdf2f38 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
8668a89a-332f-5adb-87ff-04813367b41f | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
302495c3-5f3f-555b-bf19-8ba352b3798f | note | Standard / Specification - GWS - 5.3.2
e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e | note | Verifying Document - Site Photo / Checksheet
19a36404-73ee-57c2-ad94-ea23f2a50577 | note | Frequency - Each layer
4ed90da9-8014-54fc-aff4-4d93fce754c9 | note | Activity - I
62c634e1-5096-505b-a986-ddb7ae13ae72 | note | By - SUP
d7e05ad4-017a-5c53-8850-a7a729d14f34 | checkpoint | 5.02.04 - Geotextile
f1a8bb54-9914-5908-800a-019f85bc7027 | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
94cc05b3-7ed4-549e-b03a-e2ee7b360416 | note | Standard / Specification - SS - 5
647f2bf3-b023-5467-aedc-97bbb0515d40 | note | Verifying Document - Site Photo
7279ff2c-aff4-5b1d-a3f4-f63375d504cb | note | Frequency - Each Layer
a7b243d3-c6cb-535d-90b5-65a181495255 | note | Activity - I
bd118e8a-bc42-5377-b62a-9b6acb61244a | note | By - SUP
2eb38c46-8cb7-54e6-b99a-4b79e2de53ac | checkpoint | 5.02.05 - Drainage Outlet Installation
9ee8df9f-b706-55ee-8519-02e9f3ab549c | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
a8364235-fc92-5b0f-b783-499970ee5864 | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
bfdccc2a-f87a-559a-a09d-f22ca6b2550d | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
f50624df-79b1-5d2c-a119-85e58c1d959e | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
a9df338d-dd93-5a01-b470-27f025b047c8 | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
ba32300a-18c6-51ad-9b3e-f5c37464fe0b | note | Standard / Specification - SS - 5
53567f00-05db-5a58-917d-b1a978e56890 | note | Verifying Document - Site Photo / Checksheet
6be29782-2749-5e9e-acd2-446695c190cf | note | Frequency - During Installation
342b7fa8-1803-5fd1-9c9b-a45f3d56f346 | note | Activity - I
fd19484e-4527-5d4c-ba92-996f5eaf5baa | note | By - SUP
1034be8f-e2b5-5d56-ad2f-7ae17d328c57 | checkpoint | 5.02.06 - Backfill Installation
68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
31c539fd-4460-53ad-bfdf-2e97fcb8b655 | note | Standard / Specification - GWS - 5.3.3
633cfa75-f662-58c2-a120-4024e3c6b0a4 | note | Verifying Document - Site Photo / Checksheet
6d4d0c18-479a-58d2-a5ec-cf710b5f1faa | note | Frequency - Each layer
5972cd9e-2fb0-509b-bef1-f765dd7cccb7 | note | Activity - I
b83ffa94-0016-517c-bb97-f82c899c2703 | note | By - SUP
35abd0c3-22bf-5ac6-b46a-a8a9993e38f8 | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
f13ff92b-3515-51d0-a988-a8689f2dd02b | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 | note | Standard / Specification - GWS - Table 3
6554928e-3918-5c68-b1ac-81e6cb332423 | note | Verifying Document - NDM Results
98493087-ecca-5702-9b92-25f0664f918b | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
554f611d-c99e-592d-bee2-843015f016da | note | Activity - H
ccf5b3da-cdf5-5795-9145-2a6b32d69f7e | note | By - SE
bbcbe397-d3aa-5f25-b343-5d2e0f43e6f8 | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
003d8931-bc62-5135-b7be-32aa75313eac | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
3874ad51-8f8b-575e-9170-0695e7fdc9bc | note | Standard / Specification - GWS - Table 3
4d765a6d-f986-55ae-a453-6684618ffc0e | note | Verifying Document - Clegg Result sheet
12a070cf-7dac-57ab-a68e-41e36105e8a1 | note | Frequency - Each layer
0313e548-65cb-50f0-85a4-231e5e4b576b | note | Activity - H
dcd71dcd-85cb-5dee-945b-745855383c9a | note | By - SE
e466154a-3525-5208-8981-a1953fc53c31 | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
4efbde40-a847-5874-adf2-744ee100a9d9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
78e0595b-f746-5ce0-b84e-30718f228843 | note | Standard / Specification - GWS - Table 3
afe343f9-b761-5bae-855e-8f1669892985 | note | Verifying Document - Scala Results
3242c858-14d8-526d-8fce-da11c78994d1 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
3b61ccc5-55eb-529c-ab6e-c36b4195619a | note | Activity - H
f0eff603-e0e2-56fe-a76e-7f727936301e | note | By - SE
60d12d54-946a-5d14-a179-44f6b0bbe1c4 | checkpoint | 5.03.01 - Tensar Triaxial 170
b7b6b90d-c046-44f6-84e9-98097ed32631 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 300mm is required between sheets. Engineer to inspect layer prior to backfill.
24628f91-905b-4919-9547-c3db25e1e6db | note | Standard / Specification - GWS - 4.2
54840355-d1ea-4777-9d5b-6ad907f4fc01 | note | Verifying Document - Photo record
e4c27b20-14a0-466b-932c-f2bfe6c5a0b5 | note | Frequency - Each layer - 1 layer per abutment to be inspected
92855898-8fd4-41e9-9ffc-b8cdb7a3f09f | note | Activity - HP
136c3b84-b512-41df-87e1-dba880b264ca | note | By - ENG
514384b9-8a6a-50c3-9354-b04bfb25986b | signoff | AUTHORITY HOLDPOINT
4d8b933a-5957-55bb-8b21-ef93921ef05e | checkpoint | 5.03.02 - Tensar Uniaxial RE580
0ea32e00-9760-40e8-9fe5-b080daf044a9 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. No overlapping requirements when connected with Bodkin joints. Engineer to inspect each layer prior to backfill. Grids must be taut prior to backffilling
8fb0fc4e-66e4-4c9c-b0e4-e4b8640e477c | note | Standard / Specification - GWS - 4.2
f13ceb32-2533-41ac-bfeb-dca8e273f776 | note | Verifying Document - Photo record
022bcb15-4959-4678-b859-596c2cd1f642 | note | Frequency - Each layer - 1 layer per abutment to be inspected
b48fd9c3-bfcf-450e-b240-2de1ae9976fc | note | Activity - HP
f15f51f3-5909-43a2-9ce0-74db5d1700c4 | note | By - ENG
1749caf0-95ae-558d-9e40-0cb21ba1a8ff | signoff | AUTHORITY HOLDPOINT
68eb27de-28a0-5c6b-b80b-1a0b3a7dabaf | checkpoint | 5.04.01 - Settlement Pins
6be00cc8-35f7-58b4-9aac-3e2f7da37af6 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a15120ed-c718-5d31-baef-0c8bf1202b40 | note | Standard / Specification - GWS - 6.3
c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c44e4189-f4cd-5c8a-94c5-7045748d766f | note | Frequency - Weekly for the first month, then monthly
976b9f25-82ac-5367-a238-3dc87271bf9f | note | Activity - R
f42af643-c395-58bc-a22e-585a9ebaf8f8 | note | By - SV, ENG
65bdb657-7dd2-575b-8068-4d8a3bbf8080 | checkpoint | 5.04.02 - Settlement Targets
08507682-93c4-5452-97e2-8150c20bfab6 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
480b8b47-6145-593e-9237-ad72d6db0cee | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
28d6069c-16cb-52bf-8b0f-2855091f5e5d | note | Standard / Specification - GWS - 6.4
4d86ed34-2564-57a8-98f7-1460af0da7f9 | note | Verifying Document - Survey Results (in paper as well as electronic format)
ee49474b-e7c1-5904-abb4-5613386fddb2 | note | Frequency - Weekly for the first month, then monthly
67d177c4-6ae0-544d-8cca-4963c96f1e14 | note | Activity - R
cd844407-15dc-5abf-ab6a-581e0b72a97e | note | By - SV, ENG
19e8c979-4bbd-5b44-b6f1-f5f0c60cc435 | checkpoint | 5.04.03 - Engineers Approval
129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
9c535da8-1110-57cf-bd8b-4b3a4cb67048 | note | Standard / Specification - BBO
c03b5ad1-5238-50bf-94b3-a6d95d7561a5 | note | Verifying Document - Written approval
43a8c2cd-762b-5905-a363-f38629034b45 | note | Frequency - Prior to pavement construction
e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f | note | Activity - HP
655aedea-3982-579f-8070-73df15d33ff2 | note | By - ENG
2ef33948-5bbc-5304-bec0-43db699435f7 | signoff | AUTHORITY HOLDPOINT
cd33a7f8-9b6c-5422-93be-dcae98eaa460 | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c67c36c3-6604-547c-97e6-f35b09622953 | checkpoint | 6.01.02 - Draft Redline Drawings
fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
1b08806c-38dd-54fa-9d51-79482791edaf | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
71c7e106-4037-5b64-8bc7-4d64f708bf04 | note | Standard / Specification - PS 2.2.17
a9791038-927a-56e8-92bc-092094da73cb | note | Verifying Document - Draft As-Builts Drawings
8b640c55-480e-521c-b672-75b78b29968d | note | Frequency - Prior to PC
66bc92ec-3655-5cdd-82f9-c85ade2d83b3 | note | Activity - H
0f0c9cf5-c28d-5026-9f36-cb989728faad | note | By - SV / PE
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature