## M27 SMA Pre Construction
|  |  |  | Construction Process: SMA Surfacing | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications NZTA M27: Specification For Stone Mastic Asphalt; NZTA M01-A: Specification for PG Asphalt Binder |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by (RACI) R = Responsible, A = Approve, C = Consult, I = Informed
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production) | Inspection / Test method |  |  |  |  | Designer | Eng. Rep / NZTA | Contractor | Date
1.0. Pre-Commencement Activities
1.1 | Approved JMF for Asphalt Surfacing | JMF reference in here | H | Before Works commence | Confirm requirements are followed | JMF Validated in accordance with NZTA M/27:2020 | Mix Design Report | Paving Contractor | JMF expiry date and validation details in here. And to make sure the mix design is sent to Engineer's Representative for approval prior to paving on site. | A | A | R
1.2 | Site Conditions | Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place | H | Before Works commence | Confirm requirements are followed | Weather conditions and Site is suitable for paving | Site Diary | Paving Contractor |  |  | I | R
1.3 | Roughness | Previous layer checked for suitability to achieve Specified Ride | H | Before Works commence | Confirm Specified Ride requirements can be met | Site is suitable for paving; The surface to be paved on must have a smooth longitudinal profile, and where a layer of Asphalt is to be placed over a previously constructed pavement layer, the ride quality must be confirmed with the observation of a holdpoint in the previous layer ITP. | NASSRA Report | Paving Contractor |  |  | I | R
1.4 | Traffic Loops | Communication with affected parties | H | Minimum of 7 days Before Works commence | Visual | Notify RC at least 7 days before surfacing is programmed | Communication | Paving Contractor | only required where existing traffic loops are present |  | A | R
1.5 | Paving Plan | Paving Plan to be completed | H | Before Works commence | NZTA M27: 2020 Clause 9.5.1 | Paving Plan to be completed for each shift with dimensions, location and type of (hot/cold) joints, areas and tonneages | String Sheet | Paving Contractor |  |  | I | R
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## M27 SMA Construction
|  |  |  | Construction Process: SMA Surfacing | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications NZTA M27: Specification For Stone Mastic Asphalt; NZTA M01-A: Specification for PG Asphalt Binder |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by (RACI) R = Responsible, A = Approve, C = Consult, I = Informed
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production) | Inspection / Test method |  |  |  |  | Designer | Eng. Rep / NZTA | Contractor | Date
2.0. MANUFACTURE OF ASPHALT | Manufacture of Asphalt
2.1 | Temperatures | Mixing of aggregates and bitumen | M | Constant monitoring of temperature by calibrated euipment | Plant temperature probes | PG64 V/E (Flexiplus Bind) binder mixing range: 170 to 190 deg.C NZTA M27: 2020 states max. 185 deg.C | Plant site diary | Asphalt Manufacturer |  | I | I | R
2.2 | Production Asphalt | Particle Size Distribution | M | 1 per 200t at asphalt plant | NZS 4407 Test 3.8.1 | NZTA M27: 2020 Refer to Table 5.3 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R
2.3 |  | Binder Content | M | 1 per 200t at asphalt plant |  | NZTA M27: 2020 Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R
2.4 |  | Max. Specific Gravity (MSG) of mix | M | 1 per 600t at asphalt plant |  | Report | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R
2.5 |  | Air Voids at lab design compaction | M | 1 per 600t at asphalt plant |  | NZTA M27: 2020: Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | IANZ accredited test cert | Asphalt Manufacturer |  | I | I | R
3.0. PLACING AND FINISHING | Manufacture of Asphalt
3.1 | Milling | Surface strung to ensure milling Depth is achieved | H | Before Works commence | Confirm requirements are followed | Site is suitable for paving | String Sheet | Paving Contractor |  |  | I | R
3.2 | Tack Coat, OR | Application of Tack Coat | M | Per Lot | Dip bitumen emulsion tank before and after | Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate | Site Diary | Paving Contractor |  | I | I | R
3.3 | Membrane Seal | Application of Membrane Seal | M | Per Lot | Sealing Records | Application rate, chip type and binder as per membrane seal design | Sealing Records | Paving Contractor |  | I | I | R
3.4 | Temperature | Pavement Surface | M | Start of shift and every 1 hour until temperature rising | Infrared gauge | ≥ 10 °C or as otherwise agreed with NZTA | Site diary | Paving Contractor | Must get NZTA approval if < 10°C | I | I | R
3.5 |  | Asphalt Delivery temperature | M | Every Load on delivery to the Paver Hopper | Temperature Probe | Target ≥ 150 deg.C. in the Paver Min. ≥ 130 deg.C in the Paver <130°C to be Rejected | Site Diary | Paving Contractor |  | I | I | R
3.6 |  | Compaction Temperature | M | During compaction | Temperature Probe/Infrared gauge | ≥ 125°C at commencement of compaction. < 80°C - Stop Rolling | Site diary | Paving Contractor |  | I | I | R
3.7 | Mat | Load Locate | M | Each load | M/27 | Each load can be indentified to a location using a diagram. Record includes: - Truck ID/Rego/Driver - Depart Plant Time - Arrive Site Time - AC Temp on Arrival - Tonnage - Run Width - Estimated Run Length - Calculated Area - Calculated Average Depth | Paving Run Sheet | Paving Contractor |  | I | I | R
3.8 |  | Thickness Monitoring | M | Continuously | Dipping | Target Loose Thickness -0mm / +10mm |  | Paving Contractor |  | I | I | R
3.9 |  | Compaction - NDM | M | Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density. | Insitu density and air voids | NZTA M/27: 2020 - section 9.9 |  | Paving Contractor | Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used). | I | I | R
3.1 |  | Compaction | H | Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot | Insitu density and air voids | NZTA M/27: 2020 - section 9.9 | IANZ accredited test cert. | Paving Contractor | A pavement lot shall be an essentially homogeneous section of work completed within a shift of production. The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process. | A | I | R
3.11 |  | Thickness | H | Average of 4 measurements per core | Measure Cores | LCV ≥ Specified Depth NZTA M/27: 2020 - section 9.7 | IANZ accredited test cert. | Paving Contractor |  | A | I | R
3.12 |  | Shape | M | Continuously | 3m Straight edge | Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/27: 2020 - section 9.8. Not more than 5mm under a 3m Straight Edge. | Straight Edge Record | Paving Contractor |  | I | I | R
3.13 | Paving Quality | Texture | M | Per Site (If Required) | Sand Circle or HSD | NZTA T/10: 2013 | IANZ accredited test cert. | Paving Contractor |  | I | I | R
3.14 |  | Level | M | Per Site (If Required) | As Built Survey | -0 < +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. NZTA M/27: 2020 - section 10.2 | Survey As builts | Paving Contractor |  | I | I | R
3.15 |  | Alignment | M | Per Site (If Required) | As Built Survey | ±50 mm from drawings | Survey As builts | Paving Contractor |  | I | I | R
3.16 | Post Paving Completion Checks | Site clear and cleanup | W | Each Site/Shift | Visual | Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete | Site Diary | Paving Contractor |  |  | I | R
3.17 |  | Pavement Marking | W | Each Site/Shift | Visual | Roadmarking is complete | Site Diary | Paving Contractor |  |  | I | R
3.18 |  | Cold Joint Bandaging | W | Each Site/Shift | Visual | Cold joint bandaging is complete | Site Diary | Paving Contractor |  |  | I | R
3.19 |  | Service Covers Checked | W | Each Site/Shift | Visual | Check that service covers are cleared and level with the pavement | Site Diary | Paving Contractor |  |  | I | R
3.2 |  | Traffic Loops Reinstated | W | Each Site/Shift | Visual | Check that affected traffic loops have been reinstated | Communication | Paving Contractor |  |  | I | R
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## M27 SMA Post Construction
|  |  |  | Construction Process: SMA Surfacing | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Neil Payne / Deena Tapara (Stellar Projects Ltd. (SPL) |  | Contractor's Rep. : Wayne Bowden (CM) / Sid Rudani (PM) |  | Specifications NZTA M27: Specification For Stone Mastic Asphalt; NZTA M01-A: Specification for PG Asphalt Binder |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by (RACI) R = Responsible, A = Approve, C = Consult, I = Informed
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production) | Inspection / Test method |  |  |  |  | Designer | Eng. Rep / NZTA | Contractor | Date
4.0. As Built Records | Manufacture of Asphalt
4.1 | Assessment of all test results for conformity | Review against ITP Requirements | H | For each site on the project | Review | Reporting of any non-conforming results to Engineer via NCR | NCR | Paving Contractor |  | I | A | R
4.2 | RAMM pavement and surface records | RAMM surfacing pavement data spreadsheet updated | W | For each site on the project | Prepare Data | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | RAMM Spreadsheet | Paving Contractor |  | I | A | R
4.3 | Paving Quality | Ride Quality | W | Continuous every lane | NAASRA | Max 100m Rolling Average 60 Counts/km Max 20m NASSRA 70 Counts/km Refer TNZ TM 7003 v1 (2006) | IANZ accredited test cert. | Paving Contractor |  | A | I | R
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.