## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d35d4fdc-793c-4630-8b39-897cf06e8b8f | checklist | ITP-01 - Rocker-roller Bearing Replacement Rev 0 | itp | ITP-01 - Rocker-roller Bearing Replacement
61520c4d-821e-4057-a7ce-dde5336839eb | section | Preliminaries
5136f1d1-9715-4df7-9d17-18b450e18f67 | checkpoint | 1.1 Check for Correct Documentation
69051a4a-b9db-5b3b-b216-216ff3421dac | note | FREQUENCY: Prior to starting Works and at regular intervals
6b8e7fbf-3357-5497-ba10-891d52861f33 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f7dde571-39c0-5aa6-9226-36860b573161 | note | i. using the correct and complete set of drawings
9a6b86d0-71d2-5363-b295-57b9c7766880 | note | ii. all drawings are the latest revision
97419170-86a4-5240-be5f-22fda27e21c4 | note | REFERENCE DOCUMENTS: IFC Drawings Drawing Register
3d774298-28dd-52cd-bf59-9020a0b0f8b4 | note | INSPECTION/TEST METHOD: Document Review
5a53d0d1-4851-5db4-8ec3-4a418d0724aa | note | RECORD OF CONFORMITY: This ITP
b21e388d-6eca-5876-80ba-e4d1c2a6a030 | note | HP*
1dea07ee-cbb0-55ec-8b03-7320b55434dc | note | RESPONSIBILITY: Fulton Hogan Engineer
9a32d36e-ec09-56b3-8957-c7086c7e84c8 | textbox | Date Completed:
9cefd134-efa6-4516-9cc5-e1eb496a3fc9 | checkpoint | 1.2 Structural Steel Components
be8aa69b-0d88-5c56-807a-f5c38c8ab8c0 | note | FREQUENCY: Where applicable, once, for each component
59cedeee-4ea5-540e-b9af-91671e9a5702 | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. This consists of, but is not limited to:
7ee13b8c-3d0c-50a4-932d-8731866fd428 | note | i. Certificate of Compliance
f3ba2ddd-f9db-5484-be57-bc06fa7a704f | note | ii. Material Certificates and traceability
9d761cad-80ce-56e1-b9ef-db1e4c6c29bd | note | iii. Quality Assurance check sheets
1158ad7e-f44c-5b4a-8aa5-c896c659621a | note | iv. Coating certificate(s)
1b0128f9-51d7-5d42-a5d0-3849a0f2655d | note | v. As-built Drawings to demonstrate compliance with dimensional tolerances of AS5131, Appendix F2
170d6c9b-ee6c-5204-a339-c41a215be871 | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded as a separate attachment (do not attach it here)
a98f2336-4c67-53d2-a2e1-6883bec66047 | note | REFERENCE DOCUMENTS: IFC Drawings Shop Drawings
2d2bd8bf-4ebc-5bbf-b6c1-6a12397f3a43 | note | INSPECTION/TEST METHOD: Document Review
82984185-a84b-555c-923b-6b076c93fec7 | note | RECORD OF CONFORMITY: This ITP
8df6b61e-6d4a-5956-8065-930db18f9b66 | note | HP*
4cb7539d-7463-52db-b20b-c7ca31adb0f7 | note | RESPONSIBILITY: Fulton Hogan Engineer
e57973ce-cfe3-588c-9188-0c3279df0378 | textbox | Date Completed:
e7a11e52-6ed5-4119-ab84-346ec2625594 | checkpoint | 1.3 Bearing Plate Structural Epoxy Grout, Mortar or Adhesive Product Selection
ce37ace5-28a3-5eb7-a673-38da7b9d8269 | note | FREQUENCY: Where applicable, once, for each product, prior to use
12e54714-a9df-58bd-9293-2fdf54b90378 | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
454595d6-1c9a-58f0-b0b4-f7dbe5ee5990 | note | i. Have a minimum compressive strength equal to or greater than substrate (if unknown use 40MPa)
78be424b-27d3-5cc1-a62d-575e58c066f8 | note | ii. Thickness constraints suitable to the end use
c93d3b2a-264c-56b9-8b94-e72cbaf56f4a | note | iii. Compressive strength gain suitable to the end use
93ce1ffd-7a29-5d5f-a5a6-b139dd8eb0b8 | textbox | Either, Attach: TDS & Approval, or Enter: RFI No.
ccfb1d3e-3046-5adc-81ba-e25989648401 | note | REFERENCE DOCUMENTS: IFC Drawings RFIs, Product TDS
7d19299e-363e-5b63-b719-bbcfbe0b5e4a | note | INSPECTION/TEST METHOD: Document Review
55b91d9e-c1bc-5342-a586-a12600868a72 | note | RECORD OF CONFORMITY: This ITP
f38afc62-a32a-54a7-9c94-2587feafe033 | note | HP*
9b703cff-dc48-5ce5-acc0-c2f386659689 | note | RESPONSIBILITY: Fulton Hogan Engineer
42fbeb6c-4a14-5f1b-9009-3c2b53ffe56e | textbox | Date Completed:
2fab4b7e-11a0-4cf9-b595-a5277ed7e842 | checkpoint | 1.4 Bearing Plate Pin Epoxy Resin Product Selection
88433f42-de2d-5225-8d6a-726884a3b9c5 | note | FREQUENCY: Where applicable, once, for each product, prior to use
56cf25a7-1562-5663-8d94-fb8389d61c2e | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
58b8dd24-bcc3-5ec8-bd7b-2ba3955fecdc | note | i. Have a minimum bond strength equal to or greater than substrate's (if unknown use 1.5MPa)
a8e6c6fa-f0ce-5a45-9316-7145f75d26f5 | note | ii. Compressive strength gain suitable to the end use
b22c43b3-4b76-5d1d-bd07-6097711c7916 | textbox | Either, Attach: TDS & Approval, or Enter: RFI No.
f2a458fd-3034-5d67-b45f-7f15ce4b7c10 | note | REFERENCE DOCUMENTS: IFC Drawings RFIs, Product TDS
81ef6dea-2e7b-5446-bc0a-3f2452294fa1 | note | INSPECTION/TEST METHOD: Document Review
f5f3bed7-df92-530c-bd3a-024fa8d281b4 | note | RECORD OF CONFORMITY: This ITP
ea2cef3a-716a-5b4a-a5e1-20f85bd48a28 | note | HP*
f034e485-cbc5-5b73-917d-419ddf250977 | note | RESPONSIBILITY: Fulton Hogan Engineer
bc6cfddd-c4b7-53fa-9ea7-2e68e19a54d5 | textbox | Date Completed:
98002a8a-637c-4a9a-958b-ea67808bca33 | section | Pre-replacement
c2dfb7d9-b792-4c4b-be60-e43e2eeb7489 | checkpoint | 2.1 Indentification of Defective Bearings
68fa3811-89fc-5c4d-b6b4-910e64b4af27 | note | FREQUENCY: Each replacement bearing location, when accessible
9f5cd1c9-d5bf-5020-86eb-3c85fc67e2cb | note | ACCEPTANCE CRITERIA: Ensure that the correct bearings are clearly identified and named using the Temporary Works Design Drawings.
0154fce5-be30-5551-8fad-c2486c356c1c | note | REFERENCE DOCUMENTS: Temporary Works Design
211adaae-64be-5959-80e2-cf2cf8acba30 | note | INSPECTION/TEST METHOD: Document Review, Visual
1ad1084f-4b63-54d7-8d9f-42bdf77b0f43 | note | RECORD OF CONFORMITY: This ITP
234ef297-8cc6-528f-b80b-d2e8189c71d8 | note | HP*
d77449da-769d-5070-b25d-3acc6eb901d1 | note | RESPONSIBILITY: Fulton Hogan Engineer
645c4a8b-e753-56b4-9abb-0d8734ab5425 | textbox | Date Completed:
f64f3160-01b9-44cc-96dd-20cfdad3e346 | checkpoint | 2.2 Survey of Existing Bearing Plate Heights
30b5f33e-329e-57a3-a241-2b63f8219aa9 | note | FREQUENCY: Each replacement bearing location, when accessible
e633b928-1374-5365-989c-a09ff80477c8 | note | ACCEPTANCE CRITERIA: Survey the existing bearings in reference to each other using an arbitrary datum on each pier.
c371100a-e48d-5782-8e6f-93dce4a83762 | note | ○ Note: a minumum of 2 points to determine RLs.
667de399-06fc-570b-86d6-8316700b149a | note | REFERENCE DOCUMENTS: Detailed Works Methodology
221f2b5a-f129-50af-915e-6e1d2bd5e762 | note | INSPECTION/TEST METHOD: Measure
6c4dc619-880a-5069-bbdf-57afee8941de | note | RECORD OF CONFORMITY: This ITP
c8556cfe-f9ec-5f4f-9532-73a3af760cac | note | SCP, HP*
d051be05-acb1-5001-9a66-cb696ff87415 | note | RESPONSIBILITY: Fulton Hogan Engineer
0d594bae-3b81-52a4-8b30-9bf1df929989 | textbox | Date Completed:
8afda8b9-c933-48e3-bdab-ae3a2b345400 | checkpoint | 2.3 Existing Conditions for Temporary Works
5ebe258d-34ef-53ff-872b-9f7e6a416568 | note | FREQUENCY: Each replacement bearing location, when accessible
6a324bf4-a3b4-56ad-bc4a-95fbe082f122 | note | ACCEPTANCE CRITERIA: Supervisor to inspect of the area where the Temporary Works will be located to ensure that it meets or exceeds the conditions defined in the Temporary Works Design.
ecf9673b-7e1a-5e07-b24f-6dab70e3a237 | note | ○ Photograph/Record: The existing conditions, noting any damage to the piers, including coatings Complete: Temporary Works Permit to Construct
3019389c-f886-56df-a178-7b6c5006e5b7 | note | REFERENCE DOCUMENTS: Temporary Works Design, Permit to Construct, Apply Load & Remove
14385bfb-130a-54f9-b3c1-255892352265 | note | INSPECTION/TEST METHOD: Visual Measure
3744269e-5542-521b-9ea3-2c8ecce8ea64 | note | RECORD OF CONFORMITY: This ITP
cf59efc2-c587-539f-ba97-8d5304a837e1 | note | HP*
7a783406-edd9-50bb-a631-ed1ce4cd1d8c | note | RESPONSIBILITY: Fulton Hogan Engineer
2cb2d452-b753-5ff4-910e-11c0313319fd | textbox | Date Completed:
0a899b75-a91e-49c8-8a18-79280f0c4953 | checkpoint | 2.4 Establishment of Temporary Works
17e6f0cb-c2a2-5568-a2f2-a4fbab01c56d | note | FREQUENCY: Each pair of steel girders at each replacement bearing location
e55d6002-db03-540a-91a8-ae5b1f1bee4e | note | ACCEPTANCE CRITERIA: All structural steel packers, shims, supports and hydraulic cylinders / jacks are the correct size, grade and locational tolerance nominated on the Temporary Works Design and fixed accordingly.
bb414b51-987e-578b-a832-e1e30216f1ec | note | ○ Complete: Temporary Works Permit to Apply Load
a17b971b-aad7-5bd4-a18d-6980b7f85c5b | note | REFERENCE DOCUMENTS: Temporary, Works Design, Permit to Construct, Apply Load & Remove
0cec726d-ab9e-56fe-9066-d8d9d71c2b38 | note | INSPECTION/TEST METHOD: Visual Measure
d6923a38-8fd2-554b-b15a-1fef2d267316 | note | RECORD OF CONFORMITY: This ITP
392b8566-ac59-5d33-b30f-5c50f0aba854 | note | HP*
d6658fa1-d829-5d6b-bb2e-3a7442c596eb | note | RESPONSIBILITY: Fulton Hogan Engineer
6d459d4e-3a53-56d8-8fd7-9a98f3008295 | textbox | Date Completed:
ca53ee61-90ab-4cdb-8aad-1246b16658a7 | checkpoint | 2.5 Survey of Existing Track Heights
8672ce65-33dd-5718-aa93-4f682e4181de | note | FREQUENCY: Prior to Jacking Operations
3462cd85-3e01-5f83-8b38-c47cb2216b00 | note | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
ba67cf60-afae-5e84-9ae8-7f50eee5cc99 | note | ○ Record: Pre-lift Track Heights
f6f768fe-a261-504b-b826-41a9655d814b | note | REFERENCE DOCUMENTS: Detailed Work Methodology
14e72326-c58c-5fe2-8f20-63aa617663c3 | note | INSPECTION/TEST METHOD: Verify
9c222dc7-d758-543d-8ddb-84276a85e44a | note | RECORD OF CONFORMITY: This ITP
60a0d63c-517f-5e91-b6f8-4bdb8a897a2d | note | SCP, HP*
f9a40db0-3381-5a2a-97e3-5b5412f0ebed | note | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
17f813cd-307c-527f-965e-8ba544b16fd0 | textbox | Date Completed:
2dc0ab3c-7b58-469d-a2b0-ea2f33073e7a | section | Replacement
f423a616-db37-42aa-8284-91501f7c8fb2 | checkpoint | 3.1 Jacking Operations - Raising
0ea79e53-25af-57a2-8835-d1f23d0f0250 | note | FREQUENCY: Each pair of jacking points
89d2303c-2751-5ad8-afa1-f15520ad08d5 | note | ACCEPTANCE CRITERIA: Hydraulic jacks to be raised simultaneously in a steady, controlled manner until the maximum height of 25mm is reached.
91155988-4f82-5073-9048-d05fa74b0d80 | note | ○ Locking collars to be engaged and hydraulic lines to be disconnected and capped with dust caps.
fa475df6-1634-5c92-a582-a4f5b940b076 | note | ○ Record: Maximum height and pressure gauge readings for information
971dcb5f-e78e-5377-b12d-76d24e9b2d9c | note | ○ Record: Any movement or damage to the crossheads Attach: Shore HIre's Jacking Operations ITP
840cde2a-d41b-592b-ac41-7b2a37b9eb68 | note | REFERENCE DOCUMENTS: Shorehire ITP, Detailed Work Methodology
466b74f9-3c23-55ab-bac8-01af6e2ca7df | note | INSPECTION/TEST METHOD: Visual Measure
aa901e67-94b3-512f-8f47-4bd8ce12bb9a | note | RECORD OF CONFORMITY: This ITP
45687e69-c810-5ca2-9e72-be011d89f3cf | note | IP
ff75b898-6621-560c-b5c8-7a433084ace1 | note | RESPONSIBILITY: Shore Hire, Fulton Hogan Engineer
a51fadb7-902d-57d2-930a-8f98aa1a5c9a | textbox | Date Completed:
e9c81dfc-0cfe-4023-b5c1-b7b58763d166 | checkpoint | 3.2 Survey of Existing Track Heights
82751aae-bd51-5deb-9f5d-43fafa5ec0ba | note | FREQUENCY: Post-jacking Operations, Occupation #1 Only
26293b2f-97be-562f-a922-f82a37b19a85 | note | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
4698eead-1f0e-5dfc-83a8-84c9855aab92 | note | ○ Record: Post-lift Track Heights
7df4f236-814b-5d06-8da6-2da8303ea7e9 | note | ○ Check: The readings are within 25mm from initial survey
3760ffe5-7c75-5a04-b315-ce39acf82e9a | note | REFERENCE DOCUMENTS: Detailed Work Methodology
c03cf899-97fd-50dc-b5f9-a5d34f0e26fa | note | INSPECTION/TEST METHOD: Measure
341bc9f8-c6a5-5633-a41e-af327b1ca8bc | note | RECORD OF CONFORMITY: This ITP
2bb36645-b040-599f-b8a5-8a3ad51dfe1a | note | SCP, HP*
18d01618-1806-5182-825b-d4cc3837c3a5 | note | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
d373201a-b32c-539d-bc2b-ec9729e9631c | textbox | Date Completed:
eebe4e87-9012-4990-afde-3c4a3bad27c2 | checkpoint | 3.3 Removal of Existing Bearing Componentry
290ffbe4-9339-595b-b77f-d6c78bf073d3 | note | FREQUENCY: Each defective bearing
2a170ad7-eb8e-5752-8dd6-6426eba10cea | note | ACCEPTANCE CRITERIA: Disassemble bearing componetry and safely relocate outside of the Work area.
abc3b53c-7f56-531e-9928-2aabee15a600 | note | ○ Bearing plate pins to be removed by prizing, levering or other suitable means to minimise damage to the crosshead.
fdb245ec-f7f5-50f0-a4a3-57e0d43269e3 | note | ○ Clean the area to remove any loose particles, dust and contaminants.
432d7cef-eb89-5db0-9363-05da5a8d3acd | note | ○ Note: Bearing plates may need to be flame-cut to reduce size and weight.
cd0a4fe0-48d8-5536-932e-81ed5e2e9171 | note | REFERENCE DOCUMENTS: Detailed Work Methodology
78109b72-dcc8-5850-9085-58af0e102556 | note | INSPECTION/TEST METHOD: Visual
44c00be2-c0c7-5ecb-a4c1-7828136f1e76 | note | RECORD OF CONFORMITY: This ITP
e84868a4-5fd0-5143-9544-cdde1f32bd4f | note | IP
3e696202-acd7-53d9-b306-de6fffd4cf97 | note | RESPONSIBILITY: Fulton Hogan Engineer
0dc7dcca-86c9-54c5-8911-6d9e6ac57fff | textbox | Date Completed:
4b472fd2-58d0-4761-bc2a-5be825045517 | checkpoint | 3.4 Existing Bearing Plate Pin Holes
9963feb5-797a-5a9b-942d-02d19deb0afb | note | FREQUENCY: Each bearing plate pin location
bc0bfb62-ea91-5d1d-b70d-644f06e2eb1e | note | ACCEPTANCE CRITERIA: Inspect the existing hole depth and locations to ensure compliance with the IFC Drawings - dry-fitting the replacement pin (M30 threaded rod) is recommended.
f684164c-d2ff-5b28-a9b4-9540d0d90d80 | note | ○ Where necessary, drill or core holes to achieve the required depth. Flush the hole and surrounding area to remove newly created contaminants.
840cd7f9-136e-5881-ac9d-4426a3797bbb | note | REFERENCE DOCUMENTS: Detailed Work Methodology
ca74e4ed-0644-5cd3-a648-7e69b1c5fc00 | note | INSPECTION/TEST METHOD: Visual Measure
68bb1d5e-1044-5e2d-bcc0-b26d032cc062 | note | RECORD OF CONFORMITY: This ITP
88c9ddad-bf2b-5787-b619-fd594fccce70 | note | IP
920f9283-2ba5-5567-99f4-f1ed9a6e0f5e | note | RESPONSIBILITY: Fulton Hogan Engineer
3283568d-d4eb-5076-bd47-7af4fd250bed | textbox | Date Completed:
135bb8d3-0a31-45ac-a8ac-09d891a92b10 | checkpoint | 3.5 Placement of New Bearing Componentry
35d385a9-74a8-51c3-8ed1-f3fd06a9defb | note | FREQUENCY: Each bearing
d5683880-d490-52b7-a0c4-4d9357f29d54 | note | ACCEPTANCE CRITERIA: Manoeuvre new bearings into position, measuring height and level against pre-determined survey marks using shims where necessary.
5806a0a8-af08-5109-b118-dfcc41be3523 | note | ○ Raise the bearing, mix and place epoxy bedding mortar onto the concrete surface of the crosshead and lower the bearing into the bedding epoxy mortar.
944a85de-39a5-5602-be3e-4527a8046d20 | note | ○ Where bearing components require assembly, place and tighten bolts to snug tight conditions.
da09199a-713b-58bc-824a-266665ddb805 | note | REFERENCE DOCUMENTS: Detailed Work Methodology, Product TDS
c688907a-756d-52e3-9c1f-1b784a898cb9 | note | INSPECTION/TEST METHOD: Visual Measure
a5b3236c-602e-556e-9d12-039a9601a93a | note | RECORD OF CONFORMITY: This ITP
2398ad7d-bf95-5e4d-ab5e-f60da45a86b3 | note | HP*
8d2ee734-d661-5aed-b071-697c8aa75663 | note | RESPONSIBILITY: Fulton Hogan Engineer
5e1bdc71-b18d-56b8-bb2b-865601886239 | textbox | Date Completed:
7e523c92-4854-419d-ac1b-d7434188eb15 | checkpoint | 3.6 Placement of Bearing Plate Pins
64d3fe37-b516-5bd1-963a-55c044bde71d | note | FREQUENCY: Each pin
54dc66ae-c8a6-563d-840b-a9ea4099de35 | note | ACCEPTANCE CRITERIA: While the bearing epoxy bedding mortar is wet, mix and inject epoxy bonding resin into each holes.
c0321dac-e8b4-5a16-a9bd-d8bd07332887 | note | ○ Insert the replacement bearing plate pins into the awaiting holes until the washer seats onto the top surface of the bearing plate.
fa77ba5b-6828-5d72-a204-a49c869c1520 | note | ○ Clean any residue from the plate before it sets.
826ff265-f98a-54ca-b92a-9462d973f44f | note | REFERENCE DOCUMENTS: Detailed Work Methodology, Product TDS
2ff94d4d-d227-5da3-bc0b-c19f988f9027 | note | INSPECTION/TEST METHOD: Visual
03141d15-8fa6-5329-83cd-b376891dc14a | note | RECORD OF CONFORMITY: This ITP
34011214-d41e-592d-85cd-18108a7938ac | note | IP
e29d15e5-0e9d-5d4e-a7d2-cba3d8f11672 | note | RESPONSIBILITY: Fulton Hogan Engineer
c2a8ba12-3a9b-55ff-a388-73e737a796cf | textbox | Date Completed:
40bf2cd8-d64a-4c5c-a6ea-a0cd9ddbd1d2 | section | Post-replacement
8a043443-5cd4-48f9-8686-5f50debc3984 | checkpoint | 4.1 Removal of Temporary Works
711f0c12-0520-50f0-b667-d1e0a8ca0286 | note | FREQUENCY: Each pair of steel girders at each replacement bearing location
47f3bb2b-aa18-5eea-8a77-09d7c05f4caa | note | ACCEPTANCE CRITERIA: Inspect any epoxy bedding mortar to determine if sufficient time has elapsed for it to have achieve the same strength of the crosshead (if unknown, use 40MPa).
30fab89e-7a9f-5344-a7d9-43a6f546d44e | note | ○ Where a skim coat for levelling purposes has been applied, check that it has hardened.
635fb6f1-a749-5344-af74-1f4ffaac1452 | note | ○ Complete: Temporary Works Permit to Remove
f820e421-b957-577f-b84e-99f204682c66 | note | REFERENCE DOCUMENTS: Temporary Works Design, Permit to Construct, Apply Load & Remove
c41fb3d3-bf74-5fe6-ae05-88df5f17c87f | note | INSPECTION/TEST METHOD: Visual
3679752c-997b-57fa-9cb0-2343293efe00 | note | RECORD OF CONFORMITY: This ITP
f2325c28-e6f4-5f10-9500-81aeae874ddd | note | HP*
95665a4d-6637-5e83-8ed7-0050b20f7c8a | note | RESPONSIBILITY: Fulton Hogan Engineer
ce9dd457-467f-5fb4-be65-141a0a0ec34f | textbox | Date Completed:
ed6197b3-1c79-4cc5-9ce7-6e8768c2989c | checkpoint | 4.2 Jacking Operations - Releasing
c663cb99-1b0d-5a42-9163-ddfe6fa4168a | note | FREQUENCY: Each pair of jacking points
01bf783b-679c-5b05-9feb-2b5b86be6369 | note | ACCEPTANCE CRITERIA: Hydraulic jacks to be lowered simultaneoulsy in a steady, controlled manner until the new bearings are supporting the super-structure and the pressure gauges read 0MPa.
dd3fefcd-b170-5ea8-84da-3a6e938fbd3c | note | ○ Complete: Shore Hire's Jacking Operations ITP Photograph/Record: The new conditions, noting any damage to the piers, including coatings
098af260-5b1d-5176-9948-c2b0ad14df6d | note | REFERENCE DOCUMENTS: Shorehire ITP, Detailed Work Methodology
e79c16bc-4f38-5223-928d-6e46c82dfbd4 | note | INSPECTION/TEST METHOD: Visual Measure
c3cd4a79-8186-58c8-a51e-cc51302aee8d | note | RECORD OF CONFORMITY: This ITP
4f49ee04-8b23-596b-b013-37f23f8f31ac | note | IP
c57c6573-f2b5-59e9-bfb8-876d6f4694f8 | note | RESPONSIBILITY: Shore Hire, Fulton Hogan Engineer
8b8e6264-f41f-51bb-819e-a350c3c687cf | textbox | Date Completed:
0404efe6-46cb-4101-b2a3-37827506837f | checkpoint | 4.3 Survey of Existing Track Heights
ca196a34-a2ab-57b3-9a28-2087e288214f | note | FREQUENCY: Post-bearing replacement
58c97abc-2bfb-5dcf-a2c2-1d59233396ab | note | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
04de2e61-ae0c-54fd-83dc-7c4a86bc80a7 | note | ○ Record: Post-bearing Replacement Track Heights Check: The readings are within 25mm from initial survey.
06f14c33-928d-586d-afdc-f05065f3de24 | note | REFERENCE DOCUMENTS: Detailed Work Methodology
a215055c-c9f4-580e-8c37-684af88fddfb | note | INSPECTION/TEST METHOD: Measure
37a70655-b585-577d-aa2f-7c97cc56c4db | note | RECORD OF CONFORMITY: This ITP
bfc90549-3d13-5de4-bda1-560293ad889e | note | SCP, HP*
36cd1d08-3da5-5e8a-afa1-99f4f266131d | note | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
f733a733-c70a-5bdc-b2c2-a4da43732be7 | textbox | Date Completed:
70203bb3-ac7d-42f8-ac9c-950e9b29351b | checkpoint | 4.4 Protective Coating Touch-up
652bce5c-0c65-5ef1-90d2-ec4c3e36b164 | note | FREQUENCY: Where required
74ce213f-df45-5682-8d13-82a38b7c6e70 | note | ACCEPTANCE CRITERIA: Where required, apply a tocuh-up to the bearing's protective coating following the coating specification.
a763d755-edd1-5f06-a449-4f412f700cf8 | note | REFERENCE DOCUMENTS: Coating Specification
9a947825-3daf-5a80-9f39-121f3b2cc7a4 | note | INSPECTION/TEST METHOD: Visual
c2dec73b-bbb1-5355-9ceb-f111c3b60607 | note | RECORD OF CONFORMITY: This ITP
9c2729c5-186c-5bc0-bc58-f3e7fda53871 | note | IP
37d691b2-c4d0-59fe-8058-d625f568b121 | note | RESPONSIBILITY: Fulton Hogan
1ba087be-2b4a-5682-8930-839a6d3dc5f6 | textbox | Date Completed:
7093972d-f6f9-4daa-a1c9-2538bbd01dce | checkpoint | 4.5 Client Inspection
166a2458-08e0-5da2-a561-2347a05c216c | note | FREQUENCY: Before the end of the occupation
1f2ec870-6fca-5f38-9b04-2faa9dbeb28c | note | ACCEPTANCE CRITERIA: Prior to the occupation being closed, a joint inspection is to occur with the Client to ensure that the replacement bearings are fit for purpose and any damage to the crossheads of coatings is complete.
03015fb5-3d7d-51f8-a554-f04e582dac8b | note | REFERENCE DOCUMENTS: Detailed Work Methodology
35cd9591-3733-5f00-a1c6-accd7d939b51 | note | INSPECTION/TEST METHOD: Visual
d73ec2f3-e354-5dfd-861d-327982034adb | note | RECORD OF CONFORMITY: ConQA Hold Point Release
b9fe708f-816d-5ac3-8f6b-d3db3f5f48eb | note | HP
702c03d4-f484-5bb0-88db-e8099f8db4fa | note | RESPONSIBILITY: Client
57852e48-ca92-57a5-ab4b-c89cf4670023 | textbox | Date Completed:
7e44c86a-da31-456c-b6f7-f55025708ee7 | signoff | AUTHORITY HOLDPOINT
1d5f1f25-b7f5-4891-afe9-5fd24e9a25cf | checkpoint | Final Inspection
0e35642d-1f49-55f5-85e6-6fe8628daa5e | note | The signature below verifies that this ITP has been completed in accordance with Fulton Hogan’s Quality Management Plan and verifies lot compliance with the IFC Drawings, nominated specifications & standards.
118f53e7-85d9-5883-9d3a-8897937ca6d9 | textbox | Print Name:
40f335b9-fe0e-52fa-a809-8537e098be3f | textbox | Position:
5b5bca3b-f724-5724-8950-76590eb53144 | textbox | Date: