## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Type A Pavement | [5 empty] | ITP - Type A Pavement
section | Pre-construction / Preliminary Compliance Requirements
checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
note | H
note | Minimum Test Frequency - Prior to Construction
note | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
note | Responsibility - Downer
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.2 - Drawings and Specification
note | H
note | Minimum Test Frequency - Prior to Construction
note | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
note | Responsibility - Downer
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.3 - Set out
note | H
note | Minimum Test Frequency - Prior to Construction
note | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
note | Responsibility - Designer
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.4 - Material Approvals
note | Detail of Activity - Submit testing data fir the following materials: - AP65 -GAP 40 -GAP 20 -Hardfill
note | H
note | Minimum Test Frequency - Prior to Construction
note | Inspection / Test method - Quarry Testing Data
note | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
note | • Recycled Pavement/Subgrade Improvement Material:
note | • AP40:
note | ○ CBR >20%
note | ○ Sand Equivalent > 20
note | ○ Grading < 35% passing 75um sieve
note | • AP65:
note | ○ Crushing Resistance < 100kN
note | ○ Weathering Quality Index of A,AB, AC, BA, BB or CA
note | ○ Sand Equivalent ≥ 25 if > 4% passing 75um sieve
note | ○ CBR minimum 40 using heavy compaction
note | ○ Grading
note | Responsibility - Designer
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.5 - Materials Approvals
note | H
note | Minimum Test Frequency - Prior To Construction
note | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
note | Record documents - InEight Records
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
section | Construction and Finishing
checkpoint | 600.6 - Full New Pavement - Subgrade Layer
note | Detail of Activity - Subgrade Levels
note | H
note | Minimum Test Frequency - 20m centres
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Finished Level – String Line, +0mm/-30mm (i.e. 30mm deep)
note | Record documents - QC Sheets
note | Responsibility - Contractor
note | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.7 - Full New Pavement - Subgrade Layer
note | Detail of Activity - Subgrade Quality / Soft Spots
note | H
note | Minimum Test Frequency - One per lot
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
note | Record documents - QC Sheets/Site records
note | Responsibility - Contractor
checkpoint | 600.8 - Full New Pavement - Subgrade Layer
note | Detail of Activity - Undercuts
note | H
note | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
note | Inspection / Test method - Scala Penetrometer
note | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) With the following requirement to be achieved;
note | • ≥ 3 blows per 100mm - no undercut
note | • 2-3 blows per 100mm - 200mm
note | • 1-2 blows per 100mm - 300mm
note | • <1 blow per 100mm - 450mm undercut
note | Record documents - QC Sheets/Site records
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.9 - Full New Pavement - Undercuts/Subgrade Improvement Layer/Recycled Pavement Improvements
note | Detail of Activity - Undercut Stringlines
note | H
note | Minimum Test Frequency - Every 20m
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Subgrade undercut – String Line, each lane/area once undercut is complete.
note | Tolerance: +0mm/-30mm
note | Record documents - QC Sheets (String Sheet)
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.10 - Full New Pavement - Undercuts/Subgrade Improvement Layer/Recycled Pavement Improvements
note | Detail of Activity - Backfill Layers
note | W
note | Minimum Test Frequency - Every 20m
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Backfill in 160mm-200mm layers
note | Record documents - QC Sheets
note | Responsibility - Contractor
note | Comment - Use AP40 hard fill or recycled pavement if available. We propose to use proof roll and clegg testing instead of NDM testing because of the variablity of the recycled material and the bitumen content in it making it hard to test. This supersedes clause 22.2.1 in the project Specification.
checkpoint | 600.11 - Full New Pavement - Undercuts/Subgrade Improvement Layer/Recycled Pavement Improvements
note | Detail of Activity - Backfill Stringlines
note | H
note | Minimum Test Frequency - Every 20m
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Subgrade undercut – String Line, each lane/area
note | Tolerance: +0mm/-30mm
note | Record documents - QC Sheets (String Sheet)
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.13 - Pavement Over Existing / Stabilise Existing - Subbase Layer
note | Detail of Activity - Confirm Pavement Depth
note | H
note | Minimum Test Frequency - 50m centres
note | Inspection / Test method - Test Pits / Visual Inspection
note | Acceptance Criteria - Dig/core test pits to confirm if existing pavement ≥250mm deep.
note | • If sufficient depth, mill to 200mm from FL and continue with "Pavement Over Existing / Stabilise Existing - Subbase Layer" below.
note | • If insufficient, advise WSP Engineer, mill to 450mm from FL, and complete "Full New Pavement" requirements above
note | Record documents - QC Sheets
note | Responsibility - Contractor
note | Comment - Existing pavement to measure 450mm from finished level (minimum).
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.14 - Pavement Over Existing / Stabilise Existing - Subbase Layer
note | Detail of Activity - Stringlines
note | H
note | Minimum Test Frequency - 20m centres
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Finished Level – String Line, +10mm/-30mm
note | Record documents - QC Sheets (String Sheet)
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.15 - Pavement Over Existing / Stabilise Existing - Subbase Layer
note | Detail of Activity - Beam Test
note | H
note | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
note | Inspection / Test method - Beam Testing
note | Acceptance Criteria - Review beam test results to determine if undercuts are required.
note | 1 - 2.5mm Beam Deflection:
note | • Undercut 50mm
note | • Backfill with 20/40 drainage aggregate
note | 2.5 - 5mm Beam Deflection:
note | • Undercut 100mm
note | • Backfill with AP65
note | 5+ mm Beam Deflection:
note | • Undercut 200mm
note | • Backfill with AP65
note | Record documents - QC Sheets / Lab Result Sheet
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.16 - Subbase Stabilising (During Construction)
note | Detail of Activity - MDD and OWC
note | M
note | Minimum Test Frequency - MDD and OWC 1 test per 5000m2 laid
note | Inspection / Test method - Laboratory Test
note | Acceptance Criteria - Report value only
note | Record documents - IANZ Accredited Lab Results
note | Responsibility - WSP Laboratory
checkpoint | 600.17 - Subbase Stabilising (During Construction)
note | Detail of Activity - Mat Samples (1m2 canvas)
note | W
note | Minimum Test Frequency - 1 mat weighed every 400m2
note | Inspection / Test method - Mat Samples
note | Acceptance Criteria - Subbase to be stabalised with 3% cement.
note | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
note | Record documents - QC Sheets
note | Responsibility - Contractor
checkpoint | 600.18 - Subbase Stabilising (During Construction)
note | Detail of Activity - Average usage test:
note | W
note | Minimum Test Frequency - Compare tonnes used (from delivery docket) with measured area
note | Inspection / Test method - Upon emptying the spreader/bulk tanker
note | Acceptance Criteria - Within +/- 2.5 % of the specified rate (3%)
note | Record documents - QC Sheets
note | Responsibility - Contractor
checkpoint | 600.19 - Subbase Stabilising (During Construction)
note | Detail of Activity - Plateau Density Test
note | W
note | Minimum Test Frequency - 1 Plateau Density Test per lot (take samples from behind stabiliser as required - min 3 - for lab testing to determine moisture correction)
note | Inspection / Test method - NDM
note | Acceptance Criteria - Determine minimum number of roller passes required to meet 95% MDD using both primary compaction and finishing compaction rollers. Report values. Used for moisture contect correction
note | Record documents - QC Sheets
note | Responsibility - Contractor
checkpoint | 600.20 - Subbase Stabilising (During Construction)
note | Detail of Activity - Stabilisation Depth
note | M
note | Minimum Test Frequency - Once per lot
note | Inspection / Test method - Visual Inspection (with tape measure)
note | Acceptance Criteria - Stabilised to 200mm depth.
note | Record documents - QC Sheets (Photos)
note | Responsibility - Contractor
checkpoint | 600.21 - Subbase Stabilising (During Construction)
note | Detail of Activity - Indirect Tensile Strength (ITS)
note | H
note | Minimum Test Frequency - Two (2) soaked & two (2) dry ITS - taken by IANZ accredited lab technician behind hoe
note | Inspection / Test method - Laboratory Test
note | Acceptance Criteria - Dry ITS > 500 Kpa, Soaked ITS >450 Kpa
note | Record documents - IANZ Accredited Lab Results
note | Responsibility - WSP Laboratory
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.22 - Stabilised Subbase (Post Construction)
note | Detail of Activity - Stabilised Subbase Compaction
note | H
note | Minimum Test Frequency - Backscatter NDM (1 per 200m2)
note | Inspection / Test method - NDM
note | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥ 92%
note | Record documents - IANZ Accredited Lab Results
note | Responsibility - WSP Laboratory
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.23 - Stabilised Subbase (Post Construction)
note | Detail of Activity - Stabilised Subbase Compaction
note | H
note | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
note | Inspection / Test method - NDM
note | Acceptance Criteria - Tests to be completed at 100mm depth increments starting at 200mm depth. Check for consistency/uniformity in test results.
note | Record documents - IANZ Accredited Lab Results
note | Responsibility - WSP Laboratory
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.24 - Stabilised Subbase (Post Construction)
note | Detail of Activity - Stabilised Depth
note | M
note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
note | Inspection / Test method - Core Visual Inspection
note | Acceptance Criteria - Cohesivity (cores hold together to be removed)
note | • Grading of aggregate (i.e. good mix of different stone sizes)
note | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
note | Record documents - QC Sheets (Photos / Coring Report)
note | Responsibility - Contractor
checkpoint | 600.25 - Stabilised Subbase (Post Construction)
note | Detail of Activity - Indirect Tensile Strength (ITS)
note | H
note | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
note | Inspection / Test method - Laboratory Test
note | Acceptance Criteria - Target lab results. Tolerance: Lab result +/- 25%
note | Record documents - IANZ Accredited Lab Results
note | Responsibility - WSP Laboratory
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.26 - Stabilised Subbase (Post Construction)
note | Detail of Activity - Stringlines
note | H
note | Minimum Test Frequency - Every 10m
note | Inspection / Test method - Visual Inspection
note | Acceptance Criteria - Layer Finished Level – String Line, each lane. Tolerance: +10mm/-30mm
note | Record documents - QC Sheets
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
section | Close Out
checkpoint | 600.27 - Collate above documentation
note | Detail of Activity - Document review
note | H
note | Minimum Test Frequency - Each ITP
note | Inspection / Test method - Review
note | Record documents - N/A
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.28 - As-built drawings
note | Detail of Activity - Survey
note | H
note | Minimum Test Frequency - At completion of construction
note | Inspection / Test method - As-built to be submitted at the completion of construction
note | Acceptance Criteria - As-built to be submitted at the completion of construction
note | Information to be captured: Maintain Redline drawings through works.
note | Record documents - N/A
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | 600.29 - RAMM Data
note | H
note | Inspection / Test method - Info to be submitted by the completion of project construction
note | Acceptance Criteria - Information to be captured:
note | Record documents - N/A
note | Responsibility - Contractor
signoff | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
signoff | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | BBO Engineers Rep Name:
signoff | Add Signature