## Resources
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | AHU/Fan System - Fit Off |  | AHU/Fan System - Fit Off | 24ff4347-675c-4870-b4b5-76656dfe9631
|  | section | Flexible Duct
|  | checkpoint | Flex installed as per Drawing?
|  | checkpoint | Have flex hangers been installed as per spec?
|  | checkpoint | Flex installed with minimal directional changes?
|  | checkpoint | Flex R value is as per spec?
|  | checkpoint | Duct bands installed?
|  | checkpoint | Flex – spigot connections vapour sealed?
|  | checkpoint | Correct flex size for air flow?
|  | checkpoint | Have cushion box ends of flex been left closed?
|  | section | Cushion Box.
|  | checkpoint | Installed as per drawing?
|  | checkpoint | CHBX to Flex vapour sealed?
|  | checkpoint | Clean of dirt and debris
|  | checkpoint | Duct bands been installed
|  | section | Grilles
|  | checkpoint | Clean and flush mounted
|  | checkpoint | Sitting flush with B-frame
|  | checkpoint | Correct colour?
|  | checkpoint | Correct air flow direction
|  | checkpoint | Weather proofed?
|  | section | Testing
|  | checkpoint | Has the system had a duct leakage test
| 6532e998-3ea0-5e91-9470-472fdb97bc6f | date | Date
|  | checkpoint | Received By:
|  | signoff | Date
folder-progress has incorrect meta.stepType checklist-sectioned |  | checklist | BMS Panel & Field connections Fit off |  | BMS Panel & Field connections Fit off | 3781038b-f166-4012-b4cc-93d74b00cf04
checklist-flat has incorrect meta.stepType checkpoint-group | 45e8814a-82cf-423b-a9fd-c3a56e777229 | checklist-flat | Details
|  | checklist | Pipe Insulation |  | Pipe Insulation | 6883d6fd-f89d-486e-a3d0-ac61481e0a5b
|  | section | Insulation
|  | checkpoint | Is Insulation thickness as per DPA drawings?
|  | checkpoint | Is insulation adequately strapped?
|  | checkpoint | Is insulation sealed around hangers?
|  | checkpoint | Are joints vapor sealed correctly?
|  | checkpoint | Tape sufficiently installed?
|  | checkpoint | Installation free of rips and tears?
|  | checkpoint | Correct insulation system used? i.e. Therma break
|  | section | Metal sheathing
|  | checkpoint | Correct colour / material used?
|  | checkpoint | Correct colour fixings used?
|  | checkpoint | Adequate spacing around control equipment?
|  | checkpoint | Is sheathing fit snug to insulation>
|  | checkpoint | Are joints fixed off properly?
|  | checkpoint | Sheathed to correct height?
|  | checkpoint | Installation free of dints, jagged edges, ect?
|  | checkpoint | Received By:
|  | signoff | Date
folder-progress has incorrect meta.stepType checklist-sectioned |  | checklist | BMS Sensor Fit Off |  | BMS Sensor Fit Off | 84233cf0-dce7-4985-ab91-2a8613dbef1d
checklist-flat has incorrect meta.stepType checkpoint-group | 45e8814a-82cf-423b-a9fd-c3a56e777229 | checklist-flat | Details
|  | checklist | AHU System - Rough In |  | AHU System - Rough In | 9eaecad4-4a47-4ae9-9761-1b5191c30d2d
|  | section | Duct Rough-In
|  | checkpoint | Installed as per Drawing
|  | checkpoint | Are Heights as per drawing
|  | checkpoint | Are the joints & corners sealed to comply with pressure (Pa) rating for the duct system?
|  | checkpoint | Are all cleats installed
|  | checkpoint | Insulation / passive fire wrap / coating acoustic wrap installed as per drawing?
|  | checkpoint | AHU/FCU as per DPA equipment schedule?
|  | checkpoint | Dampers and VCD’s installed & match schedule and left open?
|  | checkpoint | Have MVCD’s & SD’s been labelled.
|  | checkpoint | Have the open ends to duct been kept sealed during construction? (if applicable and where required)
|  | checkpoint | Are all spigots / branches installed, sealed and left in the closed position?
|  | checkpoint | Has Seismic been installed correctly as per DPA standard detail?
|  | checkpoint | Have all penetrations been flashed correctly, i.e. smoke sealed / acoustic sealed.
|  | checkpoint | Access panels installed as per drawing and accessible?
|  | section | Variable Air Volume (VAV)
|  | checkpoint | Are all VAV’s installed in their correct locations?
|  | checkpoint | Do all VAV’s have access for commissioning and maintenance?
|  | checkpoint | Has the VAV been supplied as per Dewpoint schedule?
|  | checkpoint | Has the HPT (Top third and downstream ) & air flow switch been installed correctly
|  | checkpoint | Has the identification label been mounted on the VAV?
|  | section | Electric Duct Heater (EDH)
|  | checkpoint | Thermal Lining installed?
|  | checkpoint | Labelled?
|  | checkpoint | AHU
|  | checkpoint | Is the AHU installed in the correct location?
|  | checkpoint | Has the AHU seismic brackets been installed?
|  | checkpoint | Has the identification label been mounted on the AHU
|  | checkpoint | Have all the filters been installed?
|  | checkpoint | Have isolation mounts been installed?
|  | checkpoint | Are all AHU’s accessible for commissioning and maintenance?
|  | checkpoint | Have UV Emitters been fitted if in use?
|  | section | ATTENUATORS
|  | checkpoint | Are all attenuators installed correctly and with correct direction of flow? (Air on / Air off to Pods)
|  | checkpoint | Does the attenuator have appropriate supports?
|  | section | Fire Dampers
|  | checkpoint | Installed as per manufactures test report?
|  | checkpoint | Have nylon bolts and cleats been installed?
|  | checkpoint | Has the fire damper been left in the open position?
|  | checkpoint | Do all fire dampers have access for maintenance
|  | checkpoint | Received By:
|  | signoff | Date
|  | checklist | Ductwork Insulation / Fire Wrap ITC |  | Ductwork Insulation / Fire Wrap ITC | ac7b23aa-4598-4bf5-8ae5-63c97e41f8cf
|  | section | Insulation
|  | checkpoint | Is Insulation thickness as per DPA drawings?
|  | checkpoint | Is insulation adequately strapped?
|  | checkpoint | Is insulation metal pinned as per AS 4859 / mechanical specification?
|  | checkpoint | Are joints vapor sealed correctly?
|  | checkpoint | Tape sufficiently installed?
|  | checkpoint | Installation free of rips and tears?
|  | checkpoint | Insulation installed above trapeze hanger i.e. not around trapeze hanger.
|  | section | Fire Wrap
|  | checkpoint | Is Insulation thickness as per DPA drawings?
|  | checkpoint | Installed to tested system
|  | checkpoint | Installation free of rips and tears?
|  | checkpoint | Received By:
|  | signoff | Date
folder-progress has incorrect meta.stepType checklist-sectioned |  | checklist | Field Connections Rough in |  | Field Connections Rough in | e56f7d63-f1cc-41b4-a97d-7478456f9abd
checklist-flat has incorrect meta.stepType checkpoint-group | 45e8814a-82cf-423b-a9fd-c3a56e777229 | checklist-flat | Details