## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DPA-ITC-M10 | [5 empty] | DPA-ITC-M10
section | Insulation
checkpoint | Is Insulation thickness as per DPA drawings?
checkpoint | Is insulation adequately strapped?
checkpoint | Is insulation metal pinned as per AS 4859 / mechanical specification?
checkpoint | Are joints vapor sealed correctly?
checkpoint | Tape sufficiently installed?
checkpoint | Installation free of rips and tears?
checkpoint | Insulation installed above trapeze hanger i.e. not around trapeze hanger.
section | Fire Wrap
checkpoint | Is Insulation thickness as per DPA drawings?
checkpoint | Installed to tested system
checkpoint | Installation free of rips and tears?
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | DPA-ITC-M11 | [5 empty] | DPA-ITC-M11
section | Insulation
checkpoint | Is Insulation thickness as per DPA drawings?
checkpoint | Is insulation adequately strapped?
checkpoint | Is insulation sealed around hangers?
checkpoint | Are joints vapor sealed correctly?
checkpoint | Tape sufficiently installed?
checkpoint | Installation free of rips and tears?
checkpoint | Correct insulation system used? i.e. Therma break
section | Metal sheathing
checkpoint | Correct colour / material used?
checkpoint | Correct colour fixings used?
checkpoint | Adequate spacing around control equipment?
checkpoint | Is sheathing fit snug to insulation>
checkpoint | Are joints fixed off properly?
checkpoint | Sheathed to correct height?
checkpoint | Installation free of dints, jagged edges, ect?
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | M01A | [5 empty] | M01A
section | Field Connections Rough In
checkpoint | Correct cable used
checkpoint | Cable Tray or catenary Installed To Specification
checkpoint | Field wiring roughed in & cable ties cut back
checkpoint | Mechanical protection used where required
checkpoint | Penetrations – All penetration sealed in accordance with acoustic / smoke and fire sealing requirements
checkpoint | End of cable runs looped up and tied up.
checkpoint | Cable end to end test prior to fit off
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M01B | [5 empty] | M01B
section | BMS Sensor Fit Off
checkpoint | Cable roughed into correct location
checkpoint | Check RLS / architectural for correct location and height
checkpoint | Fit off sensor
checkpoint | Label fitted
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M01C | [5 empty] | M01C
section | BMS Panel & Field Connections Fit Off
checkpoint | BMS Panel Installed in correct location
checkpoint | Cable glands on panel installed and secure
checkpoint | BMS Panel Terminated
checkpoint | Field equipment installed & terminated with cables and/or glands secured
checkpoint | BMS cabling in MSSB terminated & cable duct covers secure
checkpoint | BMS panel tidy and labels correct
checkpoint | BMS panel Label Fitted
checkpoint | Panel energised and ready for commissioning
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M02A Rough In | [5 empty] | M02A Rough In
section | Duct Rough-In
checkpoint | Installed as per Drawing
checkpoint | Are Heights as per drawing
checkpoint | Are the joints & corners sealed to comply with pressure (Pa) rating for the duct system?
checkpoint | Are all cleats installed
checkpoint | Insulation / passive fire wrap / coating acoustic wrap installed as per drawing?
checkpoint | AHU/FCU as per DPA equipment schedule?
checkpoint | Dampers and VCD’s installed & match schedule and left open?
checkpoint | Have MVCD’s & SD’s been labelled.
checkpoint | Have the open ends to duct been kept sealed during construction? (if applicable and where required)
checkpoint | Are all spigots / branches installed, sealed and left in the closed position?
checkpoint | Has Seismic been installed correctly as per DPA standard detail?
checkpoint | Have all penetrations been flashed correctly, i.e. smoke sealed / acoustic sealed.
checkpoint | Access panels installed as per drawing and accessible?
section | Variable Air Volume (VAV)
checkpoint | Are all VAV’s installed in their correct locations?
checkpoint | Do all VAV’s have access for commissioning and maintenance?
checkpoint | Has the VAV been supplied as per Dewpoint schedule?
checkpoint | Has the HPT (Top third and downstream) & air flow switch been installed correctly
checkpoint | Has the identification label been mounted on the VAV?
section | Electric Duct Heater (EDH)
checkpoint | Thermal Lining installed?
checkpoint | Labelled?
section | AHU
checkpoint | Is the AHU installed in the correct location?
checkpoint | Has the AHU seismic brackets been installed?
checkpoint | Has the identification label been mounted on the AHU
checkpoint | Have all the filters been installed?
checkpoint | Have isolation mounts been installed?
checkpoint | Are all AHU’s accessible for commissioning and maintenance?
checkpoint | Have UV Emitters been fitted if in use?
section | ATTENUATORS
checkpoint | Are all attenuators installed correctly and with correct direction of flow? (Air on / Air off to Pods)
checkpoint | Does the attenuator have appropriate supports?
section | Fire Dampers
checkpoint | Installed as per manufacturer's test report?
checkpoint | Have nylon bolts and cleats been installed?
checkpoint | Has the fire damper been left in the open position?
checkpoint | Do all fire dampers have access for maintenance
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | M02B | [5 empty] | M02B
section | Flexible Duct
checkpoint | Flex installed as per Drawing?
checkpoint | Have flex hangers been installed as per spec?
checkpoint | Flex installed with minimal directional changes?
checkpoint | Flex R value is as per spec?
checkpoint | Duct bands installed?
checkpoint | Flex – spigot connections vapour sealed?
checkpoint | Correct flex size for air flow?
checkpoint | Have cushion box ends of flex been left closed?
section | Cushion Box
checkpoint | Installed as per drawing?
checkpoint | CHBX to Flex vapour sealed?
checkpoint | Clean of dirt and debris
checkpoint | Duct bands been installed
section | Grilles
checkpoint | Clean and flush mounted
checkpoint | Sitting flush with B-frame
checkpoint | Correct colour?
checkpoint | Correct air flow direction
checkpoint | Weather proofed?
checkpoint | Has the system had a duct leakage test
date | What date:
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | M03 Rough In | [5 empty] | M03 Rough In
section | Electrical Rough In
checkpoint | Cable Tray and or catenary installed as per specification & earthed
checkpoint | Seismic restraints installed where required.
checkpoint | Cables roughed in
checkpoint | Cable ties cut back
checkpoint | Cable Type and Size Installed To Specification
checkpoint | Cable separation has been checked and complies
checkpoint | All external cable glands fitted and tightened
checkpoint | Penetrations – All fire and acoustic penetrations have been sealed in accordance with relevant requirements and labelled.
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M04A-DX AC Rough In | [5 empty] | M04A-DX AC Rough In
section | MO4B-DX A/C ROUGH IN
checkpoint | Cable Tray and or catenary installed as per specification & earthed
checkpoint | Check manufacturer's details prior to rough in
checkpoint | Pipe roughed in as per current drawings
checkpoint | Pipe’s sealed at ends during until fit off
checkpoint | Insulation fitted to pipe and sealed at joints
checkpoint | Pipe hangers installed and sleeved
checkpoint | Penetrations: Pipe through penetrations comply with correct fire seling / accoustics requirements
checkpoint | Drain lines run inside room to nominated tundish location
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Checked by: DPA Site Foreman
date | Date:
checkpoint | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M04B-DX AC Fit Off | [5 empty] | M04B-DX AC Fit Off
section | M04A-DX A/C FIT OFF
checkpoint | Check equipment against dpa equipment schedules prior to install and manufacturer's details
checkpoint | Indoor units mounted, fitted off and refrigerant pipes and drains connected with supports. check current construction issue drawing for correct location and heights
checkpoint | Check for damage after insall of indoor unit
checkpoint | Condenser fit-off - refrigerant pipes connected to outdoor unit, insulation sealed and covered. pipes enter condenser from wall hat-section cover, condenser on rubber mounts
checkpoint | Check for damage after insall of outdoor unit
checkpoint | Final pressure test with dry nitrogen and condensate drain lines tested for leaks
checkpoint | Evacuation of system to manaufacturer specifications- triple evacuation
checkpoint | Stop valves released and extra refrigerant added
checkpoint | System powered up, test run and operation complete- communication to be addressed and
checkpoint | Connected to central
checkpoint | Commissioning checks on start up, visual checks for abnormal noises or damage, comments
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Checked by: DPA Site Foreman
date | Date:
checkpoint | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M05A & M06A | [5 empty] | M05A & M06A
section | Duct Rough-In
checkpoint | Installed as per Drawing
checkpoint | Are Heights as per drawing
checkpoint | Are the joints & corners sealed to comply with pressure (Pa) rating for the duct system?
checkpoint | Are all cleats installed
checkpoint | Insulation / passive fire wrap / coating acoustic wrap installed as per drawing?
checkpoint | Fan as per DPA equipment schedule?
checkpoint | Dampers and VCD’s installed & match schedule and left open
checkpoint | Have MVCD’s & SD’s been labelled.
checkpoint | Have the open ends to duct been kept sealed during construction? (if applicable and where required)
checkpoint | Are all spigots / branches installed, sealed and left in the closed position?
checkpoint | Has Seismic been installed correctly as per DPA standard detail?
checkpoint | Access panels installed as per drawing and accessible?
checkpoint | Have penetrations been flashed correctly, ie smoke sealed / acoustic sealed.
checkpoint | Has the system had a duct leakage test
date | What date:
section | Duct Rough-In
checkpoint | Is the direction of flow checked and correct?
checkpoint | Is the correct fan installed as per engineering schedules including isiolation mounts?
checkpoint | Are all seismic restraints installed correctly? (if applicable and where required)
checkpoint | Have all the filters been installed?
checkpoint | Is the flexible connection installed to allow movement?
checkpoint | Has the identification label been mounted on the fan?
checkpoint | Does the fan have access for commissioning and maintenance?
section | ATTENUATORS
checkpoint | Are all attenuators installed correctly and with correct direction of flow? (Air on / Air off to Pods)
checkpoint | Does the attenuator have appropriate supports?
section | Fire Dampers
checkpoint | Installed as per manufacturer's test report?
checkpoint | Have nylon bolts and cleats been installed?
checkpoint | Has the fire damper been left in the open position?
checkpoint | Do all fire dampers have access for maintenance
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | M05B & M06B | [5 empty] | M05B & M06B
section | Flexible Duct
checkpoint | Installed as per Drawing
checkpoint | Flex installed as per Drawing?
checkpoint | Flex installed with minimal directional changes?
checkpoint | Have flex hangers been installed as per spec?
checkpoint | Flex R value is as per spec?
checkpoint | Duct bands installed?
checkpoint | Flex – spigot connections vapour sealed?
checkpoint | Correct flex size for air flow?
checkpoint | Have cushion box ends of flex been left closed?
section | Cushion Box
checkpoint | Installed as per drawing?
checkpoint | Clean of dirt and debris?
checkpoint | CHBX / Flex vapour sealed
checkpoint | Duct bands been installed
section | Grilles
checkpoint | Clean and flush mounted
checkpoint | Sitting flush with B-frame
checkpoint | Correct colour?
checkpoint | Correct air flow direction
checkpoint | Weather proofed?
checkpoint | Has the system had a duct leakage test
date | What date:
checkpoint | Received by: Dewpoint Project Manager
date | Date:
holdpoint | Inspected By
checklist | M08 Plumbing ITC | [5 empty] | M08 Plumbing ITC
section | M-08 Plumbing Installation
checkpoint | Is the pipe work installed as per the DPA workshop drawing, and schematic?
checkpoint | Has the correct material type been used as noted on the DPA workshop drawing?
checkpoint | Has the correct bracket size and type been used?
checkpoint | Are pipe hanger spacings correct?
checkpoint | Is piping supported correctly at changes of direction?
checkpoint | Is pipe work straight, level, square and parallel?
checkpoint | Have flange bolts been tightened correctly?
checkpoint | Are the flange bolts the correct size and type?
checkpoint | Have valves been free issued and checked against schedule
checkpoint | Have valves been installed in correct location
checkpoint | Have the correct size polyurethane (PU) blocks or insulation ferrules been used?
checkpoint | Are flexible coupling / bellows installed correctly?
checkpoint | Have the 15mm ball valves test points been installed across the pumps correctly?
checkpoint | Has equipment been placed in correct location and orientation ( pumps, tanks, chillers )
checkpoint | All free issued equipment as per equipment schedules? i.e. chiller / pumps / buffer tank etc
checkpoint | Are the air bleeds required and installed correctly?
checkpoint | Are the pump springs installed and adjusted correctly?
checkpoint | Is a drain valve fitted to the strainer?
checkpoint | Has chiller seismic mounts been installed during placement of chiller?
checkpoint | Has the strainer basket been removed before commissioning?
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Checked by: DPA Site Foreman
date | Date:
checkpoint | System has been air leak testing (sampled)
date | What date:
checkpoint | Have flushing loops been installed as per schematic and valves in correct position for flushing
checkpoint | Has dosing pot and expansion tank been installed as per schematic
checkpoint | Has make up water been connected
checkpoint | Have flow and return stickers been installed?
section | Condensate Drain’s
checkpoint | Does the condensate drain have fall to the tundish(s)?
checkpoint | Is there an air gap present between the top of the tundish and the end of the drain pipe?
checkpoint | Has the condensate drain been tested by running a quantity of water through the drain?
checkpoint | Has a hat section and warning tape been installed? (where applicable and where required)
checkpoint | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | M09 Fit Off | [5 empty] | M09 Fit Off
section | Electrical Fit Off
checkpoint | MSSB installed in correct location and seismically restrained
checkpoint | Dampers installed and stroked – As Per Damper/Fire Matrix
checkpoint | Field Equipment Terminated with cable entry points secure
checkpoint | Isolator Installed & Labelled
checkpoint | Are all the EDH’s installed in their correct locations?
checkpoint | Are all the EDH’s accessible for commissioning and maintenance?
checkpoint | Are all the HPT’s fitted in the top third of the EDH
checkpoint | If the heater is installed in a vertical duct with downward airflow (this is not preferred due to the location of the HPT switch), is a HPT installed above the heater?
checkpoint | MSSB Terminated
checkpoint | Labels Fitted
checkpoint | MSSB clean and tidy
checkpoint | Dead test results uploaded / attached to ITC
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | MG01 | [5 empty] | MG01
section | MG01
checkpoint | Pipe Installed as per drawings?
checkpoint | Labels Fitted as per as2896
checkpoint | Isolation valves installed as per pipe schematic?
checkpoint | Pipe supports installed, clips tightened?
checkpoint | All joints purge welded with min 15% solder
checkpoint | During install pipe ends kept sealed?
checkpoint | System pressure tested & witnessed
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | MG02 | [5 empty] | MG02
section | MG02
checkpoint | Branch pipe installed through wall as per drawing
checkpoint | Droppers installed in correct orientation to MSP
checkpoint | Backing box installed by others prior to outlet install.
checkpoint | Outlets installed with pig tails to centre of MSP
checkpoint | Pipes labelled.
checkpoint | Cross connections tests witnessed
checkpoint | Outlets pressure tested and witnessed
checkpoint | Area left clean and tidy
checkpoint | Once MSP face plate has been fitted (by others) outlet label plate installed.
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | MG03 | [5 empty] | MG03
section | MG03
checkpoint | Manifold installed in correct location
checkpoint | Pressure switches installed correctly?
checkpoint | Pressure tested, and all fittings tested for leaks
checkpoint | Bottles installed ready for commissioning.
checkpoint | Labels fitted?
checkpoint | Area left clean and tidy?
checkpoint | Medical Gas cabling fit off?
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | MG05 | [5 empty] | MG05
section | MG05
checkpoint | Cables roughed in
checkpoint | Mechanical protection installed for cables passing through wall studs?
checkpoint | Power supply by others installed in correct location and accessible?
checkpoint | Panel installed & Fit off
checkpoint | Interconnecting cables installed from valve box to alarm panel?
checkpoint | Backing box installed prior to sheeting and as per RLS / architectural?
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By
checklist | MG06 | [5 empty] | MG06
section | MG06
checkpoint | Pipes installed to valve box location
checkpoint | Valve box installed as per drawing
checkpoint | Valve box installed flush and level to wall
checkpoint | Pipe work check for cross overs
checkpoint | Interconnecting cables installed from valve box to alarm panel?
checkpoint | Mechanical protection installed for cables and pipe passing through wall studs?
checkpoint | Labels installed
checkpoint | Pressure tested and witnessed?
checkpoint | Inspected by: Sub-Contractor’s Site Foreman
date | Date:
checkpoint | Inspected by: DPA Site Foreman
date | Date:
checkpoint | READY FOR HANDOVER TO COMMISSIONING
label | Received by: DPA Project Manager
date | Date:
holdpoint | Authorised By