## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Site QA
| step |  |  | Tier 2: MEDICAL GAS
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.000; Tier 4: DPA-ITC-MG02-ROOM 0.2.000-001
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.003; Tier 4: DPA-ITC-MG02-ROOM 0.2.003-002
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.004; Tier 4: DPA-ITC-MG02-ROOM 0.2.004-003
MG02 | checklist |  |  | Tier 3: REHABILITAITON-ROOM 0.2.007; Tier 4: DPA-ITC-MG02-ROOM 0.2.007-004
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.008; Tier 4: DPA-ITC-MG02-ROOM 0.2.008-005
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.011; Tier 4: DPA-ITC-MG02-ROOM 0.2.011-006
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.014; Tier 4: DPA-ITC-MG02-ROOM 0.2.014-007
MG02 | checklist |  |  | Tier 3: REHABILITATON-ROOM 0.2.017; Tier 4: DPA-ITC-MG02-ROOM 0.2.017-008
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.018; Tier 4: DPA-ITC-MG02-ROOM 0.2.018-009
MG02 | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.017; Tier 4: DPA-ITC-MG02-ROOM 0.3.017-010
MG02 | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.001; Tier 4: DPA-ITC-MG02-ROOM 0.3.001-011
MG02 | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.003; Tier 4: DPA-ITC-MG02-ROOM 0.3.003-012
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.066; Tier 4: DPA-ITC-MG02-ROOM 0.2.066-013
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.067; Tier 4: DPA-ITC-MG02-ROOM 0.2.067-014
MG02 | checklist |  |  | Tier 3: REHABILITATION- ROOM 0.2.062; Tier 4: DPA-ITC-MG02- ROOM 0.2.062-015
MG02 | checklist |  |  | Tier 3: REHABILITATION- ROOM 0.2.063; Tier 4: DPA-ITC-MG02- ROOM 0.2.063-016
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.059; Tier 4: DPA-ITC-MG02-ROOM 0.2.059-017
MG02 | checklist |  |  | Tier 3: REHABILITATION- ROOM 0.2.049; Tier 4: DPA-ITC-MG02- ROOM 0.2.049-018
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.054; Tier 4: DPA-ITC-MG02-ROOM 0.2.054-019
MG02 | checklist |  |  | Tier 3: REHABILITATION- ROOM 0.2.051; Tier 4: DPA-ITC-MG02- ROOM 0.2.051-020
MG02 | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.055; Tier 4: DPA-ITC-MG02-ROOM 0.2.055-021
MG01 | checklist |  |  | Tier 3: REHABILITATION-L0 OXYGEN RING MAIN; Tier 4: DPA-ITC-MG01-L0 OXYGEN RING MAIN-001
MG01 | checklist |  |  | Tier 3: REHABILITATION-L0 SUCTION RING MAIN; Tier 4: DPA-ITC-MG01-L0 SUCTION RING MAIN-002
MG01 | checklist |  |  | Tier 3: REHABILITATION-L0 MEDICAL AIR RING MAIN; Tier 4: DPA-ITC-MG01-L0 MEDICAL AIR RING MAIN-003
M03 Rough In | checklist |  |  | Tier 3: REHABILITATION-L0 MEDICAL GAS CABLING; Tier 4: DPA-ITC-MG01-L0 MEDICAL GAS CABLING -001
MG06 | checklist |  |  | Tier 3: REHABILITATION MEDICAL GAS VALVE ISOLATION BOX - MGVB-00-1; Tier 4: DPA-ITC-MG06- MEDICAL GAS VALVE ISOLATION BOX - MGVB-00-1-001
MG06 | checklist |  |  | Tier 3: FOH-MEDICAL GAS VALVE ISOLATION BOX - MGVB-00-2; Tier 4: DPA-ITC-MG06-MEDICAL GAS VALVE ISOLATION BOX - MGVB-00-2-002
MG05 | checklist |  |  | Tier 3: REHABILITATION-MEDICAL GAS ALARM PANEL - MGAP-00-1; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-00-1-001
MG05 | checklist |  |  | Tier 3: REHABILITATION-MEDICAL GAS ALARM PANEL - MGAP-00-2; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-00-2-002
MG05 | checklist |  |  | Tier 3: FOH-MEDICAL GAS ALARM PANEL - MGAP-00-3; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-00-3-003
MG05 | checklist |  |  | Tier 3: GAS STORE ROOM-MEDICAL GAS ALARM PANEL - MGAP-00-4; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-00-4-004
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.002; Tier 4: DPA-ITC-MG02-ROOM 1.1.002- 022
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.003; Tier 4: DPA-ITC-MG02-ROOM 1.1.003-023
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.006; Tier 4: DPA-ITC-MG02-ROOM 1.1.006-024
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.007; Tier 4: DPA-ITC-MG02-ROOM 1.1.007-025
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.010; Tier 4: DPA-ITC-MG02-ROOM 1.1.010-026
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.013; Tier 4: DPA-ITC-MG02-ROOM 1.1.013-027
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.014; Tier 4: DPA-ITC-MG02-ROOM 1.1.014-028
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.017; Tier 4: DPA-ITC-MG02-ROOM 1.1.017-029
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.018; Tier 4: DPA-ITC-MG02-ROOM 1.1.018-030
MG02 | checklist |  |  | Tier 3: TRANSIT-ROOM 1.1.020; Tier 4: DPA-ITC-MG02-ROOM 1.1.020-031
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.069; Tier 4: DPA-ITC-MG02-ROOM 1.1.069-032
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.068; Tier 4: DPA-ITC-MG02-ROOM 1.1.068-033
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.065; Tier 4: DPA-ITC-MG02-ROOM 1.1.065-034
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.062; Tier 4: DPA-ITC-MG02-ROOM 1.1.062-035
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.061; Tier 4: DPA-ITC-MG02-ROOM 1.1.061-036
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.058; Tier 4: DPA-ITC-MG02-ROOM 1.1.058-037
MG02 | checklist |  |  | Tier 3: GEM THERAPY- ROOM 1.1.057; Tier 4: DPA-ITC-MG02- ROOM 1.1.057-038
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.054; Tier 4: DPA-ITC-MG02-ROOM 1.1.054-039
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.053; Tier 4: DPA-ITC-MG02-ROOM 1.1.053-040
MG02 | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.050; Tier 4: DPA-ITC-MG02-ROOM 1.1.050-041
MG02 | checklist |  |  | Tier 3: GEM THERAPY -TERRACE 1.E099; Tier 4: DPA-ITC-MG02-TERRACE 1.1.E099-042
MG01 | checklist |  |  | Tier 3: GEM THERAPY-L1 OXYGEN RING MAIN; Tier 4: DPA-ITC-MG01-L1 OXYGEN RING MAIN-004
MG01 | checklist |  |  | Tier 3: GEM THERAPY-L1 SUCTION RING MAIN; Tier 4: DPA-ITC-MG01-L1 SUCTION RING MAIN-005
MG01 | checklist |  |  | Tier 3: GEM THERAPY-L1 MEDICAL AIR RING MAIN; Tier 4: DPA-ITC-MG01-L1 MEDICAL AIR RING MAIN-006
M03 Rough In | checklist |  |  | Tier 3: GEM THERAPY-L1 MEDICAL GAS CABLING; Tier 4: DPA-ITC-MG01L1 MEDICAL GAS CABLING-002
MG06 | checklist |  |  | Tier 3: GEM THERAPY -MEDICAL GAS VALVE ISOLATION BOX - MGVB-01-1; Tier 4: DPA-ITC-MG06-MEDICAL GAS VALVE ISOLATION BOX - MGVB-01-1-003
MG05 | checklist |  |  | Tier 3: GEM THERAPY-MEDICAL GAS ALARM PANEL - MGAP-01-1; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-01-1-005
MG05 | checklist |  |  | Tier 3: GEM THERAPY-MEDICAL GAS ALARM PANEL - MGAP-01-2; Tier 4: DPA-ITC-MG05-MEDICAL GAS ALARM PANEL - MGAP-01-2-006
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.000; Tier 4: DPA-ITC-MG02-ROOM 2.1.000-043
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.003; Tier 4: DPA-ITC-MG02-ROOM 2.1.003-044
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.004; Tier 4: DPA-ITC-MG02-ROOM 2.1.004-45
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.007; Tier 4: DPA-ITC-MG02-ROOM 2.1.007-046
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.008; Tier 4: DPA-ITC-MG02-ROOM 2.1.008-047
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.011; Tier 4: DPA-ITC-MG02-ROOM 2.1.011-048
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.015; Tier 4: DPA-ITC-MG02-ROOM 2.1.015-049
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.017; Tier 4: DPA-ITC-MG02-ROOM 2.1.017-050
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.075; Tier 4: DPA-ITC-MG02-ROOM 2.1.075-051
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.074; Tier 4: DPA-ITC-MG02-ROOM 2.1.074-052
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE- ROOM 2.1.071; Tier 4: DPA-ITC-MG02- ROOM 2.1.071-053
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.070; Tier 4: DPA-ITC-MG02-ROOM 2.1.070-054
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.067; Tier 4: DPA-ITC-MG02-ROOM 2.1.067-055
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.066; Tier 4: DPA-ITC-MG02-ROOM 2.1.066-056
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.063; Tier 4: DPA-ITC-MG02-ROOM 2.1.063-057
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.062; Tier 4: DPA-ITC-MG02-ROOM 2.1.062-058
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.059; Tier 4: DPA-ITC-MG02-ROOM 2.1.059-059
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.058; Tier 4: DPA-ITC-MG02-ROOM 2.1.058-060
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.055; Tier 4: DPA-ITC-MG02-ROOM 2.1.055-061
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.054; Tier 4: DPA-ITC-MG02-ROOM 2.1.054-062
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.051; Tier 4: DPA-ITC-MG02-ROOM 2.1.051-063
MG02 | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.050; Tier 4: DPA-ITC-MG02-ROOM 2.1.050-064
MG03 | checklist |  |  | Tier 3: PALLIATIVE CARE-TERRACE 2.E.099; Tier 4: DPA-ITC-MG02-TERRACE 2.E.099-65
MG01 | checklist |  |  | Tier 3: PALLIATIVE CARE-L2 OXYGEN RING MAIN; Tier 4: DPA-ITC-MG01-L2 OXYGEN RING MAIN-007
MG01 | checklist |  |  | Tier 3: PALLIATIVE CARE-L2 SUCTION RING MAIN; Tier 4: DPA-ITC-MG01-L2 SUCTION RING MAIN-008
MG01 | checklist |  |  | Tier 3: PALLIATIVE CARE-L2 MEDICAL AIR RING MAIN; Tier 4: DPA-ITC-MG01-L2 MEDICAL AIR RING MAIN-009
M03 Rough In | checklist |  |  | Tier 3: PALLIATIVE CARE-L2 MEDICAL GAS CABLING; Tier 4: DPA-ITC-M03-L2 MEDICAL GAS CABLING-003
MG06 | checklist |  |  | Tier 3: PALLIATIVE CARE-MGVB-02-1; Tier 4: DPA-ITC-MG06-MGVB-02-1-004
MG05 | checklist |  |  | Tier 3: PALLIATIVE CARE MGAP-02-1; Tier 4: DPA-ITC-MG05- MGAP-02-1-007
MG05 | checklist |  |  | Tier 3: PALLIATIVE CARE-MGAP-02-2; Tier 4: DPA-ITC-MG05-MGAP-02-2-008
MG03 | checklist |  |  | Tier 3: DPA-ITC-MG03-PLANT FITOFF - ROOM 2.E.007; Tier 4: DPA-ITC-MG03-PLANT FITOFF - ROOM 2.E.007-004
| step |  |  | Tier 2: REFRIGERATION - COOLROOMS (Rough In)
M04A-DX AC Rough In | checklist |  |  | Tier 3: FDC-00-1 SYSTEM ROUGH IN; Tier 4: DPA-ITC-M04A-001 FDC-00-1 SYSTEM ROUGH IN-001
M04A-DX AC Rough In | checklist |  |  | Tier 3: FDC-00-2 SYSTEM ROUGH IN; Tier 4: DPA-ITC-M04A-002-FDC-00-2 SYSTEM ROUGH IN -002
M04A-DX AC Rough In | checklist |  |  | Tier 3: FDC-00-3 SYSTEM ROUGH IN; Tier 4: DPA-ITC-M04A-003-FDC-00-3 SYSTEM ROUGH IN-003
M04A-DX AC Rough In | checklist |  |  | Tier 3: COOLROOM 1 ROUGH IN; Tier 4: DPA-ITC-M04A-004-COOLROOM 1 ROUGH IN-004
M04A-DX AC Rough In | checklist |  |  | Tier 3: COOLROOM 2 ROUGH IN; Tier 4: DPA-ITC-M04A-005-COOLROOM 2 ROUGH IN-005
M04A-DX AC Rough In | checklist |  |  | Tier 3: FREEZER ROOM ROUGH IN; Tier 4: DPA-ITC-M04A-006-FREEZER ROOM ROUGH IN-006
| step |  |  | Tier 2: REFRIGERATION - COOLROOMS (Fit Off)
M04B-DX AC Fit Off | checklist |  |  | Tier 3: FDC-00-1 SYSTEM FIT OFF; Tier 4: DPA-ITC-M04B-001-FDC-00-1 SYSTEM FIT OFF-001
M04B-DX AC Fit Off | checklist |  |  | Tier 3: FDC-00-2 SYSTEM FIT OFF; Tier 4: DPA-ITC-M04B-002-FDC-00-2 SYSTEM FIT OFF-002
M04B-DX AC Fit Off | checklist |  |  | Tier 3: FDC-00-3 SYSTEM FIT OFF; Tier 4: DPA-ITC-M04B-003- FDC-00-3 SYSTEM FIT OFF-003
M04B-DX AC Fit Off | checklist |  |  | Tier 3: COOLROOM 1 FIT OFF; Tier 4: DPA-ITC-M04B-004- COOLROOM 1 FIT OFF-004
M04B-DX AC Fit Off | checklist |  |  | Tier 3: COOLROOM 2 FIT OFF; Tier 4: DPA-ITC-M04B-005- COOLROOM 2 FIT OFF-005
M04B-DX AC Fit Off | checklist |  |  | Tier 3: FREEZER ROOM FIT OFF; Tier 4: DPA-ITC-M04B-006- FREEZER ROOM FIT OFF-006
| step |  |  | Tier 2: REFRIGERATION - DX A/C (Rough In)
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-1 SYSTEM - AC-00-1.1 AND AC-00-1.2; Tier 4: DPA-ITC-M04A-CU-00-1 SYSTEM - AC-00-1.1 AND AC-00-1.2-001
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-2 SYSTEM - AC-00-2.1 AND AC-00-2.2; Tier 4: DPA-ITC-M04A-CU-00-2 SYSTEM - AC-00-2.1 AND AC-00-2.2-002
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-3 SYSTEM - AC-00-3.1 AND AC-00-3.2; Tier 4: DPA-ITC-M04A-CU-00-3 SYSTEM - AC-00-3.1 AND AC-00-3.2-003
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-4 SYSTEM - AC-00-4.1 AND AC-00-4.2; Tier 4: DPA-ITC-M04A-CU-00-4 SYSTEM - AC-00-4.1 AND AC-00-4.2-004
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-01-1 SYSTEM - AC-01-1.1 AND AC-01-1.2; Tier 4: DPA-ITC-M04A-CU-01-1 SYSTEM - AC-01-1.1 AND AC-01-1.2-005
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-01-2 SYSTEM - AC-01-2.1 AND AC-01-2.2; Tier 4: DPA-ITC-M04A-CU-01-2 SYSTEM - AC-01-2.1 AND AC-01-2.2-006
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-1 SYSTEM - AC-02-1.1 AND AC-02-1.2; Tier 4: DPA-ITC-M04A-CU-02-1 SYSTEM - AC-02-1.1 AND AC-02-1.2-007
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-2 SYSTEM - AC-02-2.1 AND AC-02-2.2; Tier 4: DPA-ITC-M04A-CU-02-2 SYSTEM - AC-02-2.1 AND AC-02-2.2-008
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-3 SYSTEM - AC-02-3; Tier 4: DPA-ITC-M04A-CU-02-3 SYSTEM - AC-02-3-009
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-4 SYSTEM - AC-02-4; Tier 4: DPA-ITC-M04A-CU-02-4 SYSTEM - AC-02-4-010
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-5 SYSTEM - AC-02-5; Tier 4: DPA-ITC-M04A-CU-02-5 SYSTEM - AC-02-5-011
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-02-6 SYSTEM - AC-02-6; Tier 4: DPA-ITC-M04A-CU-02-6 SYSTEM - AC-02-6-012
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-SMSR-1 SYSTEM; Tier 4: DPA-ITC-M04A-CU-SMSR-1 SYSTEM -013
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-SMSR-2 SYSTEM; Tier 4: DPA-ITC-M04A-CU-SMSR-2 SYSTEM -014
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-PR-1 SYSTEM - AC-PR-1.1 AND AC-PR-1.2; Tier 4: DPA-ITC-M04A-CU-PR-1 SYSTEM - AC-PR-1.1 AND AC-PR-1.2-015
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-5 SYSTEM - AC-00-5; Tier 4: DPA-ITC-M04A-CU-00-5 SYSTEM - AC-00-5-016
M04A-DX AC Rough In | checklist |  |  | Tier 3: CU-00-6 SYSTEM - AC-00-6; Tier 4: DPA-ITC-M04A-CU-00-6 SYSTEM - AC-00-6-017
| step |  |  | Tier 2: REFRIGERATION - DX A/C (Fit Off)
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-1 SYSTEM - AC-00-1.1 AND AC-00-1.2; Tier 4: DPA-ITC-M04B-CU-00-1 SYSTEM - AC-00-1.1 AND AC-00-1.2-001
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-2 SYSTEM - AC-00-2.1 AND AC-00-2.2; Tier 4: DPA-ITC-M04B-CU-00-2 SYSTEM - AC-00-2.1 AND AC-00-2.2-002
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-3 SYSTEM - AC-00-3.1 AND AC-00-3.2; Tier 4: DPA-ITC-M04B-CU-00-3 SYSTEM - AC-00-3.1 AND AC-00-3.2-003
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-4 SYSTEM - AC-00-4.1 AND AC-00-4.2; Tier 4: DPA-ITC-M04B-CU-00-4 SYSTEM - AC-00-4.1 AND AC-00-4.2-004
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-01-1 SYSTEM - AC-01-1.1 AND AC-01-1.2; Tier 4: DPA-ITC-M04B-CU-01-1 SYSTEM - AC-01-1.1 AND AC-01-1.2-005
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-01-2 SYSTEM - AC-01-2.1 AND AC-01-2.2; Tier 4: DPA-ITC-M04B-CU-01-2 SYSTEM - AC-01-2.1 AND AC-01-2.2-006
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-1 SYSTEM - AC-02-1.1 AND AC-02-1.2; Tier 4: DPA-ITC-M04B-CU-02-1 SYSTEM - AC-02-1.1 AND AC-02-1.2-007
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-2 SYSTEM - AC-02-2.1 AND AC-02-2.2; Tier 4: DPA-ITC-M04B-CU-02-2 SYSTEM - AC-02-2.1 AND AC-02-2.2-008
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-3 SYSTEM - AC-02-3; Tier 4: DPA-ITC-M04B-CU-02-3 SYSTEM - AC-02-3-009
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-4 SYSTEM - AC-02-4; Tier 4: DPA-ITC-M04B-CU-02-4 SYSTEM - AC-02-4-010
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-5 SYSTEM - AC-02-5; Tier 4: DPA-ITC-M04B-CU-02-5 SYSTEM - AC-02-5-011
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-02-6 SYSTEM - AC-02-6; Tier 4: DPA-ITC-M04B-CU-02-6 SYSTEM - AC-02-6-012
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-SMSR-1 SYSTEM; Tier 4: DPA-ITC-M04B-CU-SMSR-1 SYSTEM -013
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-SMSR-2 SYSTEM; Tier 4: DPA-ITC-M04B-CU-SMSR-2 SYSTEM -014
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-PR-1 SYSTEM; Tier 4: DPA-ITC-M04B-CU-PR-1 SYSTEM -015
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-5 SYSTEM - AC-00-5; Tier 4: DPA-ITC-M04B-CU-00-5 SYSTEM - AC-00-5-016
M04B-DX AC Fit Off | checklist |  |  | Tier 3: CU-00-6 SYSTEM - AC-00-6; Tier 4: DPA-ITC-M04B-CU-00-6 SYSTEM - AC-00-6-017
| step |  |  | Tier 2: BUILDING MANAGEMENT SYSTEM
M01A | checklist |  |  | Tier 3: BMS-MSSB-01-1; Tier 4: DPA-ITC-M01A-BMS-MSSB-01-1-001
M01A | checklist |  |  | Tier 3: BMS-MSSB-02-4; Tier 4: DPA-ITC-M01A-BMS-MSSB-02-4-002
M01A | checklist |  |  | Tier 3: SUB-1; Tier 4: DPA-ITC-M01A-SUB-1-003
M01A | checklist |  |  | Tier 3: PR-1; Tier 4: DPA-ITC-M01A-PR-1-004
M01C | checklist |  |  | Tier 3: BMS-MSSB-01-1; Tier 4: DPA-ITC-M01C-BMS-MSSB-01-1-001
M01C | checklist |  |  | Tier 3: BMS-MSSB-02-4; Tier 4: DPA-ITC-M01C-BMS-MSSB-02-4-002
M01C | checklist |  |  | Tier 3: SUB-1; Tier 4: DPA-ITC-M01C-SUB-1-003
M01C | checklist |  |  | Tier 3: PR-1; Tier 4: DPA-ITC-M01C-PR-1-004
M01B | checklist |  |  | Tier 3: BOH-ROOM 0.4.002; Tier 4: DPA-ITC-M01B-ROOM 0.4.002-001
M01B | checklist |  |  | Tier 3: BOH-ROOM 0.4.004; Tier 4: DPA-ITC-M01B-ROOM 0.4.004-002
M01B | checklist |  |  | Tier 3: BOH-ROOM 0.4.006; Tier 4: DPA-ITC-M01B-ROOM 0.4.006-003
M01B | checklist |  |  | Tier 3: BOH-ROOM 0.4.010; Tier 4: DPA-ITC-M01B-ROOM 0.4.010-004
M01B | checklist |  |  | Tier 3: BOH-ROOM 0.4.014; Tier 4: DPA-ITC-M01B-ROOM 0.4.014-005
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.055; Tier 4: DPA-ITC-M01B-ROOM 0.2.055-006
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.049; Tier 4: DPA-ITC-M01B-ROOM 0.2.049-007
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.063; Tier 4: DPA-ITC-M01B-ROOM 0.2.063-008
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.067; Tier 4: DPA-ITC-M01B- ROOM 0.2.067-009
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.036; Tier 4: DPA-ITC-M01B- ROOM 0.2.036-010
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.034; Tier 4: DPA-ITC-M01B-ROOM 0.2.034-011
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.033; Tier 4: DPA-ITC-M01B-ROOM 0.2.033-012
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.031; Tier 4: DPA-ITC-M01B-ROOM 0.2.031-013
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.028; Tier 4: DPA-ITC-M01B-ROOM 0.2.028-014
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.000; Tier 4: DPA-ITC-M01B-ROOM 0.2.000-015
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.003; Tier 4: DPA-ITC-M01B-ROOM 0.2.003-016
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.011; Tier 4: DPA-ITC-M01B-ROOM 0.2.011-017
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.015; Tier 4: DPA-ITC-M01B-ROOM 0.2.015-018
M01B | checklist |  |  | Tier 3: REHABILITATION-ROOM 0.2.018; Tier 4: DPA-ITC-M01B-ROOM 0.2.018-019
M01B | checklist |  |  | Tier 3: FOH-ROOM 0.1.004; Tier 4: DPA-ITC-M01B- ROOM 0.1.004-020
M01B | checklist |  |  | Tier 3: FOH-ROOM 0.1.003; Tier 4: DPA-ITC-M01B-ROOM 0.1.003-021
M01B | checklist |  |  | Tier 3: FOH-ROOM 0.1.010; Tier 4: DPA-ITC-M01B-ROOM 0.1.010-022
M01B | checklist |  |  | Tier 3: FOH-ROOM 0.1.009; Tier 4: DPA-ITC-M01B-ROOM 0.1.009-023
M01B | checklist |  |  | Tier 3: FOH-ROOM 0.1.001; Tier 4: DPA-ITC-M01B- ROOM 0.1.001-024
M01B | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.008; Tier 4: DPA-ITC-M01B-ROOM 0.3.008-025
M01B | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.006; Tier 4: DPA-ITC-M01B-ROOM 0.3.006-026
M01B | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.013; Tier 4: DPA-ITC-M01B-ROOM 0.3.013-027
M01B | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.016; Tier 4: DPA-ITC-M01B-ROOM 0.3.016-028
M01B | checklist |  |  | Tier 3: SHARED THERAPY-ROOM 0.3.017; Tier 4: DPA-ITC-M01B-ROOM 0.3.017-029
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.000; Tier 4: DPA-ITC-Mo1B-ROOM 1.1.000-030
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.007; Tier 4: DPA-ITC-M01B-ROOM 1.1.007-031
M01B | checklist |  |  | Tier 3: GEM THERAPY- ROOM 1.1.010; Tier 4: DPA-ITC-M01B- ROOM 1.1.010-032
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.014; Tier 4: DPA-ITC-M01B-ROOM 1.1.014-033
M01B | checklist |  |  | Tier 3: SHARED PATIENT AREA-ROOM 1.1.020; Tier 4: DPA-ITC-M01B-ROOM 1.1.020-034
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.038; Tier 4: DPA-ITC-M01B-ROOM 1.1.038-035
M01B | checklist |  |  | Tier 3: GEM THERAPY- ROOM 1.1.036; Tier 4: DPA-ITC-M01B- ROOM 1.1.036-036
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.035; Tier 4: DPA-ITC-M01B-ROOM 1.1.035-037
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.033; Tier 4: DPA-ITC-M01B-ROOM 1.1.033-038
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.029; Tier 4: DPA-ITC-M01B-ROOM 1.1.029-039
M01B | checklist |  |  | Tier 3: GEM THERAPY-ROOM 1.1.022; Tier 4: DPA-ITC-M01B-ROOM 1.1.022-040
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION-ROOM 1.2.002; Tier 4: DPA-ITC-M01B-ROOM 1.2.002-041
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION-ROOM 1.2.014; Tier 4: DPA-ITC-M01B-ROOM 1.2.014-042
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION - ROOM 1.2.013; Tier 4: DPA-ITC-M01B- ROOM 1.2.013-043
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION- ROOM 1.2.010; Tier 4: DPA-ITC-M01B- ROOM 1.2.010-044
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION-ROOM 1.2.000; Tier 4: DPA-ITC-M01B-ROOM 1.2.000-045
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION- ROOM 1.2.008; Tier 4: DPA-ITC-M01B- ROOM 1.2.008-046
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION-ROOM 1.2.007; Tier 4: DPA-ITC-M01B-ROOM 1.2.007-047
M01B | checklist |  |  | Tier 3: SHARED ADMINISTRATION- ROOM 1.2.009; Tier 4: DPA-ITC-M01B- ROOM 1.2.009-048
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.050; Tier 4: DPA-ITC-M01B-ROOM 2.1.050-049
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.058; Tier 4: DPA-ITC-M01B-ROOM 2.1.058-050
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE- ROOM 2.1.067; Tier 4: DPA-ITC-M01B- ROOM 2.1.067-051
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.071; Tier 4: DPA-ITC-M01B-ROOM 2.1.071-052
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE- ROOM 2.1.075; Tier 4: DPA-ITC-M01B- ROOM 2.1.075-053
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.038; Tier 4: DPA-ITC-M01B-ROOM 2.1.038-054
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.036; Tier 4: DPA-ITC-M01B-ROOM 2.1.036-055
M01B | checklist |  |  | Tier 3: PALLIAIVE CARE-ROOM 2.1.035; Tier 4: DPA-ITC-M01B-ROOM 2.1.035-056
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.032; Tier 4: DPA-ITC-M01B-ROOM 2.1.032-057
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.029; Tier 4: DPA-ITC-M01B-ROOM 2.1.029-058
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.022; Tier 4: DPA-ITC-M01B-ROOM 2.1.022-059
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.000; Tier 4: DPA-ITC-M01B-ROOM 2.1.000-060
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.008; Tier 4: DPA-ITC-M01B-ROOM 2.1.008-061
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE- ROOM 2.1.011; Tier 4: DPA-ITC-M01B- ROOM 2.1.011-062
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE-ROOM 2.1.016; Tier 4: DPA-ITC-M01B-ROOM 2.1.016-063
M01B | checklist |  |  | Tier 3: PALLIATIVE CARE -ROOM 2.1.017; Tier 4: DPA-ITC-M01B-ROOM 2.1.017-064
M01B | checklist |  |  | Tier 3: SHARED ADMIN-ROOM 2.2.003; Tier 4: DPA-ITC-M01B-ROOM 2.2.003-065
| step |  |  | Tier 2: ELECTRICAL ROUGH IN
M03 Rough In | checklist |  |  | Tier 3: MSSB-01-1; Tier 4: DPA-ITC-M03-MSSB-01-1-001
M03 Rough In | checklist |  |  | Tier 3: MSSB-01-2; Tier 4: DPA-ITC-M03-MSSB-01-2-002
M03 Rough In | checklist |  |  | Tier 3: MSSB-02-1; Tier 4: DPA-ITC-M03-MSSB-02-1-003
M03 Rough In | checklist |  |  | Tier 3: MSSB-02-2; Tier 4: DPA-ITC-M03-MSSB-02-2-004
M03 Rough In | checklist |  |  | Tier 3: MSSB-02-3; Tier 4: DPA-ITC-M03-MSSB-02-3-005
M03 Rough In | checklist |  |  | Tier 3: MSSB-02-4; Tier 4: DPA-ITC-M03-MSSB-02-4-006
M03 Rough In | checklist |  |  | Tier 3: MSSB-SUB-1; Tier 4: DPA-ITC-M03-MSSB-SUB-1-007
M03 Rough In | checklist |  |  | Tier 3: MSSB-SUB-2; Tier 4: DPA-ITC-M03-MSSB-SUB-2-008
M03 Rough In | checklist |  |  | Tier 3: MSSB-PR-1; Tier 4: DPA-ITC-M03-MSSB-PR-1-009
M03 Rough In | checklist |  |  | Tier 3: MSSB-FPR-1; Tier 4: DPA-ITC-M03-MSSB-FPR-1-010
M03 Rough In | checklist |  |  | Tier 3: IP-MSSB-1E; Tier 4: DPA-ITC-M03-IP-MSSB-1E-011
| step |  |  | Tier 2: ELECTRICAL FIT OFF
M09 Fit Off | checklist |  |  | Tier 3: MSSB-01-1; Tier 4: DPA-ITC-M09-MSSB-01-1-001
M09 Fit Off | checklist |  |  | Tier 3: MSSB-01-2; Tier 4: DPA-ITC-M09-MSSB-01-2-002
M09 Fit Off | checklist |  |  | Tier 3: MSSB-02-1; Tier 4: DPA-ITC-M09-MSSB-02-1-003
M09 Fit Off | checklist |  |  | Tier 3: MSSB-02-2; Tier 4: DPA-ITC-M09-MSSB-02-2-004
M09 Fit Off | checklist |  |  | Tier 3: MSSB-02-3; Tier 4: DPA-ITC-M09-MSSB-02-3-005
M09 Fit Off | checklist |  |  | Tier 3: MSSB-02-4; Tier 4: DPA-ITC-M09-MSSB-02-4-006
M09 Fit Off | checklist |  |  | Tier 3: MSSB-SUB-1; Tier 4: DPA-ITC-M09-MSSB-SUB-1-007
M09 Fit Off | checklist |  |  | Tier 3: MSSB-SUB-2; Tier 4: DPA-ITC-M09-MSSB-SUB-2-008
M09 Fit Off | checklist |  |  | Tier 3: MSSB-PR-1; Tier 4: DPA-ITC-M09-MSSB-PR-1-009
M09 Fit Off | checklist |  |  | Tier 3: MSSB-FPR-1; Tier 4: DPA-ITC-M09-MSSB-FPR-1-010
M09 Fit Off | checklist |  |  | Tier 3: IP-MSSB-1E; Tier 4: DPA-ITC-M09-IP-MSSB-1E-011
| step |  |  | Tier 2: PLUMBING
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE CHILLER PLANT; Tier 4: DPA-ITC-M08-PIPE CHILLER PLANT - 001
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE LEVEL 1 PLANT ROOM; Tier 4: DPA-ITC-M08-PIPE LEVEL 1 PLANT ROOM -002
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE LEVEL 2 PLANT ROOM; Tier 4: DPA-ITC-M08-PIPE LEVEL 2 PLANT ROOM -003
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE LEVEL 00; Tier 4: DPA-ITC-M08-PIPE LEVEL 00 -004
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE LEVEL 01; Tier 4: DPA-ITC-M08-PIPE LEVEL 01-005
M08 Plumbing ITC | checklist |  |  | Tier 3: PIPE LEVEL 02; Tier 4: DPA-ITC-M08-PIPE LEVEL 02-006
| step |  |  | Tier 2: DUCTWORK Rough In
M02A Rough In | checklist |  |  | Tier 3: AHU-00-1; Tier 4: DPA-ITC-M02A-AHU-00-1-001
M02A Rough In | checklist |  |  | Tier 3: AHU-00-2; Tier 4: DPA-ITC-M02A-AHU-00-2-002
M02A Rough In | checklist |  |  | Tier 3: AHU-00-3; Tier 4: DPA-ITC-M02A-AHU-00-3-003
M02A Rough In | checklist |  |  | Tier 3: AHU-00-4; Tier 4: DPA-ITC-M02A-AHU-00-4-004
M02A Rough In | checklist |  |  | Tier 3: AHU-01-1; Tier 4: DPA-ITC-M02A-AHU-01-1-005
M02A Rough In | checklist |  |  | Tier 3: AHU-01-2; Tier 4: DPA-ITC-M02A-AHU-01-2-006
M02A Rough In | checklist |  |  | Tier 3: AHU-01-3; Tier 4: DPA-ITC-M02A-AHU-01-3-007
M02A Rough In | checklist |  |  | Tier 3: AHU-02-1; Tier 4: DPA-ITC-M02A-AHU-02-1-008
M05A & M06A | checklist |  |  | Tier 3: GEF-00-1; Tier 4: DPA-ITC-M05A-GEF-00-1-001
M05A & M06A | checklist |  |  | Tier 3: KEF-02-1; Tier 4: DPA-ITC-M05A-KEF-02-1-002
M05A & M06A | checklist |  |  | Tier 3: TEF-02-1; Tier 4: DPA-ITC-M05A-TEF-02-1-003
M05A & M06A | checklist |  |  | Tier 3: GEF-02-1; Tier 4: DPA-ITC-M05A-GEF-02-1-004
M05A & M06A | checklist |  |  | Tier 3: TEF-02-2; Tier 4: DPA-ITC-M05A-TEF-02-2-005
M05A & M06A | checklist |  |  | Tier 3: GEF-02-2; Tier 4: DPA-ITC-M05A-GEF-02-2-006
M05A & M06A | checklist |  |  | Tier 3: KEF-02-2; Tier 4: DPA-ITC-M05A-KEF-02-2-007
M05A & M06A | checklist |  |  | Tier 3: MAF-01-1; Tier 4: DPA-ITC-M05AMAF-01-1-008
M05A & M06A | checklist |  |  | Tier 3: SAF-02-1; Tier 4: DPA-ITC-M05A-SAF-02-1-009
M05A & M06A | checklist |  |  | Tier 3: SPF-02-1; Tier 4: DPA-ITC-M05A-SPF-02-1-010
M05A & M06A | checklist |  |  | Tier 3: SPF-02-2; Tier 4: DPA-ITC-M05A-SPF-02-2-011
M05A & M06A | checklist |  |  | Tier 3: LRF-02-1; Tier 4: DPA-ITC-M05A-LRF-02-1-012
M05A & M06A | checklist |  |  | Tier 3: LRF-02-2; Tier 4: DPA-ITC-M05A-LRF-02-2-013
M05A & M06A | checklist |  |  | Tier 3: IP-GEF-07; Tier 4: DPA-ITC-M05A-IP-GEF-07-014
M05A & M06A | checklist |  |  | Tier 3: KEF-02-3; Tier 4: DPA-ITC-M05A-KEF-02-3-014
M05A & M06A | checklist |  |  | Tier 3: SAF-SUB-1; Tier 4: DPA-ITC-M05A-SAF-SUB-1-015
M05A & M06A | checklist |  |  | Tier 3: SAF-SUB-2; Tier 4: DPA-ITC-M05A-SAF-SUB-2-016
M05A & M06A | checklist |  |  | Tier 3: GEF-PR-1; Tier 4: DPA-ITC-M05A-GEF-PR-1-017
M05A & M06A | checklist |  |  | Tier 3: GEF-FPR-1; Tier 4: DPA-ITC-M05A-GEF-FPR-1-018
M05A & M06A | checklist |  |  | Tier 3: GEF-BIN-1; Tier 4: DPA-ITC-M05A-GEF-BIN-1-019
M02A Rough In | checklist |  |  | Tier 3: FCU-00-1; Tier 4: DPA-ITC-M02A-FCU-00-1 -009
M02A Rough In | checklist |  |  | Tier 3: FCU-00-2; Tier 4: DPA-ITC-M02A-FCU-00-2 010
M02A Rough In | checklist |  |  | Tier 3: FCU-MSB-01; Tier 4: DPA-ITC-M02A-FCU-MSB-01-011
M02A Rough In | checklist |  |  | Tier 3: FCU-MSB-02; Tier 4: DPA-ITC-M02A-FCU-MSB-02-012
M02A Rough In | checklist |  |  | Tier 3: FCU-MSB-03; Tier 4: DPA-ITC-M02A-FCU-MSB-03-013
M02A Rough In | checklist |  |  | Tier 3: FCU-MSB-04; Tier 4: DPA-ITC-M02A-FCU-MSB-04-014
| step |  |  | Tier 2: DUCTWORK Fit Off
M02B | checklist |  |  | Tier 3: AHU-00-1; Tier 4: DPA-ITC-M02B-AHU-00-1-001
M02B | checklist |  |  | Tier 3: AHU-00-2; Tier 4: DPA-ITC-M02B-AHU-00-2-002
M02B | checklist |  |  | Tier 3: AHU-00-3; Tier 4: DPA-ITC-M02B-AHU-00-3-003
M02B | checklist |  |  | Tier 3: AHU-00-4; Tier 4: DPA-ITC-M02B-AHU-00-4-004
M02B | checklist |  |  | Tier 3: AHU-01-1; Tier 4: DPA-ITC-M02B-AHU-01-1-005
M02B | checklist |  |  | Tier 3: AHU-01-2; Tier 4: DPA-ITC-M02B-AHU-01-2-006
M02B | checklist |  |  | Tier 3: AHU-01-3; Tier 4: DPA-ITC-M02B-AHU-01-3-007
M02B | checklist |  |  | Tier 3: AHU-02-1; Tier 4: DPA-ITC-M02B-AHU-02-1-008
M02B | checklist |  |  | Tier 3: GEF-00-1; Tier 4: DPA-ITC-M02B-GEF-00-1-009
M02B | checklist |  |  | Tier 3: KEF-02-1; Tier 4: DPA-ITC-M02B-KEF-02-1-010
M02B | checklist |  |  | Tier 3: TEF-02-1; Tier 4: DPA-ITC-M02B-TEF-02-1-011
M02B | checklist |  |  | Tier 3: GEF-02-1; Tier 4: DPA-ITC-M02B-GEF-02-1-012
M02B | checklist |  |  | Tier 3: TEF-02-2; Tier 4: DPA-ITC-M02B-TEF-02-2-013
M02B | checklist |  |  | Tier 3: GEF-02-2; Tier 4: DPA-ITC-M02B-GEF-02-2-014
M02B | checklist |  |  | Tier 3: KEF-02-2; Tier 4: DPA-ITC-M02B-KEF-02-2-015
M02B | checklist |  |  | Tier 3: MAF-01-1; Tier 4: DPA-ITC-M02B-MAF-01-1-016
M02B | checklist |  |  | Tier 3: SAF-02-1; Tier 4: DPA-ITC-M02B-SAF-02-1-017
M02B | checklist |  |  | Tier 3: SPF-02-1; Tier 4: DPA-ITC-M02B-SPF-02-1-018
M02B | checklist |  |  | Tier 3: SPF-02-2; Tier 4: DPA-ITC-M02B-SPF-02-2-019
M02B | checklist |  |  | Tier 3: LRF-02-1; Tier 4: DPA-ITC-M02B-LRF-02-1-020
M02B | checklist |  |  | Tier 3: LRF-02-2; Tier 4: DPA-ITC-M02B-LRF-02-2-021
M02B | checklist |  |  | Tier 3: IP-GEF-07; Tier 4: DPA-ITC-M02B-IP-GEF-07-022
M02B | checklist |  |  | Tier 3: KEF-02-3; Tier 4: DPA-ITC-M02B-KEF-02-3-023
M02B | checklist |  |  | Tier 3: SAF-SUB-1; Tier 4: DPA-ITC-M02B-SAF-SUB-1-024
M02B | checklist |  |  | Tier 3: SAF-SUB-2; Tier 4: DPA-ITC-M02B-SAF-SUB-2-025
M02B | checklist |  |  | Tier 3: GEF-PR-1; Tier 4: DPA-ITC-M02B-GEF-PR-1-026
M02B | checklist |  |  | Tier 3: GEF-FPR-1; Tier 4: DPA-ITC-M02B-GEF-FPR-1-027
M02B | checklist |  |  | Tier 3: GEF-BIN-1; Tier 4: DPA-ITC-M02B-GEF-BIN-1-028
M02B | checklist |  |  | Tier 3: FCU-00-1; Tier 4: DPA-ITC-M02B-FCU-00-1 -029
M02B | checklist |  |  | Tier 3: FCU-00-2; Tier 4: DPA-ITC-M02B-FCU-00-2 -030
M02B | checklist |  |  | Tier 3: FCU-MSB-01; Tier 4: DPA-ITC-M02B-FCU-MSB-01-031
M02B | checklist |  |  | Tier 3: FCU-MSB-02; Tier 4: DPA-ITC-M02B-FCU-MSB-02-032
M02B | checklist |  |  | Tier 3: FCU-MSB-03; Tier 4: DPA-ITC-M02B-FCU-MSB-03-033
M02B | checklist |  |  | Tier 3: FCU-MSB-04; Tier 4: DPA-ITC-M02B-FCU-MSB-04-034
| step |  |  | Tier 2: Insulation
DPA-ITC-M10 | checklist |  |  | Tier 3: DUCT INSULATION LEVEL 1 PLANT ROOM; Tier 4: DPA-ITC-M10-DUCT INSULATION LEVEL 1 PLANT ROOM -001
DPA-ITC-M10 | checklist |  |  | Tier 3: DUCT INSULATION LEVEL 2 PLANT ROOM; Tier 4: DPA-ITC-M10-DUCT INSULATION LEVEL 2 PLANT ROOM -002
DPA-ITC-M10 | checklist |  |  | Tier 3: DUCT INSULATION LEVEL 00; Tier 4: DPA-ITC-M10-DUCT INSULATION LEVEL 00 -003
DPA-ITC-M10 | checklist |  |  | Tier 3: DUCT INSULAITON LEVEL 01; Tier 4: DPA-ITC-M10-DUCT INSULAITON LEVEL 01 -004
DPA-ITC-M10 | checklist |  |  | Tier 3: DUCT INSULATION LEVEL 02; Tier 4: DPA-ITC-M10-DUCT INSULATION LEVEL 02 -005
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION CHILLER PLANT; Tier 4: DPA-ITC-M11-PIPE INSULATION CHILLER PLANT-001
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION LEVEL 1 PLANT ROOM; Tier 4: DPA-ITC-M11-PIPE INSULATION LEVEL 1 PLANT ROOM-002
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION LEVEL 2 PLANT ROOM; Tier 4: DPA-ITC-M11-PIPE INSULATION LEVEL 2 PLANT ROOM-003
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION LEVEL 00; Tier 4: DPA-ITC-M11-PIPE INSULATION LEVEL 00-004
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION LEVEL 01; Tier 4: DPA-ITC-M11-PIPE INSULATION LEVEL 01-005
DPA-ITC-M11 | checklist |  |  | Tier 3: PIPE INSULATION LEVEL 02; Tier 4: DPA-ITC-M11-PIPE INSULATION LEVEL 02-006