## Data Population
Area | Location | Lot Type | Responsible Engineer | Pay Items | Doval Access | Client Access
Whole Site | Chainage From | Asphalt | Darshin Reddy | See Pay Items Tab | David Reid | Rodney Bunk (Rodney.y.bunk@tmr.qld.gov.au)
GA-01-B | Chainage To | Clear and Grub | Jan van Wyk |  | Dan Marks | Mathew Grey (Mathew.A.Grey@tmr.qld.gov.au)
GA-02-A |  | Contractor's Site Facilities | Dan Marks |  | Jan van Wyk
GA-02-C |  | Concrete Work |  |  | Darshin Reddy
GA-03-B |  | Demolition
GA-04-A |  | Earthworks
GA-05-B |  | Electrical
Eastern Service Rd |  | Environmental Management
Western Service Rd |  | Erosion and Sediment Control
Pavement Type A |  | Geotextile
Pavement Type B |  | Landscaping
Pavement Type C |  | Linemarking
Pavements
Road Side Furniture
Rock Protection
Stabilised Pavements
Stormwater
Stripping of Topsoil
Subgrade
Subsurface Drainage
Traffic Management
Unsuitable Material

## Pay Items
Pay Item | Unit
30001.02 - Removal or demolition of culverts, complete [ID17916 - GA-02-B] | LS
30001.04 - Removal or demolition of culverts, complete [ID12609 - GA-05-A] | LS
30001.05 - Removal or demolition of culverts, complete [Property accesses - CH 11740, 12085 & 12335] | LS
30002.01 - Removal or demolition of culvert end structures (GA-02-A, LHS and RHS) | LS
30002.02 - Removal or demolition of culvert end structures [Property access CH 12475 (northern side)] | LS
30002.03 - Removal or demolition of culvert end structures (GA-01-A, LHS) | LS
30002.04 - Removal or demolition of culvert end structures (GA-03-A, LHS) | LS
30004.01 - Removal or demolition of concrete kerb including kerb crossings | m
- Installation of Culverts
30153.02 - Installation of concrete box culvert components, [2/2100x1500], [B2] environment, (ID76201 - GA-03-A) [6.0m LHS, incluidng joint between RCC and RCB] | m
- Supply and Installation of Culverts
30251.01 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter,[B2] environment, (GA-02-A) [including supply of materials and construction of the extension detail provided on drawing DD-CS-01. Refer MRTS03.1 Clause 6.4] | m
30251.02 - Supply and installation of concrete pipe culvert components, [1/1050] mm diameter, [B2] environment, (GA-02-C) | m
30251.03 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter, [B2] environment, (GA-04-A) | m
30251.04 - Supply and installation of concrete pipe culvert components, [1/1500] mm diameter, [B2] environment, (GA-05-B) | m
30251.05 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter, [B2] environment, (Property access CH 11740, new) | m
30251.06 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter, [B2] environment, (Property access CH 12085, new ) | m
30251.07 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter, [B2] environment, (Property access CH 12335, new) | m
30251.08 - Supply and installation of concrete pipe culvert components, [1/375] mm diameter, [B2] environment, (Property access CH 12475, extension) | m
30253.01 - Supply and installation of concrete box culvert components, [4/2100x2100], [B2] environment, (ID76198 - GA-01-A) [3.6m LHS, incluidng joint between RCC and RCB] | m
30254.01 - Supply and installation of concrete spanning slabs [2 / 2700] | m
- Concrete in Culverts and End Structures
30352.01 - Concrete bases in culverts | m3
a) - Concrete bases in culverts 6/2100x2100 RCBC (GA-01B) | m3
b) - Concrete bases in culverts 2/2100x1500 RCBC (GA-03B) | m3
30358.01 - End structures to culverts, reinforced concrete | m3
a) - End structures to culverts, reinforced concrete 6/2100x2100 RCBC (GA-01B) | m3
f) - End structures to culverts, reinforced concrete - GA-02A | m3
c) - End structures to culverts, reinforced concrete - GA-02C - 1050mm | m3
d) - End structures to culverts, reinforced concrete - GA-04-A | m3
b) - End structures to culverts, reinforced concrete 2/2100x1500 RCBC (GA-03B) | m3
e) - End structures to culverts, reinforced concrete - GA-05B | m3
30362.01 - Aprons to culverts, reinforced concrete | m3
a) - Aprons to culverts, reinforced concrete GA-01B | m3
b) - Aprons to culverts, reinforced concrete GA-02A | m3
c) - Aprons to culverts, reinforced concrete GA-02C | m3
d) - Aprons to culverts, reinforced concrete GA-04A | m3
e) - Aprons to culverts, reinforced concrete GA-03B | m3
f) - Aprons to culverts, reinforced concrete GA-05B | m3
30366.01 - Precast concrete end structures to culverts, [375, sloping] (Property Accesses) | each
- Pavement Drainage
30451.01 - Concrete kerb, [Type 9] | m
30451.02 - Concrete kerb, [Type 11] | m
30453.01 - Concrete channel, [Type 28] | m
30454.01 - Concrete kerb and channel, [Type 14] | m
30454.02 - Concrete kerb and channel, [Type 15] | m
- Subsurface Drainage
30551.01 - Subsoil drains, Type B, [100] mm diameter | m
30553.01 - Subsoil drain outlet connection, [100] mm diameter, [concrete headwall] | each
30554.01 - Subsoil drain clean-out, [100] mm diameter, [PVC cap] | each
30562.01 - Supply and installation of geotextile, strength class [D], filtration class [V] (Beneath rock protection at culvert inlets and outlets] | m2
- Protective Treatments
30661.01 - Hand placed concrete paving, [125] mm thick (concrete tops to medians) | m2
30661.02 - Hand placed concrete paving, [125] mm thick (concrete lined drain in cutting) | m2
30661.03 - Hand placed concrete paving, [125] mm thick [Residential driveways, in accordance with IPWEA drawings RS-049 and RS-50] | m2
30666.01 - Rock protection (d50 = 200) | m3
30666.02 - Rock protection (d50 = 300) | m3
30668.01 - Steel wire mattress protection work [Culvert GA-05-B 230 mm thick Reno mattress] | m2
MRS38 Jul 17 - Pavement Drains
- Pavement Drains
42701.01P - Pavement Drain (Provisional Quantity, if ordered) | m
42702.01P - Pavement Drain Outlets (Provisional Quantity, if ordered) | each
MRS170 Mar21 - Public Utilities in Road Projects Site Works
- Road Project Site Works - General
22109.01 - Supply and install of permanent reinforced concrete encasement / protection slab [Refer project drawing 902843, excluding kerb and channel, residential driveway, pavement drain and strain alleviating fabric and AC surfacing (scheduled separately above)] | m3
90101.01 - Liaison and co-ordination of Principal's Materials and Works [Refer to Supplementary Specification 1] | LS
90102.01 - Liaison and co-ordination of Affected Utilities Work [Refer to Supplementary Specification 2] | LS
90103.01 - Potholing to Existing Underground Public Utility Plant [Refer to Supplementary Specification 3] | LS
91001.01 - Sawcut existing pavement [Refer to Supplementary Specification 5] | m
MRS04 Nov 22 - General Earthworks
- Preparation
32001.01 - Clearing and grubbing | m2
32003.01P - Stripping of topsoil (Provisional Quantity, as directed) | m3
32007.01 - Ground surface treatment under embankment, standard | m2
32014.01P - Excavation and disposal of Unsuitable Material with individual excavation <= 10 m^3 (Provisional Quantity, as directed) | m3
32018.01P - Excavation and disposal of Unsuitable Material with individual excavation > 10 m^3 (Provisional Quantity, as directed) | m3
- Excavation
32101.01 - Excavation, all materials | m3
32118.01P - Excavation and disposal of Unsuitable Material in and below confined excavations (Provisional Quantity, as directed) [Underneath culverts GA-01-B & GA-03-B] | m3
32122.01P - Excavation and disposal of Unsuitable Material within lines of excavation, rate additional to rate for Standard Work Item 32101 (Provisional Quantity, as directed) | m3
32126.01 - Blinding concrete, [50] mm nominal thickness | m2
- Embankment
32201.01 - Embankment | m3
32210.01 - Verge fill | m3
- Existing Subgrade Testing and Treatments
32301.01 - Existing subgrade testing | Ea
32306.01P - Subgrade treatment Type A (Provisional Quantity, if ordered) | m2
32314.01P - Subgrade treatment Type C, replace with unbound granular material (Provisional Quantity, if ordered) | m3
32346.01P - Subgrade treatment Type J, bridging layer (Provisional Quantity, if ordered) | m3
- Backfill
32401.01P - Backfill with earth backfill material [where items 32014P and 32018P ordered] (Provisional Quantity, if ordered) | m3
32408.01P - Backfill with rock fill to [where items 32014P and 32018P ordered] (Provisional Quantity, if ordered) | m3
32408.01P - Backfill with rock fill to [where Item 32118 ordered, 500mm deep wrapped in geotextile, underneath culverts GA-01-B & GA-03-B including supply and installation of geotextile, strength class [D], filtration class [V]] (Provisional Quantity, if ordered). | m3
MRS05 Jul 22 - Unbound Pavements
- Unbound Pavements
40002.01 - Subtype 2.1, Unbound pavement, [Base / Pavement Type C] | m3
40003.01 - Subtype 2.2, Unbound pavement, base / property access] | m3
40004.01 - Subtype 2.3, Unbound pavement, [Subbase / Pavement Type C] | m3
40005.01 - Subtype 2.4, Unbound pavement, [Subbase / Property access] | m3
MRS10 Nov 22 - Plant-Mixed Lightly Bound Pavements
` - Plant-Mixed Lightly Bound Pavements
40602.01 - Plant-mixed Lightly Bound Improved Layer, [150 mm Type 2.1 / Pavement Type B] | m3
40602.02 - Plant-mixed Lightly Bound Improved Layer, [150 mm Type 2.3 / Pavement Type B] | m3
MRS14 Mar 22 - Road Furniture
- Road Furniture
50001.01 - Demolition of road furniture, as listed in Clause 3 of Annexure MRTS14.1 | LS
50003.01 - Removal and re-erection of road furniture, as listed in Clause 4 of Annexure MRTS14.1 | LS
- Guidance and Information Systems
50051.01 - Road edge guide posts | each
50052.01 - Supply of regulatory, warning and hazard sign faces, as listed in Clause 1.3 of Annexure MRS14.1 | LS
50056.01 - Installation of regulatory, warning and hazard signs, as listed in Clause 1.3 of Annexure MRS14.1 | LS
50061.01 - Supply, erection and removal of project signs | LS
50061.02P - Supply, erection and removal of project signs [Project recognition mesh fencing] (Provisional Quantity, if ordered) | LS
- Roadside Structures
50160.01 - Steel beam guardrail, w beam [MASH TL-3 containment capacity, including motorcycle protection rail, TMR approved product] [Refer Clause 12.1 MRTS14.1] | m
50162.01 - Steel beam guardrail, terminal type [MASH TL-3 containment capacity including motorcycle protection shield, TMR approved product] [Refer Clause 12.1 MRTS14.1] | each
MRS16 Jul 17 - Landscape and Revegetation Works (including sidetrack revegetation)
- Landscape and Revegetation - Sampling and Testing
50601.01 - Preparation of a Soil Management Plan - Construction - Form A | LS
50602.01P - Topsoil sampling and testing - Form C (Provisional Quantity) | set
50606.01P - Manufactured site topsoil sampling and testing - Form D (Provisional Quantity) | set
50610.01P - Subsoil sampling and testing - Form E (Provisional Quantity) | set
- Landscape and Revegetation - Site Won Materials
50651.01P - Manufactured site topsoil (Provisional Quantity, if ordered) | m3
- Landscape and Revegetation - Imported Materials
50701.01P - Amelioration agent - agricultural lime, dolomite and / or gypsum (Provisional Quantity, if ordered) [agricultural lime, agricultural dolomite, agricultural gypsum] | Tonne
50705.01P - Amelioration agent - organic soil conditioner (Provisional Quantity, if ordered) | m3
50709.01P - Imported topsoil (Provisional Quantity, if ordered) | m3
50713.01P - Imported mulch (Provisional Quantity, if ordered) [Aged Forest Mulch] | m3
- Landscape and Revegetation - Weed Control
50751.01P - Application of knock-down herbicide (Provisional Quantity) | m2
- Landscape and Revegetation - Ground Preparation
50801.01 - Installation of ameliorants to subsoil | m2
50802.01 - Ripping, cultivation, roughening | m2
50803.01 - Installation of topsoil [75mm - areas to be turfed and hydromulched] | m2
50803.02 - Installation of topsoil [300mm - areas to be planted] | m2
50851.01 - Seed Mix - Grassland Mix [A - Refer Clause 3.2.2 of MRTS16.1] | kg
50852.01 - Seed Mix - Woodland / Forest Mix [B - Refer Clause 3.2.3 of MRTS16.1] | kg
50855.01 - Installation of hydromulch - standard [Mix A - for revegetation of disturbed roadside areas as depicted in the typical sections] | m2
50855.02 - Installation of hydromulch - standard [Mix B - for revegetation of the footprints of the sidetrcks that are not within the clearzone] | m2
- Landscape and Revegetation Works - Turfing
50901.01 - Installation of turf [Refer Clause 3.3.1 of MRTS16.1] | m2
- Landscape and Revegetation Works - Planting
50951.01 - Installation of planting [Low Height Pavement Edge Planting – Western Service Road Table Drain (Western Batter Only). Refer MRTS16.1 Clause 3.4.1] | cont.
50951.02 - Installation of planting [Medium Height Headlight Screen Planting – Western Service Road Table Drain (Western Batter Only) Refer MRTS16.1 Clause 3.4.2] | cont.
- Landscape and Revegetation - Establishment and Monitoring
51051.01 - Establishment period | LS
51052.01P - Establishment period watering (Provisional Quantity) | LS
51056.01 - Monitoring period [90 days for Mix A, Mix B and turfed areas] | LS
51056.02 - Monitoring period [180 days for plantings] | LS
51057.01P - Monitoring period watering (Provisional Quantity) | LS
MRS45 Nov 22 - Road Surface Delineation
- Line Marking
52101.01S - Spotting only for longitudinal lines [Refer to Supplementary Specification 7] | m
52106.01 - Barrier line, both directions, 80 mm wide each line, 80 mm lateral gap between lines, colour [white], material [cold applied plasticl] | m
52109.01 - Lane line, continuous, 100 mm wide, colour [white], material [cold applied plastic] | m
52110.01 - Edge line, 150 mm wide, colour [white], material [cold applied plastic] | m
52110.02 - Edge line, 150 mm wide, colour [yellow], material [cold applied plastic] | m
52111.01 - Continuity line, 200 mm wide, colour [white], material [cold applied plastic] | m
52113.01 - Outline, 150 mm wide, colour [white], material [cold applied plastic] | m
52116.01 - Transverse lines (stop lines, holding lines, markings at Stop and Give Way signs, pedestrian crosswalk lines, arrows, shapes, symbols and numerals), colour [white], material [thermoplastic]. | m2
52117.01 - Transverse lines (diagonal and chevron markings, parking areas and kerb markings), colour [white], material [thermoplastic]. | m2
52122.01 - Audio tactile line marking - wide centreline, barrier line, both directions each 150 mm wide, 50 mm rib length, 250 mm centre to centre spacing, 10 mm rib height (applied to both lines), material [thermoplastic] | m
52125.01 - Wide centreline, barrier line, both directions, 100 mm wide each line, [gap width] gap between lines, colour [white], material [cold applied plastic] | m
- Raised Pavement Markers
52201.01 - Retroreflective raised pavement markers | each
MRS110 Mar23 - Coloured Surface Treatments
- Coloured Surface Treatments
44501.01 - Supply and placement of coloured surface treatment [Bicycle lane treatments. Refer SL drawing series) | m2
-
90501.01 - Supply and install wheel stop [Rubber, 2000 mm. Parking bay adjacent to eastern service road exit. Refer Supplementary Specification 16] | ea
MRS11 May 22 - Sprayed Bituminous Treatments (Excluding Emulsion)
- Sprayed Bituminous Treatments (excluding Emulsion)
40721.01 - Spraying bituminous material, treatment type [P], binder [AMC00], spray rate [1.0 l/m2], [Under EME2 base] | litre
40721.02 - Spraying bituminous material, treatment type [WP-A], spray rate [1.5 l/m2], [Pavement Type A, under surfacing course] | litre
40721.03 - Spraying bituminous material, treatment type [WP-A], binder [S25E], spray rate [1.5 l/m2], [Pavement Type B, under surfacing course] | litre
40721.04 - Spraying bituminous material, treatment type [I-S/S], binder [C170], spray rate [1.3 l/m2], [Pavement Type B, under EME2 base] | litre
40721.05 - Spraying bituminous material, treatment type [S/S], binder [C170], spray rate [1.3 l/m2], [Pavement Type C, under surfacing course] | litre
40721.06 - Spraying bituminous material, treatment type [D/D Second Application], binder [C170], spray rate [0.7 l/m2], [Property accesses] | litre
40721.07 - Spraying bituminous material, treatment type [D/D First Application], binder [C170], spray rate [1.7 l/m2], [Property accesses] | litre
40722.01 - Spreading cover aggregate [10mm], [160 m2/m3], [including] supply of cover aggregate, [Pavement Type A, under surfacing course] | m3
40722.02 - Spreading cover aggregate [10mm], [160 m2/m3], [including] supply of cover aggregate, [Pavement Type B, under surfacing course] | m3
40722.03 - Spreading cover aggregate [10mm], [150 m2/m3], [including] supply of cover aggregate, [Pavement Type C, under surfacing course] | m3
40722.04 - Spreading cover aggregate [7mm], [215 m2/m3], [including] supply of cover aggregate, [Property accesses, second application] | m3
40722.05 - Spreading cover aggregate [14mm], [115 m2/m3], [including] supply of cover aggregate, [Property accesses, first application] | m3
MRS30 Mar 22 - Asphalt Pavements
- Preparation of the Existing Surface
41701.01 - Preparation of the existing surface | m2
41706.01P - Strain alleviating membrane fabric strips (Provisional Quantity) | m
41710.01P - Tack coat, residual bitumen [beneath corrector course and above concrete protection slab] (Provisional Quantity) | litre
41710.02P - Tack coat, residual bitumen (0.5 l/m2. To profiled surface) (Provisional Quantity) | litre
- Medium Duty Dense Graded Asphalt
41754.01 - Medium duty dense graded asphalt in surfacing course, AC [14] M mix [Pavement Type A] | Tonne
41754.02 - Medium duty dense graded asphalt in surfacing course, AC [14] M mix [Pavement Type B] | Tonne
41754.03 - Medium duty dense graded asphalt in surfacing course, AC [7] M mix [Pavement Type C] | Tonne
MRS32 Jul 22 - High Modulus Asphalt (EME2)
- High Modulus Asphalt (EME2)
42101.01 - High modulus asphalt, EME2 mix [Corrector Course] | Tonne
42101.02 - High modulus asphalt, EME2 mix [Pavement Type A] | Tonne
42101.03 - High modulus asphalt, EME2 mix [Pavement Type B] | Tonne
- Non-Standard 90000 Series Items
92001.01P - Profiling of existing pavement [Refer to Supplementary Specification 12] | m2
92002.01P - Excavate existing asphalt and stabilised pavement patches and replace with AC20 material (100 mm nominal depth), (Provisional Quantity, as directed) [Refer to Supplementary Specification 11] | m2
MRS91 Mar 23 - Conduits and Pits
- Conduit and Conduit Fittings Underground
60007.01 - Supply and installation of [1] of [100] mm, [HDuPVC], [Orange ] conduit(s), in [ground] [Rate 3] | m
60007.02 - Supply and installation of [1] of [100] mm, [HDuPVC], [Orange ] conduit(s), in [existing unsealed road] [Rate 3] | m
60007.03 - Supply and installation of [2] of [100] mm, [HDuPVC], [Orange ] conduit(s), in [existing unsealed road] [Rate 3] | m
- Ancillary Works
60154.01 - Removal of cable jointing pit(s) (all types) | each
- Cable Jointing Pits
60204.01 - Supply and installation of cable jointing pit [600mm circular - electrical] - Rate 3 | each
60205.01 - Construction of Pit surround | each
MRS92 Mar 18 - Traffic Signal and Road Lighting Footings
- Road Lighting Footings
60351.01 - Road lighting pole footing, [600] mm diameter [ Rate 3] | each
60351.02 - Road lighting pole footing, [600] mm diameter [ Rate 2] | each
60353.01P - Road lighting pole footing extension in poor soil, 3000 mm long, [diameter] mm diameter, if ordered (Provisional Quantity) [Rate 3] | each
60357.01P - Excavation in excessively hard material, rate additional to rate for Work Items 60351, 60352 and 60353P (Provisional Quantity) - Rate3 | m3
60362.01 - Removal of road lighting pole footing [Rate 3] | each
60363.01 - Conformance and As Constructed survey for depth of footing [Rate 3] | each
60364.01 - Setting out and conformance for holding down bolts [Rate 3] | each
60367.01 - As Constructed survey for road lighting pole footing [Rate 3] | each
MRS94 Nov 22 - Road Lighting
- Road Lighting
60702.01 - Supply of [single] road lighting outreach arm, [4500] mm long (MA4) [Rate2] | each
60710.01 - Installation of [base plate mounted road lighting pole, reinstate existing] | each
60711.01 - Installation of road lighting outreach arm (included 1x MA4) [Rate 2] | each
60711.02 - Installation of road lighting outreach arm [Rate 3 reinstate existing] | each
60712.01 - Installation of road lighting outreach arm extension | each
60719.01 - Supply and installation of [base plate mounted] road lighting pole, [10000] mm vertical height, [3000] mm long [single] outreach arm, [with] outreach arm extension [underground cabling and fused junction box in pit] - Rate 3 | each
60719.02 - Supply and installation of [base plate mounted] road lighting pole, [8500] mm vertical height, [3000] mm long [single] outreach arm, [without] outreach arm extension [overhead cabling and no fused, no junction box and no pit] - Rate 2 | each
60724.01 - Supply and installation of road lighting luminaire, [Philips Roadflair], [67W Aeroscreen] [Rate 2] | each
60724.02 - Supply and installation of road lighting luminaire, [Sylvania Gerard RoadLED], [155W Aeroscreen] [Rate 3] | each
- Removal of Existing Equipment
60791.01 - Removal of road lighting equipment for salvage, [1x pole, 1 outreach with arm extension, 1x bell joint-fused] Rate 3 | each
60792.01 - Removal of road lighting equipment for disposal, [1x timber footing, 1x timber pole, 1x bracket and support hook] Rate 2 | each
60793.01 - Removal of road lighting luminaire (reinstate back at new location) | each
60793.02 - Removal of road lighting luminaire [Rate 1 - S150] | each
60793.03 - Removal of road lighting luminaire [Rate2 - M80] | each
MRS210 Nov21 - Provision of Mains Power
- Mains Connection
62101.01 - Supply of mains connection equipment including the supply of mains connection cable, [36], [LV], [25mm2], [2] cores, [ABC] [PVC] ], [Al] | each
62102.01 - Installation of mains connection including mains connection cable | each
MRS228 Jul21 - Electrical Switchboards
- Switchboards
64201.01 - Supply of top mounted switchboard and ancillary components - Rate 3 | each
64202.01 - Supply and construction of a concrete pad for the erection of switchboard post - Rate 3 | LS
64203.01 - Installation of top mounted switchboard and ancillary components - Rate 3 | each
MRS256 Nov20 - Power Cables
- Power Cables
67101.01 - Supply of underground road lighting cable, [16mm], [2] cores, [XLPE], [PVC], [Cu] - Rate 3 | m
67102.01 - Supply of aerial road lighting cable, [25mm], [2] cores, [ABC], [XLPE], [AAC] | m
67106.01 - Supply of aerial cable strain clamp | each
67107.01 - Supply of aerial cable connector, [TAP-OFF Bare Al MAIN 10-35mm2 TO 6/35mm2 ABC TAP- Rate 2 with 1x support hook] | each
67109.01 - Installation, jointing and termination of underground road lighting cable, [2 cores] - Rate 3 | m
67113.01 - Installation, jointing and termination of aerial road lighting cable, [2 cores] | m
67191.01 - Removal of underground cable [Rate 3, to be reinstated back into new conduit and pit] | m
67192.01 - Removal of aerial cable | m
VAR 001
VAR 002
VAR 003
VAR 004
VAR 005
VAR 006
VAR 007
VAR 008
VAR 009
VAR 010
VAR 011
VAR 012
VAR 013
VAR 014
VAR 015
VAR 016
VAR 017
VAR 018
VAR 019
VAR 020
VAR 021
VAR 022
VAR 023
VAR 024
VAR 025
VAR 026
VAR 027
VAR 028
VAR 029
VAR 030
VAR 031
VAR 032
VAR 033
VAR 034
VAR 035
VAR 036
VAR 037
VAR 038
VAR 039
VAR 040
VAR 041
VAR 042
VAR 043
VAR 044
VAR 045
VAR 046
VAR 047
VAR 048
VAR 049
VAR 050

## 02.01
| checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management | 9aff18c4-2ac6-4830-8ad9-d2a3d26c68dd
| section | Details
| checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
41aea416-7db1-5664-82e8-678e89e0eec7 | note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
c9757c83-97fe-5262-b79e-66761471209d | note | Check Item - Check Item
1f748fb1-00d5-5fcd-bd47-e09cad114817 | note | Reference - MRTS02 Cl. 5.2
| checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
e13fa76e-3053-5164-94be-ad3544be4dbe | note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
0bf7f4a9-afa0-587d-9c7f-76fb1141348a | note | Check Item - Hold Point 1
112ac463-f730-5f20-aa01-ff1e59d25c18 | note | Reference - MRTS02 Cl. 5.3
| signoff | HOLD POINT
| checkpoint | All traffic control devices inspected and records kept in accordance with the specification
8fb10354-90f6-5d11-8644-70b04a883526 | note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
b74e7c31-20f9-5602-9d7c-287e755439d7 | note | Check Item - Check Item
9f20cd90-7845-59b9-8ccc-fe65d81a7599 | note | Reference - MRTS02 Cl. 5.6.4
| checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
ce700513-f72e-5fcd-851b-5101b47841d0 | note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
f6d87d39-c4b4-5ff3-a3ce-d06391b79e9a | note | Check Item - Check Item
18991954-ef75-5f9f-bbda-a0f6f09ffb11 | note | Reference - MRTS02Cl. 5.6.5
| checkpoint | The minimum number of lanes to be maintained on midblock sections of road will be determined as per the method (a), (b) or (c): As Mentioned MRTS02.1 Cl .3.2, 3.3, 3.4, 3.5
1c725e72-3242-53b7-9a50-7a3bc171f6ca | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
c6cbacdf-9b71-5bf2-b016-b15a6b08e91b | note | Check Item - Check Item
dffcb04c-da1e-5191-b350-e0b6820ccee7 | note | Reference - MRTS02.1 Cl. 5.7.3
| checkpoint | Traffic may be altered from its existing route via the following Cl 3.8 MRTS02.1
f9a7e5d0-ab92-546a-8ce7-80b171b81599 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
b198ad49-9cab-5b31-b468-d2090560f564 | note | Check Item - Check Item
5ed088c3-8281-525f-801f-a947e2bbe57d | note | Reference - MRTS02.1 Cl. 5.7.4
| checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
b395370e-a935-55ee-a488-1dabb93efdd3 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
329ae948-49e2-5e96-a3ef-3794055cee0d | note | Check Item - Hold Point 2
8be6a1d7-52c0-558f-b27f-12559021c823 | note | Reference - MRTS02 Cl. 6.2
| signoff | HOLD POINT
| checkpoint | The Contractor shall provide a minimum of two VMS (one in each direction) for the works under construction on Steve Irwin Way. VMSs shall be in place a minimum of 2 weeks prior to the commencement of the works on site to provide advance warning to the road users of the impending works. The requirements of Clause 6.5.2.1 of MRTS02 shall apply with regards to their use
e44b4901-3dfb-5510-bac0-7edb7d5cda21 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
d916e978-6fb8-5fac-b85b-80436172b9ba | note | Check Item - Check Item
44ffe3c0-50b0-5f72-a563-e1e4384e34ec | note | Reference - MRTS02.1 Cl. 6.5.2.1
| checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
a0c20617-6c73-50ad-a785-76f502bb7444 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
b5cf0831-e41f-5a31-af56-b91104993677 | note | Check Item - Milestone
3a2a97bc-3a7d-5f37-84f3-372c7d87b4df | note | Reference - MRTS02 Cl. 7.5
| checkpoint | The following requirements for side tracks shall apply as Stated in MRTS02.1 Cl 5.7
666b6bc4-f3ee-576a-9b5d-2d7ea140e772 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
365f6bf0-0a10-590f-96ff-daf4d64032f7 | note | Check Item - Check Item
76ffa20b-8bcd-50b7-8779-6921c59f2f2a | note | Reference - MRTS02 Cl. 6.5.3.3
| checkpoint | The following additional control measures are required to mitigate end of queue crashes as stated in MRTS02.1 Cl 5.8
35fe3e9d-0b2a-5823-a5cf-4ed2681da19e | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
6c360ce4-7b44-58ec-820e-b1e6525e95c5 | note | Check Item - Check Item
fc6a0543-bce0-5b01-9b99-7182fbff8713 | note | Reference - MRTS02 Cl. 6.5.7
| checkpoint | On asphalt and bituminous surfaced pavements, when permanent linemarking will not be in place outside working hours, temporary raised pavements markers (Stick and Stomps) are to be installed and maintained on centre lines, lane lines and edge lines at spacing of not greater than 25 m (except for side-track tie-ins where spacing shall not exceed 5 m). Temporary pavement markers shall only be in use for a maximum of 48 hrs and shall be replaced by linemarking after such time. If the Contractor is unable to complete line spotting by the end of each day’s work and the road is to be trafficked, the Contractor shall delineate all separation and lane lines as above. Existing longitudinal lines are to be removed by abrasive blasting or approved other method approved in writing by the Administrator when temporary lanes are in place
5978bb85-7a84-543a-859d-f52107550da5 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
ce4b1a3d-dc88-51d0-ac73-6be42317cafb | note | Check Item - Check Item
867c39b0-c79a-54ff-be54-fbcfb467ea60 | note | Reference - MRTS02 Cl. 6.5.8
| checkpoint | Temporary road lighting shall be installed in accordinance with MRTS02.1 Cl 5.12
7ed7f626-711b-58b1-9cd6-601fc0a2aebb | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
6af21beb-cc3f-5cef-ad05-8749ff22f1e0 | note | Check Item - Check Item
1aa098a7-645b-5f06-aa2e-426ad395562d | note | Reference - MRTS02 Cl. 6.5.13
| checkpoint | In addition to the requirements of Clause 7.1, there is a need for an independent review to establish conformance with the approved TMP and TGS and with the performance requirements of MRTS02 – Provision for traffic
84984b16-690b-5031-94b9-7563983fb10c | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
6720a462-7805-5410-af85-2f94d028df26 | note | Check Item - Check Item
b5bb256b-5f41-513d-911d-24c079a1a0de | note | Reference - MRTS02 Cl. 7.1
| checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 8
d56970ea-e18d-5eba-bab5-91e962843d8a | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
8d737249-8f87-57e4-8478-575ba2ac0ab6 | note | Check Item - Check Item
0a306c76-0cf7-5f9a-bc8c-67c952684d6f | note | Reference - MRTS02 Cl. 9
| checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 9
86e4896e-349c-5870-a113-f2404963fdc0 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
26cdf3dd-20b4-5cb3-aa3c-51b940a5f155 | note | Check Item - Check Item
16f8dbd6-8b5f-5224-9199-7e77ffeda151 | note | Reference - MRTS02.1 Cl. 9
| checkpoint | Final Verification
38d1cbb6-fbff-5e7b-b7df-7a30948eaa5b | note | Project Manager Verify that the Above has been Constructed according to Specification
e92ac1c7-b116-5fa8-a8a6-885f3b62763f | textbox | Print Name:
51c96055-d0ee-56fc-97f4-345b0a5dcb1b | date | Date:
8d0b94f6-76b5-553a-bf31-a726e14a0612 | note | Client Verify that the Above has been Constructed according to Specification
831b9524-a353-5f6b-bff0-ce3443ecca16 | textbox | Print Name:
64e566a9-f5be-5bb5-a448-ddba630286e6 | date | Date:
| signoff | Signature

## 03.01
| checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | 37f0083d-44ef-41d9-9846-b55fe6725faa
| section | Details
| checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
1376a992-2035-59e3-9f08-b77fb9676dc1 | note | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
ebbc9dee-5700-51e5-9f2a-0fcca4486b43 | note | Check Item - Check Item
ba075458-f427-5f71-9cb6-7b1e27a7747d | note | Reference - MRTS03 Cl 9.2
| checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
bb5c926d-6283-55a1-915b-02abfc64aecc | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
02f7a40a-4dfe-5743-b5b6-fb1b01189eb8 | note | Check Item - Check Item
39c03caa-aa22-5c1a-b200-7558f7d18c04 | note | Reference - MRTS03 Cl 9.2
| checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
357b8562-a039-5ace-ad0f-98efdd040c6a | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
96779f64-f840-5f44-9ba7-4e2d08bbf17b | note | Check Item - Check Item
d82bd16c-14ff-5f0e-b8c0-3799d11d0184 | note | Reference - MRTS03 Cl 9.2
| checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
e23c44b5-d67c-569a-82bf-c3be85b7729a | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
a01a6610-8bff-552b-b325-293977d67b91 | note | Check Item - Check Item
c81fa987-7e4e-5ae3-8e4f-8aa0753f3245 | note | Reference - MRTS03 Cl 9.2
| checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
70a31081-b2d1-537f-83b1-3ca3e34c720b | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
48e43fca-992a-51dd-9d37-2b1be68cf6d2 | note | Check Item - Check Item
52154140-4539-52ff-bbd3-b3cb1e8c6b5a | note | Reference - MRTS03 Cl 9.4
| checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
4a8d3a5e-f757-55ba-9e34-6608ef560750 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2049b3f8-76c7-5a48-b8ed-069b3e9db02d | note | Check Item - Check Item
5431d770-4f91-5635-b35c-d8c7dce79387 | note | Reference - MRTS03 Cl. 9.4
| checkpoint | Kerb excavations backfilled to flush with the surrounding area.
6f817abc-6633-5835-8698-fede051418d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e482be51-a17b-567b-84c4-7020f009e2f8 | note | Check Item - Check Item
89cf0708-62b4-50d6-b243-b846ebb5e6ed | note | Reference - MRTS03 Cl. 9.4
| checkpoint | Final Verification
5bb1bcd6-6a7d-5cdf-9a8b-f6b39da6fb5f | note | Project Manager Verify that the Above has been Constructed according to Specification
29eccf8b-c4b4-57da-9586-9cab3c249118 | textbox | Print Name:
0af1bfb1-9ba9-5eca-911c-9e849be2df12 | date | Date:
b9c17899-0ee7-561b-a4a1-8879a6ad98ab | note | Client Verify that the Above has been Constructed according to Specification
9be73287-be93-5b90-a88a-298b55bc8bc9 | textbox | Print Name:
214cfb75-7d8a-5839-9092-11176ae46b87 | date | Date:
| signoff | Signature

## 03.02
| checklist | 03.02 - Supply and Installation of Precast Concrete Pipe | itp | 03.02 - Supply and Installation of Precast Concrete Pipe | f276e2e4-4e3d-485f-a8de-fbd9d5400912
| section | Details
| checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
a0a4483b-e995-5844-9f64-74a884ebea70 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fc95b8e5-02fd-5842-b0a5-ae6175175554 | note | Check Item - Hold Point 1
42b3391a-84a5-5804-a1de-28649077cc73 | note | Reference - MRTS01 Cl. 8
| signoff | HOLD POINT
| checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
d444cc9d-13ed-5ba6-bbc2-fc595e5a620b | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
de08efdc-1dfc-500b-a387-5c98fe097c6e | note | Check Item - Check Item
13b4c536-e6b9-5a02-b239-f713139f865b | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
| checkpoint | Component size, wall thickness and class is as specified in the drawings
e9e6f75f-4e23-5a83-ba86-810966f6b416 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
39e72d0b-a0bb-59dc-b9b7-7915dab4b773 | note | Check Item - Check Item
d96b89ee-96b3-5e32-b7b3-3ed86ce90281 | note | Reference - MRTS03 Cl11.2
| checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
dcd00855-5792-5ebb-9c8e-1576d2de09ef | note | Acceptance Criteria and Frequency (Project Specific) - Visual
62c4977c-47fe-5f72-b87f-82d1e04fe28f | note | Check Item - Hold Point 1
56285a9b-9f34-5363-b367-ecf167cd7a78 | note | Reference - MRTS03 Cl11.2
| signoff | HOLD POINT
| checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
45828dec-b922-5de5-a80b-3302672cc2e0 | note | Acceptance Criteria and Frequency (Project Specific) - Written
3071c3d1-a10d-5469-9b94-40cd28ec7dd6 | note | Check Item - Milestone
13b277d5-911f-56c0-a490-d6b278a0f5c1 | note | Reference - MRTS03 Cl11.3.1
| checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
76ace638-e3ab-5c49-b46c-b012bb0d0bdb | note | Acceptance Criteria and Frequency (Project Specific) - Written
3e117518-bcc7-5741-8dfa-22bf9633c5b0 | note | Check Item - Hold Point 2
e19831ad-5f04-5613-98f5-5b4514f9e6dc | note | Reference - MRTS03 Cl11.3.1
| signoff | HOLD POINT
| checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
658b8d4e-d539-554d-bc67-dc1a8c7c412b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c922ca30-38fc-5c71-b18f-deaf1625197f | note | Check Item - Check Item
a0fa44e5-2091-585c-80da-f3ead5efb155 | note | Reference - MRTS03 Cl11.3.1
| checkpoint | Excavations completed as per MRTS04
20d11575-75e6-591d-b736-b576a76957f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
736fe201-7006-567a-8d24-8d076eff6954 | note | Check Item - Check Item
302ed068-1de4-5135-b556-262ff714efcf | note | Reference - MRTS03 Cl12.3.1, MRTS04
| checkpoint | Foundation bedding and Haunch zone material placed in Accordance with MRTS04
2a6e81bf-06fe-5477-a241-2d1bf553b2f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
869ee5c5-2105-550e-aced-cb4445ccb587 | note | Check Item - Check Item
e5c3ec7c-a602-53e1-a6c9-cb81fdeac098 | note | Reference - MRTS03 Cl11.3.2
| checkpoint | Components are assembled as per manufaturers specifications
e4a01700-33ca-5d01-83af-446abfd665f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6a21feca-c78d-537f-b589-571cb08a5cf3 | note | Check Item - Check Item
76543ae0-e9ed-5b93-8886-1dccdfca6a4e | note | Reference - MRTS03 Cl11.3.3
| checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
c4639d33-d333-54c1-a1c0-694931147781 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6ecf7797-f496-5774-9e10-6e9fae17e538 | note | Check Item - Check Item
05673ca2-c635-5b7e-b030-40544b86e089 | note | Reference - MRTS03 Cl11.3.4
| checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
c6df79cb-b7fb-5609-ad0a-d40758b6d42a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b08717c8-785c-51ec-a2a8-fa4968577cfe | note | Check Item - Check Item
87d8ee24-70b4-5112-b439-614c9833dbe7 | note | Reference - MRTS03 Cl11.3.5
| checkpoint | Pipes laid with the word 'TOP', where marked, or lifting hole facing the top. Lifting holes plugged after the pipe is installed.
de05a87d-2aeb-589c-b0e4-1cce3d209ba8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
deb57e9b-1d0d-5c42-a6d6-153fbb616286 | note | Check Item - Check Item
8a6d17e5-3fc9-551e-b533-a64ee62d2851 | note | Reference - MRTS03 Cl11.3.5
| checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
5344461f-098a-59e1-8e52-826ee05599c4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5dab3919-b15e-55d1-a23c-a4c07461928c | note | Check Item - Hold Point 3
9b120fbc-7c22-5166-a891-0caf5a644b62 | note | Reference - MRTS03 Cl11.3.5
| signoff | HOLD POINT
| checkpoint | Where RCP's are required to be cut, the cut surface shall be given two coats of a surface tolerant epoxy.
b4d05b51-0b18-5410-976e-ae4b0efd8f4b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
49df6ee1-1837-5227-9e4b-ca53cd83b310 | note | Check Item - Check Item
51e60906-bffc-516f-9e79-bbc4bbf1db13 | note | Reference - MRTS03 Cl. 11.3.9
| checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
a489207f-5a62-5cf9-9b17-52a9fd575669 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
3ca77a13-c86c-51fe-82f0-b3724b541b7b | note | Check Item - Check Item
86695289-e4e5-5e46-97ba-12276c1fb0c7 | note | Reference - MRTS03 Cl. 11.3.10
| checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
94ece686-3dce-5f1f-8ab3-4a0ed77878b0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
52f85a15-bdcd-5b53-8b69-f02bae86b975 | note | Check Item - Hold Point 4
c40e27a5-32a0-5c48-be26-47853730ae4c | note | Reference - MRTS03 Cl. 11.3.10
| signoff | HOLD POINT
| checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
c8b70489-cf52-5e22-971b-a310bb9a815e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15054837-ba81-57f2-b6bd-4adc204bdcbe | note | Check Item - Check Item
c9a0ee4c-ed26-5044-b3fb-2989641e5320 | note | Reference - MRTS03.1 Cl. 1
| checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
6ffde60b-16be-5252-88a0-e595413258b9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
03fe95a0-e3c6-50af-893d-937120883b4e | note | Check Item - Check Item
001f4646-0ade-5c89-bcf5-94973f8ca747 | note | Reference - MRTS03.1 Cl. 6
| checkpoint | Final Verification
f498f173-10f8-5d3d-9e8d-220444c354b2 | note | Project Manager Verify that the Above has been Constructed according to Specification
1125a7a9-6adc-5b33-8c12-73bcec1ef178 | textbox | Print Name:
28cdb289-42a4-54ce-afc0-14a13cf4a8f1 | date | Date:
9acd3400-a965-5190-91fb-1dadb52d11ce | note | Client Verify that the Above has been Constructed according to Specification
db266d05-69b6-56a9-b7a3-33f4b1500364 | textbox | Print Name:
5ac97e2d-4838-5d59-b83b-4c813aab909f | date | Date:
| signoff | Signature

## 03.03
| checklist | 03.03 - Culvert Component/End Structure Insitu Cast | itp | 03.03 - Culvert Component/End Structure Insitu Cast | 7d790023-8b59-4add-93b6-8b21d34eeaa6
| section | Details
| checkpoint | Concrete Conforms with Cl 6.1 (MRTS 70), Concrete Mortar conforms to Cl6.2, Steel Reinforcing conforms to MRTS71, Rock Masonry conforms to Cl33, Grouted Rock Pitching complies with Cl 34, Steel Wire Matresses comply with Cl 37
06e5d28b-f267-50b7-a9df-798a879cfcb0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS70 ITP
2d07c1b4-9995-5a87-8b31-f9f03dd2856e | note | Check Item - Check Item
b84b04cf-a44d-532e-8a82-6531cb2c6479 | note | Reference - MRTS03 Cl 14.2, Cl 15.2, Cl16.2
| checkpoint | Cast-in-situ end structures such as headwalls, wingwalls, aprons and kerbs to culverts constructed in the locations specified on the project drawings and comply with standard drawings 1304, 1305 for pipe culverts and 1240, 1250 & 1260 for box culverts as applicable
280bef65-91de-5ec7-b2b3-b7ca6a82fe00 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
095baebd-5d80-5f30-b88f-f0f65e0128e9 | note | Check Item - Check Item
83e14fdd-560e-5017-b166-e33d2634143e | note | Reference - MRTS03 Cl 15.3
| checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
db77e0d2-7e74-5fb0-9bad-71740d85fd47 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
f879c085-dc8a-5b2f-81cf-7ff13a0ce7d1 | note | Check Item - Check Item
84db280a-7d41-50f3-adc9-e76177cf9d14 | note | Reference - MRTS03 Cl 15.3
| checkpoint | Endwalls, wingwalls and concrete aprons constructed without a foundation bedding unless specified otherwise in the drawings.
9a3c73e9-ce3f-58c9-91c5-1734bbd0b77b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d6359f92-c995-505f-bb12-e7943fd00bbd | note | Check Item - Check Item
2831ca28-7b88-5858-bdfc-95c929a1ad5f | note | Reference - MRTS03 Cl 15.3
| checkpoint | Endwalls and wingwalls seperated with an expansion gap unless otherwise specified on the drawings.
8b2e3fba-e819-51d0-a8ae-09a5e0388314 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
de7290f2-2fbd-5755-8e9d-ad131a43ee4e | note | Check Item - Check Item
4e2fb002-d545-5d2e-8350-14f646eaafa6 | note | Reference - MRTS03 Cl 15.3
| checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
9a129abe-c352-5da9-8355-050dbec80198 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
943c4e1e-229e-5825-bcfd-7552192b148a | note | Check Item - Check Item
87053d94-88a2-5203-937e-b3c21bb76b70 | note | Reference - MRTS03.1 Cl. 6
| checkpoint | Construction of culvert base, walls or endwalls shall include the construction of integral nib or cutoff walls where relevant
4cb1d448-0fdb-5893-8cfb-772520d0dd33 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
03ed20d9-a1bb-5d44-9d07-97f15085144b | note | Check Item - Check Item
b67de4b8-09c0-52ef-8dc3-d38716050a15 | note | Reference - MRTS03 Cl 17.3, Cl 18.3
| checkpoint | Construction of culvert base, walls or endwalls shall comply with the Geometrics Section stated in Clause 1.5. MRTS03.1. For Each Structural Element, testing requirements must contain: Dimensional, Positional, and Relative Position
67fb576b-6f8d-5b6c-819e-8c8980995364 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
168decab-9e4e-5842-a88f-03243c19ba95 | note | Check Item - Check Item
7920c70e-500d-5690-a0ca-160a95fa867c | note | Reference - MRTS03.1 Cl 1.5
| checkpoint | Final Verification
b7fd5ec4-a2aa-5567-a654-4e9ce96b8601 | note | Project Manager Verify that the Above has been Constructed according to Specification
0587223c-d2e1-5767-b904-2b1dacea5cb9 | textbox | Print Name:
8dfa17c5-d4b4-5d6c-a200-a25789a71406 | date | Date:
1d9eaa3e-b9ae-5c3d-b076-8a99bca2fc6f | note | Client Verify that the Above has been Constructed according to Specification
63abdbb3-30c1-5f4b-99a8-c5231588a2e4 | textbox | Print Name:
e6c44da6-c50d-55f0-8cac-271d03fe02bd | date | Date:
| signoff | Signature

## 03.04
| checklist | 03.04 - Pre Cast End Structure | itp | 03.04 - Pre Cast End Structure | 498fd6e5-e36c-4c23-bfd4-af252ce59495
| section | Details
| checkpoint | Precast end structure conforms to Cl6.6, Concrete Mortar conforms to Cl6.2
dcbc5dbe-596d-5f5d-b994-4b1e6e567624 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
64718153-fbcf-5796-9051-1d42d5eea229 | note | Check Item - Check Item
3d9c61da-1399-5469-bff2-c596a03ddb73 | note | Reference - MRTS03 Cl 16.2
| checkpoint | Constructed in the locations specified on the project drawings
efa51a55-2691-59de-b28b-09201dea24dd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0d9e11f9-683b-5c44-92e9-0fa67b13eee1 | note | Check Item - Check Item
bfbb230d-6b6b-5445-91b9-91120914a486 | note | Reference - MRTS03 Cl 16.3
| checkpoint | Where material on or against which end structures are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
3eb2a7e0-c941-5814-a3ce-139fad58e2f7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
b2f8c09d-a3bd-524d-a39a-f8a82e5e264f | note | Check Item - Check Item
9ccbfc64-30a2-5a08-b1e1-928287a69c4e | note | Reference - MRTS03 Cl 16.3
| checkpoint | End Structures laid on foundation bedding which provides continuous even support
28de8a30-b5fe-5a26-b467-059c224de805 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d9450b24-0550-5c5f-8383-497127d9d59f | note | Check Item - Check Item
4f864599-f0bd-5219-8768-afa5286bdcef | note | Reference - MRTS03 Cl 16.3
| checkpoint | Joints between end structure and culvert in addition to any holes and recesses are filled with cement mortar and finished smooth and uniform and cured for 48hrs
19685959-9bff-5dcd-9f72-6f4b5e32b05b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2b85ec2a-2f51-5e1c-a01b-ab24f682390b | note | Check Item - Check Item
b6d1f060-64f6-5cb8-8d61-49c76342086e | note | Reference - MRTS03 Cl 16.3
| checkpoint | Backfilling operations not undertaken during curing period and complies with MRTS04
b74f5d71-2c93-5626-b64d-ace2601a65c7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
af536b3e-2309-5136-9855-8f3bbaa5259f | note | Check Item - Check Item
070df74d-fa8d-584a-8679-39fa8155864e | note | Reference - MRTS03 Cl 16.3
| checkpoint | Geometrics: All points for which levels are shown on the drawings
e981c30e-23dc-57f6-935a-8abd6fdf7488 | note | Acceptance Criteria and Frequency (Project Specific) - Horizontal: ±100mm, Vertical Invert: ±10mm
f7594356-5f6f-51ed-a55e-b38aa02106cc | note | Check Item - Check Item
075c27b8-7cbd-5687-a351-ebb9b0adad4a | note | Reference - MRTS03.1 Cl. 1
| checkpoint | Final Verification
bfbcc263-c8fa-5be7-a5fb-2499e5339c94 | note | Project Manager Verify that the Above has been Constructed according to Specification
9be776d2-402a-5123-970b-7034cd968c5c | textbox | Print Name:
380f812e-044f-5987-87f9-a6c37d13e3dc | date | Date:
ee1aa6cb-7a6b-5a9f-a060-eed6faf29c4e | note | Client Verify that the Above has been Constructed according to Specification
5a431bef-2d6b-5252-8cd5-330ba275561d | textbox | Print Name:
42fa8ffc-22da-5fe4-b7ad-10889565d113 | date | Date:
| signoff | Signature

## 03.05
| checklist | 03.05 - Supply and Installation of Precast Box Culverts | itp | 03.05 - Supply and Installation of Precast Box Culverts | d47cec8c-51da-4afb-b547-d8979d2976e2
| section | Details
| checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
9e79299e-6960-5d0a-93ad-31a1c1776ddb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
20fed177-faf7-5996-8a48-703ffc349cbd | note | Check Item - Hold Point 1
020198cd-3784-526c-ba47-8a1080e99062 | note | Reference - MRTS01 Cl. 8
| signoff | HOLD POINT
| checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
153d5ce0-9c37-5f6a-90d6-c3cb4baf4783 | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
6a142d39-ae8a-5f30-91bd-d56b8eaa88c7 | note | Check Item - Check Item
a1040a67-bc50-5e31-acb2-173faf5026fe | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
| checkpoint | Component size, wall thickness and class is as specified in the drawings
1f6f3b4a-bacc-587d-a652-1d09c71e03b5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a2b42b98-4837-5496-ab1e-4c437e41d72f | note | Check Item - Check Item
a46b8275-42dc-5db7-8af6-42c2fc0ef67e | note | Reference - MRTS03 Cl11.2
| checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
8dbb5923-dbb9-5dcb-95f5-ceb64779e2c3 | note | Acceptance Criteria and Frequency (Project Specific) - Written
d9baef7d-5c44-54e9-ad81-9129701198a2 | note | Check Item - Milestone
9980eb63-5663-5e51-b754-e389bb829639 | note | Reference - MRTS03 Cl11.3.1
| checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
3d0067c2-ea00-58e2-9540-8a8577ca574e | note | Acceptance Criteria and Frequency (Project Specific) - Written
5322b1af-1f8a-5803-a59b-ae8b94fcaa7b | note | Check Item - Hold Point 2
b11ea47e-5508-5073-9b21-88bc538a1770 | note | Reference - MRTS03 Cl11.3.1
| signoff | HOLD POINT
| checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
cd4719b8-c8b9-561d-9b4a-4219cfcc1a56 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
33eaff4b-8e47-5a7c-9a42-62fc9b1aaa23 | note | Check Item - Check Item
a581aa7d-b875-5af9-b389-69f9f6e0000c | note | Reference - MRTS03 Cl11.3.1
| checkpoint | Excavations completed as per MRTS04
9b6d9996-e583-506f-ae4a-7a18098b6d2d | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
55338c69-a97f-55b6-9d59-e1fb1f66f3b6 | note | Check Item - Check Item
64f56378-f5c2-51b5-be1e-1bdd9e2e9f7b | note | Reference - MRTS03 Cl12.3.1
| checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
fddc0ab8-4033-55f6-8e49-bc937a4e84c3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
88a792b0-5371-5d6d-96b7-83838024ec71 | note | Check Item - Check Item
d47be2ae-ee55-58f4-ae0b-f28183be8acf | note | Reference - MRTS03 Cl14.3.1
| checkpoint | Cast in-situ concrete bases, footings, infill floors and box culverts constructed without a foundation bedding unless specified otherwise in the drawings
709b1b86-9c7d-5a9a-a224-21f1e3b4429a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
43de52f1-ac20-55ea-ad84-af96e5159329 | note | Check Item - Check Item
715ef2aa-aab9-56ab-b48e-14ec8bee3a46 | note | Reference - MRTS03 Cl14.3.1
| checkpoint | Construction of bases, footings, infill floors and box culverts include the construction of nibs and integral cut-off walls
84d825c6-aeef-5831-8059-2327ec676842 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9ec227c8-3400-57fc-96c7-289578f92125 | note | Check Item - Check Item
960fb453-c111-5596-a5d7-832d49d85f8a | note | Reference - MRTS03 Cl14.3.1
| checkpoint | Components are assembled as per manufaturers specifications
8bd23eac-3216-5b3c-a3c4-5e8faf910793 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f555a24a-0a70-5b66-9179-fc6952a53ad0 | note | Check Item - Check Item
4cea0fbf-c101-5c52-8a23-1bdb130f19a5 | note | Reference - MRTS03 Cl11.3.3
| checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
15f060e9-374c-564f-852d-2931506e57cf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
69e3ebe3-bcc1-51c8-af85-2d6d7a46909f | note | Check Item - Check Item
8c10bf21-09f9-50ef-92b2-7f2b53d3bae4 | note | Reference - MRTS03 Cl11.3.4
| checkpoint | Box culverts installed in accordance with Standard Drawings 1250 and 1260 or project drawings.
b8c23b2c-14cc-5722-8315-a8b2c7dfb211 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3bcd9d90-9632-55f8-87e5-7cf87a34382f | note | Check Item - Check Item
321ef497-19be-5754-860a-69b3f46e7861 | note | Reference - MRTS03 Cl11.3.6
| checkpoint | Holding down anchors installed to retain the units, where specified, as per the details on STD DWG 1250 and 1260.
9e382fdc-8105-5fac-8936-d970eba6f673 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
94c86848-cad9-5107-835f-34eeed1d8ffc | note | Check Item - Check Item
bc03da9d-ca49-5924-b165-79d2c7a939a9 | note | Reference - MRTS03 Cl11.3.6
| checkpoint | Where spanning slabs are installed, locating dowels installed in the tops of the units and the spanning slabs seated on continuous cement mortar pads on the adjacent unit.
de837960-5caf-5fd3-93f7-86329ea5b514 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a8fe08c4-f0f0-5ebb-bb00-736c5f21839c | note | Check Item - Check Item
a5d26168-a3ab-585b-9a1c-ed616eb2ae76 | note | Reference - MRTS03 Cl11.3.6
| checkpoint | In multiple cell culverts, the gaps between the lines of installed cells shall be a minimum of 40mm wide and filled with 1:10 leanmix with max 10mm aggregate.
7626bc71-a594-554b-902a-136bf3ce8963 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
913d19ed-5cdd-5cc2-b29b-ac575ff4090f | note | Check Item - Check Item
8f7f071f-91a9-5938-92ca-8ff0d32dfbd1 | note | Reference - MRTS03 Cl11.3.6
| checkpoint | Where spanning slabs are installed, the space between the slabs is filled with lean mix concrete.
29e2a875-6a3a-5969-a730-98a28eac4a92 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
549bcb36-dce4-502c-9408-feb0b5ee8de2 | note | Check Item - Check Item
92b346a7-5b6f-5475-a969-253a781eea69 | note | Reference - MRTS03 Cl11.3.6
| checkpoint | Lean mix backfill cured for 24 hours before any other backfill material is placed over the culvert.
59cf1749-7c17-50a3-b6d0-7962dab0165d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
72857cd1-8c67-54f0-bb11-2c0f764e574f | note | Check Item - Check Item
1658c225-7ef8-5ad9-95bd-ea672bd05ddd | note | Reference - MRTS03 Cl11.3.6
| checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
ccffbabf-d31b-55b5-84c0-44453284780a | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
588288bc-c745-57e4-a331-21397a4b5aaa | note | Check Item - Check Item
968b157e-73ec-53c7-955a-2ebc1cef683d | note | Reference - MRTS03 Cl. 11.3.10
| checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
d972053e-4788-56cd-a01f-61cad33ce760 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3d136d83-6a06-5255-b07f-3f1b581c55ae | note | Check Item - Hold Point 4
4292e1ed-e55c-5b27-800b-e5af73f22345 | note | Reference - MRTS03 Cl. 11.3.10
| signoff | HOLD POINT
| checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
5b0d9252-3fa8-5de4-b514-2e3c11d91e60 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
810ddb2c-45d4-5b9a-82b3-1ec6c9fa2be6 | note | Check Item - Check Item
b6bcf2eb-9194-514d-b6a3-a6a702ed4769 | note | Reference - MRTS03.1 Cl. 6
| checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
bfbd319b-e032-5f85-aaab-fa5ebdf7c006 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c5a233ab-7fd2-5458-abd0-e249aef51c86 | note | Check Item - Check Item
4b5923a2-a0bb-5eb7-888c-f312680d0359 | note | Reference - MRTS03.1 Cl. 1
| checkpoint | Final Verification
b153a008-efe3-53d7-86a7-e72d4ec9c408 | note | Project Manager Verify that the Above has been Constructed according to Specification
ba9c0c4e-96be-5de2-a3ac-9fbc1e1f8304 | textbox | Print Name:
00d2598d-065f-53bc-95f7-973eddfc6049 | date | Date:
15b7bcfe-9323-5005-86ea-096816430239 | note | Client Verify that the Above has been Constructed according to Specification
67f4372c-079a-5353-9dfa-06790b0eb74d | textbox | Print Name:
260fe1c7-94f5-50be-b433-e6cb474e1b17 | date | Date:
| signoff | Signature

## 03.20
| checklist | 03.20 - Kerb - Cast Insitu/Extruded | itp | 03.20 - Kerb - Cast Insitu/Extruded | de3c3009-0789-48d1-ad48-23b4a286eefe
| section | Details
| checkpoint | Supplied Concrete complies with MRTS70/71. MRTS70 and MRTS71 ITP completed.
b019d3d8-f9ab-5b53-a451-422be784c218 | note | Acceptance Criteria and Frequency (Project Specific) - ITP 70.01
b588d636-49f2-55e1-a3be-08a845bf1109 | note | Check Item - Check Item
14e6233d-0c3a-5808-88eb-368806d92e1d | note | Reference - MRTS03 Cl 18.2
| checkpoint | Cast-in-place concrete kerb / channel constructed in the locations shown on the Drawings and in accordance with the details shown on Standard Drawings (1033)
144ed543-8ec1-5fb8-9383-c3f32399e0d1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a0508be4-5629-5313-84b4-1c652e1da84d | note | Check Item - Check Item
1b81e891-9257-5329-aba4-24a6fd594fec | note | Reference - MRTS03 Cl18.3
| checkpoint | Excavations / foundation preparation in accordance with the requirements of MRTS04 General Earthworks. The ground surface moistened just prior to placing concrete.
00db06a7-df5c-5bb6-a46d-da3c320c2baa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e4b0dc37-bb45-55f7-8345-ecf62ab84f49 | note | Check Item - Check Item
b1ac3f57-5b43-5e15-a278-a4fbf34c4ecd | note | Reference - MRTS03 Cl18.3
| checkpoint | Exposed surfaces of manually placed concrete to be steel-trowel finished.
98e1fbe8-0aa3-5a12-985d-be30475930a5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4d19ae02-d480-54a6-a786-d6f8f7105f17 | note | Check Item - Check Item
db613d23-1e05-5bfe-bac2-a83a6fa802ad | note | Reference - MRTS03 Cl18.3
| checkpoint | Expansion Joints shall be installed at regular intervals not exceeding 20m. The joints shall have a compressible packing with maximum thickness of 6mm covering the full cross section.
e42385bd-7ffc-51f6-9034-87caa6409b65 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4270b8e0-3f02-5950-b87d-59a4455ab035 | note | Check Item - Check Item
696867b3-f9c3-5700-bbf8-efb9da4e7a34 | note | Reference - MRTS03 Cl18.3
| checkpoint | Contraction Joints shall be installed at regular intervals not exceeding 5m. They shall be constructed be forming grooves 40mm deep and not more that 6mm wide.
cd88e3a4-bbc1-5616-aa3d-e40a7376e200 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4777078f-d0fa-59ca-a668-d0e00048ef59 | note | Check Item - Check Item
620502c5-68d3-5f1b-8c5c-d0ffc3065f9d | note | Reference - MRTS03 Cl18.3
| checkpoint | Concrete shall be cured at least 7 days before any other roadworks operations are carried out adjacent to the kerb / channel.
2ffcb4c1-91bc-5264-8c3d-7b2530836c7e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fb675718-3855-5472-a147-fb2bf1878273 | note | Check Item - Check Item
433e4a9e-26cb-5dbb-9ae1-517bbfaa1934 | note | Reference - MRTS03 Cl18.3
| checkpoint | The Horizontal and Vertical alignments shall vary by no more than ±10mm from those specified. Alignments exhibit smooth lines. Overall dimensions are at least equal to that shown on the Drawings.
3ba75414-c222-5862-84fd-0a3b4c3df10f | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm from Drawings, 1 test per 10m (invert levels)
784139d0-c084-5ef9-b8b1-a4ef2e336bc7 | note | Check Item - Check Item
c3b54c46-76bc-5037-b6f1-4a96b6071374 | note | Reference - MRTS03 Cl18.4
| checkpoint | WATER TEST: (on channels where the longitudinal grade is less than 1%). The test carried out as soon as possible after the concrete in the channel has hardened and water shall not pond to a depth of more than 5mm
55ea93a8-4a50-5183-a76b-e0dcd4b922e8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
84b29fec-1a5c-52c6-97e0-2347709e9fbc | note | Check Item - Witness Point
082edd72-3415-5308-af17-ec5ddf046d49 | note | Reference - MRTS03 Cl18.5
| checkpoint | Final Verification
3451aa62-d848-576d-aed2-4d878fd3b7c8 | note | Project Manager Verify that the Above has been Constructed according to Specification
654f9b20-a7a0-5bf8-9267-75805919d172 | textbox | Print Name:
7212e641-ec40-537d-8f8b-b05fd9186a10 | date | Date:
4df799a0-8551-57d4-b5ef-3630232d5e5f | note | Client Verify that the Above has been Constructed according to Specification
ad2b022d-d6ac-556d-89cb-33c04441c94c | textbox | Print Name:
b28d5a62-f70f-533f-a115-b98a413793b5 | date | Date:
| signoff | Signature

## 03.27
| checklist | 03.27 - Subsoil Drains | itp | 03.27 - Subsoil Drains | b3d1a254-e5b9-4114-961c-068bf4501a2c
| section | Details
| checkpoint | Subsoil Drains constructed to appropriate dimensions, Geotextile surround and Pipe perforated with textile suround (Inspect trench prior to backfill)
ad1c200e-08d6-5440-a327-43bc8c732966 | note | Acceptance Criteria and Frequency (Project Specific) - Type B: 700x300mm Trench, 100mm Pipe - 50mm off base
ab1e13c1-ef5a-5c81-a5c2-0e42263cc796 | note | ○ Type D: 100mm Wide Trench, 40mm Strip Drain
8dcc7831-a82f-5d43-9695-9c69eb377053 | note | Check Item - Check Item
0796f484-69df-5841-a44d-cb0662a12a70 | note | Reference - MRTS03 Fig 22.1
| checkpoint | Type B subsoil drains backfilled with either 10mm/20mm drainage agregate or 20mm no fines concrete. Type D subsoil drains backfilled with either course sand or 20mm no fines concrete.
fe4a22cc-6578-5a6d-b113-47c795a27f2b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
55e0f18b-be8a-51ab-af1b-6ca362f6ef98 | note | Check Item - Check Item
a40d8616-88f1-522d-a01a-69680485dc7d | note | Reference - MRTS03 Cl22.2.5
| checkpoint | Minimum cover over strip filter drains comply with Table 22.3.1 of MRTS03 for the relevant compactor size used for construction. Hand Held Unit - 100mm, < 15 tonnes - 200mm, > 15 tonnes - 300mm
6c29ec6f-4c0c-5d0a-b49d-73a72180b377 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7d88c0a0-6216-56cb-82dd-24303282ee8c | note | Check Item - Check Item
5da413ec-060a-502b-afb5-4d7bf2f2c64c | note | Reference - MRTS03 Cl22.3
| checkpoint | Minimum grades for subsoil drains comply with Table 22.3.2 of MRTS03. Type B - 0.5%, Type D - 1.0%
ff93814e-3f48-51e0-ade0-7ff084b57e1b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8104011a-9300-5b08-923a-436c1f6382ab | note | Check Item - Check Item
9270a04f-21a4-5d4b-87ce-68ba01e3067e | note | Reference - MRTS03 Cl22.3
| checkpoint | Clean outs installed at head of all subsoil drains and at 60m intervals (Type B - pipe drain) / 50m (Type D - strip drain). Clean outs in accordance with standard drawing 1116
32cd43b8-1478-5410-8c21-c95963d3a339 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1e59ffe0-28f4-56d3-81e3-d5524bd37326 | note | Check Item - Check Item
95c7ec98-6ed7-5257-8912-95899431661b | note | Reference - MRTS03 Cl22.3, TMR SD 1116
| checkpoint | Backfill material dampened when placed in trench. Placed in 200mm layers and tamped.
189edc6c-23d1-565b-b131-d8c2683e73ab | note | Acceptance Criteria and Frequency (Project Specific) -
120ce999-ad92-5f75-b46c-e336b845bd4c | note | Check Item - Check Item
151cad01-0eac-5fa8-b3ac-80c2dbb6238a | note | Reference - MRTS03 Cl22.3
| checkpoint | Concrete outlets, surrounds ,chicken wire cones, pest proof flaps, cast iron/PVC caps, rock pitching in accordance with standard drawings.
f892dd00-9aa6-57ed-9369-6b855ec6511e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
79c84aa5-9a0e-5d2e-b47d-029b61a2a7ef | note | Check Item - Check Item
c0db0aa8-f27d-5199-a141-1cafb4e001f4 | note | Reference - MRTS03 Cl22.3, TMR SD 1116
| checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
57f44d9d-e063-56e7-bfa0-3cdfdb28022c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ad318b58-c138-55fc-8f72-38efd8d85761 | note | Check Item - Check Item
6395c350-84ef-5cb7-8caa-aadc927cb7b6 | note | Reference - MRTS03 Cl22.3, TMR SD 1116
| checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
7d9cfd7d-0184-575e-b21a-0e6fb49df31c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a320bced-78e6-5953-a5cf-ec0a6215b92a | note | Check Item - Check Item
a643e3bc-3724-57e0-9337-34baf7171736 | note | Reference - MRTS03 Cl27.4
| checkpoint | As Constructed drawings prepared / All geometric tolerance requirements met
3fc857ce-98aa-5ddd-bd9d-f4b22a9b234c | note | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
325fd4c8-12f3-5eb4-b456-a6d69fe1b986 | note | Check Item - Witness Point
| checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
e8975649-9eb4-55b0-bafe-00117cae4f80 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
285aee24-0896-5332-910d-d3859c63e555 | note | Check Item - Witness Point 4
26b96faa-9913-5390-990a-471c05d55b55 | note | Reference - MRTS03 Cl22.3
| checkpoint | Final Verification
53534733-c5d2-526d-bb03-3538b57de3f8 | note | Project Manager Verify that the Above has been Constructed according to Specification
e83f7e7a-6a61-5bea-855c-e6c73d66b4f0 | textbox | Print Name:
e53cf56f-54a8-598b-90a5-cd2a1c0ceb2b | date | Date:
cb12f9b9-2267-5b12-9e5b-c0dc56ba152a | note | Client Verify that the Above has been Constructed according to Specification
1bf0baa9-9145-54ff-8e54-cee7090fa564 | textbox | Print Name:
edcd39a6-4824-5973-90b7-2d08efed6d04 | date | Date:
| signoff | Signature

## 03.28
| checklist | 03.28 - Sheet or Strip Filter Drains | itp | 03.28 - Sheet or Strip Filter Drains | 01181507-1f8c-48b0-a14c-5d47e5858020
| section | Details
| checkpoint | Sheet filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 18mm, encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
c760f484-f8be-52fd-805b-89f198637f2b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3225ffb3-29fb-597b-b4ae-f67745a71d4b | note | Check Item - Check Item
c9543c63-d312-54d1-8811-a5fdfa4f2dde | note | Reference - MRTS03 Cl 23.2
| checkpoint | Strip filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 40mm, designed to allow the drainage of water along the drain and encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
46b216be-8da9-507b-b395-c5354523e312 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c79b40ba-1205-54d7-902e-a253fd008816 | note | Check Item - Check Item
87dbaf94-e322-5b95-baa6-3268c01dd37a | note | Reference - MRTS03 Cl 23.2
| checkpoint | The plastic core shall permit the passage of high water flows, and shall have a crush strength not less than 200kPa
0940a7ce-554f-5bfd-b5c5-5550204e7026 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cc7901c8-696e-5273-a3f8-b02a2acadab3 | note | Check Item - Check Item
726116c5-2277-5ce9-9de6-cbeb39f8642a | note | Reference - MRTS03 Cl 23.2
| checkpoint | Drainage pipes, fittings, and joining materials/procedures shall comply with the relevant requirements as specified.
51b827e7-d805-5744-99bc-66fe30ad6470 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fa5d6422-8e8d-5e1a-9bb9-4413d1a659ee | note | Check Item - Check Item
6bc22d9c-e7ba-5ed9-915e-e62640ea3e89 | note | Reference - MRTS03 Cl 23.2
| checkpoint | Concrete, where required, shall be grade N20/20 in accordance with clause 6.1
591bf22e-3878-507d-902d-2a02b1a87681 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
389c9b6c-13ae-51f2-a59e-d8539b91851c | note | Check Item - Check Item
bbc81976-944a-5d1b-9b43-bb3acd8619ab | note | Reference - MRTS03 Cl 23.2
| checkpoint | Materials shall not be exposed to heat or direct sunlight or stored directly on the ground.
d93847ae-18d5-52c2-9717-0d9e1baa3d77 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2174402c-f9bb-55a6-8f68-ca88aafa9812 | note | Check Item - Check Item
cb1cd728-6bca-54e1-92ce-7146ccc9c324 | note | Reference - MRTS03 Cl 23.3
| checkpoint | Sheet/Strip filter drains shall be constructed in the locations and in accordance with the drawings and manufacturer's recommendations.
1c952b73-0881-5884-b58f-433a764e8424 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e2ab936a-f12f-57a1-8e08-6351f7b7f227 | note | Check Item - Check Item
f0ca90a0-e709-5f16-8456-54e8e7cdcfca | note | Reference - MRTS03 Cl 23.4
| checkpoint | Where sheet filter drains are used against structures employing weepholes, the core of the drain shall have cutouts of a size and spacing recommended by the manufacturer.
f75a9b91-b4c6-54d7-a556-a0f2dd73927d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
18e575ea-b7e9-5f21-8b94-1ef9225affe7 | note | Check Item - Check Item
c1902f5a-88b9-5ac2-9c79-407d6475f9c4 | note | Reference - MRTS03 Cl 23.4
| checkpoint | Collector pipes shall be constructed to the shapes specified in the drawings and jointed in accordance with the manufacturer's recommendations.
62bf3b7f-84c4-59a8-a11e-d7876fe40e62 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3d05b17e-7b50-5d5b-8013-74f4d643116c | note | Check Item - Check Item
afe2bdb6-8dce-5a99-a62e-bfb492d6cd1e | note | Reference - MRTS03 Cl 23.4
| checkpoint | Filling around collection pipes shall be general backfill in accordance with Clause 20 of MRTS04. Fill material shall be compacted to a relative compaction not less than 97%.
cd61635e-a3f1-59cc-ad41-9c9999375ad4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e052fd19-6654-5abb-b511-4e05149a4967 | note | Check Item - Check Item
413aeaf5-e9c0-5722-b38a-92d038931b96 | note | Reference - MRTS03 Cl 23.4
| checkpoint | Concrete outlets, concrete surrounds, galvanised chicken-wire cones and pest-proof flaps shall be provided in accordance with Standard Drawing 1116.
f9f95e6b-6319-56a8-b1f3-50c246877102 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e74ab8c7-f17d-5e2e-95d5-f955f91e6f77 | note | Check Item - Check Item
2f598ad0-ce60-574c-88f8-bc9d75800668 | note | Reference - MRTS03 Cl 23.4
| checkpoint | Final Verification
f113b723-959e-5769-b67f-737f8a332407 | note | Project Manager Verify that the Above has been Constructed according to Specification
ac7b6a5f-98fd-522e-9292-1b6dc5a8e408 | textbox | Print Name:
e2ae997d-b8e6-508c-b1cd-7f51c1b61b50 | date | Date:
52d3adf0-9681-55c4-b1b9-f91f423db22a | note | Client Verify that the Above has been Constructed according to Specification
3476d98d-4eb9-5d9a-9c06-ad4c346e7474 | textbox | Print Name:
655c3f48-2b57-54fb-83d1-48ac6d71d256 | date | Date:
| signoff | Signature

## 03.41
| checklist | 03.41 - Rock Protection | itp | 03.41 - Rock Protection | f9bdb2a0-e11f-48c6-a37f-2b5ecf29d30f
| section | Details
| checkpoint | Rock complies with size requirements specified on drawings, otherwise shall be not less than 150mm and not greater than 500mm. Rock shall be well graded with not less than 50% larger than a size twice the minimum specified
6d0d6cda-f7de-58f8-bcde-c3474d0b78dd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
388a0b95-6db0-58b2-883d-4dfb4fa87c55 | note | Check Item - Check Item
6b20be6d-6acc-5f5c-a7ab-40357fcb0270 | note | Reference - MRTS03 Cl. 35.2
| checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
fc44bcae-9e5d-5a68-846e-78f4df326d6a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cead1e20-beb6-57f2-8b72-0f4de1997912 | note | Check Item - Check Item
82de12a0-6561-5c07-9d11-68056a4f6893 | note | Reference - MRTS03 Cl. 35.2
| checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
bbb71a55-f096-52ae-8c50-10147f8d4b9f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7b24cc5b-8a1b-5b5e-a5ac-1f69c8c75e3c | note | Check Item - Check Item
a63e99fb-f1f2-59ff-82d3-3062a88c6b91 | note | Reference - MRTS03 Cl. 35.3
| checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
89fedb89-050f-5482-b04b-8d40fa43bb77 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
887098b1-e11b-53dd-a594-db5be38852a5 | note | Check Item - Check Item
7a5daf02-3273-5582-beb8-deeeefaa2f17 | note | Reference - MRTS03 Cl. 35.3
| checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
255f67c4-8938-5880-838e-39fda455da61 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b14bb494-61c9-5d36-99f0-219ee7710dac | note | Check Item - Check Item
4c84708f-2f94-568e-bdcd-e9a6fe47ce9c | note | Reference - MRTS03 Cl. 35.3
| checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
14b11eb2-852f-57fb-83c5-e47aaba94502 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0ef99ef8-9b99-5078-ae07-c0470b849b28 | note | Check Item - Check Item
1e9f520b-f616-5162-8498-625a8ed4484b | note | Reference - MRTS03 Cl. 35.3
| checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
97943bac-55ad-5279-8841-c050df3e6816 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2ee3e489-552d-59e8-b1b0-17bf5ca24e49 | note | Check Item - Check Item
0f0d404b-398a-5253-8a58-bcdf8923458b | note | Reference - MRTS03 Cl. 35.3
| checkpoint | Final Verification
2b2ec93f-57b1-58cc-aab7-9c7bb2b70f16 | note | Project Manager Verify that the Above has been Constructed according to Specification
c99872ae-1de1-572e-bc96-0c2e3d283e71 | textbox | Print Name:
e3e2617b-a295-5e8e-9e9d-5d053fd579d9 | date | Date:
35162e79-9bc7-52b5-a097-370ac9d382a6 | note | Client Verify that the Above has been Constructed according to Specification
d40dcce1-501b-5662-b021-566623e88dbe | textbox | Print Name:
54b726b5-44df-5dc1-9958-b9d659d98ed5 | date | Date:
| signoff | Signature

## 04.01
| checklist | 04.01 - Clearing & Grubbing | itp | 04.01 - Clearing & Grubbing | 347fa727-1efc-4ddd-ae32-75e999adef71
| section | Details
| checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
3dd9dc98-9004-5c96-ac1a-b96c01e32889 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a1e40bf4-c06b-58cf-af46-6d7f7ef610b9 | note | Check Item - Check Item
3922b026-aa19-55ba-8f1a-e68f9fec2296 | note | Reference - MRTS04 Cl 7.2.1
| checkpoint | Tree Protection Zones installed as per Arborists recommendations
126965bd-cc26-5181-be76-ef670ad7edda | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4a3a4068-e2aa-5428-81d3-f3b1c783c5e0 | note | Check Item - Check Item
89436f80-26bc-5109-b78c-e35fdadcd739 | note | Reference - MRTS51.1 Cl 9.1
| checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
ee5edbfe-03c5-5e0d-b407-245e294ef42c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c2556bb1-f9e2-528e-94a8-e8015c6b9f77 | note | Check Item - Check Item
9d8dff4e-ae1c-55cd-9ca7-52322954acf3 | note | Reference - MRTS51.1 Cl 9.1
| checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
16eed724-724d-50b9-9671-12746f451229 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc2674dd-9230-5af9-a537-8905688b9089 | note | Check Item - Hold Point 2
bca9bce2-e397-5a41-949a-f97626da4c65 | note | Reference - MRTS04 Cl. 7.2.2
| signoff | HOLD POINT
| checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
16c7bf0e-1e5a-562a-8c27-0ade9ea05b5b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
368a4581-e640-527d-8667-e3314491d5ba | note | Check Item - Hold Point 3
85be071e-6848-5620-8513-a3f851ce7165 | note | Reference - MRTS04 Cl. 7.2.3
| signoff | HOLD POINT
| checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
b8e29a39-4369-5665-9f20-f573f4b70dd1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5621da3-3fa2-5039-b864-e9f65b6ee114 | note | Check Item - Hold Point 2
90baedd4-e496-5e12-b0f4-1e82c68ac6d9 | note | Reference - MRTS52 Cl. 7.1
| signoff | HOLD POINT
| checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
80cd5152-890f-5f43-94e3-7c6cf44050ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dee91135-52f1-521c-a117-dd9c8f02ef7d | note | Check Item - Check Item
64ecea69-d99a-5840-9470-de40c578c91b | note | Reference - MRTS04 Cl. 7.2.5
| checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
fc6318fc-5c76-516e-aad6-abab1a1d275e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
be2089ac-8686-5f84-92fb-7d183a13d218 | note | Check Item - Check Item
eea267fb-d1bb-57ff-a1d8-860d4c2cc26c | note | Reference - MRTS04 Cl. 7.2.7
| checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
14011d8f-99b1-5a41-b31e-9287fa0322da | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a77823fd-dbb3-504d-a33a-5c8a93bf9293 | note | Check Item - Check Item
f55b0130-d3db-5037-bec2-24a2deec3107 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
| checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
5cd95a74-d044-5cd7-b3e9-38ca435cc832 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1d8ab83f-7818-55fb-ab42-fe852571d513 | note | Check Item - Check Item
84d9e207-916a-5d6c-b321-dd4d1786638a | note | Reference - MRTS04.1 Cl13.1
| checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
ac606fd1-ca53-5ba6-9dd4-531cfebf73e6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
97b16364-375b-5faa-a220-362922cffb4e | note | Check Item - Check Item
27e6a8fe-da0b-5e09-aae0-bd28c0752e5e | note | Reference - MRTS04.1 Cl. 1.1
| checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
9c066d7e-46fe-557e-b76b-4b3046c4e6e7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e97e29c1-0b79-5c73-922b-4dc079c3cd86 | note | Check Item - Check Item
b5f4dc6b-c7b5-5755-8195-913d24506ee5 | note | Reference - MRTS04 Cl. 8.4.3
| checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
3cb15b11-8025-57f5-8efa-7fbe896a39ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc80d882-1e1e-540e-89d1-3f02e3cc65d5 | note | Check Item - Check Item
ff75ceae-1311-583b-8764-cb6058f3056f | note | Reference - MRTS04.1 Cl 1.4
| checkpoint | Final Verification
b61acc71-2df9-5b5b-920e-e171bdaaed83 | note | Project Manager Verify that the Above has been Constructed according to Specification
86b4f287-4bf2-5c12-adf5-0304ddb85b85 | textbox | Print Name:
e4d9e518-49f4-5c08-829e-ed1b10292dff | date | Date:
8a20e854-7e65-584a-9740-070431ae2151 | note | Client Verify that the Above has been Constructed according to Specification
9b66b5cc-203b-5993-9e26-49eef7e21064 | textbox | Print Name:
e1e9f96e-82cc-5abd-b8e9-e2e840a1788c | date | Date:
| signoff | Signature

## 04.04
| checklist | 04.04 - Ground Surface Treatment | itp | 04.04 - Ground Surface Treatment | a75b14f1-d087-414f-8eab-5b5e223294e1
| section | Details
| checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
595af5f5-9e6c-5e88-a877-3f9457b2caa7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a2671f4d-4f02-5420-888b-f22643d0ab04 | note | Check Item - Check Item
e1fd553c-daa1-54ec-97b7-86a90c9bd3c0 | note | Reference - MRTS04 Cl12.2.1.1
| checkpoint | Holes and local depresions filled with similar material and compacted in accordance with Cl15
4f02b5a5-8ad1-5c29-a42b-dc5a3cf803b2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d8914a16-b2b0-52af-99a6-6d518bc92a85 | note | Check Item - Check Item
de7286d6-8020-5b98-b246-e9e11b814b80 | note | Reference - MRTS04 Cl12.2.1.2
| checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a depth of 300mm using appropriate methods.
716e07da-8015-5d06-8df3-ba71c259a0c9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b4243325-a845-5a9b-9a06-cda02a4aee0b | note | Check Item - Check Item
238c4c43-a50b-5316-938d-9d37794780e7 | note | Reference - MRTS04 Cl12.2.1.3
| checkpoint | Construction Testing Requirements: Test Method
aaa163d0-411b-5d77-b7bb-1648e3e44d22 | note | Acceptance Criteria and Frequency (Project Specific) -
2662127c-f586-5466-be73-74785f3326de | textbox | Max. Lot Size
0743d0fe-db7e-5775-a169-fe0e1e3a0f7c | textbox | Min. Testing Frequency
e08c834a-56b0-5024-a1d6-fb19c5e9d130 | textbox | Min. No. of Tests
857f1e82-9456-599c-bb8d-3d76136c134c | note | Check Item - MRTS04
9e532f14-4d1b-5d3d-9093-412a7e656313 | note | Reference - Table A1
| checkpoint | Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
f5d01188-ef0b-588a-bdc9-8831a456ea49 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: 5000m2
8b690ade-c340-5353-89cd-1b9caf04c914 | note | ○ 1 per 500m2
03fe4036-86c9-517b-b498-a7b0f9816930 | note | ○ 1 per lot
6918118a-1d56-5c33-b450-234345644975 | note | Check Item - Check Item
f08b97b0-4bba-5d2f-9669-11bad017edff | note | Reference - Table 15.3b
| checkpoint | Final Verification
7d1f7497-f5af-5ff0-abca-d75e7853cdd1 | note | Project Manager Verify that the Above has been Constructed according to Specification
71a1d213-4a10-5fb7-9e07-aaa9f9517ad9 | textbox | Print Name:
362c8e3f-65d6-55c3-b973-ef4721122de4 | date | Date:
2b6d0143-7db2-5e04-a07e-bcc728e97eef | note | Client Verify that the Above has been Constructed according to Specification
40111999-47e1-57cd-bd64-4e688206ca23 | textbox | Print Name:
a4b8f496-821e-5964-a29c-509db0410af1 | date | Date:
| signoff | Signature

## 04.05
| checklist | 04.05 - Embankment | itp | 04.05 - Embankment | 2cc90eb6-0203-42af-99d4-428902d4288b
| section | Details
| checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
a1aa0d21-da04-5a86-b720-74f4ff9e8cc8 | textbox | General Fill Class:
16a4987e-3a90-5192-991c-6e09b624e7f2 | note | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
4014a67d-a211-5b55-8d0b-c805057af267 | note | ○ WPI< 1200, PI>= 7,
e12a5122-7867-5598-95d1-95ab52f9d125 | note | ○ % passing .075mm 15 - 30
5942d7a4-61c1-570b-9060-32d9eab7e738 | note | General fill material Class B
691e19a7-c9aa-5364-bbd5-1eb413b79088 | note | ○ 1200 < WP < 2200
cbd5e919-59d0-5d84-9e73-b565b2fddbd0 | note | General fill material Class C
cd6fa889-981d-521c-a9ac-bc9cbfc7ce0c | note | ○ 2200 < WP < 3200
de27beb7-bfec-5418-801f-077a964d7531 | note | General fill material Class D
151e4237-627b-51c9-b3c6-118de366ccee | note | ○ 3200 < WP < 4000, PI <=50
1973a3d7-5c52-59ea-8fc0-461cc1e02cf0 | note | – CBR as Specified
413051b8-8841-5299-bbe5-2cb923024907 | note | Check Item - Check Item
8fbb8599-03fe-5d57-95a4-223d295fcc0d | note | Reference - MRTS04 Cl14.3.1 Table 14.3.1
| checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
77e319d0-6648-57c6-8245-a4daa5a74e60 | note | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
c743d7f6-c623-53de-8732-6217cd71fa7f | note | Check Item - Check Item
ea01497b-6c7d-58d7-bf86-42013b6c8dd1 | note | Reference - MRTS04 Cl14.2.3
| checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
28d642cb-c6da-5393-a46f-86f0851b60e9 | note | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
92d95c17-c091-5073-b88b-d740b40c2867 | note | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
e6186743-d402-5f4b-b47d-99ae7bffb1ba | note | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
07f2a177-d5f5-556a-854a-3fc3322480af | note | Check Item - Check Item
| checkpoint | Compaction methods suitable for material type
e59863b8-8fb3-5b2b-a30c-5ae1bd2e360c | textbox | Compaction Method:
ad31bbf5-c391-551d-8f5b-8684aa7aa325 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
63889c30-3627-55af-8904-bfa1d58db7f6 | note | Check Item - Check Item
082ba57a-8c87-5d41-841f-73b0638bd865 | note | Reference - MRTS04 Cl15.2
| checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
c5df139f-9339-588d-8f4b-440fe96a63c3 | note | – General Fill 150-300mm
ffea4a3e-682b-5965-b089-e981abe00905 | note | – Fill in Water Retaining Fill 150-200mm
9313f2ef-e7ba-57b8-a58f-2e5fc5fb88ce | note | – Subgrade 100- 200mm
c7c7549e-4238-543c-b3d5-1a6232e4ce8c | note | – Backfill except Sand 100mm-100mm
e114d098-1a55-521f-bfd1-0ac89682f314 | note | – Sand 150-300mm
86c885c8-a7b8-54e0-a957-17885052986b | note | Acceptance Criteria and Frequency (Project Specific) - RDD%
8f6aa05d-e025-5d5d-9a3c-882d59adcb6f | note | ○ Insitu - >95%
fecba45a-3ad0-5955-9376-8ecd2a59ef1e | note | ○ Bottom of Excavations - >95%
27fb4596-31cd-52eb-a634-372cc811d3c1 | note | ○ Subgrade (A/B) - >97%
ce634243-c54f-5fc4-b3c9-5ca2b6f35c99 | note | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
bfde3b5e-f6f3-5b2b-80c6-823e0ab9f3a3 | note | ○ Road Embankment(A/B) ->95%
e0a1ebfc-3556-5c7d-ad34-add0ac1bf8c1 | note | ○ Road Embkmnt(C/D)' -90<96%
cd484fd7-c665-5a70-9413-b74d237f3399 | note | ○ Road Embkmnt(C/D)* ->95%
a8e6aaeb-a324-5fe2-b9a9-f25bbf8f2102 | note | ○ Levee Embkmnt(A/B) - >97%
6ef6244c-7641-5e8a-bbab-487d7bbd6391 | note | ○ Backfill(Sand) - >70%
5ee5fb08-cebd-5bb2-9ee2-c6440ccbe88f | note | ○ Backfill(Not Sand) - >95%
f3cb6f5f-45be-5a00-ab12-22bab56ef78b | note | ' High Rainfall Zone
53159ec8-e528-5d59-a473-fd41ad5c74ea | note | *Low Rainfall Zone
4a502050-b387-50a3-9f1c-9bf9077ef5ed | note | Check Item - Check Item
49794bc2-00b3-56ff-85bf-2dad1b55cd03 | note | Reference - MRTS04 Cl15.3
| checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
728e6de1-2ebf-5f73-af44-059cffb94d37 | textbox | Rainfall Zone:
b4d6d751-a92c-5e34-862d-b4b3769e78d7 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
c3d90473-750d-5e3b-abef-0fa3fabacb8a | note | Check Item - Check Item
0adaadbd-18aa-5019-aa7d-04ebe5ffbccb | note | Reference - MRTS04 Cl15.3
| checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
d2ff51e4-e424-57f2-87b6-7240a15e6cd0 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
f6bbdf36-6815-5e99-ac8d-55dd17f93bf6 | note | Check Item - Witness Point 4
960c8a4a-335b-5b93-8fe2-2dcb5a8ae698 | note | Reference - MRTS04 Cl15.4
| checkpoint | Geotextile placed at interchange between compaction methods
b115f93f-cef7-5e8e-9876-9e43f6354ae3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
75d799e9-4fd0-5e69-89ed-9e906dd8e4f9 | note | Check Item - Check Item
cb16144e-067c-51de-a28a-641d2a6872b8 | note | Reference - MRTS04 14.3.2
| checkpoint | Within Geometric Tolerance
498def81-b056-5339-ac0e-c5b2f7be4bd9 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
4a26e6fd-68f4-58a4-8ab9-c7e65b55ad04 | note | Check Item - Check Item
c5931352-9897-570e-a99e-458767931766 | note | Reference - MRTS04.1 Cl1.2
| checkpoint | Construction Testing Requirements: Test Method
4788f896-815e-5353-97f3-37ae66460c89 | note | Acceptance Criteria and Frequency (Project Specific) -
cb55050b-4ee0-51b7-aedf-7e7eda4213a4 | textbox | Max. Lot Size
f0e56dee-2fb2-5fc8-8076-64a8275c9469 | textbox | Min. Testing Frequency
87d9aa2f-d431-5e18-8f2d-ae45a6a82b5d | textbox | Min. No. of Tests
9619f23e-4393-54eb-8c0a-329effb22d21 | note | Check Item - MRTS04
feaf88db-8bd2-51da-9ee7-c04104cfec70 | note | Reference - Table A3
0dfaa04f-bce6-5960-ba6d-8220fae674ab | note | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
| checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
bcdcbf66-182b-51aa-9bad-fbe175d29e72 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
f0182e87-272c-5e7d-a30c-d256a30dbd8b | note | ○ 1 per 500m2/per layer
69760b4a-8ea5-544d-8bf8-73b2af7cb339 | note | ○ 4 per lot
2821a6ed-a34e-5227-b9f6-1bcb757a1b5a | note | Check Item - Check Item
cb5588f5-a489-55e5-9444-a178dad01b39 | note | Reference - Table A1
| checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
9425a27c-99c9-5bf4-a1a7-2186dcdb6afd | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
ce562955-912e-59ff-a35a-add54fe9e85f | note | ○ 1 per 500m2/per layer
0a9101b7-512f-5add-a6d7-706717126346 | note | ○ 4 per lot
86a9f1a3-24d9-5a88-b050-fa379752f266 | note | Check Item - Check Item
47cada0c-8cfa-5308-8451-a5e42367267f | note | Reference - Table A1
| checkpoint | Grading: Q103A
21b0072e-2eac-5885-9829-592d81ffa54f | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
6bc72226-f2e2-52d4-954f-3f0b3e932ecb | note | ○ 1 per 1000m2/per layer
9487b450-51d4-5332-8c3b-6d68b2046168 | note | ○ 2 per lot
3e163da9-33c4-52bc-b66c-330bb30c80d5 | note | Check Item - Check Item
16d19aa5-f99a-5cbc-8b14-b41f6b867d66 | note | Reference - Table A1
| checkpoint | Plasticity Index: Q105
80f8990c-55a2-53f9-b77c-3189e5da113a | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
0f9862d2-7f32-5929-90b1-7fbb7a24b2f7 | note | ○ 1 per 1000m2/per layer
fd004da2-b9f1-58cb-a01f-cbd94d83a35f | note | ○ 2 per lot
2f2c049c-0acf-5723-bb77-d64b12b0bf45 | note | Check Item - Check Item
9ea3d7aa-9738-574b-918b-6b86e9a2e910 | note | Reference - Table A1
| checkpoint | Stockpile Testing Requirements: Test Method
c4aae7f9-b116-5d35-bba3-45681a7b78a7 | note | Acceptance Criteria and Frequency (Project Specific) -
a20f0ac7-32c9-5cb4-a4b3-f7e0dc82715a | textbox | Max. Lot Size
a19713b5-f967-5c5d-9cab-d2e594cc2f38 | textbox | Min. Testing Frequency
ba3b382b-cdb5-5fa6-889c-0a9e700f2d24 | textbox | Min. No. of Tests
5b90e127-ccd7-58fd-bfb4-5be861f0e3c4 | note | Check Item - MRTS04
c8d68830-081e-5b30-acf7-8102ccaebb68 | note | Reference - Table A3
| checkpoint | Grading: Q103A
0f9e3b05-ede3-5480-9ff1-73c6923b5550 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
1247fa2f-bf82-5eec-b500-51a25eb6971f | note | ○ 1 per 1000m3
3bed1a33-fa5f-53a3-a0e2-993c80d61151 | note | ○ 2 per lot
37014746-cf9d-5f6b-ae3d-fe41c1586647 | note | Check Item - Check Item
fd72e2b7-c283-5bf4-9f15-87d7f2aa98c9 | note | Reference - Table A1
| checkpoint | Plasticity Index: Q105
f9cfab3e-37aa-5999-a365-666039b772cf | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
cf5ddcad-4e4b-508b-af79-e56f7cfb901b | note | ○ 1 per 1000m3
b0863e52-be88-5cab-8916-07661fa5c18f | note | ○ 2 per lot
2e328f08-2bcd-5525-b23c-aa975812f260 | note | Check Item - Check Item
a9e9c030-87cc-5cb5-b35c-5d07fe630e5e | note | Reference - Table A1
| checkpoint | Emerson Class Number: As 1289.3.8.1
6549fd0f-a9a1-564e-ab93-1263306da4af | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
b9301692-beaf-5e6d-9f8c-bbd45de37af2 | note | ○ 1 per 1000m3
1dfd2889-7d64-525f-bce5-8f337e30e77a | note | ○ 2 per lot
f7a39d57-389d-5a4d-a3c5-1764fc9b670a | note | Check Item - Check Item
3a4c0b5c-8d4c-5d8b-8b0d-93091ed6518f | note | Reference - Table A1
| checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
09bd6ffb-2063-570c-85be-c38eac4d6e9c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c4cc6bea-91ca-5a81-9e6c-979e37ae6eb1 | note | Check Item - Hold Point 8
63b9c316-5f31-5dbe-b23c-90363e840e7f | note | Reference - MRTS04 Cl. 14.2.1
| signoff | HOLD POINT
| checkpoint | Final Verification
93ad04a9-f6fc-5ec1-9d25-1e7fdb062e77 | note | Project Manager Verify that the Above has been Constructed according to Specification
48e86a15-16ef-57ed-b8ec-a9d95f4baaa9 | textbox | Print Name:
768044fd-e4dd-5c2e-96e0-b058bc1a6339 | date | Date:
86504da8-55f1-5e68-95d1-a42c1d924e21 | note | Client Verify that the Above has been Constructed according to Specification
bb4f9919-df4b-5465-ba7c-b641a7a88eff | textbox | Print Name:
1725b43c-54ba-5b81-bb81-6e849b49b042 | date | Date:
| signoff | Signature

## 04.06
| checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation | 9799bde9-0abe-4294-a42c-baf0fe4bf412
| section | Details
| checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
68b23b0b-65b6-5f83-88d6-2d6111cadbe9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bf31d91b-8b3c-50b4-9432-d613e101d77f | note | Check Item - Hold Point 4
1b821854-3e12-5262-bc70-f9e3a75be518 | note | Reference - MRTS04 Cl. 9.4
| signoff | HOLD POINT
| checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
b79117ed-1569-545a-a1de-f66c09258a49 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
e089c10f-bb65-5e7c-8e57-d7ccd540c132 | note | Check Item - Hold Point 6
0d2f7054-5062-5bba-8be8-842b76408ea1 | note | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
| signoff | HOLD POINT
| checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
d9dd488c-7c42-522e-8bde-79228247f1f0 | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
ddd7d3c2-9551-5525-ad91-a0150721bee1 | note | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
b59356e7-3236-50ba-8b14-a9e114114db4 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
8848a95c-c27d-536f-81e9-c907c73b855b | note | Check Item - Hold Point 6
fb10fb17-596c-5bb4-a1f7-2170cac61794 | note | Reference - MRTS04 Cl.13.3.2.2
| signoff | HOLD POINT
| checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
6e85e54a-d234-5c6a-ab34-325f84132ea1 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
7d9365e4-8213-5d97-821e-103ab3647cff | note | Check Item - Check Item
677c9b38-4a3e-54ac-8332-8ab55fbf45ed | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
| checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
8a1c0a6c-4bed-5d6a-8ca3-7d5b2dbb84b8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d9e617d4-71b4-54e6-80f8-fafaa447370e | note | Check Item - Check Item
f251b915-4bbf-5767-b50c-9b9e28c4ab63 | note | Reference - MRTS04 Cl. 13.3.3.3
| checkpoint | Dewatering of excavations shall comply with requirements of EMP
d733ac0c-7b90-5d80-8450-7eab3828a951 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e372974b-d385-5389-907e-401a929fad6a | note | Check Item - Check Item
071f703e-6b28-51fa-b452-86cf45b79e71 | note | Reference - MRTS04 Cl. 13.3.8
| checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
0ed5e209-5418-5a5c-bde6-fa2b37ab771d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5f6aec55-0876-51a2-91a0-f861c6e67e6a | note | Check Item - Check Item
8ee60e6d-396f-51cf-aaac-389e4245cf2b | note | Reference - MRTS04 Cl. 16.1
| checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
5675d067-1af4-5d14-a14f-c1877fce1e80 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e1b9a86b-b8fc-57bf-8b93-aa9f891975b8 | note | Check Item - Check Item
57e568f1-1344-593a-8b66-d693e44a84c3 | note | Reference - MRTS04 Cl. 13.3.2.4
| checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
86cade6a-ab80-5919-b8df-5e3717092c6b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3cfb98a9-60a4-57bc-9f91-5974bb4087f6 | note | Check Item - Check Item
95680249-fb8d-5e7c-a4c0-e9f97e9d055c | note | Reference - MRTS04 Cl. 13.3.3.1
| checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
bd626daa-cfc1-5e9f-804c-7ebf77793a79 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f0915ff0-9737-5a3e-bb18-fe86d89ad5cd | note | Check Item - Check Item
5d1ac3ae-3b3e-5e18-bd22-a7ad37a4274e | note | Reference - MRTS04 Cl. 13.3.3.2
| checkpoint | Final Verification
662150f9-f138-5e7b-b45d-1069a5e608e6 | note | Project Manager Verify that the Above has been Constructed according to Specification
c4a97108-a83d-5497-90f4-e92d2192c1bb | textbox | Print Name:
26a2a4f9-3376-5797-a9dc-d1183e9fd114 | date | Date:
3adcb239-3b5f-5dc5-ad2f-2f5e8d83e983 | note | Client Verify that the Above has been Constructed according to Specification
907123fa-62aa-50b3-b323-01c3b7ab9579 | textbox | Print Name:
97393ec7-b5c2-5948-8d0d-30efe38ea4b7 | date | Date:
| signoff | Signature

## 04.07
| checklist | 04.07 - Structure Excavation (Unsuitable) | itp | 04.07 - Structure Excavation (Unsuitable) | ba1e7f64-c043-4a23-8cfe-5c3aea70a31f
| section | Details
| checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or pottentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
b2b9c0e4-8d57-53fe-95e7-2e5d255482f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15e43e41-f5b6-591a-afef-f18d3dbf2140 | note | Check Item - Hold Point 4
15009b5b-8a06-56b1-bfed-fa56a7dc4800 | note | Reference - MRTS04 Cl9.4
| signoff | HOLD POINT
| checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
e89f433f-9307-5824-a035-3c61bd4f42a8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c41f65ec-499d-5848-9587-17c765c67fed | note | Check Item - Hold Point 5
a515d902-3b3e-528e-9bc5-4f444d47d5c5 | note | Reference - MRTS04 Cl10.
| signoff | HOLD POINT
| checkpoint | Where shown on the drawings or specified elsewhere, a layer of blinding concrete shall be placed over the foundation material as soon as practical. The top surface of the blinding concrete shall be screeded neatly to the shape and levels shown on the drawings
46285dc2-4a74-58e8-8a66-cbe78992fdfa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
24440c51-4534-5ffa-9af0-95a84ced2e94 | note | Check Item - Check Item
ab8371bc-3582-53f2-a5b5-18d2fa453a78 | note | Reference - MRTS04 Cl13.3.4.1
| checkpoint | The widths of excavations for culverts shall be the minimum necessary for their construction and placement of backfill against them, provided that nowhere shall such widths be more than those shown on standard drawings 1359.
a8121e46-26ca-5284-9dad-86bdaff593cd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f8e3200e-4b1b-5c42-b387-d6c3682c8d9f | note | Check Item - Check Item
b1527d0c-8033-59bb-9cc6-457c479dda5f | note | Reference - MRTS04 Cl13.3.6
| checkpoint | The material in the bottom of excavations shall comply with the density requirements of Clause 15 and compacted to a depth of at least 150mm.
5271f035-8b4f-54f1-a679-38e460c76eb3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3c740341-e9a8-54d8-804d-a66777bc1c62 | note | Check Item - Check Item
2799b328-8bfc-5f01-a1a1-aff1b071c47f | note | Reference - MRTS04 Cl13.3.6
| checkpoint | Compaction: Q140A, Bottom of excavations = 95%
2cc43152-7fcf-58c7-ae3a-d1d354865c17 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: each culvert or end structure
044ae034-b9e4-5653-8970-485a734be095 | note | ○ Min. Test Frequency: 1 per 50m2
3ab28f71-f853-57e8-8c79-f313d0e16512 | note | ○ Min. no of Tests: 2 per lot
7c25f12d-d4a6-508d-9041-6227f00067fc | note | Check Item - Check Item
c5d95a5a-f6a0-581c-8406-5f4e3d69885e | note | Reference - Table A2 No. 2.6
| checkpoint | Supplementary Requirements as per Clause 22 MRTS04. The material used in backfilling unsuitable material excavations, in addition to the requirements specified in Clause 18.3.4.2 of MRTS04, shall satisfy the minimum CBR requirements of Clause 3 of this annexure.
f9112143-e826-5aa2-9394-8a3a2d2257bf | note | Acceptance Criteria and Frequency (Project Specific) - Testing requirements
1dc48a5a-b38e-5379-84e4-755d4ce181eb | note | Check Item - Check Item
2052d3bc-f81c-548d-931e-9d4b71b47c63 | note | Reference - MRTS04.1 Cl. 13
| checkpoint | No areas on Site are available for the disposal of excess and Unsuitable Material. If no areas are indicated, all such material shall be removed from the Site
7e189bc3-7d0a-5bcf-9b05-12a79d187c30 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4834d80e-a9b7-52d2-a852-63f3f56802bb | note | Check Item - Check Item
bd155164-1f92-5485-82b2-9378620e5b8a | note | Reference - MRTS04.1 Cl. 5
| checkpoint | Final Verification
b63d961c-f52a-50c6-8700-6bdcca893b2c | note | Project Manager Verify that the Above has been Constructed according to Specification
b81c3b21-6bad-5732-860f-e0a1c284bf44 | textbox | Print Name:
8cff5bdb-b805-5342-b039-fd272a7b267b | date | Date:
e5b62619-42f7-528a-9c20-2d3f05d4f7ae | note | Client Verify that the Above has been Constructed according to Specification
167129e6-57aa-55f5-aff6-2fdd064c750c | textbox | Print Name:
b25b443d-ef80-56e5-b5a0-296839ed3423 | date | Date:
| signoff | Signature

## 04.08
| checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil | bdb2fc37-3ead-4226-a310-8804c0cc3a39
| section | Details
| checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
e6d89158-b8c2-5d33-b029-474853144d97 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7b8e3b5f-f95a-519d-9d02-08fa8d4e461d | note | Check Item - Check Item
12b8ac0b-e5ab-56a5-9788-b2eb0025723b | note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
| checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
933b3fea-f889-5d0d-bc75-c01ea0fa4aa3 | note | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
598acc21-c490-5914-a349-f935e36e0603 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
b639b10e-3277-501b-a4d6-be933f1ba42b | note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
239f20d1-129a-5ffb-8412-9b4f894afefa | note | Check Item - Check Item
34675555-1f83-50d7-a667-b8ec9f9c8334 | note | Reference - MRTS04 Cl. 8.3
| checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
e01f5c60-3bf3-5d6e-af58-58e24f63edae | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
2554794d-f7eb-5559-9777-59aa9d312057 | note | Check Item - Check Item
6190ebe4-115d-5d5d-8569-8df257d5cf3d | note | Reference - MRTS04.1 Cl. Cl. 5
| checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
0bde2e1e-4418-5caf-bd8c-094f5239d417 | note | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
b503fffb-e27e-523f-b6f2-2683c45fd83e | note | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
2778dbec-bad7-58ce-9422-9e02f7cd5d03 | note | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
02d265ed-acc2-5cc6-91ca-3fc51a8be009 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
dbaf4b49-4a99-5327-9bab-0d2354d576a5 | note | Check Item - Hold Point
13c6c313-4c1d-5b2e-91d4-407bed9ff0be | note | Reference - MRTS04.1 Cl. 2.2
| signoff | HOLD POINT
| checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
02b215bf-d6ae-5cb5-a2d7-a1ea62b1779c | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
aabee7d6-e922-5aea-98ff-655e184703ed | note | Check Item - Hold Point
ed28e0f2-44db-536b-8910-324cea54d87f | note | Reference - MRTS04 Cl. 8.4.3
| signoff | HOLD POINT
| checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
974987ac-0f80-5540-98ec-3e8eeecf7464 | note | Topsoil Stockpiles are;
9e12a158-c15a-5a19-b182-61d068b6fb46 | note | ○ Less than 3m High
7f4b99fa-9594-5468-85d5-5896f845993d | note | ○ Less than 10m wide
f580bf5c-f5c3-50a3-9ad6-ea8662afff05 | note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
aaac51e4-aa0b-5453-b8f6-f7d6ee210a46 | note | ○ Stockpiled for the minimum duration
19151f61-3b09-5042-8b0e-4b93cadabe84 | note | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
f6f7a820-5a4a-53c8-9e36-6cb5a0f24780 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b285871c-f280-5216-bf9c-d1c56634137e | note | Check Item - Check Item
3a1e3afa-a0c5-59f7-ac85-c74a82d13a57 | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
| checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
0d66b0a9-d10c-5af4-abd9-1b0e51ae69d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8d63ee9c-6b5c-5f7a-a6c3-13869114865f | note | Check Item - Hold Point 2
edf0bf19-7a4c-598f-acaf-768d733d847b | note | Reference - MRTS52 Cl. 7.1
| signoff | HOLD POINT
| checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
d4286122-40af-5285-9214-232bb9a1cf99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c5075f31-8234-5f49-b013-11f993a6f391 | note | Check Item - Check Item
e549a47f-eb9b-581b-bcb7-24cdbfb766d8 | note | Reference - MRTS04 Cl 8.4.5
| checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
7be29b6a-799c-58a0-8878-056750f9bb2a | note | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
70482b47-3439-55cf-93f4-20cb1878578f | note | Check Item - Survey Report
98507c1b-6d8e-532e-813c-d934bdd5cc82 | note | Reference - MRTS04 Cl 8.4.5
| checkpoint | Final Verification
be7ccd43-a4df-5815-9b26-7c5dab810777 | note | Project Manager Verify that the Above has been Constructed according to Specification
d27219d6-c765-5545-a57b-2e3778bf9603 | textbox | Print Name:
dc89ffc2-4edd-512c-9919-fe1183841d99 | date | Date:
7902f7ce-c22f-55da-9be1-65205f117d91 | note | Client Verify that the Above has been Constructed according to Specification
90c55ba0-1af8-52d9-8047-ca36d9e02a75 | textbox | Print Name:
a2a09728-3fdf-59fc-a0a1-1cf877eddc4d | date | Date:
| signoff | Signature

## 04.10
| checklist | 04.10 - Backfill | itp | 04.10 - Backfill | 8222edf3-bf16-4708-83f6-c954ef9ea809
| section | Details
| checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
94d1eb5a-787a-5e4d-b639-74c95382655c | note | Acceptance Criteria and Frequency (Project Specific) - Written
05646d9c-d471-56f5-89f2-15139e8bd3a4 | note | Check Item - Hold Point 11
13eee10b-3f27-5294-8c27-c134499ab5e4 | note | Reference - MRTS04 Cl19.1
| signoff | HOLD POINT
| checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
3b83419e-004b-5b05-be1e-42ca03587fcc | note | Acceptance Criteria and Frequency (Project Specific) - Grading
54d31915-0210-5413-94e7-496b58dbd9f9 | note | Check Item - Witness Point 6
213232a9-5063-53c7-bf3d-68692ec9a716 | note | Reference - MRTS04 Cl19.2.2, Cl19.3.1
| checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
df49e4f5-b84f-5285-9403-4e5666b1dd3a | note | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
a99b3371-ec51-5cd6-83e7-7973e80f873a | note | Check Item - Check Item
6219b883-a930-5cac-a497-732beda4c2da | note | Reference - MRTS04 Cl19.3.1
| checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
ca973dd6-cbc5-578c-b699-8d8c716bcd50 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7c8059f1-7328-5229-a3e7-8748ed957a8d | note | Check Item - Hold Point 12
a44e1bff-a000-5f6e-881b-68951420c702 | note | Reference - MRTS04 Cl19.3.3
| signoff | HOLD POINT
| checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
8c61f25d-156a-53cb-89f0-613de2ab27cd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8fdedbb6-248a-5443-b51b-3a14d7dc4846 | note | Check Item - Check Item
e2b184e8-82f1-5818-979e-2b25e53d3a46 | note | Reference - MRTS04 Cl19.3.3
| checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
c5a86cbb-ed15-5d91-9c8c-0b7d99cebd09 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
80dd2986-69c3-56ee-9dc2-fb6ea62c74b7 | note | Check Item - Check Item
03dd0bef-5c71-5260-a551-5f9dc0156418 | note | Reference - MRTS04 Cl19.3.4
| checkpoint | Construction Testing Requirements: Test Method
0ed667cb-5b6d-5c80-b65e-87801a7bc2f6 | note | Acceptance Criteria and Frequency (Project Specific) -
174506e6-efa9-5032-b760-491699553b3b | textbox | Max. Lot Size
ae9e509c-2d49-509a-806b-f1e0ae2595a6 | textbox | Min. Testing Frequency
da53c570-8c92-54b0-b0f8-c8c5f636c71e | textbox | Min. No. of Tests
b1eba52c-c94d-5e87-934a-ef36d78bfe9e | note | Check Item - MRTS04
e5de6205-cc64-5789-839d-a1ccd9d74c5c | note | Reference - Table A3
| checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
24b5bed8-8b89-5915-aa84-59eb827d94f6 | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
48c66d8c-a5ae-5073-83a9-5a065eaecf40 | note | ○ 1 per 100m3
bff77ce7-4910-5718-a96a-a46827e13fdc | note | ○ 2 per lot
16704d1c-5b1d-59db-8305-2b37f5ae0f0e | note | Check Item - Check Item
4c3969aa-811b-5eae-8398-d07d9ce1b2ad | note | Reference - Table A1
| checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
ab9ed9dc-eb07-56aa-a927-2d5f2f7b6d0b | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
b11a6336-5f15-530c-a40a-489bdcd36db6 | note | ○ 1 per 100m3
2cd6b36e-5a0e-5d13-8ca5-129b5714cd62 | note | ○ 2 per lot
ae612dfb-e946-56be-81ad-c32c076e1dea | note | Check Item - Check Item
3927f1ea-9fcb-5d7b-890d-e95bff91d8cd | note | Reference - Table A1
| checkpoint | Stockpile Testing Requirements: Test Method
2ba0fa9b-b485-53ee-8f8c-18bf4c4af975 | note | Acceptance Criteria and Frequency (Project Specific) -
13826a42-530f-549e-8e3b-df3555615c9a | textbox | Min. Testing Frequency:
86a35aee-f217-56c9-84c8-4bfa0fcb9076 | textbox | Quarry Source
1f553e07-3446-5566-ab96-aa402fe17122 | textbox | Other Source
8f9e38cf-595c-5132-b494-4deacfc90858 | note | Check Item - MRTS04
90f4af0e-8a97-5fa9-a728-0aba6862cffa | note | Reference - Table A3
| checkpoint | Grading
3dd62a88-8768-58da-9811-a3ffc2a580e6 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
828dedc7-e21a-5dc0-9381-0f9cf34d3e3c | note | Check Item - Check Item
b24cd711-3a20-51f9-b59a-3047eee7d4bd | note | Reference - Table A1
| checkpoint | Plasticity Index
4c48843e-7c1b-54d7-bef8-218e518d0ee3 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
5997f007-1b46-5219-b85c-08eceeb6dc93 | note | Check Item - Check Item
3c96f12c-1ea3-5ac5-a474-732a62271a60 | note | Reference - Table A1
| checkpoint | Linear Shrinkage
59fc8d9a-846b-5696-86ac-93110f45bfee | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
8a770d43-f437-5922-abf5-449a33629c7b | note | Check Item - Check Item
17c0f3ee-789b-55cf-8fd7-ff781350ad91 | note | Reference - Table A1
| checkpoint | Emerson Class Number: AS 1289.3.8.1
16bd2482-bf58-5a10-bbcb-f1944a6f398e | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
11de5da9-c9a9-508e-91ca-33375b42a049 | note | Check Item - Check Item
0c700686-4e69-5a11-9408-b8581c33bd0b | note | Reference - Table A1
| checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
78ec5edd-db47-5b7a-954c-b77e4a08a6b7 | note | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
3bc68593-afb0-5926-a094-f447a756e218 | note | Check Item - Check Item
bf792c76-156f-53df-8004-a9e77c3dd827 | note | Reference - Table A1
| checkpoint | Final Verification
932d79ba-7323-5ad6-b2be-b0bbca3c2171 | note | Project Manager Verify that the Above has been Constructed according to Specification
b46d1c87-56c1-5050-b307-61968f99193a | textbox | Print Name:
3ad9fcab-4dd9-5a2c-8bcd-fbdd4b98759e | date | Date:
db5ccf17-17fd-5a17-8fab-fee7e1e38121 | note | Client Verify that the Above has been Constructed according to Specification
b314368b-20a0-5d48-b033-b17f5a848179 | textbox | Print Name:
275c628c-b7b8-5923-b327-e653b9e5fa6c | date | Date:
| signoff | Signature

## 04.11
| checklist | 04.11 - Demolition of Road Furniture | itp | 04.11 - Demolition of Road Furniture | 1ed88023-bd70-4c17-a607-58a6fc86af62
| section | Details
| checkpoint | Road furniture to be removed are as listed in MRTS14.1.
b6e06540-c4b4-5f7e-a1b6-0a5168c86f24 | note | Check Item - Check Item
fed17806-9243-5af6-8236-e766e93e8f35 | note | Reference - MRTS14.1
| checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
ddc9927b-821b-50cb-9060-1f152cefe383 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32c9c5b9-87d9-59da-a5eb-38276d2f8e89 | note | Check Item - Check Item
07afacb9-62a6-51e2-b784-9ee7f683b7e1 | note | Reference - MRTS14 Cl.7.3
| checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
2658c603-778b-5cc1-a28c-2abab94c0265 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b2df8a78-366c-513e-ac6f-6bdbb0ad15be | note | Check Item - Check Item
adb60bfe-a1bb-5d55-8e29-e98ff032e057 | note | Reference - MRTS14 Cl.7.3
| checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
1057cf79-a6c6-59fd-a905-7fcc383b7b64 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8a080751-d533-598a-97b4-fd7d9715943f | note | Check Item - Milestone
b69d9395-02e6-5881-9104-3db3bbb36fa0 | note | Reference - MRTS14 Cl.7.3
| checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
7db3b729-5ed6-57f7-b0e5-e04bbd6e0c1c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
57b3f406-6c4f-5a68-93d5-ee36e38d91bc | note | Check Item - Hold Point 2
4361c49a-33e0-5770-82cc-aa04c90e0841 | note | Reference - MRTS14 Cl.9
| signoff | HOLD POINT
| checkpoint | Final Verification
bd0ea02d-6c30-5946-9892-d0b3c2fb5009 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
c5958301-2094-5285-a0ea-91a36598cdd3 | textbox | Print Name:
cf974ac5-9db7-5bfe-8173-94243cf84ded | date | Date:
29f96107-0865-5025-88e5-353842d59cde | note | Project Manager Verify that the Above has been Constructed according to Specification
f5c8eeb0-8a0c-5454-814e-9ba08e0d89e9 | textbox | Print Name:
1f108189-451a-5cdc-8068-351393920515 | date | Date:
| signoff | Signature

## 04.18
| checklist | 04.18 - Subgrade Testing | itp | 04.18 - Subgrade Testing | 897e351e-d717-49bf-9228-093a564ee0fe
| section | Details
| checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
d5c6d92e-bee0-5812-aba9-624e75c6fe17 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
693415dc-53c7-5f1e-9f3f-ea3c1d175e50 | note | Check Item - Witness Point 5
d04330d5-e80f-55fb-b615-b2f77028ce6e | note | Reference - MRTS04 Appendix B.3
| checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
2d3960d4-9af9-5a1e-b324-5590fcf368ca | note | Acceptance Criteria and Frequency (Project Specific) - Testing
3cf93129-8c1e-5523-9481-2252796f4959 | note | ○ 1.5m below subgrade in CUT
f74206f0-b8c3-51a8-b81f-4ad8f52cd632 | note | ○ 2.0m below subgrade in EMBANKMENT
4f3e038f-9a34-5131-a447-2f549142d8eb | note | Check Item - Check Item
842e2c53-77df-5779-a931-66a6706a5465 | note | Reference - MRTS04 Appendix B.3
| checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with RMS Test Method T103
c3621f2d-3975-5eb0-8d38-f4726495fd4c | note | Acceptance Criteria and Frequency (Project Specific) - Testing
5fe48adf-1f2e-52c3-8e17-49ada7e4483d | note | Check Item - Check Item
105a4501-242f-5b11-a70a-6a50ac2cf356 | note | Reference - MRTS04 Appendix B.3.1
| checkpoint | Fill Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include: – Lab preconditioning, – Field compaction using construction methods propsed for the works. The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5.
f8a26221-4f6c-5caa-af82-21144266adb4 | note | Acceptance Criteria and Frequency (Project Specific) - Pre-Conditioning
3d5288f8-ca9e-5162-8ad9-693ad205a2fa | note | Check Item - Check Item
5d4f8d17-3d87-5817-85ac-22e0c0bbc102 | note | Reference - MRTS04 Appendix B.4
| checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
58720a5a-a4f2-5c33-95f5-18af8877ad84 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports
e45d36fb-8933-5c67-b645-02db1e8c0634 | note | Check Item - Check Item
0d2f1377-aa44-5281-a3fc-71aaf60dbaf3 | note | Reference - MRTS04 Cl. B3.2.2
| checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
c929fa17-1118-5f26-8594-f056e53d1f19 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bd969b27-93cb-5350-b6f2-c67102e2ad86 | note | Check Item - Witness Point 6
848a1a1c-8c6a-5792-9e03-f3931b503c96 | note | Reference - MRTS04 Appendix B.4
| checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
3b837d98-ecc9-5927-a885-1385f923a808 | note | Acceptance Criteria and Frequency (Project Specific) - Testing per material type
b259e00a-9da3-532a-a8e8-8a8139a15960 | note | Check Item - Check Item
865d5abf-dbf9-5d9e-8bd5-570a9421b4cb | note | Reference - MRTS04 Cl. B.4 & MRTS04.1 Cl 3
| checkpoint | Final Verification
9a5a0b88-c118-53d7-846a-dd63e27b97c2 | note | Project Manager Verify that the Above has been Constructed according to Specification
a822b498-88b8-599a-95d5-7484e6b03481 | textbox | Print Name:
7d8444a8-df70-5d2d-9b41-f6c80d307043 | date | Date:
fdf695d5-60b1-571c-ac87-38e7b5841964 | note | Client Verify that the Above has been Constructed according to Specification
39320e1a-1711-547d-ae47-ac16d9f26cdb | textbox | Print Name:
98a7f351-dcaf-538a-b312-86bff1b53750 | date | Date:
| signoff | Signature

## 05.01
| checklist | 05.01 - Unbound Pavement | itp | 05.01 - Unbound Pavement | 8c9edf36-d30d-4fbf-846d-1df96b1c0ed8
| section | Details
| checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
f2a5d430-366c-55e3-b61b-f32a9e5af955 | note | Acceptance Criteria and Frequency (Project Specific) - Qty per lot
7a5f9555-46cc-5f8e-85fe-84959fe9e6fc | note | Check Item - Milestone
982a5d12-9534-557a-9494-9b28e4f29d20 | note | Reference - MRTS05 App. A Table A1
| checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
1db14d54-4658-55f2-af41-b640b0b76ca8 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of Registration Certificate per quarry
76f50598-7aba-5ea7-81fe-2b2652ff28b1 | note | Check Item - Milestone
da8de415-34a5-5a53-b71f-0399f2b4deba | note | Reference - MRTS05 Cl.6.2
| checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator
7a0ec204-65a6-5267-926a-742bd946797a | note | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
dee01ee2-02df-59f0-ba57-a8553feb23ba | note | Check Item - Hold Point 1
bd8e45ba-1d29-59ae-acf3-ef768a3f9aaa | note | Reference - MRTS05 Cl 5.2.1
| signoff | HOLD POINT
| checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
b69cedb2-af7d-583c-86c6-c6349ea78d76 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of production procedure
042fde6b-2c38-5665-9bad-489f3f2a38a2 | note | Check Item - Milestone
742b7e10-f5ef-55ee-b762-7492cc70ab55 | note | Reference - MRTS05 CL 5.2.2
| checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works
18a25104-7808-50c1-b5a6-0631f4f7bceb | note | Acceptance Criteria and Frequency (Project Specific) - Written Permission from Administrator
9b338f5e-3e48-5f01-8d3d-58aada94cb0d | note | Check Item - Hold Point 2
2e24606f-0a96-5f4a-9d30-773640930f9d | note | Reference - MRTS05 Cl.6.1
| signoff | HOLD POINT
| checkpoint | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
0f1bfc18-2b7f-57c5-a54f-7bac5fb1998f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d4b58dff-8e3a-54aa-a2c6-73a587c98999 | note | ○ Layer Thickness: 75mm - 250mm
f645ee39-620b-5781-a06a-41f011a579dd | note | Check Item - Check Item
75fc0db4-e628-5e75-8021-13e94e9875ff | note | Reference - MRTS05 Table 8.3.3
| checkpoint | Relative Dry Density Requirements: C.V of RDD >= 100% MDD for Type 1 Materials, = 100% SDD for type 2.3, 2.4 and 2.5
1c848720-599e-5a9b-b15c-12aedc00943e | note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD (1 test / 500m2, min 1 / production day, min 4 per lot)
f8c06bf9-ab44-515b-9f32-4da2661cdf6e | note | Check Item - Check Item
868eea88-f5ab-545b-95f3-d648133f9119 | note | Reference - MRTS05 Table 8.4.3
| checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
82e61acd-eb83-5414-b343-851d59ba27b3 | note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
75ec01ee-27c8-5433-bca9-eaaaab920001 | note | Check Item - HOLD POINT 3
de960dc9-8a9d-53cd-8460-86b3834c65e7 | note | Reference - MRTS05 Cl. 8.2
| signoff | HOLD POINT
| checkpoint | Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
482e448d-4be9-5c01-a8dd-37d15cb3bb8c | note | Acceptance Criteria and Frequency (Project Specific) - S < 60% (1 test / 500m2, min 4 / lot)
9d931edb-6897-58a1-9569-c9c26185d41a | note | Check Item - HOLD POINT 4
9bec60bd-c584-5d0a-9fdb-e4c297d5a056 | note | Reference - MRTS05 Table 8.3.4.1
| signoff | HOLD POINT
| checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
ba2a2561-4f99-5ec9-8b0a-8fdf75a8d720 | note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
45d218cf-2af8-5469-a5ef-e5f266d16b71 | note | ○ Additional tests as directed by the Administrator
5f59186c-b946-5199-96ec-bd2bb1cb24aa | note | Check Item - Check Item
197e4e4a-9077-54f3-96ce-cc0a11d1f7a6 | note | Reference - MRTS05 Table A3
| checkpoint | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
e4451af1-5aa2-59ff-8f51-2099a7dec458 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
768b6d8c-e2ae-5264-97f6-b3d6ab8efe3c | note | ○ ±15 mm in all other cases (1 test / 20m)
15e70f8a-c223-509d-b6cf-2171670588f4 | note | Check Item - Check Item
d83c730b-e285-53db-b5f5-534d165b42e9 | note | Reference - MRTS05.1 Cl.8.4.4.3
| checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
37d915d6-32d3-5e59-9cf1-96f55a76553f | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
186e40b2-52b2-5050-ae40-413b7d5fb2e1 | note | Check Item - Check Item
b3fac0e2-2873-5ac4-8b6b-6b2c8f3fe5d4 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
| checkpoint | Deviation from a 3m straight edge shall be less than 5mm.
91ed184b-a0ba-5bbf-90b5-285d7c450f17 | note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
b057f188-d1c8-5bb5-a76f-8404912c4416 | note | ○ Less than 5mm
879adebe-cce2-5a41-b97b-6f4d256ecade | note | ○ 1 test per 20m
204566b8-04f9-5bba-84f5-a6c850fa8209 | note | Check Item - Check Item
3ed16498-3214-5080-a5a2-159b34547749 | note | Reference - MRTS05 Cl. 8.4.5
| checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
1a420e5e-1a4f-5387-a786-f4b998a85e10 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
dc15db05-b287-5dbe-be27-b0cf12656d7e | note | Check Item - Witness Point
7d7ec734-bf96-5feb-bddd-f4ce4d252973 | note | Reference - MRTS05 Cl.9.4.7
| checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
bb65589b-4098-5553-a580-b5938e409eab | note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
42815a47-f3b4-547b-aeec-c7353a89902a | note | Check Item - Check Item
b78be81e-a32b-5fc0-a4fb-a5ceb365c0bc | note | Reference - MRTS05 Cl.8.4.4.4
| checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the administrator for acceptance. Roughness shall be less than 2.31m/km.
a66046f0-70da-5c8e-9cdd-aeec3c127a45 | note | Acceptance Criteria and Frequency (Project Specific) - Less than 2.31m/km, 1 test per 500m
0de4713d-8871-5703-9eea-bfec8eb69d12 | note | Check Item - Check Item
187d9e4b-d163-54b1-8e56-d6a9870af365 | note | Reference - MRTS05 Cl.8.4.6
| checkpoint | The finished surface of any unbound pavement layer shall: – be hard and homogenous in apperance, – not have any loose, segregated or contaminated areas, – have the coarse particles slightly exposed, – not be affected by delamination, and, – not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
70675c6e-2b84-5fc2-8a3a-f4c408470b34 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b620aead-43bb-53f1-acf4-452fd751da2d | note | Check Item - Check Item
2f941501-87c2-59ef-98b3-5fd3aa53567c | note | Reference - MRTS05 Cl.8.3.5.1
| checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
a76d1e76-cf28-533a-b9ef-53347814febd | note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
609554ae-1d1d-530d-b701-098712b85a10 | note | Check Item - Hold Point 5
1780a408-bd6b-5549-bd65-e0cb321f2b2a | note | Reference - MRTS05 Cl.9.1
| signoff | HOLD POINT
| checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed, b) the surface finish of the layer complies with the requirements of Clause 8.3.5, c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator, d) the layer has been presented to the Administrator for inspection, and, e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
898f28ab-cec9-5acb-8e8f-76b8bc56aa67 | note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
82edeb68-327a-5f4c-b944-8922d1877950 | note | Check Item - Hold Point 6
b0567f91-1170-53dd-ab1b-8722fb0b9c05 | note | Reference - MRTS05 Cl.9.5.1
| signoff | HOLD POINT
| checkpoint | Final Verification
0e93c6a4-9760-5adf-b762-d2f42170c8c0 | note | Project Manager Verify that the Above has been Constructed according to Specification
fa7ee7ff-7e57-52e6-85c0-747977f459b0 | textbox | Print Name:
b9f12ad4-5074-5833-85aa-935a07422409 | date | Date:
f6ee7a8c-272f-5185-a8fd-326bc16784b0 | note | Client Verify that the Above has been Constructed according to Specification
fec325f7-8df5-5b1b-9f6d-c99412708778 | textbox | Print Name:
749ceb92-8a38-510f-9de0-578fffb21f5e | date | Date:
| signoff | Signature

## 10.01
| checklist | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | itp | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | e68c583e-c5c4-4cf4-bb26-48a3900144c3
| section | Details
| checkpoint | No lightly bound pavement works commenced until all relevant construction procedures have been accepted by the Administrator.
93524386-75f1-58ac-a2e4-f4c00dda7016 | note | Acceptance Criteria and Frequency (Project Specific) - Written
2a04dff7-a8ce-5cf6-a6d0-86255adfd9c1 | note | Check Item - HOLD POINT 1, Milestone
1c78d82b-b746-50cb-b7a9-95250a5d0d52 | note | Reference - Clause 5.2 MRTS10
| signoff | HOLD POINT
| checkpoint | Lightly Bound Pavement Constution Procedure submitted to Administrator at least 14 days prior to commencement of pavement works.
d59fada3-3133-5932-9245-4bbca39149c0 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
539c74cb-900c-5734-9f16-3531f2520d61 | note | Check Item - Milestone
9da74c9c-7643-5ccd-8ffc-1860dbc76e7f | note | Reference - MRTS10 Clause 5.2.1
| checkpoint | The unbound pavement material to be used as part of the plant-mixed lightly bound pavement conforms to the requirements of MRTS05.
feb4ba75-53fb-5a45-873a-3a211bbad081 | note | Acceptance Criteria and Frequency (Project Specific) - Written
30ec1592-eb58-5c22-b1a6-d80cf50bde88 | note | Check Item - Hold Point 2
c7fd698e-fec3-5a0b-a361-c21a3c099c9d | note | Reference - MRTS10 Clause 6.1
| signoff | HOLD POINT
| checkpoint | Regsitered mix design and terget content of stabilisation agent nominated and submitted to Administrator along with: 1. Stabilised Mix Design Certificate, 2. Quarry Registration Certificate
8e93c3bd-1e1d-5760-b543-35cea7720835 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
9c6817b9-1aa6-58f2-96f2-27f991da2cb9 | note | Check Item - HOLD POINT 3
7365213b-18f7-53ee-9b84-7560eb389965 | note | Reference - MRTS10 Clause 7.1
| signoff | HOLD POINT
| checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
0ff670a3-679c-5885-be96-2dcc17c8a422 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
50951a9c-3571-5401-b2c9-8621fd6246d5 | note | Check Item - WITNESS POINT 1
e32ba109-cd5e-5e9f-8246-ecb069580c17 | note | Reference - MRTS10 Clause 8.1
| checkpoint | Prior to continuing works after completion of the trial, records which demonstrate compliance submitted to the Adminstrator for acceptance.
b50db97e-afc2-514c-be41-4fa2f9ce778a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5dbe8e51-2702-5e07-8838-baa061c30449 | note | Check Item - Hold Point 4
48641e02-c7b0-582d-b5a8-b181f8509bff | note | Reference - MRTS10 Clause 8.1
| signoff | HOLD POINT
| checkpoint | Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
65c30d0e-25e9-53f3-bdd8-50cc9f62bc6c | note | Acceptance Criteria and Frequency (Project Specific) - Written
a62446a0-ff01-55db-9f5e-b72fd505815e | note | Check Item - Check Item
768c2c97-6e9e-540b-8cca-80c5c0a9c1dd | note | Reference - MRTS05 Clause 7
| checkpoint | Equipment as specified in approved construction procedure.
3773705a-8d59-5b45-ac04-e7370276c766 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
70c5367a-99fa-5455-bcb5-799c20f66e3f | note | Check Item - Check Item
c8313ef2-4e78-5d8f-bb25-be488b6f020a | note | Reference - MRTS10 Cl.8.2.1
| checkpoint | The time between the commencement of mixing the stabilisation agent into the unbound material and the completion of compaction of a single layer is less than the allowable working time. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Tested working time shown on the mix desing certificate, b) Four hours
7077a2fc-f237-5afd-80d3-c0e0c5e5114b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c1e6fcfd-4542-5f20-9677-258d098237e8 | note | Check Item - Check Item
6aace8a3-e53f-5711-91aa-8cb54cf36a64 | note | Reference - MRTS10 Clause 8.2.3
| checkpoint | Lightly bound pavements not constructed when: a) air temperature is less than 10°C or greater than 40°C, b) during rain or when rain is likely to fall during placement, c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the pavement layers
237762d8-e9bd-523c-bf1c-f017dc0c873c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
55d9c2df-2334-50ed-b931-a25dec18438b | note | Check Item - Check Item
7a0e7e62-60ce-5493-b0f2-7d4ee2c74f89 | note | Reference - MRTS10 Clause 8.2.4
| checkpoint | Individual compacted layer thicknesses in accordance with Table 8.2.7.1. Minimum - 125mm, Maximum - 250mm
22c37dff-d68a-5b1c-808b-32b6855c1d6c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
985049e4-d74d-57ba-9fef-837b957f2d0e | note | Check Item - Check Item
dcb68474-451c-5a79-95ca-10a5c7312ccc | note | Reference - MRTS10 Clause 8.2.7.1
| checkpoint | Where a lightly bound pavement layer is to be overlaid directly with another lightly bound pavement layer, the finished surface is hardcut to uniformly roughen the surface across the full width of the layer.
e22bfe0b-744b-5ab5-8998-d57957a1ff07 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e1b345f9-dc4f-5845-9b0d-02c0defa4c41 | note | Check Item - Check Item
32ca2de4-1856-5dc3-be97-e4dbf41eaee2 | note | Reference - MRTS10 Clause 8.2.7.2
| checkpoint | Unless constructed in the same shift, a cement slurry is applied to the hard-cut surface prior to placing the next lightly bound pavement layer.
399f3e06-ddda-5ef2-b561-e72582cfc165 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d4bdef8a-6990-5fc7-add3-92451de0e057 | note | Check Item - Check Item
bb666ab6-5c72-5940-b968-925c22d1f35b | note | Reference - MRTS10 Clause 8.2.7.2
| checkpoint | Each layer of lightly bound pavement cover with the next layer or bituminous surfacing within seven days of placement. Lightly bound layers not covered with a sprayed seal or prime within 48 hours of placement.
5fdb2f89-f994-5e25-820f-6bf4e09a82a8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
07977225-5f63-5c6f-92de-dbc34de16341 | note | Check Item - Check Item
e6b86826-0fcd-519a-8f7f-a0656e3cd811 | note | Reference - MRTS10 Clause 8.2.9
| checkpoint | Longitudinal joints offset by a min. 150mm from joints in underlying layers, located away from wheel paths and in the final layer coincide with the lane-marking or change in crossfall. Transverse joints offset by a min. 2.0m from joints in underlying layers.
3a2b6951-134a-578c-a967-0985639a48df | note | Acceptance Criteria and Frequency (Project Specific) - Visual
192bec1f-f98b-5ab7-86bf-7f82ea02f142 | note | Check Item - Check Item
0c8ef922-a85c-51ad-8db0-119734b745f2 | note | Reference - MRTS10 Clause 8.2.10
| checkpoint | For fresh joints between adjoining or adjacent run, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
9c7e1f91-724e-56c8-a3c1-8eb4aabfa412 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
112f5853-28ea-500a-88ba-52c3a2e9a551 | note | Check Item - Check Item
2aa99caa-87fb-547c-b5c7-eadfcceec0d3 | note | Reference - MRTS10 Cl. 8.2.10.1
| checkpoint | Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
edb3d510-0b12-5002-a734-6a4029a24bd6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7872c724-2d46-5fac-9787-6b6805760767 | note | Check Item - Check Item
a4d2aaa5-f5cb-5b0d-92ca-ad87ea909f67 | note | Reference - MRTS10 Cl. 8.2.10.2, Cl.6.4
| checkpoint | With the exception of vehicles directly involved with curing, compliance testing, sealing operations and construction of overlaying pavements and subsoil/pavement drains, lightly bound layers not opened to traffic until the lost has been tested and passes proff rolling.
51f2d4a2-5768-5d22-8842-137ed899f542 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b9f08238-fde1-5666-8974-4e85faf8fedf | note | Check Item - Check Item
e8a2f492-f1af-5fcc-81f1-6e055c3542f9 | note | Reference - MRTS10 Clause 8.2.11
| checkpoint | Intelligent Construction (IC) rollers shall be used to compact lightly bound pavement material
e1551ae7-3f14-53ad-a7c3-158d0c56c2d1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
aefd6086-5411-57ad-8add-f66760d46eb9 | note | Check Item - Check Item
840910ef-00db-58fe-b8a2-56e9346dd475 | note | Reference - MRTS10.1 Clause 8.2.1.7
| checkpoint | The actual content of stabilising agent for each lot complies with the requirements in Table 8.3.2. Min/Max Value = Target Content +/- MPV (Mixing-Plant-Variability)
68e2992f-2758-534d-8d47-1268e093184a | note | Acceptance Criteria and Frequency (Project Specific) - Written
e3fceb2a-4c91-5ca5-b23f-fd3c2f37c71a | note | Check Item - Check Item
b50623b6-d534-5c8e-88d6-ad6a59002a89 | note | Reference - MRTS10 Clause 8.3.2
| checkpoint | Unconfined compressive strength between 1 - 2MPa
cefaf07a-ae59-57ef-808d-eea9e8036e4f | note | Acceptance Criteria and Frequency (Project Specific) - Written
7507dfee-d162-58db-ab3e-9ec4f208f614 | note | Check Item - Check Item
6d984c02-8771-5804-b28e-eb0a3f38d267 | note | Reference - MRTS10 Clause 8.3.3
| checkpoint | The characteristic value of relative compaction shall not be less than 100%, except for the upper most layer of lightly bound base which shall not be less than 102% Compaction testing will be conducted at the 4hrs working time after batching.
ec86fcd6-471b-506d-823c-4f10d56a4d32 | note | Acceptance Criteria and Frequency (Project Specific) - Written
eafec25f-add2-57bf-a826-f6f59914a1c0 | note | Check Item - Check Item
7db5da92-0157-5c20-8d4e-68fb6436f468 | note | Reference - MRTS10 Clause 8.3.4
| checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
d4c024e3-029d-5107-b8ce-df2262fc1ad2 | note | Acceptance Criteria and Frequency (Project Specific) - Written
8503558e-f2d3-5944-a433-3254fd47bb95 | note | Check Item - Check Item
e5330b41-9b46-506d-83d3-2bda6d758cc6 | note | Reference - MRTS10 Clause 8.3.5.2
| checkpoint | The primary tolerance for the Lightly Bound Layer shall be ± 10mm. Further, the total thickness of the constructed Lightly Bound Layer shall be within -20mm, +unspecified of the specified thickness.
ce50129c-b50e-5167-b542-80bc931eaa18 | note | Acceptance Criteria and Frequency (Project Specific) - Written
e562bb63-9668-5b4a-9575-f06795034d9c | note | Check Item - Check Item
3ff89423-450d-565b-a7ca-b4d4b94dcf16 | note | Reference - MRTS10 Clause 8.3.5.3
| checkpoint | Deviation of a straight edge placed anywhere on the surface shall not exceed 5mm over 3m
cc91ff7f-257e-59fa-a15e-2d7f9b5c6cc3 | note | Acceptance Criteria and Frequency (Project Specific) - Written
b1a3cf8b-311e-54c8-bcd2-0e2d1dab489b | note | Check Item - Check Item
af538da6-e65e-5499-befd-626fa92dd4f2 | note | Reference - MRTS10 Clause 8.3.6
| checkpoint | Crossfall shall not differ from the designed crossfall by more than 0.5% absolute.
085b5012-48e8-54b5-a3f7-25f1e1e0e1b6 | note | Acceptance Criteria and Frequency (Project Specific) - Written
407da7e2-9971-5bb1-8420-d8007914c285 | note | Check Item - Check Item
eae07fab-1732-5238-b810-cf26883435fa | note | Reference - MRTS10 Clause 8.3.5.4
| checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
8292e9a2-7686-53e9-8d05-d0ce2fa4d94b | note | Acceptance Criteria and Frequency (Project Specific) - Written
911dee14-047a-5eca-8828-e45718f939a2 | note | Check Item - Check Item
4c2f040f-4e52-5a80-a950-6c5db4f63117 | note | Reference - MRTS10 Clause 8.3.5.2
| checkpoint | The Maximum Road Roughness shall not be greater than (Rs) "2.31m/km"
3ba926b3-6ecd-5f93-ae64-087e5bfc3f96 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e8886a08-2f65-5f12-8d1e-7b1bbc9a2ab2 | note | Check Item - Check Item
3573ed19-1fc1-5838-8cda-af6aa075b333 | note | Reference - MRTS10.1 Clause 8.3.7
| checkpoint | For lightly bound layers that are to be covered by a sprayed bituminous surfacing, the maximum ball penetration is less than 3mm
c5284f1d-edc8-5d87-8285-8de61c7f0306 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b65425e2-bb46-5d1c-9184-8ca9927aa4e5 | note | Check Item - Check Item
e2fd76f8-cfa0-5e9a-91dd-13b8a8301387 | note | Reference - MRTS10 Clause 8.3.8
| checkpoint | The perceptible surface deformation test shall be undertaken in the presence of the Administrator
912dd5bb-1318-55c1-9d33-f304650177a2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b169a53a-5e88-511a-8150-f0782497e454 | note | Check Item - WITNESS POINT
833d8ac1-11a6-5bcd-9d89-3eb726a1b2a6 | note | Reference - MRTS10 Clause 9.4.10
| checkpoint | No lightly bound layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed, the surface finish comlies with Clause 8.2.7 and the layer presented to the Administrator.
eac7523d-e9d5-5e80-90ea-e836fd85995b | note | Acceptance Criteria and Frequency (Project Specific) - Written
0aec6ddc-16b0-5ed3-933c-18ff60584c8f | note | Check Item - HOLD POINT
672d068c-8cbc-5512-aff0-ea9830fb33da | note | Reference - MRTS10 Clause 9.5.1
| signoff | HOLD POINT
| checkpoint | Final Verification
0199bb74-a824-5c0c-868c-62b8235c1655 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
2157dd81-ddc4-54e6-891c-a0885d757862 | textbox | Print Name:
c273b327-c4d3-57e6-8011-974529921625 | date | Date:
6b6beb2c-426a-5fb3-a84b-39fc2e959b22 | note | Project Manager Verify that the Above has been Constructed according to Specification
8d92e30e-ff26-5fe6-8ebf-0716cd70bb97 | textbox | Print Name:
4aa0c75e-c5c3-5803-b17b-387e49b7cbcd | date | Date:
| signoff | Signature

## 14.01
| checklist | 14.01 - Supply and Installation of Road Signs | itp | 14.01 - Supply and Installation of Road Signs | 393e26fb-b009-463c-a6fa-adaaafe8e847
| section | Details
| checkpoint | Dismantling of items to be salvaged
f1f04215-6d94-5225-8fda-59fa342d57e8 | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
2f1b43e0-0a8d-589c-a852-26c7ca36780a | note | Check Item - Hold Point 1
570cf34b-7274-5c01-af70-4a851c046969 | note | Reference - Cl8.2
| signoff | HOLD POINT
| checkpoint | Dismantling of items to be re-erected
406d0193-5511-5117-b4fb-211b1c3b071f | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
bccd78d8-b1d0-5a14-8fc5-4209bd59d463 | note | Check Item - Hold Point 2
7ba0fc4c-6875-5d80-ae11-4a41ba63b06a | note | Reference - Cl9.2
| signoff | HOLD POINT
| checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings
b4806570-176a-540a-bc03-77ff919852c1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e32363c-edd4-5f32-9424-976efa2c566d | note | Check Item - Check Item
4e05e087-1a54-562d-be83-002fada0da26 | note | Reference - MRTS14 CL 13.2
| checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744
7dce8d8b-b5ff-5570-be3e-1598dc198790 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3ace6e70-7be1-5bb6-8414-975634dca2ec | note | Check Item - Check Item
c6b37961-f7c1-5fd5-89f7-d1a388666e1b | note | Reference - MRTS14 CL 13.2
| checkpoint | Other materials may be considered but evidence of the full approvalof the department will be provided to the administrator prior to their use.
db98355e-651d-5133-a174-701169350ec8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
884f729f-3c69-536a-8eaa-e04ce3789867 | note | Check Item - Hold Point
597d8500-8c12-560b-af6e-70a2271e29c2 | note | Reference - MRTS14 CL 13.3.1.1
| signoff | HOLD POINT
| checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3
3cb03e6c-b7ce-57f5-9621-67cf7ed32903 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
70479deb-b874-530c-8f8f-8f84bd34dffa | note | Check Item - Check Item
ea12c465-e7b5-5207-b6ce-54409051b247 | note | Reference - MRTS14 Cl 13.3
| checkpoint | Sign faces are fabricated in accordance with the requirements of the Design Guide for Road signs to the size specified in the contract
c5497613-b83b-50fd-84c7-4cf638cc2e83 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
da8abfb2-00a8-598c-8fe6-a8ec67d6aab5 | note | Check Item - Check Item
9bf296eb-d043-5c1b-8648-695776df90ad | note | Reference - MRTS14 Cl 13.4
| checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
bbb75d39-f3eb-56fb-bb99-a9ed77d7af49 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9999590b-b42f-5cdd-ae21-cb91f424eedb | note | Check Item - Check Item
b72e4728-ab92-5947-bdfb-ddd85b9eacf5 | note | Reference - MRTS14 Cl 14.2.3
| checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required
d89eba31-8d0a-5bbb-9cf5-66668985569b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e1a04bb4-a239-5901-8da5-bbbdf8dada9f | note | Check Item - Check Item
13f14e95-a44a-530d-8e21-d4a451fa29ec | note | Reference - MRTS14 Cl 14.2.3
| checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
aab4717b-faac-50af-bbeb-3882ff1e0927 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a80eb913-1029-5d6b-8251-02c4ec94db82 | note | Check Item - Check Item
1bc78eff-802a-5040-8368-97439c5152ba | note | Reference - MRTS14 Cl 14.3
| checkpoint | Erection of Road Signs
183e779c-6689-5057-b063-55010999eab3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2f733da6-7d84-529d-aa5f-0a9d5e126a54 | note | Check Item - Witness Point
4b708ee4-e560-5e24-855b-366b0fe139f9 | note | Reference - MRTS14 Cl 14.4
| checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD
aa006874-96a5-5a40-867c-4b296d28f77f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d88514bb-0767-5476-a664-00236592e851 | note | Check Item - Check Item
247cf827-2f08-51b5-93fc-b78d4ada8cb7 | note | Reference - MRTS14 Cl 14.4.2
| checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete
a5bce75b-4a48-5d72-b2ae-ecb8ff192a4b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d35faf5c-3eeb-5c6b-808f-5058a43a78d4 | note | Check Item - Check Item
d13556c3-81ac-5481-85b6-83f7ac4e2a88 | note | Reference - MRTS14 Cl14.4.5
| checkpoint | Final Verification
b9d44045-4847-596a-ae58-fc0fdba7fa45 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
72dbec55-8ba2-5ae3-a0b5-690ee225e61f | textbox | Print Name:
ed3917da-7544-54f1-933c-4217f268dd5f | date | Date:
eea3988a-d78a-534d-abfb-50a8214b5dab | note | Project Manager Verify that the Above has been Constructed according to Specification
0fa4a573-2c11-5103-8e51-d7ce840f8424 | textbox | Print Name:
5da37242-6f63-5a7c-924f-9b54c9a9eabb | date | Date:
| signoff | Signature

## 16.01
| checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works | 19f71020-f39e-4bb0-8f6a-a317cd84edea
| section | Details
| checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
e02a5794-88d7-5e1d-80a8-c37fa6abc3e9 | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
4d54f3a1-1952-5d6c-9693-0f50729c167b | note | Check Item - Hold Point 1
ced6efa3-13fd-5085-906b-86dcef5c17c1 | note | Reference - MRTS16 Cl 5.2.1
| signoff | HOLD POINT
| checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
8bd28810-11a1-5686-a9e6-f0f62400431d | note | Acceptance Criteria and Frequency (Project Specific) - Plan
98bc7afe-3fc1-5d8f-80a6-f34df9142bfe | note | Check Item - Hold Point 2
fdbc2094-49f9-55fb-be70-f3ff6ac52505 | note | Reference - MRTS16 Cl 5.2.2
| signoff | HOLD POINT
| checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
fbb520d8-beff-513c-97c5-b233c4cbb7c8 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
e1af8a80-3ad5-5304-b544-6a72eea957f2 | note | Check Item - Hold Point 3
0288e99f-4b22-5379-9279-684c5dca30f1 | note | Reference - MRTS16 Cl 5.3.1
| signoff | HOLD POINT
| checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
4273085e-061d-5386-a860-bf1adaf5fe58 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
298ad3d9-ca19-581f-bf26-978d5773ae02 | note | Check Item - Hold Point 5
79978db7-5862-5920-bae4-f649499d8e30 | note | Reference - MRTS16 Cl 5.3.3
| signoff | HOLD POINT
| checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
30e6c1c6-c003-581d-afe6-7f84319cc577 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
7ba6478d-8992-5767-b20d-b5ca7f49b755 | note | Check Item - Hold Point 6
44d1587e-6520-5786-8a0f-f864933e3376 | note | Reference - MRTS16 Cl 5.3.4
| signoff | HOLD POINT
| checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
cc592aef-8e97-5917-b5df-e72c190171c0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8b23bad2-fa82-50bd-be88-96525dcc981f | note | Check Item - Check Item
9b6ccd9a-39eb-5ff6-8d1f-020e3c4a5d16 | note | Reference - MRTS16 Cl 7
| checkpoint | Materials are stored to ensure no deterioration or contamination occurs
f5079c02-0f2d-52c8-a031-1222b7392391 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fd1bb572-37be-5f06-84f9-3e679b6a92a7 | note | Check Item - Check Item
368f161a-cc75-5d46-bbc9-5c2c844eb440 | note | Reference - MRTS16 Cl 7
| checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
d70422f9-7ea9-53b3-ba03-3296389337c9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
80f58ad1-cf7c-5fdb-9699-20c91daf442b | note | Check Item - Check Item
42188b4a-cf84-57d8-b2e0-622a5fad0660 | note | Reference - MRTS16 Cl 7
| checkpoint | containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
559b2012-2813-5a2c-9438-016082477a99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
37a11c42-73de-519f-bfe8-cc38dfbddeba | note | Check Item - Check Item
1f725a8b-88e6-514c-a71f-e418ef5e2e3a | note | Reference - MRTS16 Cl 7.6.2
| checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
5b029271-917e-56ac-9843-93e81ad664f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
746a99b1-8036-5cec-8e80-3137b54a8f74 | note | Check Item - Check Item
85416049-d5b6-50f6-9631-81d9c3fb77f2 | note | Reference - MRTS16 Cl 8
| checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
02f981ca-5002-53b2-a076-973dc80950b4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9738105e-1682-5f3f-8e3c-8e3d1904b12f | note | Check Item - Check Item
c1a10595-ff22-5554-856a-36a09ec09fb2 | note | Reference - MRTS16 Cl 8.4 TMR SD 1644
| checkpoint | Site is weed free prior to ground preparation operations
dce06f87-1b90-5736-9773-d58bda932679 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d090ae69-af79-5931-a812-40f87ec1f34a | note | Check Item - Witness Point
77e12620-7d91-5835-82ef-03655f60f12f | note | Reference - MRTS16 Cl 8.3
| checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
3ecfc8d7-e496-51bd-8fd5-4c1c3828390a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c9478829-4934-570f-96a2-973af41c56aa | note | Check Item - Witness Point
176d671a-e075-5e96-baef-3e61a39390bd | note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
| checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
55ec06cb-1b3a-50e4-a0ce-d50a3e4003ec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
74f3efb2-6b34-52a1-babf-765ec5f1b182 | note | Check Item - Hold Point 7
18bffffe-bc9a-5e24-80b0-e3b9aa7d2a73 | note | Reference - MRTS16 Cl 8.2.1
| signoff | HOLD POINT
| checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
a2406fac-2faa-56ea-99bc-cc0314fba5bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d94d90ca-d6b5-5aed-b28a-13a770f1c854 | note | Check Item - Hold Point 8
13c9b02e-8dba-596d-b88e-8d7b595aa986 | note | Reference - Cl 8.4.1.1
| signoff | HOLD POINT
| checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
41ce37b6-86f6-5d7a-9000-bf6b95143a54 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
bedbb909-b72e-5750-abe6-23efd0f4e29a | note | Check Item - HOLD POINT
966961fb-c5f6-5a9b-b125-f32e72edadee | note | Reference - CTS16 Cl. 3.1.6
| signoff | HOLD POINT
| checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
49b0844d-9720-5d14-9315-767f421992ea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
45de65ae-03cb-560d-9493-3aea3834114d | note | Check Item - Witness Point
d15abcc0-5319-5130-bc91-99f506149efd | note | Reference - MRTS16 Cl 8.4.2.1
| checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
d55d7876-d547-5e29-969b-ec7b7c970f22 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
88011a8c-40ff-5f73-ad9d-737c658404a1 | note | c) on the day turf is delivered to site
0c8274be-97f1-5b70-ae63-6671c565a1e0 | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
76f34a62-8295-5bcd-939f-501ab9b0f546 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
24f1d140-a423-58c2-8cf9-06f3792213ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
339c3bd7-df33-52d6-8869-2c5b0fe9d3f1 | note | Check Item - Check Item
4a93ae59-77c5-5d42-a396-dbdc35d36526 | note | Reference - MRTS16 Cl 8.5.2.
| checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
61f2cc4c-83c7-57e2-afca-6c54f0b8c03c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4bfd8ab5-57bd-5169-afd2-0b758448d372 | note | Check Item - Check Item
3bb0dc1c-bdd8-5067-9ae1-9af8f331ce98 | note | Reference - MRTS16 Cl 8.5.1.3
| checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
285c388e-7db8-55d4-9cc3-0b2d4fde492c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e6b42fca-cc27-51c9-8d1c-3b3e09dd78df | note | Check Item - Check Item
f727944b-836c-5621-a4ef-5b8e95395a7d | note | Reference - MRTS16 Cl 8.2.1.4
| checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
9ec6d670-b5cb-5414-8e9d-404f2e3c2a74 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
47e46723-a76c-5acd-9b5f-711715620594 | note | Check Item - Check Item
de6b84d0-a1fd-5359-9e48-0d3b8209c9ac | note | Reference - MRTS16 Cl 8.5.1.3
| checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
48ab6613-900d-5c04-a6f3-653a3871c535 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
61316ddb-559e-5ab2-829f-676d5d364995 | note | Check Item - Check Item
8f7f4ea4-c74e-52fe-b61e-7db89c03f7cf | note | Reference - MRTS16 Cl 8.5.2
| checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
ea21bcbf-8cd9-5fbd-8ad9-5ee08a37eda0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
567e9623-302a-57ee-bc22-f58a9ddb507a | note | Check Item - Check Item
0e722d6b-701e-58a3-bd51-3b225655fa32 | note | Reference - MRTS16 Cl 7.6.3.1
| checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
eecf6001-365f-5d5d-b610-95fe4327521d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
da7855c2-acd2-5660-a048-986cb232983c | note | Check Item - Check Item
187a3bff-8e03-52ac-a35e-6eaeec871c7b | note | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
| checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
aef73a14-74c4-5c84-97e6-e155ae0bde50 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
24d1ddb1-3dd0-5ce6-81b3-b46e9d02c8eb | note | Check Item - Check Item
7bd2ad14-9d9f-5ea0-af7c-dd6ba9c490f8 | note | Reference - MRTS16 Cl 8.5.3.2
| checkpoint | Administrator notified of plant delivery to allow for inspections
902df27d-4ac9-5e63-82d7-ca2dbfccfb4a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
92c4a71d-b3af-5894-90e8-92fee63e5d9f | note | Check Item - Witness Point
2dd0998d-a849-5123-a854-e4797f4699d8 | note | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
| checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
f83911a0-24b8-5616-ae28-4f111a177dae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e19886cd-1f3d-5b00-b5fb-0d84f01f7e6f | note | Check Item - Hold Point 11
e7b0e553-8cc3-5b80-9a7f-b6145f54cf85 | note | Reference - MRTS16 Cl 8.5.3.3
| signoff | HOLD POINT
| checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
b4bb8a22-c368-5dc1-83a2-b39b9bee2cd8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b39407e8-6f5e-5104-8220-594c95c2d3de | note | Check Item - Check Item
8f6faf45-d9f0-5b4d-993c-42ea5ca418c7 | note | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
| checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
51db7e20-c709-54b8-929d-3c84858e0dee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5703490b-c7ed-5a20-87b6-f0f3894bfa6f | note | Check Item - Check Item
3741b924-4127-5878-9b25-f12e1df5e688 | note | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
| checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
96737e04-2a91-5273-a778-3e152c4cf7fe | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dfbfe192-cc8c-5966-885b-dec956ceec81 | note | Check Item - Check Item
1caee86a-578b-5888-8034-bc063af2b573 | note | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
| checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
5fe0c2f7-d342-5ee5-8845-8df77f068849 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cbfbd3f2-0480-59ea-afe1-021e6a875afe | note | Check Item - Milestone
25693dbd-5b69-5b77-8c90-bdb267aafef3 | note | Reference - MRTS16 Cl 9.1
| checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
de1164eb-352f-55b1-9c14-37135c6f0196 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
71257aaf-1bce-5f48-b84b-820a0a55b3e0 | note | Check Item - Check Item
5970c46b-6322-5ee4-8ca7-8a02f5e1fed2 | note | Reference - MRTS16 Cl 9.1.1
| checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
8b748c94-ec81-55bb-9c61-3a232e5edb07 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d2343d69-328b-5588-a020-43d8ca1e8365 | note | Check Item - Hold Point 10
304526cf-8ac9-52ae-8b18-47254cd515af | note | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
| signoff | HOLD POINT
| checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
e41e498e-b804-5bae-abd0-62d5f9f23549 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5daf087-f259-5613-a9a4-f53106854a9a | note | Check Item - Milestone
841fe638-2308-562d-8570-20e692fb98cc | note | Reference - MRTS16 Cl 9.2
| checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
95981efc-38c5-5bd3-a13d-481e389c88cb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
655ee0e8-f7ac-5c89-8ca6-c7bc2fc3a80e | note | Check Item - Check Item
c1fd175d-b9dd-51e3-b2d4-f4c2adcf5991 | note | Reference - MRTS16 Cl 9.2.1
| checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
191e5770-c82b-5b8e-b9ee-95b6ce6c0f31 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fbfc098f-75b3-57be-8a16-52594bdd529a | note | Check Item - Milestone
9711e982-b7c7-508b-8100-2471a79e63fe | note | Reference - MRTS16 Cl 9.2
| checkpoint | Final Verification
df4273e7-5534-5e24-92d7-928f77000c29 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
5d275c16-e026-5c40-b650-93a46535e399 | textbox | Print Name:
cebdfbb6-7f96-5ca4-a334-b395b90de09c | date | Date:
5c54828f-a59b-594b-ac4a-94a65aa2ae98 | note | Project Manager Verify that the Above has been Constructed according to Specification
bfc415f7-9c57-566d-9d57-c8708c47c09f | textbox | Print Name:
4a592f3e-8d3c-5257-ac36-34c91c2b6287 | date | Date:
| signoff | Signature

## 16.02
| checklist | 16.02 - Turfed Areas | itp | 16.01 - Landscape and Revegetation Works | 19f71020-f39e-4bb0-8f6a-a317cd84edea
| section | Details
| checkpoint | Installation of Turf Shall Comply with Project specific Requirements listed in MRTS16 Annexure.
e02a5794-88d7-5e1d-80a8-c37fa6abc3e9 | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
4d54f3a1-1952-5d6c-9693-0f50729c167b | note | Check Item - Hold Point
ced6efa3-13fd-5085-906b-86dcef5c17c1 | note | Reference - MRTS16.1 Cl 3.3.1
| signoff | HOLD POINT
| checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
8bd28810-11a1-5686-a9e6-f0f62400431d | note | Acceptance Criteria and Frequency (Project Specific) - Plan
98bc7afe-3fc1-5d8f-80a6-f34df9142bfe | note | Check Item - Hold Point 8
fdbc2094-49f9-55fb-be70-f3ff6ac52505 | note | Reference - MRTS16 Cl 8.5.2 & MRTS16 CL 8.4.1.1
| signoff | HOLD POINT
| checkpoint | Topsoil shall be installed within three days from the completion of the subsoil operations. Topsoil shall be spread to the required depth. (75mm)
fbb520d8-beff-513c-97c5-b233c4cbb7c8 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
e1af8a80-3ad5-5304-b544-6a72eea957f2 | note | Check Item - Witness Point 6
0288e99f-4b22-5379-9279-684c5dca30f1 | note | Reference - MRTS16 Cl 8.5.2
| checkpoint | Subsoil operations shall occur immediately after the application of amelioration agents. As per Table 8.5.2
4273085e-061d-5386-a860-bf1adaf5fe58 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
298ad3d9-ca19-581f-bf26-978d5773ae02 | note | Check Item - Witness Point 3,4, or 5
79978db7-5862-5920-bae4-f649499d8e30 | note | Reference - MRTS16 Cl 5.3.3
| checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
d70422f9-7ea9-53b3-ba03-3296389337c9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
80f58ad1-cf7c-5fdb-9699-20c91daf442b | note | Check Item - Check Item
42188b4a-cf84-57d8-b2e0-622a5fad0660 | note | Reference - MRTS16 Cl 7
| checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
559b2012-2813-5a2c-9438-016082477a99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
37a11c42-73de-519f-bfe8-cc38dfbddeba | note | Check Item - Hold Point 7
| note | Reference - MRTS16 Cl 8.2.1
1f725a8b-88e6-514c-a71f-e418ef5e2e3a | signoff | HOLD POINT
| checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
49b0844d-9720-5d14-9315-767f421992ea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
45de65ae-03cb-560d-9493-3aea3834114d | note | Check Item - Witness Point
d15abcc0-5319-5130-bc91-99f506149efd | note | Reference - MRTS16 Cl 8.4.2.1
| checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
d55d7876-d547-5e29-969b-ec7b7c970f22 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
88011a8c-40ff-5f73-ad9d-737c658404a1 | note | c) on the day turf is delivered to site
0c8274be-97f1-5b70-ae63-6671c565a1e0 | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
76f34a62-8295-5bcd-939f-501ab9b0f546 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
24f1d140-a423-58c2-8cf9-06f3792213ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
339c3bd7-df33-52d6-8869-2c5b0fe9d3f1 | note | Check Item - Check Item
4a93ae59-77c5-5d42-a396-dbdc35d36526 | note | Reference - MRTS16 Cl 8.5.2.
| checkpoint | Subsoil Testing Requirements Completed as per requirements of Form D & Form E
61f2cc4c-83c7-57e2-afca-6c54f0b8c03c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4bfd8ab5-57bd-5169-afd2-0b758448d372 | note | Check Item - Check Item
3bb0dc1c-bdd8-5067-9ae1-9af8f331ce98 | note | Reference - MRTS16 CL 4.1
| checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
61f2cc4c-83c7-57e2-afca-6c54f0b8c03c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4bfd8ab5-57bd-5169-afd2-0b758448d372 | note | Check Item - Check Item
3bb0dc1c-bdd8-5067-9ae1-9af8f331ce98 | note | Reference - MRTS16 Cl 8.5.1.3
| checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
285c388e-7db8-55d4-9cc3-0b2d4fde492c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e6b42fca-cc27-51c9-8d1c-3b3e09dd78df | note | Check Item - Check Item
f727944b-836c-5621-a4ef-5b8e95395a7d | note | Reference - MRTS16 Cl 8.2.1.4
| checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
9ec6d670-b5cb-5414-8e9d-404f2e3c2a74 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
47e46723-a76c-5acd-9b5f-711715620594 | note | Check Item - Check Item
de6b84d0-a1fd-5359-9e48-0d3b8209c9ac | note | Reference - MRTS16 Cl 8.5.1.3
| checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
48ab6613-900d-5c04-a6f3-653a3871c535 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
61316ddb-559e-5ab2-829f-676d5d364995 | note | Check Item - Check Item
8f7f4ea4-c74e-52fe-b61e-7db89c03f7cf | note | Reference - MRTS16 Cl 8.5.2
| checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
5fe0c2f7-d342-5ee5-8845-8df77f068849 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cbfbd3f2-0480-59ea-afe1-021e6a875afe | note | Check Item - Milestone
25693dbd-5b69-5b77-8c90-bdb267aafef3 | note | Reference - MRTS16 Cl 9.1
| checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
e41e498e-b804-5bae-abd0-62d5f9f23549 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5daf087-f259-5613-a9a4-f53106854a9a | note | Check Item - Milestone
841fe638-2308-562d-8570-20e692fb98cc | note | Reference - MRTS16 Cl 9.2
| checkpoint | Final Verification
df4273e7-5534-5e24-92d7-928f77000c29 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
5d275c16-e026-5c40-b650-93a46535e399 | textbox | Print Name:
cebdfbb6-7f96-5ca4-a334-b395b90de09c | date | Date:
5c54828f-a59b-594b-ac4a-94a65aa2ae98 | note | Project Manager Verify that the Above has been Constructed according to Specification
bfc415f7-9c57-566d-9d57-c8708c47c09f | textbox | Print Name:
4a592f3e-8d3c-5257-ac36-34c91c2b6287 | date | Date:
| signoff | Signature

## 28.01
| checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities | c756dde2-9940-4d6e-a3aa-ca2f27e22f3e
| section | Details
| checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
d9664ad5-afbf-5d3e-909f-55fc1dcec1d0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f0303df1-cdbd-5f2b-b6b5-c8c8a7ccee2a | note | Check Item - Check Item
028c437e-7bab-54aa-aa84-6416ad7b9623 | note | Reference - MRTS28 Cl. 4.2
| checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
56a5c25e-b6ae-5546-8592-49a4ba586cd9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
74f00c90-a700-5162-aca7-b208a6e1ea60 | note | Check Item - Check Item
c44f1505-ffad-5559-9408-54ac7ad522ad | note | Reference - MRTS28 Cl. 4.3
| checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
acb6e814-cb30-50da-8e20-9766e8c67bf7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6f8e1472-1d03-50ed-a233-b113b9d57711 | note | Check Item - Check Item
2d99ac01-8ed6-5d9b-a348-8a8cf813f475 | note | Reference - MRTS28 Cl. 4.4.2
| checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
effce50d-4cad-561a-b802-f496b21f33b4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
23710a6e-e871-53c8-9883-7778ed3751bb | note | Check Item - Check Item
633f6ee6-36df-56f7-9442-712f3b9cd97c | note | Reference - MRTS28 Cl. 4.5.7
| checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
393043de-3efb-521c-bec7-348ab302d627 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
868c867b-f265-5326-aafa-6838e4b8f1ca | note | Check Item - Check Item
4ab87af1-0cc4-5f41-92c8-bf86d97dcc99 | note | Reference - MRTS28 Cl.4.5.1
| checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
73c064de-a22c-53ce-a3ac-45b3ca934e44 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ee29b8e2-961e-5e89-9c8a-35f257432d81 | note | Check Item - Check Item
84a7e4c7-6409-5c69-864e-71d8c519cf87 | note | Reference - MRTS28.1, C.l 3
| checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
2e6db49b-9975-5d92-9b5e-735ba8ac198f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
92907c29-e23f-53f7-9fe8-d61ffbe38354 | note | Check Item - Check Item
bd11fa64-3283-512f-8904-41400facd530 | note | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
| checkpoint | Final Verification
aea9d900-6449-5596-90ba-e486cb56fc93 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
7ea4dd13-1a86-55e2-8c36-b446c53b1936 | textbox | Print Name:
2e2ba587-6f0b-53f1-b1d8-d792a8b40e9e | date | Date:
f0c30b2c-aa34-5da8-b87c-b6229c7ecb9f | note | Project Manager Verify that the Above has been Constructed according to Specification
274e90d3-5a50-59de-9806-99cf1182b846 | textbox | Print Name:
09f2b0dd-3073-5251-acca-213bc3f1a790 | date | Date:
| signoff | Signature

## 30.01
| checklist | 30.01 - Dense Graded Asphalt | itp | 30.01 - Dense Graded Asphalt
| section | Details
| checkpoint | Submission of Asphalt Quality Plan (7 days)
cff89afe-4512-5429-a84c-366427ed28b7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
14d1566c-c811-5b17-969f-ef715076e9f0 | note | Check Item - Milestone
4f905ca2-c40d-5a6b-9f6c-4256a5a4d73a | note | Reference - MRTS30 Cl 5.2
| signoff | HOLD POINT
| checkpoint | Recommencement of production after non conforming Tensile Strength Ratio
ab7d678e-7afe-52bc-88e7-84c6e8857eee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
84f1c1af-916d-552d-95d3-d1cd16d95425 | note | Check Item - HOLD POINT
4e7ac1d7-d25f-5284-ad70-7bb67a8078d7 | note | Reference - MRTS30 Cl 7.2.5
| checkpoint | Submission of Asphalt Mix Design Certificate (7 days)
bdebbf90-8a22-571d-a177-e419c46bc7fc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6fd07fee-de8b-596f-9cb1-a70694b69b4b | note | Check Item - Milestone
63c541d8-b808-5165-8d42-1dbb69108b7e | note | Reference - MRTS30 Cl 7.3.3
| checkpoint | Incorporation of asphalt into the Works
98cec33f-6a14-568e-b4d6-8b0f120d1fab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9e9fecce-bfcb-5b09-9266-2331287220f9 | note | Check Item - HOLD POINT
7421c3eb-666a-5008-b9e5-d5f665334a33 | note | Reference - MRTS30 Cl 7.4.1
| signoff | HOLD POINT
| checkpoint | Acceptance of a non conforming or nonstandard mix design for incorporation into the Works
f6b08746-be6f-5ce8-b11c-a195b21d0d93 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8a53dbb7-831b-53b0-8c2d-6d052838ac22 | note | Check Item - HOLD POINT
beb3f370-ec48-52b8-86c3-967176bf2e67 | note | Reference - MRTS30 Cl 7.4.1
| signoff | HOLD POINT
| checkpoint | Approval to place asphalt over weak substrate substrate
dc9cfbe6-39ab-5484-a7bb-8d6322a74338 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
569c1cd9-fd97-5cb1-a941-458aa713b264 | note | Check Item - Witness Point
54e1fd76-ff03-5a18-8ab3-401c6d04915e | note | Reference - MRTS30 Cl 8.2.2
| signoff | HOLD POINT
| checkpoint | Proof rolling of substrate
96e0fe59-c8bb-585b-b150-dfcf7f39e89d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
68536088-4842-5515-8af3-d41755d5fc68 | note | Check Item - Witness Point
bd8d6a6f-9fd7-5694-8958-5e0cb17bd21b | note | Reference - MRTS30 Cl 8.2.2
| checkpoint | Mark out of cracks to be filled substrate
c9450925-58c0-5c9b-a80e-35db6d6d0b03 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2c759f73-8555-53c4-8da9-b686133ddb67 | note | Check Item - Witness Point
6e493d5b-c791-53d5-9004-01dfcea9c742 | note | Reference - MRTS30 Cl 8.2.3
| checkpoint | Marking out the areas on which strain alleviating fabric strips are to be applied
bd135a60-a96f-5756-bf42-46e4e129e888 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a1f85857-c1a3-5405-a106-588849a0e3ee | note | Check Item - Witness Point
9b3325af-ea4c-5bf4-9b94-c8caea354876 | note | Reference - MRTS30 Cl 8.2.4
| checkpoint | Approval to place asphalt at a nonconforming layer thickness
e7a9e27d-9bd3-5d89-a769-09e0dd53dcdd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6dc55bd8-d3a5-54a2-ade9-370c708c7f22 | note | Check Item - Witness Point
e1287edc-05ea-584b-885a-956823779aa1 | note | Reference - MRTS30 Cl 8.6.2
| signoff | HOLD POINT
| checkpoint | Approval to place asphalt at a nonconforming pavement temperature
aad5e32a-dc1e-5cd5-90a7-1d37c8b6f2d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
103b604c-d286-5aa0-8d1a-69e853ca776d | note | Check Item - Witness Point
103b604c-d286-5aa0-8d1a-69e853ca776d | note | Reference - MRTS30 Cl 8.7
c99793a7-6b2a-5e85-b5c5-e3310e7b2984 | note | HOLD POINT
| checkpoint | Placing of the nominated mix (after placement trial)
e5e8f547-f90e-5861-ae9c-910d72de7f57 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
88b263b5-b736-5290-a945-4811585bccea | note | Check Item - Witness Point
88b263b5-b736-5290-a945-4811585bccea | note | Reference - MRTS30 Cl 8.11
01814570-0a14-5253-85f5-11da03d4f253 | note | HOLD POINT
| checkpoint | Final Verification
7bc9b72b-9fc0-564f-805b-c241f3e07621 | note | Project Manager Verify that the Above has been Constructed according to Specification
be682a36-7b5e-5d35-ac66-4c034ea15f0d | textbox | Print Name:
06f130e3-a1dc-5632-b536-5c2e1635ca24 | date | Date:
21c43270-6e26-5067-858b-3debad5218aa | note | Client Verify that the Above has been Constructed according to Specification
3be3710f-5b26-5c7e-aafa-f2868e0cb0f5 | textbox | Print Name:
977d7645-2545-5268-8288-dd26526cd5d2 | date | Date:
| signoff | Signature

## 45.01
| checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation | 22ad63be-978a-4abb-8e5b-ccf513cd2f0b
| section | Details
| checkpoint | All material conforms to requirements set out in Clause 6 of MRTS45.
cff89afe-4512-5429-a84c-366427ed28b7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
14d1566c-c811-5b17-969f-ef715076e9f0 | note | Check Item - Check Item
4f905ca2-c40d-5a6b-9f6c-4256a5a4d73a | note | Reference - MRTS45 Cl 6
| checkpoint | Installtion of Pavement Markings conforms to requirements set out in Clause 7.
ab7d678e-7afe-52bc-88e7-84c6e8857eee | note | Acceptance Criteria and Frequency (Project Specific) - Visual
84f1c1af-916d-552d-95d3-d1cd16d95425 | note | Check Item - Check Item
4e7ac1d7-d25f-5284-ad70-7bb67a8078d7 | note | Reference - MRTS45 Cl 7
| checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
bdebbf90-8a22-571d-a177-e419c46bc7fc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6fd07fee-de8b-596f-9cb1-a70694b69b4b | note | Check Item - Check Item
63c541d8-b808-5165-8d42-1dbb69108b7e | note | Reference - MRTS45 Cl 7.2
| checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
98cec33f-6a14-568e-b4d6-8b0f120d1fab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9e9fecce-bfcb-5b09-9266-2331287220f9 | note | Check Item - Check Item
7421c3eb-666a-5008-b9e5-d5f665334a33 | note | Reference - MRTS45 Cl 7.3
| checkpoint | In addition to Cl. 7.3, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
f6b08746-be6f-5ce8-b11c-a195b21d0d93 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8a53dbb7-831b-53b0-8c2d-6d052838ac22 | note | Check Item - Hold Point 1
beb3f370-ec48-52b8-86c3-967176bf2e67 | note | Reference - MRTS45 Cl 7.3
| signoff | HOLD POINT
| checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
dc9cfbe6-39ab-5484-a7bb-8d6322a74338 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
569c1cd9-fd97-5cb1-a941-458aa713b264 | note | Check Item - Hold Point 2
54e1fd76-ff03-5a18-8ab3-401c6d04915e | note | Reference - MRTS45 Cl 7.4
| signoff | HOLD POINT
| checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
96e0fe59-c8bb-585b-b150-dfcf7f39e89d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
68536088-4842-5515-8af3-d41755d5fc68 | note | Check Item - Check Item
bd8d6a6f-9fd7-5694-8958-5e0cb17bd21b | note | Reference - MRTS45 Cl 7.5
| checkpoint | All Markings are of uniform thickness and intensity
5d667388-4b8d-53d0-ad46-caa78f870295 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
379d6f41-46b9-5311-a57a-cc98f766a5e4 | note | Check Item - Check Item
f21dfdf2-728d-5e97-aa98-89e3007c25c5 | note | Reference - MRTS45 Cl 7.5.2.3
| checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
c9450925-58c0-5c9b-a80e-35db6d6d0b03 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
2c759f73-8555-53c4-8da9-b686133ddb67 | note | Check Item - Check Item
6e493d5b-c791-53d5-9004-01dfcea9c742 | note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
| checkpoint | A primer was placed just prior to thermoplastic materials as per manufacturers specifications
bd135a60-a96f-5756-bf42-46e4e129e888 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a1f85857-c1a3-5405-a106-588849a0e3ee | note | Check Item - Check Item
9b3325af-ea4c-5bf4-9b94-c8caea354876 | note | Reference - MRTS45 Cl 7.5.3.1
| checkpoint | Thermoplastic shall be applied at a temperature as per the manufacturers specifications
e7a9e27d-9bd3-5d89-a769-09e0dd53dcdd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6dc55bd8-d3a5-54a2-ade9-370c708c7f22 | note | Check Item - Check Item
e1287edc-05ea-584b-885a-956823779aa1 | note | Reference - MRTS45 Cl 7.2, Cl 7.5.3.2
| checkpoint | Thermoplastic applied at a minimum of 2mm thickness
aad5e32a-dc1e-5cd5-90a7-1d37c8b6f2d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
103b604c-d286-5aa0-8d1a-69e853ca776d | note | Check Item - Check Item
c99793a7-6b2a-5e85-b5c5-e3310e7b2984 | note | Reference - MRTS45 Cl 7.5.3.3
| checkpoint | Raised Pavement Markers installed in accordance with Cl 4.6.3 of the MUTCD
e5e8f547-f90e-5861-ae9c-910d72de7f57 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
88b263b5-b736-5290-a945-4811585bccea | note | Check Item - Check Item
01814570-0a14-5253-85f5-11da03d4f253 | note | Reference - MRTS45 Cl 7.6
| checkpoint | Material complies with luminance and retro-reflectivity requirements
c7104eca-122c-50e6-91e5-66419436ab0a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c8fef48c-c34d-51fc-a5e4-05d450ab7591 | note | Check Item - Check Item
fd0be12a-ddb4-5559-8a43-e3ab092b49df | note | Reference - MRTS45 Cl 7.7.6
| checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
e1909178-bf65-5845-9fb7-cfae159f8760 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5a200a4e-a7f0-5667-b5f3-8daac00fe078 | note | Check Item - Check Item
bf211823-7e08-5538-9288-163c8c1a220a | note | Reference - MRTS45 Cl 7.8
| checkpoint | Completed Pavement Markings are uniform, clean and well-defined edges with deformation and conforms to dimensions as set out in the MUTCD
4f181ab7-d880-54ab-9610-fddd6704f681 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cc2bc0ba-4e70-588f-9053-9ff9613dd566 | note | Check Item - Check Item
08ec2b4f-9583-513b-b94c-a8293680c67f | note | Reference - MRTS45 Cl 7.9
| checkpoint | Pavement Markings conform to all tolerances
7c568802-dcae-5218-905b-aef91d92928f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f3feecb0-1545-53f8-8810-64ab84c44c54 | note | Check Item - Check Item
8b80d48b-d2cd-5e31-a6c2-4f29a93fa1f2 | note | Reference - MRTS45 Cl 7.9
| checkpoint | Quality Verification Requirements, Test Method
197c06c8-a12b-5b64-937a-05e69c0f2703 | note | Acceptance Criteria and Frequency (Project Specific) -
7ed91524-cfb4-5d04-9dea-f39d7619be3d | textbox | Min. Testing Frequency
707c750b-f30e-5149-8543-ae110b8379bb | textbox | Min. No. of Tests
f7fb1e54-90d9-50fe-9990-3e7d852f823f | note | Check Item - MRTS45
27f7529e-0461-51cb-84ae-9255be8f404a | note | Reference - Annexure
| checkpoint | Materials
053f4ae9-7a93-59c3-85d8-1f58f6dfa642 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch, 1 test
f9039d89-34d0-5ebc-8a83-6f7042805fff | note | Check Item - Check Item
cab9a69a-f77e-51e5-bac8-150a3d7181ac | note | Reference - MRTS45.1
| checkpoint | Thickness of Pavement markings: Longtitudinal lines, Transverse markings
3aec3e9d-1fa6-5d8e-93a7-492e6eb172f4 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot/ 1 test
6be3fa57-2969-56b3-a17b-11cafb0a83ea | note | ○ 1 per lot/ 1 test
2968b104-d97b-50cc-a44c-a428531152f7 | note | Check Item - Check Item
1a3d793c-d8d8-5515-a48b-bf81eb9c3c4f | note | Reference - MRTS45.1
| checkpoint | Dimensions of Pavement markings: Longtitudinal lines, Transverse markings
48572bc9-907f-5cbb-acda-554075d570ac | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 200m/ 1 test
5db68764-bcb2-5462-86c4-3de53e4f0c5e | note | ○ 1 per type/ 1 test
6d4904c7-0339-564f-be1c-d12e4ecbbfce | note | Check Item - Check Item
51357039-9690-555c-9625-50a15d66d629 | note | Reference - MRTS45.1
| checkpoint | Dimensions of raised pavement marker placement
ef32906f-a425-5185-a35e-6ad3b83f11d2 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 50 / 1 test
cb6f64ec-9f23-578b-991a-7dfabd6c03b3 | note | Check Item - Check Item
c7e57abc-e11a-5932-90d9-2810da85d6f1 | note | Reference - MRTS45.1
| checkpoint | Retroreflectivity
212b0ffa-06cd-53e4-ab39-3b84477e2a3e | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot / 1 test
9c1c8b47-b55f-5fb6-ad7f-02119c1a6529 | note | Check Item - Check Item
2af0e5d0-002f-55df-a783-e1996bc403f8 | note | Reference - MRTS45.1
| checkpoint | Skid Resistance
9b458a83-9430-5b8e-871e-3838d67df7f7 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch / 1 test
c2baba60-fb1e-5afe-9c1c-8faa9ea314d7 | note | Check Item - Check Item
4601d502-a1f3-598e-a39b-94435d8570cc | note | Reference - MRTS45.1
| checkpoint | Final Verification
7bc9b72b-9fc0-564f-805b-c241f3e07621 | note | Project Manager Verify that the Above has been Constructed according to Specification
be682a36-7b5e-5d35-ac66-4c034ea15f0d | textbox | Print Name:
06f130e3-a1dc-5632-b536-5c2e1635ca24 | date | Date:
21c43270-6e26-5067-858b-3debad5218aa | note | Client Verify that the Above has been Constructed according to Specification
3be3710f-5b26-5c7e-aafa-f2868e0cb0f5 | textbox | Print Name:
977d7645-2545-5268-8288-dd26526cd5d2 | date | Date:
| signoff | Signature

## 51.01
| checklist | 51.00 - Environmental Management Systems | itp | 51.00 - Environmental Management Systems | 31ce4bdc-f0da-4b33-a1d7-6780c1f0ca44
| section | Details
| checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
b2342113-6a63-5a4f-89e3-99dd750a57c5 | note | Check Item - Milestone
b42a10db-ef20-5b18-a53f-4d6b1a84e578 | note | Reference - MRTS51 Cl. 6.3
| checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
00038d48-ff92-5a18-b26d-9a0b255d8fb4 | note | Check Item - Hold Point 1
11ae484d-2dc5-55c9-aabe-eb2fa847220c | note | Reference - MRTS51 Cl. 6.3
| signoff | HOLD POINT
| checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
8a35ef57-06ee-5eda-be1e-2219faf0be45 | note | Check Item - Hold Point 2
e0ef7410-b5b7-51a2-97fe-d23ddfd8b391 | note | Reference - MRTS51 Cl. 6.4
| signoff | HOLD POINT
| checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
22e50ab9-b3c6-54f7-8910-2cb0305a92a7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
89d7e948-1ec3-50a7-92cb-0cc780a6a62f | note | Check Item - Check Item
7c240845-7d4d-5ce5-ac98-85ca0fe4d09e | note | Reference - MRTS51 Cl. 7.1
| checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
927fba6b-0bf7-5698-935d-f89818d3e1d2 | note | ○ Landfill Gas Requirements
00903281-549f-5c92-b476-a7731e2e0b82 | note | ○ Contaminated Land Requirements
7d71ba08-28ab-53df-8ccf-6e6741d3797b | note | ○ Water Quality Requirements
1068973a-21da-5329-810e-f1846ce933b6 | note | ○ Bio Security Requirements
fc8d3f0b-95cc-531d-8834-3266d5e5563e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1698c892-6402-5cab-bca7-e4dcee6c4d89 | note | Check Item - Check Item
4e5cb805-67f2-5345-82f8-205b4bc39c96 | note | Reference - Contract Documents
| checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
d6c7c0c0-a7f0-5419-a44a-6b6d2c4c7e08 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bb333034-0408-53b6-b78d-65dfffd5cde3 | note | Check Item - Check Item
7693c201-2e7c-551c-94b0-67ae4ccd8741 | note | Reference - MRTS51 Cl. 8.4.1
| checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
701c4929-686b-590c-88b7-8c14c8077e56 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
798ba5ee-25ba-5ba3-be7a-a4e89885cb95 | note | Check Item - Check Item
15805cf9-d941-5704-9228-bf36a6c1b121 | note | Reference - MRTS51 Cl. 8.5.2
| checkpoint | Project records shall include all noise monitoring results if required
24fffd8a-6846-5389-97ed-5e76d9a5d06c | note | Check Item - Check Item
8ee3cb17-5bb4-5e95-a0cf-11fbf4bdb11d | note | Reference - MRTS51 Cl. 8.6.3
| checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
f99276a2-a139-576a-a5cf-0f7b8816c60c | note | Check Item - Check Item
6d2bcf5a-df97-5a68-8315-e635bc0fe055 | note | Reference - MRTS51 Cl. 8.6.2.3
| checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
7dcc64f5-1990-5292-b64f-39af12b5fb31 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e2ca4d09-4525-5dae-a052-906567f99e55 | note | Check Item - Check Item
cee4d10b-0d29-5f72-a850-c4f12871f398 | note | Reference - MRTS51.1 Cl. 8.6.1
| checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
73edeca6-ac93-5f2e-bc59-48b4142bc39f | note | Check Item - Check Item
3f41a922-1f9e-53b4-a925-70fb0121acfe | note | Reference - MRTS51.1 Cl. 8.6.2
| checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
dab0375a-d1d8-571c-b0ab-d8940857507b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2c243f17-9876-5d2b-9664-1f3bb2f4b6e8 | note | Check Item - Check Item
1f35fd9f-2a34-5c61-90b8-53af3f59e27a | note | Reference - MRTS51 Cl. 8.7.3
| checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
15da82da-acab-5845-8625-c56b525df92c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5ceac32a-036e-5f51-afda-098a8a28cedb | note | Check Item - Check Item
3ec7c74a-8e9a-5a7e-9622-1f3bb1ff58db | note | Reference - MRTS51 Cl. 8.8
| checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
df72a48d-ea7a-54db-ba9f-69298cd5f19d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4da276f4-3099-5682-af92-899995db6f4b | note | Check Item - Check Item
6b068101-c664-5ebe-bcaa-ca7d7299957f | note | Reference - MRTS51 Cl. 8.9.1
| checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
90803cdd-afe7-52dc-8959-4b8d6f0d39e6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4edc8d02-2e5c-5773-9a9a-a749c7f922aa | note | Check Item - Check Item
5f18021c-88dd-52d8-ad17-e439c6a99d17 | note | Reference - MRTS51 Cl. 8.10.1
| checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
b6e6f51d-9511-5527-8def-28ea619202bb | note | Check Item - Check Item
6386889a-282a-54e7-a8c8-6beae546c3d4 | note | Reference - MRTS51.1 Cl. 8.10.3
| checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
dbc7eabd-87d3-51d4-86db-f918dc16ad42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e69d80e-8955-537a-a3cd-e99204060390 | note | Check Item - Check Item
3ac1cfb6-485f-5140-a00f-0a165a0c9be9 | note | Reference - MRTS51 Cl. 8.11.1
| checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
f3dd0de4-d5dd-5baa-88b8-7dc773ff31cf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4b24cefe-9d6c-5654-9349-a860a55bc562 | note | Check Item - Check Item
bfc4dd9e-af6a-50a2-9889-140b10900b74 | note | Reference - MRTS51 Cl. 8.12.2
| checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
2aca0a91-b08e-5214-b33f-92f02d56092b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
984d9c8b-61fc-5d0c-90ad-69cbe64c6ad0 | note | Check Item - Check Item
12d7000e-08ca-5681-85e1-c50ed97971b4 | note | Reference - MRTS51 Cl. 8.13.2
| checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
daaa8a32-f285-5388-8d64-0269dcd3e94d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b290434c-06d6-54a8-ab59-58fe69175a8b | note | Check Item - Check Item
de53b0a9-f289-51df-a179-beda922bf3a5 | note | Reference - BCC Supplied Certificate
| checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
62438789-269b-5f5e-b3b6-787ca37d9f98 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4e7f94be-253a-5327-9a53-2c5aa5daecd9 | note | Check Item - Check Item
7d871c09-06d0-5b59-8b97-73aa1f895c65 | note | Reference - MRTS51.1 Cl4.2
| checkpoint | Maintan a animal tamping register inline with the SMP
cd366fc7-46e1-569f-bfff-e2f86fcbf700 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b5afda87-abda-5364-9b78-b19c41070d14 | note | Check Item - Check Item
9b19601b-078e-52a3-be5f-92743469328f | note | Reference - SMP requirement
| checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
4039491b-1fd7-57c0-bae4-06344db28b47 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
04982222-dc4c-5094-8bc5-674fd1616c0c | note | Check Item - Check Item
c00cbd39-9651-52b8-b908-222d99400cfd | note | Reference - MRTS51 Cl. 8.14.1
| checkpoint | Final Verification
f26b0b9a-e68a-5d84-909e-70bae8b1cc95 | note | Project Manager Verify that the Above has been Constructed according to Specification
408c3a11-b514-559a-85a7-ff925ad38867 | textbox | Print Name:
81041d08-204d-53ab-af9f-a1670e7bd824 | date | Date:
6669e8ab-d5b8-5091-8cee-3db4018bc2e0 | note | Client Verify that the Above has been Constructed according to Specification
16d650a2-5495-5e3a-846e-c731ac50a2fa | textbox | Print Name:
bce5f991-c587-5bc9-95c2-cae30ace7a37 | date | Date:
| signoff | Signature

## 52.01
| checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control | 2aa43ab3-86f6-46ce-89d7-12f2a1601309
| section | Details
| checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
b9f7953a-aa02-51f2-959b-b09532bd32db | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
723a2936-a564-5572-b760-c02839a27284 | note | Check Item - Hold Point 1
2620837e-22aa-514e-9a82-7f16df207281 | note | Reference - MRTS52 Cl. 6.1
| signoff | HOLD POINT
| checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
351821c6-9dce-557f-825b-da5e31de1d04 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
5de1a36f-f023-55e7-b1e0-06252d8947c2 | note | Check Item - Hold Point 2
8d91b496-d85f-5a88-a9af-75d8ab1b2d3a | note | Reference - MRTS52 Cl. 7.1
| signoff | HOLD POINT
| checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
b0f59a9d-6c2f-530a-98bd-28285810845d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8795358a-aa5d-50d9-963a-449b5cf2d53d | note | Check Item - Records
146c7ca7-3d06-500f-8084-343d6ab9c028 | note | Reference - MRTS52 Cl. 8.1
| checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
74985fc5-147b-5c3e-984d-49ae857eb953 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
02b8677f-81f8-525c-b447-d16c06a15970 | note | Check Item - Records
7811f0d5-7192-50e5-b3cb-28386345b2c7 | note | Reference - MRTS51 Cl. 8.2.3.2.1
| checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
58fd9a96-dd65-5ad5-9d88-bdb07ad94fee | note | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
1c6558fc-785e-50b3-bdab-a1b30d524e83 | note | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
2b207b65-2409-5eed-a6b9-3ba33d8b7c4f | note | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
e05739a1-359b-5ee2-87e6-41bd5951d102 | note | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
97737b63-e942-5a39-b90e-5a9649ab4284 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
371fac44-33c6-54e3-9ad8-3b0470ad5e4c | note | Check Item - Check Item
fa9a612f-2ad4-5d15-bcde-a514c1ed2905 | note | Reference - MRTS51 Cl. 7.2
| checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
95aec901-7ac7-5830-8f50-b444cd0c74a5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c5af3c1c-e17d-5560-a635-172080dd2b96 | note | Check Item - Check Item
50df2dab-ad76-55a2-85f7-e7dfc7627ab8 | note | Reference - MRTS51 Cl. 7.3
| checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
ea183d62-fe38-5c67-b32f-46f0c41e1130 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
02d86e97-c9f2-5bb0-8a9b-08dd34c80606 | note | Check Item - Records
0b5f303d-54e7-5da1-a6b8-1ddda54f7e31 | note | Reference - MRTS51 .1 Cl. 4.1.1
| checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
e8cac93a-3c26-5e9c-b925-2bf00c0a3f0d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e35dfac1-e27d-5d28-bafc-612ad1c22665 | note | Check Item - Records
74978ad4-f723-53a1-b657-0b107fdcb80a | note | Reference - MRTS51.1 Cl. 4.1.3
| checkpoint | Final Verification
1fa722cc-87df-5f1e-9739-d4c2c885a735 | note | Project Manager Verify that the Above has been Constructed according to Specification
bfee4659-e2b6-511d-aedd-7b726c6e9c6f | textbox | Print Name:
8f17cb8f-71b0-5f6c-a152-3911346d6ad9 | date | Date:
0fa62980-a831-58ba-83cc-a9f2c421b5f6 | note | Client Verify that the Above has been Constructed according to Specification
2b3aa6ee-029e-5420-92bd-5c5ff53badae | textbox | Print Name:
ee8174ca-2445-54ad-b203-c11bff996c19 | date | Date:
| signoff | Signature

## 70.01
| checklist | 70.01 - MRTS70 Special Class Concrete | 75c16999-beb7-4b55-9059-290bc55880da
| section | Details
| checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
7673d6e9-5c7b-5263-88f1-84a485fdfbe3 | note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
01540ee4-97c0-5b3d-945a-09ca2c231b54 | note | Check Item - Check Item
abc95a54-376f-5b20-bd1b-cd512ebd4441 | note | Reference - MRTS70 Cl 13.1
| checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
05d0e4e0-56f5-5e8b-b2ea-c1c48589f3c0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
daf51ca7-c306-5d4e-8646-00a641a404b6 | note | Check Item - Milestone
5963dac0-068c-5fe5-bf9a-4731c8a8c22f | note | Reference - MRTS70 Cl 15.3
| checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
b1635bd7-4773-5d50-93b7-55561c22816f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c0eaf6a0-6a75-571c-94a8-ad90eb2c80f5 | note | Check Item - Hold Point 2
32f38b3c-43cf-58bd-af23-d5e7f6ff6e79 | note | Reference - MRTS70 Cl 15.3
| signoff | HOLD POINT
| checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
7ca5b920-16e3-5f9b-aae5-e98b67282c68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9dee83eb-1a33-552a-90fa-43c96946f6e8 | note | Check Item - Hold Point 3
46f9578a-dcff-546a-b745-a8be00a8b257 | note | Reference - MRTS70 Cl 15.4.1
| signoff | HOLD POINT
| checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
74f47c8e-09d4-5af8-8e55-f19c799a70fe | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32348487-2c00-5216-8a0d-32d73c5d58b4 | note | Check Item - Hold Point 4
7351af4a-aeee-5dae-8597-909811f4d493 | note | Reference - MRTS70 Cl 15.6
| signoff | HOLD POINT
| checkpoint | No concrete shall be placed in the Works until:
954a3f92-2422-5286-a235-079b45bd0452 | note | a) the formwork and reinforcement have been inspected
eba6423a-37c5-554d-be64-25c3d306b336 | note | b) all foreign material has been completely removed from the forms
107a44b9-f63e-5f99-823b-9077d2c4c964 | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
bceca7ec-b26f-57ed-af3c-e1fb0cd13776 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8faf13a5-6765-5b02-b3ad-e2a6cc8a99a6 | note | Check Item - Hold Point 5
8ae4bf0b-8e8e-5f45-90c4-424a959724a9 | note | Reference - MRTS70 Cl 15.6.1
| signoff | HOLD POINT
| checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
81ed9974-9daf-5daf-ad5b-5ca1eb847006 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1aafb273-0e69-5775-bde3-1ecd6c1aff95 | note | Check Item - Witness Point
294115e3-4442-5d62-8f5a-7196adf311c7 | note | Reference - MRTS70 Cl 15.6.1
| checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
301b10b4-164c-5e1b-b07f-709f14f25fe0 | note | Acceptance Criteria and Frequency (Project Specific) -
2d82ed7f-a54f-5f30-aa8f-9e4bd02b9950 | note | Slump Test: ¦¦ Spread Test:
4675c9ab-8794-5fa1-bec2-5067aee8b503 | note | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
1374ae34-88cf-5000-aab1-dfc9223cd71a | note | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
8d6aee61-33a5-5aa0-888e-613a33636835 | note | 80<110 - ±20
fde55960-19d7-5bae-bd48-6b7283ebf45f | note | 110<150 - ±30
477a910a-9d3b-5a52-9dab-a7d80a7363f6 | note | 150< 200 - ±40
cd9b76ec-f4e2-5e91-95a5-aa1351c26a05 | note | Every Load
a75d2c28-fca7-55c7-bd49-0624078306e6 | note | Check Item - Check Item
cbd0ac18-457e-51e2-ac48-93ff34365175 | note | Reference - MRTS70 AS 1379 Table 6
| checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
884cae92-d7de-5700-8907-99184f403390 | note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
be3ccc48-357b-5d63-8c90-f016db276ce7 | note | ○ 4-10 Loads - 4 Samples
d8006661-92e3-5b7e-8296-92e628a5c9fd | note | ○ 11-23 Loads - 5 Samples
dee24497-37d3-5527-a683-296e1676c8f8 | note | ○ >24 Loads - n/4
f17c1dee-24a9-5d3c-9b3c-c397e12422cd | note | Check Item - Test Results
6f9efa1a-8d9f-5c69-a6b0-bac878ef3551 | note | Reference - MRTS70 Cl 15.2
| checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
cdd28392-52ac-5b0b-8739-79b83bdb2c55 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b0fa31c8-a772-5b37-a5c7-beda7c382567 | note | Check Item - Check Item
6de19bcc-086d-5dc7-847c-1b2ed526b738 | note | Reference - MRTS70 Cl 16.5.2
| checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
544389b6-38b8-5695-a1d8-5d8c207b2f5a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3be26b44-b702-5347-bf31-dfda510f9ec2 | note | Check Item - Check Item
f65696cc-8431-50f5-8a84-4799f245e92f | note | Reference - MRTS70 Cl.16.5.1
| checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
e03f1815-efde-5fee-bbe4-edb0e712dd42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
16728447-6dda-5672-adb5-4eafc40a9a2d | note | Check Item - Hold Point 7
9da9b862-7f93-5734-8b56-cd74def7b79c | note | Reference - MRTS70 Cl 15.13
| signoff | HOLD POINT
| checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
d1adcf51-2236-5009-a06d-0fa91d84014c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2c2bc963-79c8-5ae3-89eb-18abff9877a8 | note | Check Item - Hold Point 6
6e29e47c-cea2-50ed-8cdd-8e96bed26097 | note | Reference - MRTS70 Cl 15.8
| signoff | HOLD POINT
| checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
71b05a02-0078-5d5c-9a45-cbee220e1bad | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d65f268b-79d4-5dfa-93bf-e89b6607d235 | note | Check Item - Witness Point
691cf93e-03d1-5b9a-99fd-f35bb077c889 | note | Reference - MRTS70 Cl 15.8
| checkpoint | Following removal of forms
2032b894-988d-5fbd-8733-2154479b0f2f | note | ○ Fins and unwanted projections are ground off
6d80465d-ac93-54cd-bde8-5c2a3c3828c0 | note | ○ Pockets and honeycombed areas repaired using approved methods
b161e366-0efc-5f8b-9577-1a3b85bc00cc | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
78d0b73f-8505-5ed1-b921-df8abc0d675d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4670750e-507a-53d9-97b3-2fd17eeeae18 | note | Check Item - Check Item
244cdf90-8d0c-5413-be90-5e9054c3275e | note | Reference - MRTS70 Cl 16.8.1
| checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
c736d015-6f28-5b51-8432-6f83892fafb1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
3fd32484-4ec0-5f5a-8bf8-a83f5a12c8d1 | note | Check Item - Check Item
1e4a4ea8-cc62-5d2f-ab13-413dda142279 | note | Reference - MRTS70 Cl 15.7.3
| checkpoint | Acceptance or Rejection of Hardened Concrete
7b544a7d-e794-57c7-8bb3-49ee1bffce31 | note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
038c04d3-3d55-5081-8638-3830810d0a9f | note | b) < Fc (Ave 3 consective samples from Lot)
01342202-d078-5d95-8934-d1ae8ef04bcd | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
c35803d5-7c39-5126-94fa-ab63f6c9cc2c | note | In addition
56a53bf7-5d93-5bbe-91cd-b1d8b6b5cde4 | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
a3ae08f8-0a12-5b21-a048-6084c85dbd2f | note | Check Item - Test Results
28576de6-e50d-5909-9b2f-a7fb583387e7 | note | Reference - MRTS70 Cl 12.5
| checkpoint | Final Verification
77140dfc-23bd-5f31-b46d-8037889de18f | note | Project Manager Verify that the Above has been Constructed according to Specification
6ecf3767-5ece-50f2-a582-8a4620a60bc8 | textbox | Print Name:
c8495920-8a1c-519c-bb90-659306f336c9 | date | Date:
bce60626-0b44-59b5-910e-3f8bf2dffbfb | note | Client Verify that the Above has been Constructed according to Specification
ca27b47a-0aac-5410-b70f-fc974001452d | textbox | Print Name:
bb1d92a5-4f97-535b-9f7d-ed2375b7be5d | date | Date:
| signoff | Signature
| section | Details: Concrete Record
| checkpoint | 1 - Date
| date | Truck 1:
| date | Truck 2:
| date | Truck 3:
| date | Truck 4:
| checkpoint | 2 - Docket
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 3 - Time Batched
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 4 - Truck Arrival Time
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 5 - Load Size (m3)
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 6 - Mix
| checkpoint | 7 - Slump (mm)
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 8 - Slump Time
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 9 - Concrete Arrival Temperature (˚C)
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 10 - Ambient Temperature at time of slump (˚C)
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 11 - Time Start delivery
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 12 - Time Finish Delivery
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:

## 70.02
| checklist | 70.02 - MRTS70 Normal Class Concrete | e6fe82a7-e19c-41e6-bf33-99a454a1e40f
| section | Details
| checkpoint | Concrete class - The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
7d95f0a0-73d7-5720-8be1-1b25c13a5be9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3f6cdb1f-8b95-5a62-b848-d39e94899929 | note | Check Item - Check Item
2db1632a-2de6-5094-a64f-0e98bcb678a4 | note | Reference - MRTS70 Cl 17.1
| checkpoint | Acceptance and rejection of hardened concrete - Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall betested on a project assessment basis, where more than 25 m³ of concrete is used:
eccbf692-3f45-5402-842c-f5dc02f3bc08 | note | a) signpost footings and plinths with dimension greater than 150 mm
bf76f034-284d-56e2-9303-4a9054879721 | note | b) spill through or rock grouting, and
bf7ab743-63d5-5429-9da7-d7e3aa0f81f1 | note | c) manually placed kerb and channel on or alongside concrete base.
25f921fb-b63f-5acd-943e-f2856dc93528 | note | ○ Production assessment reports in accordance with AS 1379 shall be submitted to the Administrator
b07c1b79-159c-515f-a32e-19ad6a9e1c07 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e10a6b1a-929a-5d39-b4dd-a564dbf76d7b | note | Check Item - Test Results
3a946558-348c-5892-af18-36d8388a13c5 | note | Reference - MRTS70 Cl 17.8
| checkpoint | Approval of falsework - All formwork shall be subject to inspection and approval by the Administrator
2303c03e-d1b5-5a3a-8c73-2a2b58c99ab9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
88216553-5041-5fe2-9822-b7617d683376 | note | Check Item - HOLD POINT
ffdebc89-7d24-526d-ab3d-8bb600f6bc5e | note | Reference - MRTS70 Cl 17.10
| signoff | HOLD POINT
| checkpoint | Approval of formwork - All formwork shall be subject to inspection and approval by the Administrator
6e410e02-826d-5d0f-802d-579e5c4a0477 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
68f1b8e3-818c-5f9c-89a4-092f626087a1 | note | Check Item - HOLD POINT
0c8974de-1485-5c33-8b74-076f53828954 | note | Reference - MRTS70 Cl 17.11
| signoff | HOLD POINT
| checkpoint | Supports (bar chairs and spacers) - All bar chairs and spacers shall comply with AS/NZS 2425
a856d75e-5f8e-5fac-9247-e0dbda33af5f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b8dd5251-8360-5705-b9fa-b4e4f7b12ebc | note | Check Item - Check Item
8a07cd17-6f3d-55d5-88a0-d96e77e1d8e5 | note | Reference - MRTS70 Cl 17.11.1
| checkpoint | Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground / bedding and the concrete
52686cf5-7ecf-5489-9399-3ffc0048c365 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3371877c-f597-5f31-987a-b7cd9a2c7013 | note | Check Item - Check Item
19390b28-d55b-5c7d-a279-7d6412117d64 | note | Reference - MRTS70 Cl 17.12.1
| checkpoint | Approval to place concrete - No concrete shall be placed in the Works until the formwork and reinforcement have been inspected, and all foreign material has been completely removed from the forms.
9300da8a-9490-5175-bd56-a6fde8a5d65e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2536dcaa-5fe6-5487-8810-8473528babb5 | note | Check Item - HOLD POINT
0bc3bf6a-0a77-544d-9d75-db3122ecb2f4 | note | Reference - MRTS70 Cl 17.12.1
| signoff | HOLD POINT
| checkpoint | Placing of concrete - The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
fee17761-3286-5e5b-b7cc-d4eb065a0811 | note | Check Item - Witness Point
8002f1e2-ee6d-5c36-aa22-8bf34a1b4b10 | note | Reference - MRTS70 Cl 17.12.1
| checkpoint | Removal of formwork - For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed.
700433c3-62a3-51b1-9bd5-a3baa401b6ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
03d56e8a-5f5c-5cb9-94ae-13f252f5fe35 | note | Check Item - HOLD POINT
095448ee-0626-5a2f-8aa9-1bd7fc6f6f22 | note | Reference - MRTS70 Cl 17.16
| signoff | HOLD POINT
| checkpoint | Final Verification
47fd21af-94cd-5269-b0ba-680c9e9a8a07 | note | Project Manager Verify that the Above has been Constructed according to Specification
7e8df5c0-2521-5945-913d-97715c9766ac | textbox | Print Name:
d7b638d8-4b41-5bc7-90cd-7c23f3ce59c4 | date | Date:
5b27c1ac-0819-5da7-9a57-0052e806b1cf | note | Client Verify that the Above has been Constructed according to Specification
3e57fb79-3cfa-57fb-b724-fd1a01359cf6 | textbox | Print Name:
362111bc-80d6-59ab-929a-612797aa1bcc | date | Date:
| signoff | Signature
| section | Details: Concrete Record
| checkpoint | 1 - Date
| date | Truck 1:
| date | Truck 2:
| date | Truck 3:
| date | Truck 4:
| checkpoint | 2 - Docket
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 3 - Time Batched
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 4 - Truck Arrival Time
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 5 - Load Size (m3)
| textbox | Truck 1: | m3
| textbox | Truck 2: | m3
| textbox | Truck 3: | m3
| textbox | Truck 4: | m3
| checkpoint | 6 - Mix
| checkpoint | 7 - Slump (mm)
| textbox | Truck 1: | mm
| textbox | Truck 2: | mm
| textbox | Truck 3: | mm
| textbox | Truck 4: | mm
| checkpoint | 8 - Slump Time
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 9 - Concrete Arrival Temperature (˚C)
| textbox | Truck 1: | ˚C
| textbox | Truck 2: | ˚C
| textbox | Truck 3: | ˚C
| textbox | Truck 4: | ˚C
| checkpoint | 10 - Ambient Temperature at time of slump (˚C)
| textbox | Truck 1: | ˚C
| textbox | Truck 2: | ˚C
| textbox | Truck 3: | ˚C
| textbox | Truck 4: | ˚C
| checkpoint | 11 - Time Start delivery
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:
| checkpoint | 12 - Time Finish Delivery
| textbox | Truck 1:
| textbox | Truck 2:
| textbox | Truck 3:
| textbox | Truck 4:

## 70.03
| checklist | 70.03 - Supply of Concrete
| section | Details
| checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS70 Cl 9.2
| checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
2273804f-ba3f-58d2-8ddc-3b7e6307b212 | note | Check Item - Milestone
aa33854f-f6cf-5347-82a1-e2ea8fb5e70b | note | Reference - MRTS70 Cl 17.6.1
| checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS70 Cl 13.1
| checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS70 Cl 15.11.1
| checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Milestone
| note | Reference - MRTS70 Cl15.5
| checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
| note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
| note | Check Item - Witness Point
| note | Reference - MRTS70 Cl 15.1.1
| checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Hold Point 1
| note | Reference - MRTS70 Cl 15.1
| signoff | HOLD POINT
| checkpoint | Final Verification
| note | Project Manager Verify that the Above has been Constructed according to Specification
| textbox | Print Name:
| date | Date:
| note | Client Verify that the Above has been Constructed according to Specification
| textbox | Print Name:
| date | Date:
| signoff | Sign ITP