## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 16.02 - Turfed Areas | itp |  |  |  |  | 16.02 - Turfed Areas
section | Details
checkpoint | Installation of Turf Shall Comply with Project specific Requirements listed in MRTS16 Annexure.
note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
note | Check Item - Hold Point
note | Reference - MRTS16.1 Cl 3.3.1
signoff | HOLD POINT
checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Hold Point 8
note | Reference - MRTS16 Cl 8.5.2 & MRTS16 CL 8.4.1.1
signoff | HOLD POINT
checkpoint | Topsoil shall be installed within three days from the completion of the subsoil operations. Topsoil shall be spread to the required depth. (75mm)
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Witness Point 6
note | Reference - MRTS16 Cl 8.5.2
checkpoint | Subsoil operations shall occur immediately after the application of amelioration agents. As per Table 8.5.2
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Witness Point 3,4, or 5
note | Reference - MRTS16 Cl 5.3.3
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 7
note | Reference - MRTS16 Cl 8.2.1
signoff | HOLD POINT
checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.4.2.1
checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
note | c) on the day turf is delivered to site
note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.2.
checkpoint | Subsoil Testing Requirements Completed as per requirements of Form D & Form E
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 CL 4.1
checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.2.1.4
checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.2
checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.1
checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.2
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature