## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - Subsoil Drainage | itp | ITP - Subsoil Drainage | 1035220e-4de9-4281-9747-f52bcce72f91
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
| checkpoint | 1.01 - Drainage aggregate
64e7a062-b7cb-502e-9117-6a98902d6241 | note | Detail of Activity / Test - Crushing Resistance
5b38e53c-7053-5f71-bbb9-faa013ced117 | note | Action (Hold, Monitor, Witness) - H
d2bf7384-7eda-504d-9180-a67be0043101 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
2bc4e6d4-942f-5b74-9a6f-05481af9783f | note | Inspection / Test method - NZS4407:3.10
e6ca1a10-a4b3-5a6e-8819-7ecb8ba4042d | note | Acceptance Criteria - > 100KN
516d62ce-61f0-519e-a716-98aab2a40b1d | note | Record documents (QCP - Quality Control Portal) - IANZ report
fd56c3c1-bb49-5608-9a35-7a448b7b07a6 | note | Responsibility - Contractor
c77e9cea-3aad-5b8a-98c6-a4e5850e8d76 | note | Designer / PTG - A
cc1f6e8b-729e-584b-862d-a1627a7b89bb | note | Eng. Rep / NZTA - I
b6ed475e-42b6-5246-8e38-3bd6eee99bab | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - Drainage aggregate
293b03d2-2b08-5bd3-adfc-8276920019ac | note | Detail of Activity / Test - Particle size distribution
ec132bcf-a34e-50aa-a34c-adc397cef5a0 | note | Action (Hold, Monitor, Witness) - H
2f87f67d-f118-53f3-932a-663b6d839501 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
49408d58-dbc1-5fee-8c52-f9ad93b4b383 | note | Inspection / Test method - NZS4407:3.8.1
196d44ba-1c4d-5a10-8376-e4285d58d7be | note | Acceptance Criteria - As per TNZ F/2
bc1db75e-6127-5f3c-a85f-7a449749e48a | note | Record documents (QCP - Quality Control Portal) - IANZ report
678e96c5-4eaa-5f2f-8924-6181c36f65c3 | note | Responsibility - Contractor
c6efc85c-be42-535b-9d9f-511f55aaa4a1 | note | Designer / PTG - A
009c3d2b-b43c-56bf-8610-99db4c96a97c | note | Eng. Rep / NZTA - I
2a8839fd-f546-5bb6-9974-0fd20ae248c7 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - Pipe
e216823d-1d92-551a-9d30-229de4c76fc9 | note | Detail of Activity / Test - Subsoil Pipe Material
7fa00227-5586-581a-8320-961e4b50e114 | note | Action (Hold, Monitor, Witness) - H
4df14647-f91f-56d2-9738-eef988ad31a4 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
94f702d5-938a-5914-838d-4baf33e30105 | note | Inspection / Test method - Dockets for each delivery
8bfddd07-4382-581a-aae0-0a1bb827f928 | note | Acceptance Criteria - Compliance with TNZ F/2
fef19b13-a9e5-5be4-81dd-8d6d6e5795c9 | note | Record documents (QCP - Quality Control Portal) - Delivery Docket
e4621bda-7285-5eb2-8522-3aa0d61ce2a4 | note | Responsibility - Contractor
871b0e1f-ff97-51a3-8d71-f6d0b82a6004 | note | Designer / PTG - A
b5362abe-06df-528f-b54e-9f098fb8069e | note | Eng. Rep / NZTA - I
c1f4fe18-af75-58e8-8fc7-8a9b291b49a3 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 3.12 - Alignment
2347b048-0d29-5685-8be1-5875d34a331a | note | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
a1e95f65-4e7c-5a5d-a8d5-9a3918568319 | note | Action (Hold, Monitor, Witness) - H
e1a9977b-e85c-5c47-ba06-e418c3351a8d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
b716644c-db99-53de-b315-e6339ef336e2 | note | Acceptance Criteria - Engineers Approval
42f47c24-0362-5f0f-a47a-8e6646ec0951 | note | Responsibility - Engineers Representative
5d8837a7-2bfe-59b2-b8cc-4ddf9f14e98f | note | Designer / PTG - A
2cd2c944-71d1-5b33-a705-f9667ed423c6 | note | Eng. Rep / NZTA - I
35318f00-a1ba-517f-9f61-a1494fdf4f55 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Excavation
45f87071-fbfc-5b06-a3c7-c5e1148d1777 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
79b232e5-e734-502d-802d-7dda955ab71a | note | Action (Hold, Monitor, Witness) - M
d3f548cf-a3c3-5359-a53c-b313b6f30df2 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
a826072e-a7b1-5c40-a041-097580457208 | note | Inspection / Test method - Visual / Photo
408c859d-dc6d-5202-bc43-912a4545695f | note | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present
d7888499-3457-5125-a1bc-43e5cce27ab4 | note | Record documents (QCP - Quality Control Portal) - Checksheet
180d82f0-d274-5004-a9af-e746eb4eef45 | note | Responsibility - Contractor
0fec3e8d-abe8-52d3-ba74-33b1d60f8951 | note | Designer / PTG - A
4b0aa123-670a-540f-a583-84b31c876d1c | note | Eng. Rep / NZTA - I
fc3fd29d-700b-5332-ae21-156a0733ba2b | note | Contractor - R
| checkpoint | 3.14 - Trench Lining
b9658788-cea7-5db7-84a7-befeeb96a25d | note | Detail of Activity / Test - A29 or other approved Bidim to be placed and wrapped around Trench.
11f2332f-6ece-5f0e-93f0-90d691640591 | note | Action (Hold, Monitor, Witness) - M
9058df20-1f46-54c1-8eb6-20c8898db198 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
d735d523-8435-5d53-81eb-c9b7a2424f61 | note | Inspection / Test method - Visual / Photo
04a8e670-3704-5672-adbc-08f36d0cc58f | note | Acceptance Criteria - Minimum Width 300mm.
a04b8a4a-06cb-5736-bca9-99478a429054 | note | Record documents (QCP - Quality Control Portal) - Checksheet
546b12c6-83cc-563c-98b6-28f5d1121e95 | note | Responsibility - Contractor
94f109fb-d361-56cb-8b8a-7a6b9f16e2e4 | note | Designer / PTG - A
fff34920-501b-5cfe-bfa7-907b4fb1ab7b | note | Eng. Rep / NZTA - I
d399d136-55b4-5244-ab0d-78d641d8285c | note | Contractor - R
| checkpoint | 3.15 - Pipe laying
3a397c4e-b90b-5f22-857d-94a4e5b11c0b | note | Detail of Activity / Test - Pipe must have 100mm of Cushion. Drainage 60:40 Material to be used.
07d10577-c3e2-53c7-b413-6d322df89ef6 | note | Action (Hold, Monitor, Witness) - M
5945b6c0-1a19-5070-8a0a-4298ddffc454 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
1c58fa63-a6f3-54a2-8212-6a63538d90cc | note | Inspection / Test method - Visual / Photo
acac2d88-d236-59a9-8a9b-7e5b5fee41d9 | note | Acceptance Criteria - Minimum 100mm
874e680d-198c-5525-9346-500332eb9f51 | note | Record documents (QCP - Quality Control Portal) - Checksheet
b5c27e33-1b1b-5a36-8470-393b94282e91 | note | Responsibility - Contractor
5b430ea0-1b40-5bc6-b45b-9b96d5b849a5 | note | Designer / PTG - A
bf3cdf29-7d4b-5703-adb6-d156be648991 | note | Eng. Rep / NZTA - I
da65414e-1a63-51c6-a63a-a9439453c2fd | note | Contractor - R
| checkpoint | 3.16 - Pipe laying
df4baec8-c4a0-5023-a677-779ce67373ab | note | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
cb68b808-125a-55cb-abaf-d50a5416156a | note | Action (Hold, Monitor, Witness) - M
f3fdc347-b4af-53fd-b85c-89c08443edac | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
c2db367f-5711-59e1-bcc9-926ef470c7c0 | note | Inspection / Test method - Visual / Photo
c3bc8b9f-a924-57f4-8534-76ad56dee8bb | note | Acceptance Criteria - As Per Drawings
9d6505ee-e1b7-5dcc-87e6-0cc4d049d180 | note | Record documents (QCP - Quality Control Portal) - Checksheet
fe469aeb-f452-52dc-a48a-559f9a6cf628 | note | Responsibility - Contractor
da74c741-6b38-57fd-817d-ff44fce5d2c4 | note | Designer / PTG - A
0a8754c6-2055-5a1e-afd9-0f975d76faa1 | note | Eng. Rep / NZTA - I
a0dc744e-d959-5c84-8a7e-774ab76d361e | note | Contractor - R
| checkpoint | 3.17 - Backfill
3747bf93-3484-515d-ac41-55e5b10fdfc0 | note | Detail of Activity / Test - Drainage 60:40 Material to be used.
525f16be-e9f5-5e48-8e58-5672a8aaa7fa | note | Action (Hold, Monitor, Witness) - M
40b93bc5-548f-5082-ad0c-b79ab3f903b9 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
96d6929c-2fd1-5a86-a754-94505c2860ff | note | Inspection / Test method - Visual / Photo
8ed19015-994a-5ca0-b9fc-50e113d2a250 | note | Acceptance Criteria - As Per Drawings
978c27e4-2007-5846-b779-7bf8faf3a986 | note | Record documents (QCP - Quality Control Portal) - Checksheet
950eab89-8af2-5aab-8744-ad1387fbff98 | note | Responsibility - Contractor
2b8cb141-4932-5ad2-9382-69ebb385149e | note | Designer / PTG - A
76c9bec4-cfa3-5081-9c60-0709075ff9a5 | note | Eng. Rep / NZTA - I
3864f6a1-b1c6-5d2f-a23e-2bac3bd8dd03 | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b05f4af3-084d-5f81-8ec5-d9dbf93186f6 | textbox | Contractor's Rep Name:
dfa062aa-1428-59d1-8f6d-a24a6a8929bf | textbox | Engineer's Rep. Name:
6f79261e-d138-5c67-b01e-d835e15f5235 | date | Date:
| signoff | Add Signature
| checklist | Shoulder Clearing Checklist | itp | Shoulder Clearing Checklist | 6bbfb255-b493-4437-b829-9a352584fbf3
| section | Pre-site checks for the following
| checkpoint | Photos taken @ Pre start of works
31f33bbd-b990-58c9-8b9d-cc285d03fdb9 | note | Responsibility - FP/Su
f8a85bed-dcec-5d78-a485-fa951ca62bd8 | note | Comment - Field evidence for ITP
| checkpoint | Check culverts in vicinty of work inlet/outlets
33ca181a-550a-5984-b965-e85fb5d2de8b | note | Responsibility - FP/Su
89e19212-9364-5f6b-8da2-1cf5d168e948 | note | Comment - Field evidence for ITP
| checkpoint | Edge Delineators - offset position to re-instate if required
fcf70c19-6229-509d-8d08-222fc744504c | note | Responsibility - FP/Su
ac60b28b-00d3-58d0-8842-51662efa6209 | note | Comment - Field evidence for ITP
| checkpoint | Permanent Roadside Signage - Offset position to re-instate if required
ff28d3da-8737-5e5d-9079-8732e62388da | note | Responsibility - FP/Su
24b5329e-5718-56e3-9ea6-2ee18fcb9644 | note | Comment - Field evidence for ITP
| checkpoint | Photos - Post completion of works
9404eeba-5ce8-5a5c-a782-4b0e1a108e33 | note | Responsibility - FP/Su
08d6ecf5-a0b7-56fb-b83a-285aa90dbcd4 | note | Comment - Field evidence for ITP