## B02-UBG
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Project Name |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA F/2, F/5 & Regional Infrastructure technical specifications (RITS) |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Designer / PTG | Eng. Rep / NZTA | Contractor | Date
1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
1.01 | Drainage aggregate | Crushing Resistance | H | 1 Test per material per source | NZS4407:3.10 | > 100KN | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | Particle size distribution | H | 1 Test per material per source | NZS4407:3.8.1 | as per IFC drawing | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.03 | Pipe | Subsoil Pipe Material | H | each delivery | Dockets for each delivery | Compliance with TNZ F/2 | Delivery Docket | Contractor |  | A | I | R | dd/mm/yy
2.0. CONSTUCTION
3.12 | Alignment | Subsoils to be placed behind the Kerb line or as instructed by Engineer | H | For each site where subsoil is required |  | Engineers Approval |  | Engineers Representative |  | A | I | R | dd/mm/yy
3.13 | Excavation | Excavtion of Trench should be within tolerances. | M | For each site where subsoil is required | Visual / Photo | Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified | Checksheet | Contractor |  | A | I | R | dd/mm/yy
3.14 | Trench Lining | A29 or other approved Bidim to be placed and wrapped around Trench. | M | For each site where subsoil is required | Visual / Photo | Minimum Width 300mm. | Checksheet | Contractor |  | A | I | R | dd/mm/yy
3.15 | Pipe laying | Pipe must have 100mm of Cushion. Drainage 60:40 Material to be used. | M | For each site where subsoil is required | Visual / Photo | Minimum 100mm | Checksheet | Contractor |  | A | I | R | dd/mm/yy
3.16 |  | 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge | M | For each site where subsoil is required | Visual / Photo | As Per IFC Drawings | Checksheet | Contractor |  | A | I | R | dd/mm/yy
3.17 | Backfill | Drainage 60:40 Material to be used. | M | For each site where subsoil is required | Visual / Photo | As Per IFC Drawings | Checksheet | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.