## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Subsoil Drainage | itp |  |  |  |  | ITP - Subsoil Drainage Rev 1
section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint | 1.01 - Drainage aggregate
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - > 100KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Drainage aggregate
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - as per IFC drawing
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Pipe
label | Detail of Activity / Test - Subsoil Pipe Material
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
label | Inspection / Test method - Dockets for each delivery
label | Acceptance Criteria - Compliance with TNZ F/2
label | Record documents (QCP - Quality Control Portal) - Delivery Docket
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTUCTION
checkpoint | 3.12 - Alignment
label | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Acceptance Criteria - Engineers Approval
label | Responsibility - Engineers Representative
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Excavation
label | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.14 - Trench Lining
label | Detail of Activity / Test - A29 or other approved Bidim to be placed and wrapped around Trench.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Minimum Width 300mm.
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.15 - Pipe laying
label | Detail of Activity / Test - Pipe must have 100mm of Cushion. Drainage 60:40 Material to be used.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Minimum 100mm
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.16 - Pipe laying
label | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per IFC Drawings
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.17 - Backfill
label | Detail of Activity / Test - Drainage 60:40 Material to be used.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per IFC Drawings
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
holdpoint | Add Signature