## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Stormwater (Infrastructure) - 203 - Rev B | itp |  |  |  |  | ITP - Stormwater (Infrastructure) - 203 - Rev B
section | 1.01 Stormwater Rip Rap Materials
checkpoint | 1.01.1 - Rip Rap Rock Source Properties
label | Acceptance / Conformance Criteria - The Riprap Source shall be tested for Point Load Strength, UCS Rock, Weathering Index, Crushing Resistance, and Solid Density.
label | Standard / Specification - PS 16.8.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.2 - D50=150mm RipRap - Grading
label | Acceptance / Conformance Criteria - The D50=150mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
label | Standard / Specification - PS 16.8.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.3 - D50=250mm RipRap - Grading
label | Acceptance / Conformance Criteria - The D50=250mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
label | Standard / Specification - PS 16.8.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 per 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 1.02 Subsoil Drainage Materials
checkpoint | 1.02.1 - Subsoil Drainage Pipe
label | Acceptance / Conformance Criteria - Pipes shall be high density polyethylene (HDPE) smooth bore perforated corrugated plastic pipe as shown on the Drawings and shall comply with the requirements of NZTA F/5.
label | Standard / Specification - PS 16.11.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 1.02.2 - Filter Material
label | Acceptance / Conformance Criteria - Filter material shall be placed around drainage pipe as shown on the Drawings and shall comprise no fines AP20/AP40 material.
label | Standard / Specification - PS 16.11.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 1.03 HDPE Liner
checkpoint | 1.03.1 - HDPE Liner
label | Acceptance / Conformance Criteria - The liner is to be 1mm thick HDPE material complying with GRI GM13 and fixed to the surface in accordance with the manufacturer’s specifications.
label | Standard / Specification - PS 16.19.1
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 1.03.2 - HDPE Liner Bedding
label | Acceptance / Conformance Criteria - The sand membrane shall be clean sand free from contamination.
label | Standard / Specification - PS 16.19.2
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 1.04 Stormwater Geogrid and Geofabric
checkpoint | 1.04.1 - Geofabric
label | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval at least two weeks before commencement of the works.
label | Standard / Specification - PS 16.29.2
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 1.04.2 - Biaxial Geogrid
label | Acceptance / Conformance Criteria - The biaxial geogrid shall be manufactured in accordance with a management system which complies with the requirements of BS EN ISO 9001, BS 14001. The Contractor shall submit the full details of the geogrid they propose to use for approval at least 2 weeks before commencement of the works.
label | Standard / Specification - PS16.29.3
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 1.05 Bioretention Soil Media
checkpoint | 1.05.1 - Bioretention Soil Media.
label | Acceptance / Conformance Criteria - Test results for soil filtration media material properties are submitted to the Engineer including ASTM F1815-06 test results, pH, clay content, organics content and material grading curve.
label | Standard / Specification - PS 16.38
label | Verifying Document - Datasheet
label | Frequency - Prior to installation
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
section | 2.01 Services
checkpoint | 2.01.1 - Existing Services
label | Acceptance / Conformance Criteria - The Contractor is required to identify all known utility service crossings or encroachment, within 5m horizontally, of the proposed drainage alignments.
label | Standard / Specification - PS 16.5.4
label | Verifying Document - Survey Records
label | Frequency - Prior to excavation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.01.2 - Service Support
label | Acceptance / Conformance Criteria - The Contractor shall support all existing services affected by the works whether these services cross-or are located alongside the excavation.
label | Standard / Specification - PS 16.5.4
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.01.3 - Utility Operators Approval
label | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Obtain written approval from the relevant Utility Operators for any construction activities within the vicinity of their service(s).
label | Standard / Specification - PS 16.5.4
label | Verifying Document - Written Approval
label | Frequency - Prior to commencing with any construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.4 - Utility Operators Requirements
label | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Undertake the construction activities within the vicinity of the service in compliance with the with the relevant Utility Operator’s requirements.
label | Standard / Specification - PS 16.5.4
label | Verifying Document - Site Records
label | Frequency - Prior to commencing with any construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.5 - Protection of Pipelines / Structures During Construction
label | Acceptance / Conformance Criteria - Where construction plant is required to be operated over pipelines Table B1 of AS/NZS 3725:2007 shall apply in determination of the minimum depth of fill (cover) required. A temporary embankment, extending not less than 15m on both sides of the pipe/culvert, shall be used to provide the necessary cover.
label | Standard / Specification - PS 16.5.5
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 2.02 Stormwater General
checkpoint | 2.02.1 - Setout
label | Acceptance / Conformance Criteria - Prior to the commencement of any drainage works for a particular drainage line, the Contractor shall set out the line, level, and position of the proposed drainage line, including inlet and outlet positions and levels, and present it to the Engineer for their consideration. The Contractor shall provide at least 48 hours’ notice to the Engineer ahead of set-out and allow 48 hours for the Engineer to respond prior to commencing work.
label | Standard / Specification - PS 16.6.1
label | Verifying Document - Survey Records
label | Frequency - Prior to the commencement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02.2 - Dealing with Water
label | Acceptance / Conformance Criteria - The Contractor shall maintain all trench inverts free from flowing or accumulated water. Water arising from, or draining into, the trench shall be drained or pumped. Any sumps required shall be refilled to formation level as directed by the Engineer.
label | Standard / Specification - PS 16.7.1
label | Verifying Document - Site Records
label | Frequency - During Works
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 2.03 Soakage Pits and Infiltration Trench
checkpoint | 2.03.1 - Soakage Pit Sealing
label | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
label | Standard / Specification - PS 16.12.2.2
label | Verifying Document - Site Records
label | Frequency - Each Hole
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.03.3 - Soakage Pit Lids
label | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
label | Standard / Specification - PS 16.12.2.2
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.03.4 - Infiltration Trench Excavation
label | Acceptance / Conformance Criteria - The trench/excavation shall be free of roots and projections or obstructions. Where over excavation has occurred, the bottom shall be brought back to grade using excavated material which is only lightly compacted in position to the same extent as the undisturbed surrounding soil. No loose soil shall be left in the excavation after restoration to finished grade.
label | Standard / Specification - PS 16.12.3.1
label | Verifying Document - Site Records
label | Frequency - Each Trench
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.03.5 - Trench Inspection
label | Acceptance / Conformance Criteria - All trenches in existing ground shall be inspected by the Engineer prior to commencement of laying filter cloth. Any unsuitable foundation material shall be removed at the Engineers direction.
label | Standard / Specification - PS 16.12.3.1
label | Verifying Document - Engineers Approval
label | Frequency - Prior to commencement of laying filter cloth
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03.6 - Groundwater
label | Acceptance / Conformance Criteria - If groundwater is encountered in the trench/excavation the Contractor shall seek instructions from the Engineer on how to proceed.
label | Standard / Specification - PS 16.12.3.1
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 2.04 Drainage Media
checkpoint | 2.04.1 - Placement of Drainage Media
label | Acceptance / Conformance Criteria - The drainage media (100-150mm rock) shall be carefully placed in the clean, excavated area after the excavated material has been removed and the excavation site cleared of potentially contaminating material and the excavation lined with filter cloth. The drainage media shall be lightly and uniformly compacted. No mechanical compaction equipment shall be used. The drainage media shall not be placed or lightly compacted if the excavation is flooded or the in-situ soils saturated.
label | Standard / Specification - PS 16.12.3.3
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 2.05 Place D50 250mm Rip Rap
checkpoint | 2.05.1 - Rip Rap Placement
label | Acceptance / Conformance Criteria - The Contractor shall place D50 = 250mm size rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
label | Standard / Specification - PS 16.14.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 2.06 Rip Rap Rock Flumes
checkpoint | 2.06.1 - Rip Rap Placement
label | Acceptance / Conformance Criteria - The Contractor shall place D50 rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
label | Standard / Specification - PS 16.17.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.06.2 - Geotextile Protection
label | Acceptance / Conformance Criteria - The contractor shall minimise the height from which rock is placed on order to reduce the risk of damage to the filter fabric layer. Rock shall not be dropped from >0.5m height.
label | Standard / Specification - PS 16.17.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.06.3 - Face Alignment
label | Acceptance / Conformance Criteria - The face of the rock rip rap shall be placed at the gradient shown on the drawings and the termination at each end against existing slopes is to be keyed into and to approximately match the adjacent slope and placed in general accordance with ‘Section 10 Filling’ of TNZ F/1:1997 to achieve a compact mass with minimal voids and good interlock of rock fragments.
label | Standard / Specification - PS 16.17.2
label | Verifying Document - Survey Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 2.07 Geofabric
checkpoint | 2.07.1 - Geotextile Filter Fabric Protection
label | Acceptance / Conformance Criteria - Construction plant shall not travel over exposed fabric. A minimum cover of 200mm of fill material shall be in place before construction plant is operated above the fabric.
label | Standard / Specification - PS 16.18.1, PS 16.12.3.2
label | Verifying Document - Site Records
label | Frequency - Before Trafficking
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 2.07.2 - Geotextile Filter Fabric Lab
label | Acceptance / Conformance Criteria - Geotextile filter fabric shall have a minimum overlap of 500mm at any joins.
label | Standard / Specification - PS 16.18.1, PS 16.12.3.2
label | Verifying Document - Site Records
label | Frequency - Each Joint
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 2.09 Bioretention Soil Media
checkpoint | 2.09.1 - Exclusion Zones (Bioretention and Infiltration Devices)
label | Acceptance / Conformance Criteria - The contractor is to establish fenced-off exclusion zones at the start of the works to avoid plant / machinery tracking and over-compacting bioretention and infiltration device formations such that the hydraulic conductivity of the existing ground is not compromised. The exclusion zone shall at a minimum cover the extent of the device base area.
label | Standard / Specification - PS 16.39.1
label | Verifying Document - Site Records
label | Frequency - At the start of the works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.09.2 - Interface Finish
label | Acceptance / Conformance Criteria - Bioretention devices operation as it provides a poor interface with the media. A rough finish such as that achieved with a toothed digger bucket is preferred.
label | Standard / Specification - PS 16.21
label | Verifying Document - Site Records
label | Frequency - Each Device
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.09.3 - Suitability of existing soil for infiltration and bioretention areas.
label | Acceptance / Conformance Criteria - Bioretention device and infiltration device formations are to be inspected by the Engineer prior to laying of bioretention or filtration media to confirm the suitability of the existing ground.
label | Standard / Specification - PS 16.38
label | Verifying Document - Site Records
label | Frequency - prior to laying of bioretention or filtration media
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 2.09.4 - Bioretention Soil Media placement
label | Acceptance / Conformance Criteria - The soil media layer is required to line the invert of all bioretention devices and placed in a single lift to 50 mm above the finished level. The finished surface shall be reasonably smooth, uniform and free of obvious hollows and humps. Care shall be taken to avoid overhandling the soi
label | Standard / Specification - PS 16.21.1
label | Verifying Document - Site Records
label | Frequency - Each Device
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.09.5 - Compaction
label | Acceptance / Conformance Criteria - The soil media shall be raked without any form of mechanical compaction.
label | Standard / Specification - PS 16.21
label | Verifying Document - Site Records
label | Frequency - Each Device
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.09.6 - Infiltration testing
label | Acceptance / Conformance Criteria - Once the bioretention devices have been completed, it shall be tested by double-ring infiltrometer for permeability. The rate shall be >50 mm/hr and not exceed 500 mm/hr. Alternative testing means must be approved by the Engineer.
label | Standard / Specification - PS 16.21.1
label | Verifying Document - Site Records
label | Frequency - Each Device upon completion
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.09.7 - Landscaping Approval
label | Acceptance / Conformance Criteria - Once the media is placed the Contractor shall notify the Engineer. If the Engineer is satisfied with the soil placement, they will advise the Contractor that landscaping can commence. Stabilisation with grass seed shall be carried out within seven days once approval is obtained from the Engineer.
label | Standard / Specification - PS 16.21
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Landscaping
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 2.12 Rock Riprap for Erosion Protection
checkpoint | 2.12.1 - Geotextile fabric installation
label | Acceptance / Conformance Criteria - Geotextile fabric shall be laid directly on the existing ground to protect the liner from damage due to punctures. It is assumed that the existing ground will be sand from the existing geotechnical information provided. If this is not the case the Engineer must be notified to allow for remedial treatment prior to the placement of the geofabric.
label | Standard / Specification - PS 16.24.6
label | Verifying Document - Site Records
label | Frequency - During Placement
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.12.2 - Impermeable liner installation
label | Acceptance / Conformance Criteria - An impermeable liner is required to line the entire wetland base and batters to avoid ground stability issues near the gully embankment. Particular care should be taken to ensure water tightness around inlet and outlet structures as per the Drawing details.
label | Standard / Specification - PS 16.24.5
label | Verifying Document - Site Records
label | Frequency - During Placement
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 2.13 Rock Riprap for Erosion Protection
checkpoint | 2.13.1 - Organic Material Removal
label | Acceptance / Conformance Criteria - Prior to placement of rock riprap, all organic material is to be removed, followed by the placement and anchorage of a Class E geotextile (in accordance with TNZ Specification F/7 Geotextile).
label | Standard / Specification - PS 16.25.1
label | Verifying Document - Site Records
label | Frequency - Prior to placement of rock riprap
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 2.14 Void Filled Riprap
checkpoint | 2.14.1 - Rip Rap Mixing
label | Acceptance / Conformance Criteria - Mix the material thoroughly using additional moisture and control procedures that ensure a homogenous mixture where the fines fill the inherent voids in the riprap without displacing riprap.
label | Standard / Specification - PS 16.26.3
label | Verifying Document - Site Records
label | Frequency - Prior to Placement
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.14.2 - Rip Rap Placement
label | Acceptance / Conformance Criteria - Place the blended mixture of approximate 2 x D50 thickness, minimising segregation of material. Some additional mixing may be required after the initial placement where there is segregation or areas that consist of smaller void fill materials.
label | Standard / Specification - PS 16.26.4
label | Verifying Document - Site Records
label | Frequency - During Placement
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.14.3 - Rip Rap Compaction
label | Acceptance / Conformance Criteria - The mixture shall be consolidated by driving over it with a loader or tamping with an excavator bucket to create a tight, dense interlocking mass.
label | Standard / Specification - PS 16.26.5
label | Verifying Document - Site Records
label | Frequency - During Placement
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 2.14.4 - Rip Rap Surface
label | Acceptance / Conformance Criteria - Where a surface layer of topsoil is specified, moist topsoil shall be placed over the void filled riprap and compacted to a dense stable state. Prior to placement of topsoil, the riprap placement must be reviewed by the Engineer. Additional topsoil shall be added to any areas that settle.
label | Standard / Specification - PS 16.26.9
label | Verifying Document - Engineers Approval
label | Frequency - Prior to placement of topsoil
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 2.17 Swales
checkpoint | 2.17.1 - Swale invert
label | Acceptance / Conformance Criteria - Swale invert shall have a uniform gradient and the line and level at any point shall not vary by more than ±20mm from the vertical set-out position and ±50mm for the horizontal set-out position
label | Standard / Specification - 16.34.4
label | Verifying Document - Survey
label | Frequency - Each Swale
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 2.17.2 - Swale batters
label | Acceptance / Conformance Criteria - Swale batters shall be uniform slope and the line and level of the top of the batter shall uniform slope and not vary by more than ±50mm from the vertical set-out position and ±50mm for the horizontal set-out position.
label | Standard / Specification - 16.34.4
label | Verifying Document - Survey
label | Frequency - Each Swale
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 2.17.3 - Grated Trench Drain
label | Acceptance / Conformance Criteria - Grated Trench Drains shall be installed as per Manufacturers specifications
label | Standard / Specification - PS 16.34
label | Verifying Document - Site Records
label | Frequency - As per manufacturers specifications
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 2.18 As Built Records
checkpoint | 2.18.1 - Survey Requirements - Stormwater Systems – Above ground:
label | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings: Treatment swales, wetlands, basin’s location, profile and grade. Diversion Drain location, profile, and grade. Trench excavation and invert. Line, levels and grade of kerb and channels. Rodding eye locations.
label | Standard / Specification - PS 16.33
label | Verifying Document - Survey
label | Frequency - All above ground Stormwater Systems
label | Verification Activity: Activity - I
label | Verification Activity: By - SV