## Sheet1
Pressure test | Pressure test new pipeline and fittings | Y | Once constructed | Re-Bound test | Succesful bounce test m7 or reference test m5 | Test Report signed by engineer | Water Tech | Pressure test | DETAIL OF ACTIVITY - Pressure test new pipeline and fittings | HOLD POINT - Y | WHEN/HOW OFTEN - Once constructed | INSPECTION/TEST METHOD - Re-Bound test | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Succesful bounce test m7 or reference test m5 | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Test Report signed by engineer | RESPONSIBLE - Water Tech | COMMENTS - | Pressure test
Flush lines | Pig all lines | Y | Once constructed | Visual Inspection | After pigging water is clear |  | Water Tech | Flush lines | DETAIL OF ACTIVITY - Pig all lines | HOLD POINT - Y | WHEN/HOW OFTEN - Once constructed | INSPECTION/TEST METHOD - Visual Inspection | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - After pigging water is clear | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - | RESPONSIBLE - Water Tech | COMMENTS - | DETAIL OF ACTIVITY - Pressure test new pipeline and fittings
Disenfection | Chlorinate all pipe lines and fittings | Y | Once Lines flushed | Water sample | Engineer to witness | Photo's of FAC test strips | Water Tech | Disenfection | DETAIL OF ACTIVITY - Chlorinate all pipe lines and fittings | HOLD POINT - Y | WHEN/HOW OFTEN - Once Lines flushed | INSPECTION/TEST METHOD - Water sample | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Engineer to witness | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Photo's of FAC test strips | RESPONSIBLE - Water Tech | COMMENTS - | HOLD POINT - Y
Flush lines | Flush chlorinated water from lines | Y | Once successful chlorination | Water sample | Pass E-Coli Test | Lab Test Result | Site Supervisor | Flush lines | DETAIL OF ACTIVITY - Flush chlorinated water from lines | HOLD POINT - Y | WHEN/HOW OFTEN - Once successful chlorination | INSPECTION/TEST METHOD - Water sample | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Pass E-Coli Test | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Lab Test Result | RESPONSIBLE - Site Supervisor | COMMENTS - | WHEN/HOW OFTEN - Once constructed
Water Shut down | Connect new lines to existing lines and water connections | Y | Once testing Completed | N/A | Water shut down plan accepted by WDC | Water Shut Down Notice | Site Supervisor | Water Shut down | DETAIL OF ACTIVITY - Connect new lines to existing lines and water connections | HOLD POINT - Y | WHEN/HOW OFTEN - Once testing Completed | INSPECTION/TEST METHOD - N/A | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Water shut down plan accepted by WDC | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Water Shut Down Notice | RESPONSIBLE - Site Supervisor | COMMENTS - | INSPECTION/TEST METHOD - Re-Bound test
Reinstatement | Reinstate all surfaces to original condition or better |  | After connections complete | Visual Inspection | As per Engineering Code of Practice |  | Site Supervisor | Reinstatement | DETAIL OF ACTIVITY - Reinstate all surfaces to original condition or better | HOLD POINT - | WHEN/HOW OFTEN - After connections complete | INSPECTION/TEST METHOD - Visual Inspection | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - As per Engineering Code of Practice | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - | RESPONSIBLE - Site Supervisor | COMMENTS - | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Succesful bounce test m7 or reference test m5
Final Inspection with Engineer | Site walk over with Engineer |  | Once all works completed | Visual Inspection | Acceptance by Engineer | Defects list | Site Supervisor | Final Inspection with Engineer | DETAIL OF ACTIVITY - Site walk over with Engineer | HOLD POINT - | WHEN/HOW OFTEN - Once all works completed | INSPECTION/TEST METHOD - Visual Inspection | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Acceptance by Engineer | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Defects list | RESPONSIBLE - Site Supervisor | COMMENTS - | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Test Report signed by engineer
As Builts | Surveyor to draw up as builts |  | Once all works completed | N/A | Acceptance by Engineer as per 1.21 | As-Built Drawings | Project Manager | As Builts | DETAIL OF ACTIVITY - Surveyor to draw up as builts | HOLD POINT - | WHEN/HOW OFTEN - Once all works completed | INSPECTION/TEST METHOD - N/A | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Acceptance by Engineer as per 1.21 | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - As-Built Drawings | RESPONSIBLE - Project Manager | COMMENTS - | RESPONSIBLE - Water Tech
Practical Completion | Certificate given by Engineer |  | When requested | N/A | Given by Engineer | Practical Completion Certificate | Project Manager | Practical Completion | DETAIL OF ACTIVITY - Certificate given by Engineer | HOLD POINT - | WHEN/HOW OFTEN - When requested | INSPECTION/TEST METHOD - N/A | ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Given by Engineer | RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Practical Completion Certificate | RESPONSIBLE - Project Manager | COMMENTS - | COMMENTS -
Flush lines
DETAIL OF ACTIVITY - Pig all lines
HOLD POINT - Y
WHEN/HOW OFTEN - Once constructed
INSPECTION/TEST METHOD - Visual Inspection
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - After pigging water is clear
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED -
RESPONSIBLE - Water Tech
COMMENTS -
Disenfection
DETAIL OF ACTIVITY - Chlorinate all pipe lines and fittings
HOLD POINT - Y
WHEN/HOW OFTEN - Once Lines flushed
INSPECTION/TEST METHOD - Water sample
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Engineer to witness
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Photo's of FAC test strips
RESPONSIBLE - Water Tech
COMMENTS -
Flush lines
DETAIL OF ACTIVITY - Flush chlorinated water from lines
HOLD POINT - Y
WHEN/HOW OFTEN - Once successful chlorination
INSPECTION/TEST METHOD - Water sample
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Pass E-Coli Test
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Lab Test Result
RESPONSIBLE - Site Supervisor
COMMENTS -
Water Shut down
DETAIL OF ACTIVITY - Connect new lines to existing lines and water connections
HOLD POINT - Y
WHEN/HOW OFTEN - Once testing Completed
INSPECTION/TEST METHOD - N/A
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Water shut down plan accepted by WDC
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Water Shut Down Notice
RESPONSIBLE - Site Supervisor
COMMENTS -
Reinstatement
DETAIL OF ACTIVITY - Reinstate all surfaces to original condition or better
HOLD POINT -
WHEN/HOW OFTEN - After connections complete
INSPECTION/TEST METHOD - Visual Inspection
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - As per Engineering Code of Practice
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED -
RESPONSIBLE - Site Supervisor
COMMENTS -
Final Inspection with Engineer
DETAIL OF ACTIVITY - Site walk over with Engineer
HOLD POINT -
WHEN/HOW OFTEN - Once all works completed
INSPECTION/TEST METHOD - Visual Inspection
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Acceptance by Engineer
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Defects list
RESPONSIBLE - Site Supervisor
COMMENTS -
As Builts
DETAIL OF ACTIVITY - Surveyor to draw up as builts
HOLD POINT -
WHEN/HOW OFTEN - Once all works completed
INSPECTION/TEST METHOD - N/A
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Acceptance by Engineer as per 1.21
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - As-Built Drawings
RESPONSIBLE - Project Manager
COMMENTS -
Practical Completion
DETAIL OF ACTIVITY - Certificate given by Engineer
HOLD POINT -
WHEN/HOW OFTEN - When requested
INSPECTION/TEST METHOD - N/A
ACCEPTANCE CRITERIA/SPECIFICATION REFERENCE - Given by Engineer
RECORD REQUIRED OR SIGN AND DATE WHEN COMPLETED - Practical Completion Certificate
RESPONSIBLE - Project Manager
COMMENTS -