## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Kaiteriteri Footpath and Boardwalk |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 553801 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Tasman District Council |  |  |  |  | B | Report by Breach | CM | Contract Manager | Mark Frost | MF
Contract Number: | [5 empty] | C | Check | CS | Construction Supervisor | Mike Kennedy | MK
Area/ Sub-System: | Martin Farm Road, Kaiteriteri |  | Lot ID Number: |  |  | D | Dimension Inspection | CEC | Civil Engineering Cadet | Tyler Peppin | TP
[6 empty] | E | Examine | CH | Consent Holder
ITP Number: |  |  | Version: |  |  | H | Hold Point | WSP | WSP Engineer | WSP Engineer
ITP Description: | [5 empty] | I | Inspection | C | Contractor | Downer
Discipline: | Construction |  |  |  |  | M | Monitor on Random Basis | SC | Sels Civil | Sels Civil
Specification: | [5 empty] | O | Operation | TDC | Tasman District Council | Tasman District Council
[6 empty] | R | Review
Drawings: | [5 empty] | S | Subcontractor
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Peppin |  | Date: | 24/08/2023 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
Consent Conditions 1.0
1.1 | Appoint contact person for Councils monitoring officer. | / | Prior to works | / | Once | Hold Point | CH | Consent Holder
1.2 | Appoint ecologist | / | Prior to works | / | Once | Hold Point | CH | Consent Holder
1.3 | Advise council montoring officer of contact people (Rep, Principal Contractor, Ecologist) | / | Prior to works. (ongoing, and within one day of changes | / | Once | Hold Point | CH | Consent Holder
1.4 | Advise monitoring officer of works commencing | / | 10 working days prior to works. (and when sediment control measures placed and 24hrs prior to measures being removed | / | Once | Hold Point | CH + C | Consent Holder + Contractor
1.5 | Site meeting between principal contractor, ecologist, monotoring officer, iwi officer | / | Prior to works | / | Once | Hold Point | CH + C | Consent Holder + Contractor
1.6 | Iwi monitor to be appointed, and forward evidence of this to monitoring officer | / | 10 working days prior to works. | / | Once | Hold Point | CH | Consent Holder
1.7 | Prepare construction management plan, traffic management plan and spill management plan - see conditions for requirements | Engineer to inspect plans | 15 working days prior to works | / | Once | Hold Point | CH + C | Consent Holder + Contractor
1.8 | Penguin management plan submitted to council | Engineer to inspect plans | 15 working days prior to works | / | Once | Hold Point | CH | Consent Holder
1.9 | Lizard management by Ecologist 2-10 days prior to vegetation removal in specific areas | / | 2-10 days prior to vegetation clearance in specific areas | / | Once | Hold Point | CH + C | Consent Holder + Contractor
1.1 0 | Clean machinery prior to arrival on site | / | Prior to arrival on site | / | Once | Hold Point | C | Contractor
1.11 | Access routes (on foot) identified to works areas to avoid vegetation | / | Identified on-site prior to works impacting estuary vegetation | / | Once | Hold Point | C | Contractor
1.12 | Erect notices at each end of works site prior to works commencing | / | 2 working days prior to works (minimum) | / | Once | Hold Point | CH + C | Consent Holder + Contractor
1.13 | Provide written notice to neighbours prior to works commencing | / | 2 working days prior to works (minimum) | / | Once | Hold Point | CH + C | Consent Holder + Contractor
Safety 2.0
2.1 | Traffic Control | Safety | According to TMP | Check by STMS | Every 2 hours | Verification | C | Contractor
2.2 | Temporary traffic bypass | A temporary carriageway is required to divert traffic around the site, this is to remain open at all times | In accordance with specification and drawings | A maintained all weather bypass suitable for heavy traffic | Once | Verification | C | Contractor
2.3 | Locate services | / | Services located by Delta, Chorus and TDC prior to commencing works. | / | Once | Verification | C | Contractor
Earthworks 3.0
3.1 | Compaction of nongranular subgrade | NDM as per TNZ F/1 clause 10.5.2 | Min. 98% at MDD | Visual | 100m² | Hold Point | SC | Sels Civil
3.1 | Subgrade surface finishing tolerance | Stringline measurements | Within 30mm over 3 metres | Visual | Every 20m | Verification | CS | Construction Supervisor
Pavement Construction 4.0
4.1 | Surface tolerances of subbase | Stringline measurements | -25mm +5mm | Visual | Every 20m | Verification | CS | Construction Supervisor
4.2 | Surface tolerances of basecourse | Stringline measurements | -5mm + 15mm | Visual | Every 20m | Verification | CS | Construction Supervisor
4.3 | Compaction of subbase (Field Dry Density) | NDM as per TNZ B/02 clause 7.6 | ≥ 95% ave. ≥ 92% min | Inspection | 1 lot ( 5 tests) | Hold Point | SC | Sels Civil
4.4 | Compaction of basecoursde (Field Dry Density) | NDM as per TNZ B/02 clause 7.6 | ≥ 98% ave at MDD. ≥ 95% min | Inspection | 1 lot ( 5 tests) | Hold Point | SC | Sels Civil
4.5 | Saturation | NDM as per TNZ B/02 clause 12 | Less than 80% | Inspection | 1 per 110m² | Hold Point | SC | Sels Civil
4.6 | Surface Shape | 3 metre straight edge | Maximum 10mm | Visual | Every 20m | Hold Point | CS | Construction Supervisor
4.7 | Surface FInishing | Visual as per TNZ B/02 clause 7.8 | Mosaic FInish | Visual | 100% of surface | Verification | CS | Construction Supervisor
Basecourse 4.1
4.1.1 | Sand Equivalent | As per NZS 4407:2015 | ≥ 40 | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 | Hold Point | WSP / TDC | WSP / TDC
4.1.2 | Clay Index | As per NZS 4407:2015 | ≤ 3 passing 75um | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 |  | WSP / TDC | WSP / TDC
4.1.3 | Plasticity Index | As per NZS 4407:2015 | ≤ 5 passing 425um | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 |  | WSP / TDC | WSP / TDC
4.1.4 | Broken Face Content | As per NZS 4407:2015 | 70% with 2 broken faces | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 |  | WSP / TDC | WSP / TDC
4.1.5 | Particle Size Distribution | As per NZS 4407:2015 | To be within envelope limits | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 |  | WSP / TDC | WSP / TDC
4.1.6 | Crushing Resistance | As per NZS 4407:2015 | 130kN - 10% fines passing 2.36mm | Council / Engineer to approve materials | 2min for quantities greater than 400m3 refer TNZ M/4 clause 4.1 |  | WSP / TDC | WSP / TDC
4.1.7 | Weathering Quality Index | As per NZS 4407:2015 | AA,AB,AC,BA,BB, or CA | Council / Engineer to approve materials | 1* |  | WSP / TDC | WSP / TDC
4.1.8 | CBR (soaked) | As per NZS 4407:2015 | ≥ 80 | Council / Engineer to approve materials | 1* |  | WSP / TDC | WSP / TDC
Subbase 5.0
5.1 | Sand Equivalent | As per NZS 4407:2015 | ≥ 25 | Council / Engineer to approve materials | 1min for quantities greater than 400m3 2min | Hold Point | WSP / TDC | WSP / TDC
5.2 | Broken Face Content | As per NZS 4407:2015 | 70% with 2 broken faces | Council / Engineer to approve materials | 1min for quantities greater than 400m3 2min |  | WSP / TDC | WSP / TDC
5.3 | Particle Size Distribution | As per NZS 4407:2015 | To be within envelope limits | Council / Engineer to approve materials | 1min for quantities greater than 400m3 2min |  | WSP / TDC | WSP / TDC
5.4 | Crushing Resistance | As per NZS 4407:2015 | 110kN | Council / Engineer to approve materials | 1min for quantities greater than 400m3 2min |  | WSP / TDC | WSP / TDC
5.5 | Weathering Quality Index | As per NZS 4407:2015 | AA,AB,AC,BA,BB, or CA | Council / Engineer to approve materials | 1* |  | WSP / TDC | WSP / TDC
5.6 | CBR (soaked) | As per NZS 4407:2015 | ≥ 80 | Council / Engineer to approve materials | 1* |  | WSP / TDC | WSP / TDC
Asphaltic Concrete 8.0
8.1 | Surface shape on completion | 3 metre straight edge | Maximum 5mm | Visual | / | Hold Point | CS | Construction Supervisor
8.2 | Depth | Ruler measurement | -0mm +5mm | Visual | / | Hold Point | CS | Construction Supervisor
Boardwalk 9.0
9.1 | Refer to DRG 5-G3445.40 | / | Built to plan | Inspection | When Required | Hold Point | WSP / TDC | WSP / TDC
9.2 | Post set out | Ruler measurement / and stringline | Spacing and alignment | inspection | prior to comencement of driving piles | Hold point | WSP | WSP / C
9.3 | Depth of piles | Pre marked on Piles | Minimum 2.5m | measuremnt on piles | all | Visual | WSP | WSP / C
9.4 | Resistance |  | 60kN | Blows of driver record | all | visual | WSP | construction Supervisor
* Within last three (3) months of delivery to site.

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: