## Sheet1
Enviro B-LV+700X+250NS
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | CIDD Alerts
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | Enviro Flex FC/ Sika Flex Pro
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro B-LV
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro 700X
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro 250NS
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Site engineer/foreman batch inspection review
SIGNOFF | site engineer/foreman sign off
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Records - Subcontractor Contracts Admin Confirmation
Label | Sample Approval Ref.
SIGNOFF | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Records - Site Engineer/ Foreman Confirmation
SIGNOFF | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
Label | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
Label | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat, including all nails, penetrations and corners. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
Label | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in Showers
Label | Records - Site Engineer/ Foreman Confirmation
SIGNOFF | Hold Point (Mandatory) - work not to proceed without approval
Checkpoint | Cracks in Substrate - AS2870 Table 2.10
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman pre commencement inspection review
SIGNOFF | Site engineer/ foreman inspection - sign off
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Checkpoint | Substrate Preperation - AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman substrate preperation inspection review
SIGNOFF | Site Engineer/Foreman Inspection sign off
Label | Ensure Surface is prepared to receive primer application. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
SECTION | PRIME COAT- EACH LOCATION
Checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
Label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
Label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | Application - Enviro Epoxy BL-V Product TDS
Label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Priming Inspection Review
SIGNOFF | Site Engineer/Foreman Inspection sign off
SECTION | BOND BREAKER- EACH LOCATION
Checkpoint | Caulking - AS 3740 2021 & AS 4654.1
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating.
Label | Records - Time stamped photograph
Label | Records - Thickness with fillet gauge
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman bond breaker inspection review
SIGNOFF | Site Engineer/Foreman inspection sign off
SECTION | FIRST BASE COAT - EACH LOCATION
Checkpoint | Weather/RH - 700X Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Product Mixing - 700X Product TDS
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | Application- 700X Product TDS
Label | • 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor first base coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman first base coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
SECTION | ENVIRO 700X - SECOND COAT
Checkpoint | Weather/RH - 700X Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Product Mixing - 700X Product TDS
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Application- 700X Product TDS
Label | • 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
Label | Minimum application requirements set forth relevant Australian Standards to be followed
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor Second base coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Second base coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | ELT Testing - Delfasco Holiday Tester
Label | Conduct Electronic Leak Testing ( ELT) on area membraned
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman QA inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
SECTION | DETAILING- EACH LOCATION
CHECKPOINT | Vertical Termination Detailing - AS 4654.2
Label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Detailing inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
SECTION | FIRST TOP COAT - EACH LOCATION
Checkpoint | Weather/RH - 250NS PRODUCT TDS
Label | Apply within 5-35°C RH must be 35-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Mixing- 250NS PRODUCT TDS
Label | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | APPLICATION - 250NS PRODUCT TDS
label | • 250NS to be applied using roller and brush. •Ensure Product is cured for 24 hours prior to second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor first top coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman first top coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
SECTION | SECOND TOP COAT - EACH LOCATION
Checkpoint | Weather/RH - 250NS PRODUCT TDS
Label | Apply within 5-35°C RH must be 35-85%
Label | Screenshot - Temperature and weather forecast
select | Inspection | Surveillance point, Witness point
Checkpoint | Mixing- 250NS PRODUCT TDS
Label | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
select | Inspection | Surveillance point, Witness point
Checkpoint | APPLICATION - 250NS PRODUCT TDS
label | • 250NS to be applied using roller and brush. •Ensure Product is cured for 24 hours prior to second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor second coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman second top coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off