## Sheet1
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | CIDD Alerts
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | Enviro Seal WB
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Enviro CSH
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Site engineer/foreman batch inspection review
SIGNOFF | site engineer/foreman sign off
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Sample Approval Ref.
SIGNOFF | Hold Point (Mandatory) - Subcontractor Contracts Admin inspection sign off
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Records - Site Engineer/ Foreman Confirmation
SIGNOFF | Hold Point (Mandatory) - Site engineer/ foreman first of type inspection sign off
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Cracks in Substrate - AS2870 Table 2.10
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman pre commencement inspection review
SIGNOFF | Site engineer/ foreman inspection - sign off
SECTION | SUBSTRATE PREPERATION - EACH LOCATION
Checkpoint | Substrate Preperation - AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
Label | Records - Time stamped photograph
select | Inspection | Surveillance point, Witness point
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site engineer/foreman substrate preperation inspection review
SIGNOFF | Site Engineer/Foreman Inspection sign off
SECTION | FIRST SEALER COAT - EACH LOCATION
Checkpoint | Application
Label | Spray or roll concrete Sealer on substrate
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor first Sealer coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman first sealer coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off
SECTION | SECOND SEALER COAT - EACH LOCATION
Checkpoint | Application
Label | Spray or roll concrete Sealer on substrate
Label | Records - time stamped photograph
select | Inspection | Surveillance point, Witness point
Checkpoint | Subcontractor second Sealer coat inspection review
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman second sealer coat inspection review
SIGNOFF | Site Engineer/foreman inspection sign off