## Project Breakdown
On Site QA
Building A
First Floor
|  |  | Unit 1 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 2 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 3 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 4 | Stud Install Checklist 1
Balustrade Checklist 1
|  | Second Floor | Unit 5 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 6 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 7 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 8 | Stud Install Checklist 1
Balustrade Checklist 1
| Building B | First Floor | Unit 14 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 15 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 16 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 17 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 18 | Stud Install Checklist 1
Balustrade Checklist 1
|  | Second Floor | Unit 19 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 20 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 21 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 22 | Stud Install Checklist 1
Balustrade Checklist 1
|  |  | Unit 23 | Stud Install Checklist 1
Balustrade Checklist 1

## Checklists
checklist | Stud Install checklist
checkpoint | washers nut and lock nut install behind sub straight
checkpoint | s/s bush install inline with weather line
checkpoint | EPDM washer install between sub straight and s/s bush
checkpoint | correct amount of stud protruding in front of the bush
checkpoint | top stud height to top of cap flashing
checkpoint | centres between studs vertically
checkpoint | centres between studs horizontally
checklist | Balustrade Checklist 1
checkpoint | Bolts/Screws tight
checkpoint | Balustrade plumb
checkpoint | Handrail straight
checkpoint | balustrade free of scratches
checkpoint | Balustrade installed with no more than 100mm gap between cladding screens
checkpoint | Balustrade installation 1m above the cap flashing