## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 1.2BMT Head Flashing |  | 1.2BMT Head Flashing | 5a30030f-2c47-4ad0-9e81-84bc10a5fe41
| checkpoint | Air Seal
| checkpoint | Install Architraves
| checkpoint | Paint reveals and architraves
| checklist | Block N & K South Elevation Infills |  | Block N & K South Elevation Infills | 2333b45b-a2b9-409f-9d5e-6619222f71e9
| checkpoint | Remove Asbestos
| checklist | Block N & K South Elevation Infills - Stage 2 |  | Block N & K South Elevation Infills - Stage 2 | f0b39514-69d6-41dd-8690-fab840721dca
| checkpoint | Remove asbestos panels
| checkpoint | Inspect Timber Framing
| checkpoint | Install Rigid Wall Underlay
| checkpoint | Install Flashing tape
| checkpoint | Install Cavity Battens
| checkpoint | Install Cavbat Battens
| checkpoint | Install Powder Coated Aluminium Flashing
| checklist | Block N East Elevation 2 |  | Block N East Elevation 2 | ef36feec-5525-4402-8923-5cae67d90a63
| checkpoint | Remove Asbestos
| checkpoint | Inspect timber framing
| checkpoint | Install Rigid Wall Underlay
| checkpoint | Install Cavity Battens
| checkpoint | Install 9mm Fibre Cement board
| checkpoint | Install Trims
| checkpoint | Paint
| checklist | Drainage Checklist |  | Drainage Checklist | 68dbf08b-f7c6-4110-9782-408928152be8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Sheilds installed or benched
| checkpoint | Good ground confirmed
| checkpoint | Man hole installed
| checkpoint | Bidim cloth installed
| checkpoint | Bedding material install
| checkpoint | Pipe layed with fall
| checkpoint | welds documented
| checkpoint | Box and pour corbal
| checkpoint | Haunch manhole
| checkpoint | Test line
| checkpoint | Trench backfilled
| checkpoint | Sump leads installed
| checklist | Exterior Wall Framing Building Paper |  | Exterior Wall Framing Building Paper | fbff7d74-b5d2-43de-aa1e-274fbf178e0e
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Proclima installed
| checkpoint | Correct Laps
| checklist | Exterior Wall Framing Framing |  | Exterior Wall Framing Framing | 5c1b3273-94af-4247-bc17-14b4984e8745
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Correct wall size
| checkpoint | Straight and Plumb
| checkpoint | Correct nogging installed
| checkpoint | WCC Pre Wrap inspection
| checklist | Exterior Wall Framing RAB |  | Exterior Wall Framing RAB | ffd335b8-f006-47ef-a394-b31246862a57
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Correct size
| checkpoint | Nail centres
| checklist | Fire Rated Sub Floor Checklist |  | Fire Rated Sub Floor Checklist | 177ce6eb-081b-436b-a6d6-60e80b18ffd7
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Blocks to underside of Joist
| checkpoint | Ryan Fire Batts installed
| checklist | Firth 20 Series Block Checklist |  | Firth 20 Series Block Checklist | 33d639a2-1a85-4ef6-88b9-5cfc42779e59
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Reo installed
| checkpoint | Concrete filed Blocks
| checkpoint | Capping installed
| checklist | Foundations/Footings Checklist |  | Foundations/Footings Checklist | 4ee86af7-a049-47c4-a2ce-e20c12efd11a
| section | WA-WC Grids
| checkpoint | HD12 Reo
| checkpoint | 400 Cs
| checkpoint | Concrete Cover
| section | Sub Floor Insitu Wall
| checkpoint | HD12 Reo
| checkpoint | 400 Cs
| checkpoint | Concrete Cover
| section | Ramp Beam
| checkpoint | HD12
| checkpoint | HD16
| checkpoint | 300 Cs
| checkpoint | SE72 Mesh
| checkpoint | R16 installed in pile
| checkpoint | Concrete Cover
| checkpoint | Paint Pile End Cap
| section | Stairs Beam
| checkpoint | HD16
| checkpoint | R10 - 250
| checkpoint | R16 installed in pile
| checkpoint | Concrete Cover
| checkpoint | Paint Pile End Caps
| section | WCC - Pre Foundation Inspection
| checkpoint | Inspection completed
| checklist | Fume Cupboards |  | Fume Cupboards | e57604b6-ac20-4bfe-a6f7-37f01d496099
| checkpoint | Commissioned Results
| checkpoint | Remove existing Fume Vents
| checkpoint | Install Ply upstand
| checkpoint | Membrane and Cricket
| checkpoint | Install Fume Vent
| checkpoint | Welded Aluminium Cap flashing
| checkpoint | Boot Flashing and drive clamp
| checkpoint | Recomissioned results
| checklist | In ground services |  | In ground services | 6c882722-a814-46f5-8f75-065f3936efa8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | CCTV existing services
| checklist | Lower Roof |  | Lower Roof | 92c0ee06-cdc9-49d3-8ac5-eed59c311950
| checkpoint | Delap photos
| checkpoint | Clean Roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 40mm PIR
| checkpoint | New Fibretite Membrane
| checkpoint | New Fascias
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipies
| checklist | nAJ0 - Window |  | nAJ0 - Window | 3757d6b5-621b-4c4a-856b-9430adeb2cf9
| checkpoint | Window removed
| checkpoint | New Window Opening
| checkpoint | Sill chamered to form Fall
| checkpoint | Window Tape
| checkpoint | Sill Flashing Installed
| checkpoint | Cavity Batten Installed
| checkpoint | Window Installed
| checkpoint | Head Flashing Installed
| checkpoint | Gib and Architraves
| checkpoint | Window opener installed
| checklist | New Roading - S2 - Checklist |  | New Roading - S2 - Checklist | 54f6472b-aac9-4467-9e31-90820086ba05
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Make good asphalt
| checkpoint | Reinstate road markings
| checklist | New Roading Checklist |  | New Roading Checklist | 6cf64292-bfae-4478-ada0-524f2e4c17e7
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Scrape existing
| checkpoint | Proof roll
| checkpoint | Hold point - Inspection
| checkpoint | Install hard fill
| checkpoint | Kerbs installed
| checkpoint | Asphalt installed
| checkpoint | Road marking installed
| checkpoint | Signs installed
| checklist | Northern Elevation |  | Northern Elevation | 85d0e381-eb48-4d68-abe7-fd7906f64396
| checkpoint | Existing damaged weatherboard
| checkpoint | New replacement
| checkpoint | Paint
| checklist | Phase 2 Block N &K - Cladding |  | Phase 2 Block N &K - Cladding | 65c58dc3-88c1-4f31-bd03-921be42c7bac
| checkpoint | Remove Asbestos
| checkpoint | Inspect timber framing
| checkpoint | Install Rigid Wall Underlay
| checkpoint | Membrane upstand
| checkpoint | Install Cavity Battens
| checkpoint | Install 9mm Fibre Cement board
| checkpoint | Install Trims
| checkpoint | Paint
| checklist | Phase 2 Block N &K - Lower R1 |  | Phase 2 Block N &K - Lower R1 | 235dc29a-e88e-4c9a-85d2-c76bed1339a6
| checkpoint | Delap photos
| checkpoint | Remove roofing iron
| checkpoint | Remove existing cap flashings
| checkpoint | Install new base deck
| checkpoint | New 80mm PIR
| checkpoint | New Fibretite Membrane
| checkpoint | New Fascias
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipes
| checklist | Phase 2 Block N &K - Lower Roof |  | Phase 2 Block N &K - Lower Roof | 5daf359f-3560-40a2-be82-0e4a2d571c98
| checkpoint | Delap photos
| checkpoint | Clean Roof
| checkpoint | Remove existing cap flashings
| checkpoint | Remove skylights
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 40mm PIR
| checkpoint | New Fibretite Membrane
| checkpoint | New Fascias
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipes
| checklist | Phase 2 Block N &K - Upper Roof |  | Phase 2 Block N &K - Upper Roof | 498734f3-fe9d-488d-994a-c2959d9194b5
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 40mm PIR
| checkpoint | New Fibretite Membrane
| checkpoint | New Fascias
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipes
| checklist | Phase 3 Block M & L - Awning Roof |  | Phase 3 Block M & L - Awning Roof | bfbf2a7b-4f41-424c-8a4d-6525bba301bb
| checkpoint | Remove Existing Clearlite
| checkpoint | Install new Fibreglass Roofing
| checkpoint | Install closed cell profiled foam strip
| checkpoint | Install Apron Flashing
| checkpoint | New Gutters and Down Pipes
| checklist | Phase 3 Block M & L - Upper Roof |  | Phase 3 Block M & L - Upper Roof | f1fcb9b7-f9ec-48e5-b99b-13a513b7af5f
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 80mm PIR
| checkpoint | Taper PIR closest to spouting
| checkpoint | New Aluminium Drip Edge
| checkpoint | New Fibretite Membrane
| checkpoint | Penetration through roof
| checkpoint | New Fascias
| checkpoint | Install Pressure Bars
| checkpoint | New Gutters and Down Pipes
| checklist | Pile End Steel Connections Checklist |  | Pile End Steel Connections Checklist | 1b8f4d00-0536-4865-8bc9-fb5c514e3b6c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Grid Line W1
| checkpoint | Grid Line W2
| checkpoint | Grid Line W3
| checkpoint | Grid Line W4
| checkpoint | Grid Line W5
| checkpoint | Grid Line W6
| checkpoint | Grid Line W7
| checkpoint | Grid Line W8
| checklist | Precast retaining wall |  | Precast retaining wall | 7883a39d-4355-4a77-a9ce-ac4c0a86c56d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Excavation and batter back
| checkpoint | Shop drawings sign off
| checkpoint | Excavate ground beam and post holes to depth/good ground
| checkpoint | Ground beam DPM and form work
| checkpoint | 25mm poly above services
| checkpoint | R10 stirrups @ 200 centers
| checkpoint | Install 1200 long Galv starters for future extension
| checkpoint | Hold point - pre pour inspections
| checkpoint | Off Site inspections of precast panels
| checkpoint | Ucs installed in line and plumb
| checkpoint | precast panels installed - no gaps over 100mm
| checkpoint | Grouting of joints
| checkpoint | Install protection sheet
| checkpoint | Install soil drain with inspection point
| checkpoint | Backfill
| checklist | Roofing Plywood |  | Roofing Plywood | eca97b6e-fe7c-4121-a082-e88908785818
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Correct size
| checkpoint | 100mm fixing pattern
| checkpoint | 200mm fixing pattern
| checklist | Roofing Purlins |  | Roofing Purlins | e10ce29b-f36c-4830-b390-313087c4ddbc
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Correct size and grade
| checkpoint | Correct centres
| checkpoint | Outrigger connections
| checklist | S3 - Final Checklist |  | S3 - Final Checklist | 887b0271-5916-4bba-b284-a85386543f44
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Sewer conection in road
| checkpoint | Connect existing School sewer
| checkpoint | Connect Water to town main
| checkpoint | Connect Sprinkler to town main
| checkpoint | Make good road
| checklist | Site works |  | Site works | 652a16da-ab4d-4fd1-9eb4-392e31e2353d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Services located
| checkpoint | Protected trees marked out
| checkpoint | Silt protection in place
| checkpoint | Wheelwash station installed
| checkpoint | Scrape vegetation
| checklist | Skylights Framing |  | Skylights Framing | 4e7d0ad8-0d31-4924-9e39-4bf75119ddfe
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Correct size
| checkpoint | Correct conections
| checkpoint | Upstand built
| checkpoint | Flashings installed
| checkpoint | Window installed
| checklist | SP3a Block H/M Link Foyer - Lower Parapet Wall |  | Lower Parapet Wall | b92f4653-8c14-49d5-883b-3ef9e33f79cd
| checkpoint | Install additional framing for sheet joins
| checkpoint | Install RAB Board
| checkpoint | Install Intello Wrap
| checkpoint | Cavity closer installed
| checkpoint | Cavity Battens - 400cs
| checkpoint | 9mm Fibre Cement cladding
| checkpoint | Fascias with air vent.
| checkpoint | Painting cladding and fascias
| checklist | SP3a Infills Panels - 1 |  | SP3a Infills Panels - 1 | db5c1fba-8c71-4798-8fda-562f0bd67a49
| section | Details
| checkpoint | Remove ACM
| checkpoint | Install RWU
| checkpoint | Install Cavity Battens
| checkpoint | Install Castellated batten
| checkpoint | Install new aluminium flashing panel
| checklist | SP3a Infills Panels - 2 |  | SP3a Infills Panels - 2 | ac07bcec-e521-4b56-bf74-cfefb73d3385
| section | Details
| checkpoint | Remove ACM
| checkpoint | Install RWU
| checkpoint | Install Cavity Battens
| checkpoint | Install Castellated batten
| checkpoint | Install new aluminium flashing panel
| checkpoint | Aluminium Soaker behind head flashing
| checklist | SP3a LVLs |  | SP3a LVLs | bcd5cd03-b887-4cb7-809e-b6aa5c1fdf11
| section | Details
| checkpoint | Steel Bracket to internal corner
| checkpoint | New Hyspan to roof edge
| checkpoint | Conections to existing steel beam
| checkpoint | Doube studs with straps
| checklist | SP3a Roof |  | SP3a Roof | dd181874-e0e5-450c-b82d-c654557fde10
| checkpoint | Remove ACM and Demo
| checkpoint | Assess Framing
| checkpoint | Multi grips and hold down straps
| checkpoint | New furrings @ 900cs
| checkpoint | New roof 2 degrees
| checkpoint | New Purlins @ 1200cs
| checkpoint | HOLDPOINT Engineers sign off
| checkpoint | Tray dec Installed
| checkpoint | Plinth framing
| checkpoint | Vapour Barrier
| checkpoint | 80mm PIR installed
| checkpoint | 60-80mm Taped PIR
| checkpoint | Drip edge flashing
| checkpoint | Fibretite Membrane installed
| checkpoint | Pressure Bar to drip edge
| checkpoint | Fascia installed
| checkpoint | Gutter and downpipes installed
| checklist | SP3a South wall |  | SP3a South wall | fe98e968-f9a6-4ce1-a4e5-99e24ee1fc67
| section | Details
| checkpoint | Install additional framing for sheet joins
| checkpoint | Install RAB Board
| checkpoint | Install Intello Wrap
| checkpoint | Penetration flashing to wrap
| checkpoint | 0.9 BMT Aluminium Flashing
| checkpoint | Cavity closer installed
| checkpoint | Cavity Battens - 600cs
| checkpoint | 9mm Fibre Cement cladding
| checkpoint | Fascias with air vent.
| checkpoint | Painting cladding and fascias
| checklist | SP3a West wall |  | SP3a West wall | 1822b21f-7019-467d-a148-8a5b740a8394
| checkpoint | Install New 290x90 Beam
| checkpoint | Reframe wall
| checkpoint | Install Structural fixings
| checkpoint | HOLDPOINT Engineers Sign off
| checkpoint | Install RAB Board
| checkpoint | Install Intello Wrap
| checkpoint | 0.9 BMT Aluminium Flashing
| checkpoint | Cavity closer installed
| checkpoint | Cavity Battens - 400cs
| checkpoint | 9mm Fibre Cement cladding
| checkpoint | Fascias with air vent.
| checkpoint | Painting cladding and fascias
| checklist | SP3a Windows |  | SP3a Windows | 3e627149-cb7d-46d3-9a00-16566c0dc481
| checkpoint | Remove windows
| checkpoint | Re Frame Windows to new openings size
| checkpoint | Chamfered sill
| checkpoint | Window flashing tape
| checkpoint | Fibretite continued into window opening
| checkpoint | WANZ - Aliminmium Angle installed
| checkpoint | Sill flashing
| checkpoint | Windows installed
| checkpoint | Head Flashing installed
| checkpoint | Air seal
| checkpoint | Reveals Installed
| checkpoint | Archtraves installed
| checkpoint | Painting completed
| checklist | SP3b Block I |  | SP3b Block I | 41745164-bfe7-476e-a45d-1c608a3ab3b0
| checkpoint | Remove ACM
| checkpoint | Clean Roof
| checkpoint | Screw Exisiting roofing iron
| checkpoint | Install parapet framing
| checkpoint | Install plywood to parapet
| checkpoint | Lay PIR Infills
| checkpoint | Install vapour barrier
| checkpoint | Install 80mm PIR
| checkpoint | 60-80mm Taped PIR installed
| checkpoint | Drip edge flashing
| checkpoint | Fibretite membrane installed
| checkpoint | Install Membrane over parapet
| checkpoint | Lay new Torch on up parapet
| checkpoint | Parapet flashing installed
| checkpoint | Fascias installed
| checkpoint | Pressure bar to drip edge
| checkpoint | Gutter and downpipes installed
| checklist | SP3b Block I - Cladding East |  | SP3b Block I - Cladding East | 4a550aeb-f7d7-45ba-96a2-44ffb8da82fd
| checkpoint | Remove exisitng ACM
| checkpoint | RAB installed
| checkpoint | 150mm dressed Membrane
| checkpoint | 0.7mm Aluminium Flashing
| checkpoint | uPVC cavity closer
| checkpoint | Timber batten install @ 400cs
| checkpoint | Castellated batten for top vent
| checkpoint | New 9mm Easylap cladding
| checkpoint | New H3.1 29mm Fascia
| checklist | SP3b Block I - Cladding North |  | SP3b Block I - Cladding North | 2c752378-f577-4e3f-8bb5-056e32aed36e
| checkpoint | Remove exisiting ACM
| checkpoint | Remove exisitng Flashings and inspect substrate
| checkpoint | Install new 12mm plywood to upstand
| checkpoint | Dress fibretite
| checkpoint | Install New 0.9 Aluminium Flashing
| checkpoint | Install new Fascia
| checklist | SP3b Block I - Infill Panels |  | SP3b Block I - Infill Panels | 83d6164d-ccac-4413-9aa8-be7859534ccb
| checkpoint | Remove ACM
| checkpoint | Install RWU
| checkpoint | Install Cavity Battens
| checkpoint | Install Castellated batten
| checkpoint | Install new aluminium flashing panel
| checklist | SP3b Block I - Windows |  | SP3b Block I - Windows | 27810cb2-5e49-4d65-8852-fb76b77f9460
| checkpoint | Remove existing window
| checkpoint | Re frame to new opening size
| checkpoint | Chamfered sill
| checkpoint | Dress Membrane onto window sill
| checkpoint | Install sill flashings
| checkpoint | Install window
| checkpoint | Install Head flashing
| checkpoint | Air seal installed
| checkpoint | Architraves
| checkpoint | Window winders installed
| checklist | SP3C Block H - Stage 1 - Awning Roof |  | SP3C Block H - Stage 1 - Awning Roof | 74ca16f0-b5df-42e9-8ebb-de57be2f07bd
| checkpoint | Remove Existing Clearlite and spouting
| checkpoint | Stop and repaint structural fascia
| checkpoint | Install new Fibreglass Roofing
| checkpoint | Install closed cell profiled foam strip
| checkpoint | Install Apron Flashing
| checkpoint | New Gutters and Downpipes
| checklist | SP3C Block H - Stage 1 - Upper Roof |  | SP3C Block H - Stage 1 - Upper Roof | f1f5df52-9597-44d0-a538-6e85b555ff51
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Remove existing Heat pump units
| checkpoint | Remove Existing Titain board
| checkpoint | Install new plywood upstand
| checkpoint | MHA to inspect condition of existing RAB system
| checkpoint | Form new parapet at membrane to metal roof junction
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 80mm PIR
| checkpoint | Taper PIR closest to spouting
| checkpoint | New Aluminium Drip Edge
| checkpoint | New Fibertite Membrane
| checkpoint | Penetration through roof
| checkpoint | New Fascias
| checkpoint | Install Pressure Bars
| checkpoint | New Gutters and Down Pipes
| checkpoint | Reinstate heat pump units
| checkpoint | New Flashing at membrane to RAB junction
| checkpoint | Install cavity closer
| checkpoint | Install new Extotec as Titain board
| checkpoint | Paint Cladding
| checklist | SP3C Block H - Stage 2 - Awning Roof |  | SP3C Block H - Stage 2 - Awning Roof | 3483ecff-9eff-4083-af91-01301371a635
| checkpoint | Remove Existing Clearlite
| checkpoint | Stop and repaint structural fascia
| checkpoint | Install new Fibreglass Roofing
| checkpoint | Install closed cell profiled foam strip
| checkpoint | Install Apron Flashing
| checkpoint | New Gutters and Downpipes
| checklist | SP3C Block H - Stage 2 - Upper Roof |  | SP3C Block H - Stage 2 - Upper Roof | 8105b28d-bf00-4de3-b773-79f17e0bccbb
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 80mm PIR
| checkpoint | Taper PIR closest to spouting
| checkpoint | New Aluminium Drip Edge
| checkpoint | New Fibertite Membrane
| checkpoint | Penetration through roof
| checkpoint | New Fascias
| checkpoint | Install Pressure Bars
| checkpoint | New Gutters and Downpipes
| checklist | SP3C Block H - Stage 3 - AJ010-AJ013 |  | SP3C Block H - Stage 3 - AJ010-AJ013 | c5242e77-8e35-4389-bbe1-e5e71183942b
| checkpoint | Remove existing window
| checkpoint | Re frame to new opening size
| checkpoint | Chamfered sill
| checkpoint | Dress Membrane onto window sill
| checkpoint | Install sill flashings
| checkpoint | Install window
| checkpoint | Install Head flashing
| checkpoint | Air seal installed
| checkpoint | Architraves
| checkpoint | Window winders installed
| checklist | SP3C Block H - Stage 3 - AJ017-AJ018 |  | SP3C Block H - Stage 3 - AJ017-AJ018 | 877be4e1-6e76-4ce8-aebb-224c4a3581fd
| checkpoint | Remove existing window
| checkpoint | Re frame to new opening size
| checkpoint | Chamfered sill
| checkpoint | Dress Membrane onto window sill
| checkpoint | Install sill flashings
| checkpoint | Install window
| checkpoint | Install Head flashing
| checkpoint | Air seal installed
| checkpoint | Architraves
| checklist | SP3C Block H - Stage 3 - Art room roof |  | SP3C Block H - Stage 3 - Art room roof | db5c2176-0685-428b-b058-7548f16af3c5
| checkpoint | Replace corroded fixings
| checkpoint | Prime roof
| checkpoint | Paint roof
| checklist | SP3C Block H - Stage 3 - H-I link Roof |  | SP3C Block H - Stage 3 - H-I link Roof | 82d3549c-3c0a-4930-9454-c5610a9579de
| checkpoint | Demo existing roof
| checkpoint | Assess Framing
| checkpoint | New 140 x 45 joists @ 400cs
| checkpoint | New Ply substrate at 3 degrees
| checkpoint | Form new box gutters
| checkpoint | Tray dec Installed
| checkpoint | Vapour Barrier
| checkpoint | 80mm PIR installed
| checkpoint | 60-80mm Taped PIR
| checkpoint | Drip edge flashing
| checkpoint | Fibertite Membrane installed
| checkpoint | Welded saddle flashing
| checkpoint | Pressure Bar to drip edge
| checkpoint | Fascia installed
| checkpoint | Install new rainwater head
| checkpoint | Gutter and downpipes installed
| checklist | SP3C Block H - Stage 3 - Upper Roof |  | SP3C Block H - Stage 3 - Upper Roof | 5f180f27-75d3-48a8-bf1e-581f7cbae74c
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 80mm PIR
| checkpoint | Taper PIR closest to spouting
| checkpoint | New Aluminium Drip Edge
| checkpoint | New Fibertite Membrane
| checkpoint | Penetration through roof
| checkpoint | New Fascias
| checkpoint | Install Pressure Bars
| checkpoint | New Gutters and Downpipes
| checklist | SP3C Block H - Stage 3 - Wall cladding |  | SP3C Block H - Stage 3 - Wall cladding | 02d887c1-c8c2-4185-ac6f-f391cf827f0e
| checkpoint | Install additional framing for sheet joins
| checkpoint | Install RAB Board
| checkpoint | Install Intello Wrap
| checkpoint | Penetration flashing to wrap
| checkpoint | 0.9 BMT Aluminium Flashing
| checkpoint | Cavity closer installed
| checkpoint | Cavity Battens - 600cs
| checkpoint | 9mm Fibre Cement cladding
| checkpoint | Fascias with air vent.
| checkpoint | Painting cladding and fascias
| checklist | SP4a Block F - Bathroom |  | Bathroom | 6b894aed-9097-4d74-88c4-6898280e6070
| section | Bathroom
| checkpoint | Extend Concrete nibs
| checkpoint | Install Subfloor framing
| checkpoint | Subfloor plumbing
| checkpoint | Subfloor Drainage Inspection
| checkpoint | Earthwool R2.6 90mm fitted batts
| checkpoint | New Subfloor Plywood
| checkpoint | Re frame Exterior 140mm Walls
| checkpoint | Install Internal walls
| checkpoint | Install Double Studs -As per Structural Drawings
| checkpoint | Install new roof rafters
| section | Exterior Wall Cladding
| checkpoint | Pre Wrap Inspection
| checkpoint | Install 6mm RAB Board
| checkpoint | Extasana Adhero
| checkpoint | H3.1 Cavity battens
| checkpoint | Pre Clad Inspection
| checkpoint | JH Easylap Cladding
| checkpoint | Soffit linings
| checkpoint | Paint
| section | Internal Linings
| checkpoint | Ensure all services in wall - 1st Fix
| checkpoint | Inspect Door openings
| checkpoint | 140mm Walls Pink Batts R3.6
| checkpoint | 90mm Walls Pink Batts Silencer
| checkpoint | Pre line Building Inspection
| checkpoint | Pre line Plumbing Inspection
| checkpoint | Pre line Electrical - Terry Moes
| checkpoint | 12mm Ecoply
| checkpoint | Post Line Inspection
| checkpoint | 9mm Villaboard
| checkpoint | Plaster finish L4
| checkpoint | Skirts and archs
| checkpoint | Paint
| checklist | SP4a Block F - Block F Foyer Roof |  | Block F Foyer Roof | d65abe5b-cc9e-4815-9e5c-f315c9beff52
| checkpoint | Remove existing cladding and ACM
| checkpoint | Demo box gutter
| checkpoint | Rebuild box gutter 1:100
| checkpoint | Install Vapour barrier and 20-40mm PIR
| checkpoint | Fibreclad Scupper Drip Edge
| checkpoint | Install continuous length of Fibretite
| checkpoint | Install new Purlins
| checkpoint | 0.55BMT Flashing for vapour control
| checkpoint | Install new Base deck With Vapour barrier control Foam
| checkpoint | RL Butyl Tape to all Side laps
| checkpoint | Install Post and Rail System
| checkpoint | New 0.9BMT eave flashing with Proclim,a Solitex Mento 3000
| checkpoint | Vented comb closure installed
| checkpoint | New Top Deck 0.55BMT Multirib Colourcote MagnaFlow
| checkpoint | Install Rain head and Downpipes
| checklist | SP4a Block F - Drama Room Cladding |  | Drama Room Cladding | bf7fa829-bf24-421f-8b64-f0a6c3ef4a1e
| checkpoint | New framing to allow for easylap cladding
| checkpoint | Insulation installed
| checkpoint | RAB 6mm Installed
| checkpoint | Fibretite dress onto RAB
| checkpoint | Proclima Adhero Installed
| checkpoint | Cavity Closer and battens installed
| checkpoint | JH Easylap cladding installed
| checkpoint | JH Easylap Painted
| checklist | SP4a Block F - Hall Cladding |  | Hall Cladding | 7896cae6-67c9-420c-8463-51682e8f84c6
| checkpoint | New framing to allow for easylap cladding
| checkpoint | Insulation installed
| checkpoint | RAB 6mm Installed
| checkpoint | Fibretite dress onto RAB
| checkpoint | Proclima Adhero Installed
| checkpoint | Install Two part Apron flashing
| checkpoint | Cavity Closer and battens installed
| checkpoint | JH Easylap cladding installed
| checkpoint | JH Easylap Painted
| checklist | SP4a Block F - New Stairs |  | New Stairs | fb0a9fe6-c497-44bb-b50b-c2836fa5b71d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Excavate footing
| checkpoint | Inspect Reo
| checkpoint | Pour Concrete
| checkpoint | Install Posts & Handrails
| checkpoint | Install Tredsafe AA125 Stair nosings
| checklist | SP4a Block F - West Elevation Wall |  | West Elevation Wall | 6d18e953-4494-4024-aaa8-3ce4ac65d118
| checkpoint | Remove ACM
| checkpoint | Framesaver first floor framing
| checkpoint | Re place ground level framing
| checkpoint | Install structural Items SR 006 CBP
| checkpoint | Install double stud framing for new cladding
| checkpoint | Install RAB 15mm Plywood
| checkpoint | Install Proclima Adhero
| checkpoint | Install Cavity battens
| checkpoint | Install JH Easylap Fibre cement cladding
| checkpoint | 0.70BMT Interstorey Flashing
| checkpoint | Install Wall cowls
| checkpoint | Paint Cladding
| checkpoint | Install sensor light
| checklist | SP4a Block F - West Wall Window Install |  | West Wall Window Install | cdb6fb9b-bbe2-43bd-8e16-20e714972319
| checkpoint | Re frame Opening
| checkpoint | Tape window opening
| checkpoint | Install WANZ Bar
| checkpoint | Install Window
| checklist | Stage 2 Roof - AJ |  | Stage 2 Roof - AJ | 57e388ec-d8ef-4554-a0a6-65b3b80bc0fe
| checkpoint | Remove existing window
| checkpoint | Re frame to new opening size
| checkpoint | Chamfered sill
| checkpoint | Dress Membrane onto window sill
| checkpoint | Install sill flashings
| checkpoint | Install window
| checkpoint | Install Head flashing
| checkpoint | Air seal installed
| checkpoint | Architraves
| checkpoint | Window winders installed
| checklist | Stage 3 - Duct Bracing |  | Stage 3 - Duct Bracing | 33a64b48-79c9-4c1b-84b4-78747f6c7408
| checkpoint | Solid Blocking (200mm Long)
| checkpoint | 4-12g Screws 150mm Long Each Side
| checkpoint | Gripple GS19 Braces
| checklist | Stage 3 - Library Exterior - East & West |  | Stage 3 - Library Exterior - East & West | f34118cd-bc20-4538-a04e-3cb8d7410a2b
| checkpoint | Remove Asbestos Soffit
| checkpoint | Remove 3 Windows
| checkpoint | Lap new Building Paper
| checkpoint | Install new Weatherboards
| checkpoint | Install Scribers
| checkpoint | Install H3.2 Soffit Blocking
| checkpoint | Install Soffit Flashing
| checkpoint | Install Soffits
| checkpoint | Paint Weatherboard
| checkpoint | Paint Soffits
| checklist | Stage 3 - Library Exterior - North |  | Stage 3 - Library Exterior - North | ce716b90-d0f1-4aec-b224-7a7adbee34f0
| checkpoint | Remove Asbestos Soffits
| checkpoint | Remove Existing Windows
| checkpoint | Check Windows Openings Sizes
| checkpoint | Install Jamb Battens
| checkpoint | Install New Flashing Tape - 50mm lap onto Building Paper
| checkpoint | Install New Weatherboard Below Windows
| checkpoint | 0.9BMT Powder Coated Aluminium Sill Flashing
| checkpoint | Install New Wall Underlay
| checkpoint | Install New Weatherboards
| checkpoint | Install New Windows
| checkpoint | Install Fascia Between Windows
| checkpoint | Install Scribers
| checkpoint | Install H3.2 Soffit Blocking
| checkpoint | Install Soffit Flashing
| checkpoint | Install Villaboard Soffit
| checkpoint | Paint Weatherboards
| checkpoint | Paint Soffits
| checklist | Stage 3 - Library Exterior - South |  | Stage 3 - Library Exterior - South | 0ca3583b-eec3-450b-826f-21c48ec81c06
| checkpoint | Remove Windows
| checkpoint | Remove Existing Cladding
| checkpoint | New Framing - New Bottom Plate DPC
| checkpoint | New RWU - Proclima Self Adhesive
| checkpoint | Install H3.2 Timber Plate with DPC
| checkpoint | Install 1.2BMT Base flashing - 15Deg Slope
| checkpoint | Install Cavity Closer
| checkpoint | Install Easylap Cladding
| checkpoint | Install Castellated Batten
| checkpoint | Install 1.2 Aluminium Soffit Flashing
| checkpoint | Paint Cladding
| checklist | Stage 3 - Library Interior - North, East & West |  | Stage 3 - Library Interior - North, East & West | b75c676f-e97a-4d72-873d-def549d7ea43
| checkpoint | Remove Windows
| checkpoint | Reframe Wall
| checkpoint | Install Windows
| checkpoint | Airseal Around Windows
| checkpoint | Install Insulation
| checkpoint | Install Structural Plywood
| checkpoint | Install Skirtings
| checkpoint | Install Architraves
| checkpoint | Install Autex
| checkpoint | Install Ceiling Flashing Trim
| checklist | Stage 3 - Library Interior -Careers Room |  | Stage 3 - Library Interior -Careers Room | 75579881-0cd0-4b00-a2d6-4ebeeaebf602
| checkpoint | Remove Windows
| checkpoint | Reframe Wall
| checkpoint | Install Windows
| checkpoint | Airseal Around Windows
| checkpoint | Install Insulation
| checkpoint | Install Structural Plywood
| checkpoint | Install Skirtings
| checkpoint | Install Architraves
| checkpoint | Install Autex
| checklist | Stage 3 - Plywood Brace Walls |  | Stage 3 - Plywood Brace Walls | 94ab479d-5443-4a58-98e1-75f9c204e79f
| checkpoint | New Full Height Studs & Nogs
| checkpoint | New Bottom Plate Fixing @ 600 Centres
| checkpoint | Install Hold Down Brackets
| checkpoint | 12G Timber Screws 125mm Long
| checkpoint | M12 Bolts into SHS Post
| checkpoint | New 12mm F8 Ply Bracing 125mm FH Nails
| checklist | Stage 3 - Rafter to Ridge |  | Stage 3 - Rafter to Ridge | 814a5da2-edd7-4597-b873-d3f96d5c6ab1
| checkpoint | 100 UC 15 Steel Frame
| checkpoint | M16 x2 Bolts
| checkpoint | 10mm thick Tee Brackets
| checkpoint | 100 x6 EA Between Rafters
| checkpoint | Double Timber Blocking up to Ridge
| checkpoint | CPC80 Each side of Rafters
| checkpoint | 2x Lumberlok Multistraps
| checklist | Stage 3 - Roof |  | Stage 3 - Roof | 5d98e3fa-7d48-4372-a32f-afc2989359f4
| checkpoint | Remove Satellite Dish
| checkpoint | Remove Existing Corrugated Iron
| checkpoint | Remove Gutters & Down Pipes
| checkpoint | Inspect Roof Rafters
| checkpoint | Inspect Services
| checkpoint | Install Roof Insulation - 25mm gap
| checkpoint | Install Blocking between Existing Outriggers
| checkpoint | Install Fascia
| checkpoint | Paint Fascia
| checkpoint | Install Drispace GN2500N Fascia Vent
| checkpoint | Install VB20 Venting Batten
| checkpoint | Install Eave Flashing
| checkpoint | Install Wire netting
| checkpoint | DRISTUD FRU38 Roof Underlay
| checkpoint | Terminate at Top Batten
| checkpoint | Install VB10 Venting Batten
| checkpoint | Install Space Eaves Comb Filler G1275
| checkpoint | Install Colorcote Magnaflow Roofing (Smokey)
| checkpoint | Up Turn Stop Ends
| checkpoint | 40mm Between Sheets at Ridge
| checkpoint | Install Ridge Vent RV10DT
| checkpoint | Install Ridge Flashing - 10mm Gap from Roof
| checkpoint | Type 17 14G x 140mm Timbertite Screws
| checkpoint | 125mm Box Colorcote Gutter on External Brackets 10mm Gap
| checklist | Stage 3 - Tie Beams |  | Stage 3 - Tie Beams | 1d35558c-85c7-4eb1-87dc-fffa461217cc
| checkpoint | 45x6 EA Tie Beam
| checklist | Stage 3 - Top Plate Fixing |  | Stage 3 - Top Plate Fixing | d8cb3fab-ea9a-46b4-9fc8-59a29718db27
| checkpoint | 80x6 G300 Plate
| checklist | Stage 3 Extension Block K&i |  | Phase 3 Block N&K | 62412db1-11a1-4761-9a58-c702eb27dd2f
| checkpoint | Remove Existing Membrane roof
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove Existing cap flashing
| checkpoint | Install screws to substrate
| checkpoint | Install through infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 40mm PIR
| checkpoint | New Fibertite Membrane
| checkpoint | New Fascias
| checkpoint | Frame Parapet
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipies
| checklist | Stage 4 - Easylap Cladding |  | Easylap Cladding | a6c1c0df-8b50-4929-a035-2bb6425ec553
| checkpoint | RAB Board - Adhero Wrap
| checkpoint | Cavity Closer
| checkpoint | CLD Battens - 400 crs
| checkpoint | Easylap panels
| checkpoint | Painting Completed
| checklist | Stage 4 - Fibretite Roof |  | Fibretite Roof | 9a4c08ae-0bf8-417e-b825-ef335c4662e1
| checkpoint | Frame membrane roof - 400 centres
| checkpoint | 19mm Plywood install
| checkpoint | Vapour Barrier
| checkpoint | PIR Board
| checkpoint | Fibretite Membrane
| checkpoint | Membrane Upstands
| checkpoint | Diverters
| checkpoint | Box gutter
| checklist | Stage 4 - Roof |  | Roof | 6d9ce565-415f-4b22-9161-42ac6d8dde10
| checkpoint | Remove Roof Iron
| checkpoint | Clean and encapsulate asbestos
| checkpoint | New 140mm Rafters 600mm ctrs
| checkpoint | New 140mm Outriggers
| checkpoint | New 90x45 props to end of rafters
| checkpoint | New 90x45 Mid span props
| checkpoint | Extend wall to support 140mm rafters.
| checkpoint | 2/90 x 3.15 skew nails + 2 wire dogs
| checkpoint | Insulation
| checkpoint | Intello to seal exterior
| checkpoint | Roof bracing straps
| checkpoint | Additonal purlins
| checkpoint | Purlin Fixings Bugle 14 Guage
| checkpoint | Fascia installed
| checkpoint | Fascia painted - all four sides
| checkpoint | 0.9BMT Colorcote Alugard eaves
| checkpoint | Wire Netting
| checkpoint | Vent Eave Combs Filler - G1275
| checkpoint | Magnaflow 0.55 BMT Roofing
| checkpoint | Vent Back Flashings
| checkpoint | Apron Flashings
| checkpoint | 300mm Box Gutter
| checkpoint | Downpipes - brackets @800mm Crs
| checklist | Stage 4 - Weatherboard Cladding |  | Weatherboard Cladding | c402e027-31d9-45ba-bdd2-d21e5b53eb3c
| checkpoint | Apron Flashing Installed
| checkpoint | RAB Board - Adhero Wrap
| checkpoint | Cavity closer
| checkpoint | Cavity Battens - 400mm Crs
| checkpoint | Weatherboard Installed
| checkpoint | Painting completed
| checklist | Stage 4 - Windows - AJ001 & AJ002 |  | Windows - AJ001 & AJ002 | f7950aa6-aa59-41b0-8fa8-571c255e8c58
| checkpoint | Remove Windows
| checkpoint | Re frame new opening sizes
| checkpoint | 100m SHS
| checkpoint | WANZ Bar
| checkpoint | Flashing Tape
| checkpoint | Cavity Batten
| checkpoint | Window installed
| checkpoint | Window winders
| checklist | Stage 4 - Windows - AJ003 |  | Windows - AJ003 | b8f827f6-2511-4a63-949f-28619ee1ade6
| checkpoint | Remove Windows
| checkpoint | Re frame new opening sizes
| checkpoint | 100m SHS
| checkpoint | Membrane dressed into sill
| checkpoint | Sill Flashing
| checkpoint | Flashing Tape
| checkpoint | Cavity Batten
| checkpoint | Window installed
| checkpoint | Window winders
| checklist | Stage 4 - Windows - AJ004 & AJ005 |  | Windows - AJ004 & AJ005 | e8bf74b7-9778-4990-b4db-18e28fe72299
| checkpoint | Remove Windows
| checkpoint | Re frame new opening sizes
| checkpoint | Membrane dressed onto sill
| checkpoint | Sill Flashing
| checkpoint | Flashing Tape
| checkpoint | Cavity Batten
| checkpoint | Window installed
| checkpoint | Window winders
| checklist | Stage 5 - Roof |  | Roof | da2c98d6-60fe-4d1c-8bd7-b5dc0d0f1ce7
| checkpoint | Remove Roof Iron
| checkpoint | Clean and encapsulate asbestos
| checkpoint | New 140mm Rafters 600mm ctrs
| checkpoint | New 140mm Outriggers
| checkpoint | New 90x45 props to end of rafters
| checkpoint | New 90x45 Mid span props
| checkpoint | Extend wall to support 140mm rafters.
| checkpoint | 2/90 x 3.15 skew nails + 2 wire dogs
| checkpoint | Insulation
| checkpoint | Intello to seal exterior
| checkpoint | Roof bracing straps
| checkpoint | Additonal purlins
| checkpoint | Purlin Fixings Bugle 14 Guage
| checkpoint | Fascia installed
| checkpoint | Fascia painted - all four sides
| checkpoint | 0.9BMT Colorcote Alugard eaves
| checkpoint | Wire Netting
| checkpoint | Vent Eave Combs Filler - G1275
| checkpoint | Magnaflow 0.55 BMT Roofing
| checkpoint | Vent Back Flashings
| checkpoint | Apron Flashings
| checkpoint | 300mm Box Gutter
| checkpoint | Downpipes - brackets @800mm Crs
| checklist | Sub Floor Framing Checklist |  | Sub Floor Framing Checklist | 739d954b-d137-468b-b168-4b08e1a7cdfe
| section | Piles
| checkpoint | Piles cut to height
| section | Bearers - 190x45
| checkpoint | Bearer - pile connections
| section | Joists - 140x45
| checkpoint | 400mm Cs
| checkpoint | Double Boundary Joist
| checkpoint | Full Depth Blocking over bearers
| section | 21mm Plywood
| checkpoint | Correct screw Cs
| checkpoint | Stainless Steel Screws
| checkpoint | Staggered sheet layout
| checklist | Timber Portals |  | Timber Portals | 567b3baf-938c-47d2-8dd9-92dc3e53a7f8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Base connections
| checkpoint | Apex connections
| checkpoint | Knee Connections
| checklist | Timber retaining wall and fence |  | Timber retaining wall and fence | bedea412-9853-454f-84ce-3b7589b2b4c7
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Excavate post holes to depth/good ground
| checkpoint | Hold point - pre pour inspections
| checkpoint | Install timber whallers
| checkpoint | Install soil drain
| checkpoint | Backfill
| checkpoint | Install structural fence posts
| checkpoint | M12 stainless bolts with 50x50 washers
| checkpoint | 90x70 Rails with CPC 40 top and bottom
| checkpoint | staggered palings with 95mm max gap
| checklist | Underground Services Checklist |  | Underground Services Checklist | 529e6a7d-c1fa-4fca-99c3-b208ed08fca8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Storm Water
| checkpoint | Electrical
| checkpoint | Sewer
| checkpoint | Data
| checkpoint | Sprinkler
| checkpoint | WCC - Sub Floor Drainage Inspection
| checklist | Upper Roof |  | Upper Roof | d7fd38ac-84de-49f8-a504-899785a60c24
| checkpoint | Delap photos
| checkpoint | Clean roof
| checkpoint | Remove existing cap flashings
| checkpoint | Install screws to substrate
| checkpoint | Install Trough Infill PIR
| checkpoint | New Vapour Barrier
| checkpoint | New 40mm PIR
| checkpoint | New Fibretite Membrane
| checkpoint | New Fascias
| checkpoint | Parapet flashing
| checkpoint | Gutters and Down pipies
| checklist | Water Supply Checklist |  | Water Supply Checklist | 7cafc8e6-0d44-4f6a-bc14-372f24f0ca68
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Sheilds installed
| checkpoint | Good ground confirmed
| checkpoint | Bidim cloth installed
| checkpoint | Bedding material install
| checkpoint | Pipe installed with clearance and cover
| checkpoint | Trench backfilled
| checkpoint | Test line
| checklist | Weatherboard Replacement |  | Weatherboard Replacement | 2a993ab6-d284-4b65-8fd1-95bacdfb1e2a
| checkpoint | Existing damaged weatherboard
| checkpoint | New replacement
| checkpoint | Paint