## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Precast retaining wall |  | Precast retaining wall |  | 7883a39d-4355-4a77-a9ce-ac4c0a86c56d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Excavation and batter back
| checkpoint | Shop drawings sign off
| checkpoint | Excavate ground beam and post holes to depth/good ground
| checkpoint | Ground beam DPM and form work
| checkpoint | 25mm poly above services
| checkpoint | R10 stirrups @ 200 centers
| checkpoint | Install 1200 long Galv starters for future extension
| checkpoint | Hold point - pre pour inspections
| checkpoint | Off Site inspections of precast panels
| checkpoint | Ucs installed in line and plumb
| checkpoint | precast panels installed - no gaps over 100mm
| checkpoint | Grouting of joints
| checkpoint | Install protection sheet
| checkpoint | Install soil drain
| checkpoint | Backfill