## Sheet1
CheckList | Punch window
Section | Opening check
Checkpoint | Visual inspect opening prepration, report any damages of concrete or waterproofing
Checkpoint | Check R/O Size, report if R/O is out of tolerance
Section | Joinery Install
Checkpoint | Check the joinery if any damages
Checkpoint | Frame installed in correct position & Level
Checkpoint | All joinery fixings install as per drawing&detail
Checkpoint | All fixings oversealed on frame and no tooling damage on frame
Checkpoint | No packers visable out of line where airseal is to be installed
Checkpoint | Joinery trade clean
Section | Rainshield angle Install
Checkpoint | Visual inspect flashing if any damages
Checkpoint | Jamb angle bed seal and install as per detail
Checkpoint | Head angle bed seal and install as per detail
Section | Airseal seal Install
Checkpoint | PEF Rod install correctly and sealant ratio achieved
Checkpoint | Sealant applied as per spec
Section | Glass
Checkpoint | Glazed and no damage
Section | Installer sign off
Check point | All elements completed correctly as per drawing