## Sheet1
3.1 | Material Delivery | Inspect for damage and wear, Confirm items are correct as per drawings and Specifications | -Pipes shall be DN600 Class 2 RCRRJ - Items are approved as per contract specification - DCC approved | Photos, delivery docket, MDD results CHAR(AMP) Materials grading for backfill materials | On Delivery | Visual | C | QE | 3.1 - Material Delivery | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications | Acceptance Criteria - -Pipes shall be DN600 Class 2 RCRRJ - Items are approved as per contract specification - DCC approved | Verifying Document - Photos, delivery docket, MDD results CHAR(AMP) Materials grading for backfill materials | Frequency - On Delivery | Inspection Type (Visual, other) - Visual | Inspection: Key - C | Inspection: By - QE | 3.1 - Material Delivery
3.2 | Set out | Set out completed by an approved surveyor marked allignment | Allignment set out matches drawings or aggreed by the Engineer | Survey marks, photos | Prior to commencement of works | Visual, Instrumental | H | SV SP QE PM ER | 3.2 - Set out | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer | Verifying Document - Survey marks, photos | Frequency - Prior to commencement of works | Inspection Type (Visual, other) - Visual, Instrumental | Inspection: Key - H | Inspection: By - SV SP QE PM ER | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
3.3 | Embedment Zone Materials - AP20 | Visual quality check AP20 is evenly graded granular material free of detritus | Material Approval by Quality Engineer | Photograph | On Delivery | Review CHAR(AMP) Approval | R | QE | 3.3 - Embedment Zone Materials - AP20 | Inspection Point: Quality Control Activity - Visual quality check AP20 is evenly graded granular material free of detritus | Acceptance Criteria - Material Approval by Quality Engineer | Verifying Document - Photograph | Frequency - On Delivery | Inspection Type (Visual, other) - Review CHAR(AMP) Approval | Inspection: Key - R | Inspection: By - QE | Acceptance Criteria - -Pipes shall be DN600 Class 2 RCRRJ - Items are approved as per contract specification - DCC approved
3.4 | Backfill Material - AP65 | Submission of Test Sheets for review | Material Approval by Engineer Rep | Test Certification | Once | Review CHAR(AMP) Approval | R | QE ER | 3.4 - Backfill Material - AP65 | Inspection Point: Quality Control Activity - Submission of Test Sheets for review | Acceptance Criteria - Material Approval by Engineer Rep | Verifying Document - Test Certification | Frequency - Once | Inspection Type (Visual, other) - Review CHAR(AMP) Approval | Inspection: Key - R | Inspection: By - QE ER | Verifying Document - Photos, delivery docket, MDD results CHAR(AMP) Materials grading for backfill materials
3.5 | Pavement Preparation Material - M440 | Submission of Test Sheets for review | Material Approval by Engineer Rep | Test Certification | Once | Review CHAR(AMP) Approval | R | QE ER | 3.5 - Pavement Preparation Material - M440 | Inspection Point: Quality Control Activity - Submission of Test Sheets for review | Acceptance Criteria - Material Approval by Engineer Rep | Verifying Document - Test Certification | Frequency - Once | Inspection Type (Visual, other) - Review CHAR(AMP) Approval | Inspection: Key - R | Inspection: By - QE ER | Frequency - On Delivery
4.1 | Trench Excavation | - Excavate to achieve required depth to invert as per C111 to C113 - Trench width to allow for sufficient clearance to accomodate trench shield and effective compaction between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | - Allow 150mm for bedding - Allow for cover as per long section drawing (minimum cover of 750mm). | Photos, measurement checks | During Installation | Visual | C | SP QE CM | 4.1 - Trench Excavation | Inspection Point: Quality Control Activity - - Excavate to achieve required depth to invert as per C111 to C113 - Trench width to allow for sufficient clearance to accomodate trench shield and effective compaction between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length | Acceptance Criteria - - Allow 150mm for bedding - Allow for cover as per long section drawing (minimum cover of 750mm). | Verifying Document - Photos, measurement checks | Frequency - During Installation | Inspection Type (Visual, other) - Visual | Inspection: Key - C | Inspection: By - SP QE CM | Inspection Type (Visual, other) - Visual
4.3 | Foundation | Scala tests on base of trench | Minimum of 3 blows per 100mm to achieve a CBR 5 or 100kPa Ground Bearing Pressure | Test results | During installation, per 20m | Visual, On site test | H | SP QE ER | 4.3 - Foundation | Inspection Point: Quality Control Activity - Scala tests on base of trench | Acceptance Criteria - Minimum of 3 blows per 100mm to achieve a CBR 5 or 100kPa Ground Bearing Pressure | Verifying Document - Test results | Frequency - During installation, per 20m | Inspection Type (Visual, other) - Visual, On site test | Inspection: Key - H | Inspection: By - SP QE ER | Inspection: Key - C
4.2 | 40 Clean drain detail | Install undercut detail if soft ground conditions or groundwater is encountered. | - 200mm depth Clean 40 wrapped in Bidim A29 geotextile | Photos | During Installation | Visual | C CHAR(AMP) I | SP QE ER | 4.2 - 40 Clean drain detail | Inspection Point: Quality Control Activity - Install undercut detail if soft ground conditions or groundwater is encountered. | Acceptance Criteria - - 200mm depth Clean 40 wrapped in Bidim A29 geotextile | Verifying Document - Photos | Frequency - During Installation | Inspection Type (Visual, other) - Visual | Inspection: Key - C CHAR(AMP) I | Inspection: By - SP QE ER | Inspection: By - QE
4.4 | Install Pipe | Pipe installed to grade as per drawing C111-C113 and referencing Project Specification - Appendix D2 | - Pipe not damaged during installation - Pipe installed to grade within tolerances specification GP 3.1.8 | Photos, Grade check sheet, Survey of position for asbuilt | During installation | Visual, instrumental | C CHAR(AMP) I | SP QE ER | 4.4 - Install Pipe | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C111-C113 and referencing Project Specification - Appendix D2 | Acceptance Criteria - - Pipe not damaged during installation - Pipe installed to grade within tolerances specification GP 3.1.8 | Verifying Document - Photos, Grade check sheet, Survey of position for asbuilt | Frequency - During installation | Inspection Type (Visual, other) - Visual, instrumental | Inspection: Key - C CHAR(AMP) I | Inspection: By - SP QE ER | 3.2 - Set out
4.5 | Embedment zone | Embedment material shall be AP20 as approved by the Engineer (Refer section 3.3 of this ITP) | - Min 150mm bedding - 150mm overlay | Photos Site Check Measurements | During Installation | Visual, measurement check | C | SP QE | 4.5 - Embedment zone | Inspection Point: Quality Control Activity - Embedment material shall be AP20 as approved by the Engineer (Refer section 3.3 of this ITP) | Acceptance Criteria - - Min 150mm bedding - 150mm overlay | Verifying Document - Photos Site Check Measurements | Frequency - During Installation | Inspection Type (Visual, other) - Visual, measurement check | Inspection: Key - C | Inspection: By - SP QE | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
4.6 | Backfill and Compact | Backfill AP65 in 200mm (Materials to be layers of compacted material as approved bt the Engineer (Refer Section 3.4 of this ITP) - Compaction testing one test every two layers as required | 95% MDD in roads, paths, and pavements | Photos, Compaction test results | During Installation, compaction testing per 50m of pipeline or per straight section of pipeline at each alternate layer | Visual, On Site test | H | SP QE ER | 4.6 - Backfill and Compact | Inspection Point: Quality Control Activity - Backfill AP65 in 200mm (Materials to be layers of compacted material as approved bt the Engineer (Refer Section 3.4 of this ITP) - Compaction testing one test every two layers as required | Acceptance Criteria - 95% MDD in roads, paths, and pavements | Verifying Document - Photos, Compaction test results | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline at each alternate layer | Inspection Type (Visual, other) - Visual, On Site test | Inspection: Key - H | Inspection: By - SP QE ER | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
4.7 | Materials compaction | Each Layer (200mm) compaction using plate compactor 8No back and forward passes | Compacted layer is 200mm | Photos, visual, measurement | 16No passes (8no x 2) | Visual, Photograph | V | SP QE ER | 4.7 - Materials compaction | Inspection Point: Quality Control Activity - Each Layer (200mm) compaction using plate compactor 8No back and forward passes | Acceptance Criteria - Compacted layer is 200mm | Verifying Document - Photos, visual, measurement | Frequency - 16No passes (8no x 2) | Inspection Type (Visual, other) - Visual, Photograph | Inspection: Key - V | Inspection: By - SP QE ER | Verifying Document - Survey marks, photos
4.8 | Pavement reinstatement and surfacing | Place and compact M440 as approved by the Engineer (Refer Section 3.5 of this ITP) basecourse in preparation for 50mm asphalt | - Average 98% MDD in roads with no test lower than 95%. - Over cut trench 100mm from trench wall - Prep 50mm below staright edge | Photos, Compaction test results | During Installation, compaction testing per 50m of pipeline or per straight section of pipeline | Visual, On Site test | H | SP QE ER | 4.8 - Pavement reinstatement and surfacing | Inspection Point: Quality Control Activity - Place and compact M440 as approved by the Engineer (Refer Section 3.5 of this ITP) basecourse in preparation for 50mm asphalt | Acceptance Criteria - - Average 98% MDD in roads with no test lower than 95%. - Over cut trench 100mm from trench wall - Prep 50mm below staright edge | Verifying Document - Photos, Compaction test results | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline | Inspection Type (Visual, other) - Visual, On Site test | Inspection: Key - H | Inspection: By - SP QE ER | Frequency - Prior to commencement of works
5.1 | CCTV | CCTV inspection to confirm pipeline conforms with specification | Pipeline will fail is any of the following is visible: - pipe misalignment or deformation more than 5% of the pipe diameter - defects such as open joints, potruding laterals, cracked barrels, or similar | Test Records, CCTV footage | Every section of pipe completed | On-Site Test | H | SP QE CM ER | 5.1 - CCTV | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification | Acceptance Criteria - Pipeline will fail is any of the following is visible: - pipe misalignment or deformation more than 5% of the pipe diameter - defects such as open joints, potruding laterals, cracked barrels, or similar | Verifying Document - Test Records, CCTV footage | Frequency - Every section of pipe completed | Inspection Type (Visual, other) - On-Site Test | Inspection: Key - H | Inspection: By - SP QE CM ER | Inspection Type (Visual, other) - Visual, Instrumental
5.2 | Leak Testing | Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4 | Engineer Approval | Test Records | Every section of pipe installed | On-Site Test | H | SP QE CM ER | 5.2 - Leak Testing | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4 | Acceptance Criteria - Engineer Approval | Verifying Document - Test Records | Frequency - Every section of pipe installed | Inspection Type (Visual, other) - On-Site Test | Inspection: Key - H | Inspection: By - SP QE CM ER | Inspection: Key - H
5.3 | Red pen markups | Complete mark up of any changes from supplied drawings | Installation complete | Original Drawings CHAR(AMP) Documentation | After completion of pipe section | Measure CHAR(AMP) Record | H | SP QE CM ER | 5.3 - Red pen markups | Inspection Point: Quality Control Activity - Complete mark up of any changes from supplied drawings | Acceptance Criteria - Installation complete | Verifying Document - Original Drawings CHAR(AMP) Documentation | Frequency - After completion of pipe section | Inspection Type (Visual, other) - Measure CHAR(AMP) Record | Inspection: Key - H | Inspection: By - SP QE CM ER | Inspection: By - SV SP QE PM ER
5.4 | As-Built Survey | At project completion | Engineer approval | As-Built Drawings | Completion of Project | Submission of Documentation | R | ER | 5.4 - As-Built Survey | Inspection Point: Quality Control Activity - At project completion | Acceptance Criteria - Engineer approval | Verifying Document - As-Built Drawings | Frequency - Completion of Project | Inspection Type (Visual, other) - Submission of Documentation | Inspection: Key - R | Inspection: By - ER | 3.3 - Embedment Zone Materials - AP20
Inspection Point: Quality Control Activity - Visual quality check AP20 is evenly graded granular material free of detritus
Acceptance Criteria - Material Approval by Quality Engineer
Verifying Document - Photograph
Frequency - On Delivery
Inspection Type (Visual, other) - Review CHAR(AMP) Approval
Inspection: Key - R
Inspection: By - QE
3.4 - Backfill Material - AP65
Inspection Point: Quality Control Activity - Submission of Test Sheets for review
Acceptance Criteria - Material Approval by Engineer Rep
Verifying Document - Test Certification
Frequency - Once
Inspection Type (Visual, other) - Review CHAR(AMP) Approval
Inspection: Key - R
Inspection: By - QE ER
3.5 - Pavement Preparation Material - M440
Inspection Point: Quality Control Activity - Submission of Test Sheets for review
Acceptance Criteria - Material Approval by Engineer Rep
Verifying Document - Test Certification
Frequency - Once
Inspection Type (Visual, other) - Review CHAR(AMP) Approval
Inspection: Key - R
Inspection: By - QE ER
4.1 - Trench Excavation
Inspection Point: Quality Control Activity - - Excavate to achieve required depth to invert as per C111 to C113 - Trench width to allow for sufficient clearance to accomodate trench shield and effective compaction between springline of the pipe and trench wall or an adjacent pipe - Floor of trench to be even across width and length
Acceptance Criteria - - Allow 150mm for bedding - Allow for cover as per long section drawing (minimum cover of 750mm).
Verifying Document - Photos, measurement checks
Frequency - During Installation
Inspection Type (Visual, other) - Visual
Inspection: Key - C
Inspection: By - SP QE CM
4.3 - Foundation
Inspection Point: Quality Control Activity - Scala tests on base of trench
Acceptance Criteria - Minimum of 3 blows per 100mm to achieve a CBR 5 or 100kPa Ground Bearing Pressure
Verifying Document - Test results
Frequency - During installation, per 20m
Inspection Type (Visual, other) - Visual, On site test
Inspection: Key - H
Inspection: By - SP QE ER
4.2 - 40 Clean drain detail
Inspection Point: Quality Control Activity - Install undercut detail if soft ground conditions or groundwater is encountered.
Acceptance Criteria - - 200mm depth Clean 40 wrapped in Bidim A29 geotextile
Verifying Document - Photos
Frequency - During Installation
Inspection Type (Visual, other) - Visual
Inspection: Key - C CHAR(AMP) I
Inspection: By - SP QE ER
4.4 - Install Pipe
Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C111-C113 and referencing Project Specification - Appendix D2
Acceptance Criteria - - Pipe not damaged during installation - Pipe installed to grade within tolerances specification GP 3.1.8
Verifying Document - Photos, Grade check sheet, Survey of position for asbuilt
Frequency - During installation
Inspection Type (Visual, other) - Visual, instrumental
Inspection: Key - C CHAR(AMP) I
Inspection: By - SP QE ER
4.5 - Embedment zone
Inspection Point: Quality Control Activity - Embedment material shall be AP20 as approved by the Engineer (Refer section 3.3 of this ITP)
Acceptance Criteria - - Min 150mm bedding - 150mm overlay
Verifying Document - Photos Site Check Measurements
Frequency - During Installation
Inspection Type (Visual, other) - Visual, measurement check
Inspection: Key - C
Inspection: By - SP QE
4.6 - Backfill and Compact
Inspection Point: Quality Control Activity - Backfill AP65 in 200mm (Materials to be layers of compacted material as approved bt the Engineer (Refer Section 3.4 of this ITP) - Compaction testing one test every two layers as required
Acceptance Criteria - 95% MDD in roads, paths, and pavements
Verifying Document - Photos, Compaction test results
Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline at each alternate layer
Inspection Type (Visual, other) - Visual, On Site test
Inspection: Key - H
Inspection: By - SP QE ER
4.7 - Materials compaction
Inspection Point: Quality Control Activity - Each Layer (200mm) compaction using plate compactor 8No back and forward passes
Acceptance Criteria - Compacted layer is 200mm
Verifying Document - Photos, visual, measurement
Frequency - 16No passes (8no x 2)
Inspection Type (Visual, other) - Visual, Photograph
Inspection: Key - V
Inspection: By - SP QE ER
4.8 - Pavement reinstatement and surfacing
Inspection Point: Quality Control Activity - Place and compact M440 as approved by the Engineer (Refer Section 3.5 of this ITP) basecourse in preparation for 50mm asphalt
Acceptance Criteria - - Average 98% MDD in roads with no test lower than 95%. - Over cut trench 100mm from trench wall - Prep 50mm below staright edge
Verifying Document - Photos, Compaction test results
Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
Inspection Type (Visual, other) - Visual, On Site test
Inspection: Key - H
Inspection: By - SP QE ER
5.1 - CCTV
Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
Acceptance Criteria - Pipeline will fail is any of the following is visible: - pipe misalignment or deformation more than 5% of the pipe diameter - defects such as open joints, potruding laterals, cracked barrels, or similar
Verifying Document - Test Records, CCTV footage
Frequency - Every section of pipe completed
Inspection Type (Visual, other) - On-Site Test
Inspection: Key - H
Inspection: By - SP QE CM ER
5.2 - Leak Testing
Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
Acceptance Criteria - Engineer Approval
Verifying Document - Test Records
Frequency - Every section of pipe installed
Inspection Type (Visual, other) - On-Site Test
Inspection: Key - H
Inspection: By - SP QE CM ER
5.3 - Red pen markups
Inspection Point: Quality Control Activity - Complete mark up of any changes from supplied drawings
Acceptance Criteria - Installation complete
Verifying Document - Original Drawings CHAR(AMP) Documentation
Frequency - After completion of pipe section
Inspection Type (Visual, other) - Measure CHAR(AMP) Record
Inspection: Key - H
Inspection: By - SP QE CM ER
5.4 - As-Built Survey
Inspection Point: Quality Control Activity - At project completion
Acceptance Criteria - Engineer approval
Verifying Document - As-Built Drawings
Frequency - Completion of Project
Inspection Type (Visual, other) - Submission of Documentation
Inspection: Key - R
Inspection: By - ER