## Table 1
Inspection and Test Plan Details | [8 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec | Criteria |  | Frequency | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 | Lot Identification |  | Contractor | Technical Specification | Location of Works identified in accordance with project technical specification |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | CHK
2 | Underlying Lot Conforms |  | Contractor | Technical Specification | Foundation preparation works completed in underlying lot. |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | CHK
3 | General Fill Material Requirement |  | Contractor | Technical Specification | Grading Requirements 75mm sieve –100% passing 19mm Sieve - 80 to 100% passing 2.36mm sieve - 30 to 100 % passing 0.075mm Sieve –15-90% passing Indicator requirements Plasticity Index – 10 to 40% Liquid Limit – 20 to 60% Emerson Class 2 (minimum) Organic content 2% (maximum) |  | 1/Lot | Laboratory test Certificate | RSA | WP |  | Senex | WP
3 | Fill placement |  | Contractor | Technical Specification | General Fill Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer. ≥ 96 % standard MDD. NOTE: ≥ 98% standard MDD for the Earthen Ring Beam General Fill Section. -2% to +2% of OMC |  | Each Lot | ITP Verification Checklist/Lot Map Laboratory test Certificate | RSA | WP |  | Senex | WP
Inspection and Test Plan Details | [8 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec | Criteria |  | Frequency | Record | Resp | Type | Signoff | Resp | Type | Signoff
4 | Testing |  | Contractor | Technical Specification | General Fill SDDR – 3 per 2500m3 PSD – 2 per 2500m3 Atterberg – 2 per 2500m3 Emerson – 2 per 2500m3 General fill – Earth Ring Beam SDDR – 1 every 50 m(lineal) |  | 1/Lot | Laboratory test Certificate | RSA | HP |  | Senex | WP
5 | Survey |  | Contractor | Technical Specification | RSA shall submit 50%, 100% tank pad foundation fill placement completion survey to the superintendent within 48 hours of each milestone achievement |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | HP |  | Senex | HP
Built in accordance with this document: |  |  |  |  | Signed Position |  |  |  | Date
Test results received. Lot conforms to Specification: |  |  |  |  | Signed Position |  |  |  | Date
Document Status
Revision Status |  | Responsible Person |  | Signed | Dated | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: