## Table 1
Inspection and Test Plan Details | [8 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec | Criteria |  | Frequency | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 | Lot Identification |  | Contractor | Technical Specification | Location of Works identified in accordance with project technical specification |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | CHK
2 | Material Approval |  | Contractor | Technical Specification | Material shall meet the requirements under Queensland Department of Main Roads Technical Specification (MRTS)05 Type 2.5. |  | 1/Stockpile | Laboratory test Certificate | RSA | CHK |  | Senex | CHK
3 | Proof Rolling Subgrade acceptance |  | Contractor | Technical Specification | Main Roads Technical Specification (MRTS) 04 General Earthworks Section 18.3.2 or similar method as approved by the Superintendent while in the presence of the Client |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | WP |  | Senex | WP
4 | Placement of material |  | Contractor | Technical Specification | Access track and ring road capped with 200 mm depth gravel. Placed in continuous, approximately horizontal layers having a compacted thickness of not less than 75 mm and not more than 200 mm. If the surface of any layer is smooth it must be lightly scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer. |  | 1/Lot | ITP Verification Checklist/Lot Map | RSA | CHK |  | Senex | CHK
5 | Material Testing |  | Contractor | Technical Specification | Capping Material shall be tested for material characteristics, moisture, and compaction. >98% SDDR -2% dry to +2% wet OMC Capping Material: SDDR – 3 per 500m3 PSD – 2 per 500m3 Atterberg – 2 per 500m3 CBR – 2 per 500m3 |  | 1/Lot | Laboratory test Certificate | RSA | HP |  | Senex | HP
6 | As built Survey |  | Contractor | Technical Specification | Finished levels checked for Vertical and horizontal tolerances as required. |  | 1/Lot | Survey as Built | RSA | HP |  | Senex | HP
Built in accordance with this document: |  |  |  |  | Signed Position |  |  |  | Date
Test results received. Lot conforms to Specification: |  |  |  |  | Signed Position |  |  |  | Date
Document Status
Revision Status |  | Responsible Person |  | Signed | Dated | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: