## Table 1
Inspection and Test Plan Details | [8 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec | Criteria |  | Frequency | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 | Lot Identification |  | Contractor | Technical Specification | Location of works identify as per IFC drawings |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
2 | Gypsum Application |  | Contractor | Technical Specification | Apply gypsum to batters and table drains at rate of 2t/ha, scarify subsoil to a minimum depth of 150mm and apply water at 10mm/m2 to create adequate topsoil bond with the subgrade |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
3 | Topsoil Amelioration |  | Contractor | Technical Specification | Topsoil to be ameliorated with DAP Fertilizer at the rate of 150kg per Ha. |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
4 | Respreading of Topsoil |  | Contractor | Technical Specification | Topsoil is to be placed 300mm thick and trim with grader and scarify to a depth of 100mm.Surface left in a roughened state with horizontal rills running across the slopes to minimise potential erosion. |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK |  | Senex | CHK
5 | Seeding/Hydro mulch |  | Contractor | Technical Specification | The Contractor shall submit a proposed seed mix and hydro mulch / growth medium specifications for approval by the Company’s Representative |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | HP |  | Senex | HP
6 | Watering of Topsoil |  | Contractor | Technical Specification | Watering 10mm/m2 every day for first 8 days, then every second day to get to a total of 14 irrigation days. |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | WP |  | Senex | WP
7 | Survey |  | Contractor | Technical Specification | As-constructed survey has been completed to record the surface levels on completion. The Contractor shall submit results of each survey to the superintendent within 48hours of undertaking the Survey. |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | HP |  | Senex | HP
Built in accordance with this document: |  |  |  |  | Signed Position |  |  |  | Date
Test results received. Lot conforms to Specification: |  |  |  |  | Signed Position |  |  |  | Date
Document Status
Revision Status |  | Responsible Person |  | Signed | Dated | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: