## Table 1
Inspection and Test Plan Details | [10 empty] | Contractor |  | Client
Item | Inspection Activity |  | Work By | Standard / Spec |  | Criteria |  |  | Frequency | Record | Resp | Type | Resp |  | Type
1 | Lot Identification |  | Contractor | Technical Specification |  | Location of works identified as per IFC drawings |  |  | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK | Senex |  | CHK
Temporary Sediment and Erosion Control
2 | Clear identification and demarcation of ‘no go zones’ (where required) |  | Contractor | Technical Specification |  | Remove vegetation and disturb soil only in those areas approved for construction work to occur |  |  | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex |  | CHK
3 | Installation of temporary sediment and erosion control devices |  | Contractor | Technical Specification |  | Construction of earth bunds Installation of coir logs and Silt Fence Excavation of sediment catch sumps . |  |  | 1/Lot | ITP Verification Checklist | RSA | HP | Senex |  | HP
4 | Sediment and erosion control device ongoing inspections |  | Contractor | Technical Specification |  | Inspection of sediment and erosion control devices completed to be completed at the below frequencies Rain: >50mm in on day or >100mm over 4 days Prior to shift breaks |  |  | Ongoing | Environmental Routine Checklist | RSA | WP | Senex |  | WP
Permanent Sediment and Erosion Control – Rip Rap (Rock Protection)
5 | Underlying Lot conformance - Subgrade |  | Contractor | Technical Specification |  | The Superintendent must have a visual inspection of the subgrade, prior to the placement of the Separation Geotextile. |  |  | 1/Lot | ITP Verification Checklist | RSA | HP | Senex |  | HP
6 | Conformance Separation Geotextile Material |  | Contractor | Technical Specification |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data Certificates. |  |  | 1/Lot | ITP Verification Checklist | RSA | HP | Senex |  | HP
7 | Conformance Rip Rap |  | Contractor | Technical Specification |  | The Contractor shall supply the Superintendent with manufacturer Quality Control (MQC) data certificates. |  |  | 1/Lot | ITP Verification Checklist | RSA | HP | Senex |  | HP
8 | Separation geotextile placement |  | Contractor | Technical Specification |  | Installation method comply with the requirements of the technical specification and the IFC drawings. Laps to geotextiles shall be a minimum 0.6m The Superintendent shall inspect the placement of Geotextile for conformance with this Technical Specification prior to placement of overlying layers. |  |  | 1/Lot | ITP Verification Checklist | RSA | HP | Senex |  | HP
9 | Rip Rap Placement |  | Contractor | Technical Specification |  | A Safe Work Method Statement for the placement of Rip Rap shall be provided to superintendent. Rip rap to be placed by excavator over the separation geotextile. Rock finished smoothed to the final lines and levels. |  |  | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex |  | HP
10 | Acceptance of works (Rip rap) |  | Contractor | Technical Specification |  | The Superintendent must approve the finish surface and underlying separation geotextile installation of the Rip Rap prior to completion of works. |  |  | 1/Lot | ITP Verification Checklist / MDR | RSA | CHK | Senex |  | HP
Permanent Sediment and Erosion Control – RCP and Headwall
11 | RCP Installation |  | Contractor | Technical Specification |  | Excavation to design invert levels allowing for 100-250mm bedding sand (or equivalent) 600 Rubber ring joint Class 4 RCP installed with barrels laid straight free from damage. Sand (or equivalent) haunching and overlay to approximately 150mm above pipe |  |  | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex |  | CHK
12 | Backfilling |  | Contractor | Technical Specification |  | Trench backfilled and tested in line with requirements for Fill 96% +/-2% moisture |  |  | Min 2 test per Lot | Test Reports | RSA | CHK | Senex |  | CHK
13 | Headwall |  | Contractor | Technical Specification |  | 2 x 600DN Headwalls installed on 100-250mm sand bedding to required invert levels Headwall installed flush with RCP pipe and grouted neat. |  |  | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex |  | CHK
14 | Acceptance of works (RCP and Headwalls) |  | Contractor | Technical Specification |  | Conformance certificates supplied by manufacturer All required test reports provided to client As-constructed survey data obtained |  |  | 1/Lot | ITP Verification Checklist / MDR | RSA | CHK | Senex |  | HP
Built in accordance with this document: Signed Position Date
Inspection Test Plan
Revision Status |  | Responsible Person |  |  | Signed |  | Dated | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: