## Sheet1
01 | Lot Identification | Contractor | Technical Specification | Location of works identified as per IFC drawings | 1/Lot | ITP Verification Checklist/Lot drawing | RSA | CHK | Senex | CHK | 01 - Lot Identification | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Location of works identified as per IFC drawings | Frequency - 1/Lot | Record - ITP Verification Checklist/Lot drawing | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - CHK | 01 - Lot Identification
02 | Survey control and Setout | Contractor | Technical Specification | Confirm centres of both sump and tank locations | 1/Lot | ITP Verification Checklist | RSA | HP | Senex | HP | 02 - Survey control and Setout | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Confirm centres of both sump and tank locations | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - HP | Client: Resp - Senex | Client: Type - HP | Work By - Contractor
03 | Excavation of sump | Contractor | Technical Specification | Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site) Sump excavated to correct dimensions in line with Concept Tanks (CT) OPS-ATLW- PE-GAR-004 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | WP | 03 - Excavation of sump | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site) Sump excavated to correct dimensions in line with Concept Tanks (CT) OPS-ATLW- PE-GAR-004 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Standard / Spec - Technical Specification
04 | Installation of HDPE sump base and chamber at correct height and level | Contractor | Technical Specification | Poly sump base to be installed at 200mm below leak detection pipe. Sump chamber installed plumb to correct height minimum 150mm above top of tank | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | WP | 04 - Installation of HDPE sump base and chamber at correct height and level | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Poly sump base to be installed at 200mm below leak detection pipe. Sump chamber installed plumb to correct height minimum 150mm above top of tank | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Criteria - Location of works identified as per IFC drawings
05 | Backfill - Sump | Contractor | Technical Specification | Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification | 1/Lot | ITP Verification Checklist / Test | RSA | CHK | Senex | HP | 05 - Backfill - Sump | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification | Frequency - 1/Lot | Record - ITP Verification Checklist / Test | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - HP | Frequency - 1/Lot
06 | Leakage pipe trench excavation | Contractor | Technical Specification | Trench excavated to correct lines and levels in line with CES drawings. 1:100 fall to sump Sufficient excavation width to facilitate installation. | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | WP | 06 - Leakage pipe trench excavation | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Trench excavated to correct lines and levels in line with CES drawings. 1:100 fall to sump Sufficient excavation width to facilitate installation. | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Record - ITP Verification Checklist/Lot drawing
07 | Installation of 50mm HDPE leakage pipe | Contractor | Technical Specification | 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements. Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress. Pipe to be left exposed at centre of sump pit | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | WP | 07 - Installation of 50mm HDPE leakage pipe | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements. Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress. Pipe to be left exposed at centre of sump pit | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Contractor: Resp - RSA
08 | Surface Water Runoff | Contractor | Technical Specification | DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain | 1/Lot | ITP Verification Checklist | RSA | CHK | Senex | WP | 08 - Surface Water Runoff | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain | Frequency - 1/Lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Contractor: Type - CHK
09 | Backfill - Trench | Contractor | Technical Specification | Backfill in accordance with CES requirements and general earthworks specifications 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas) | Min 2 tests per lot | ITP Verification Checklist / Test Report | RSA | CHK | Senex | WP | 09 - Backfill - Trench | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Backfill in accordance with CES requirements and general earthworks specifications 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas) | Frequency - Min 2 tests per lot | Record - ITP Verification Checklist / Test Report | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - WP | Client: Resp - Senex
10 | Acceptance of work | Contractor | Technical Specification | Work completed in accordance with CES requirements. Compaction reports received and meeting specification As-constructed survey data obtained | Once per lot | ITP Verification Checklist | RSA | CHK | Senex | HP | 10 - Acceptance of work | Work By - Contractor | Standard / Spec - Technical Specification | Criteria - Work completed in accordance with CES requirements. Compaction reports received and meeting specification As-constructed survey data obtained | Frequency - Once per lot | Record - ITP Verification Checklist | Contractor: Resp - RSA | Contractor: Type - CHK | Client: Resp - Senex | Client: Type - HP | Client: Type - CHK
02 - Survey control and Setout
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Confirm centres of both sump and tank locations
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - HP
Client: Resp - Senex
Client: Type - HP
03 - Excavation of sump
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Located at 3m outside from the hinge point of the tank pad. To be trenched to a depth of 3.17 m (to be confirmed on site) Sump excavated to correct dimensions in line with Concept Tanks (CT) OPS-ATLW- PE-GAR-004 0.8m diameter excavation to design depth. Sump pit depth to be determined onsite ensuring sufficient fall from tank centre to sump
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
04 - Installation of HDPE sump base and chamber at correct height and level
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Poly sump base to be installed at 200mm below leak detection pipe. Sump chamber installed plumb to correct height minimum 150mm above top of tank
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
05 - Backfill - Sump
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Backfill in accordance with CT requirements. Compaction testing in line with Earthworks specification
Frequency - 1/Lot
Record - ITP Verification Checklist / Test
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - HP
06 - Leakage pipe trench excavation
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Trench excavated to correct lines and levels in line with CES drawings. 1:100 fall to sump Sufficient excavation width to facilitate installation.
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
07 - Installation of 50mm HDPE leakage pipe
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - 50mm HDPE pipe and bends installed in accordance with CT and manufacturer requirements. Minimum 150mm cover at centre of tank Pipe installed on 50mm sand bedding (optional) as per CT recommendations HDPE pipe riser installed 300mm above FSL at centre of tank, temporary seal to prevent sediment ingress. Pipe to be left exposed at centre of sump pit
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
08 - Surface Water Runoff
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - DN110 HDPE pipe for construction surface water runoff to be installed 1:100 fall to swale drain
Frequency - 1/Lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
09 - Backfill - Trench
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Backfill in accordance with CES requirements and general earthworks specifications 98% +/-2% moisture (Ring beam area) 96% +/-2% moisture (All other areas)
Frequency - Min 2 tests per lot
Record - ITP Verification Checklist / Test Report
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - WP
10 - Acceptance of work
Work By - Contractor
Standard / Spec - Technical Specification
Criteria - Work completed in accordance with CES requirements. Compaction reports received and meeting specification As-constructed survey data obtained
Frequency - Once per lot
Record - ITP Verification Checklist
Contractor: Resp - RSA
Contractor: Type - CHK
Client: Resp - Senex
Client: Type - HP