## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Retention Pile Checklist |  |  |  |  | Yes | Retention Pile - (NFH V.200521) | 0afa1406-fdb6-44a3-a22a-b0f21406ff33
checkpoint-group |  |  | section | Retention Pile Pre Pour
checkpoint-status |  |  | checkpoint | Documentation & Setout
label | c45453e1-ed36-52a0-82b6-0543765ca152 |  | note | Drawing & Revision Number(s): ST-0-070-0PW00-S01 / Rev 2
label | da6de81e-f963-5c87-b81a-550fffd18099 |  | note | Survey Set Out refer ST-0-070-0PW00-S01
checkpoint-status |  |  | checkpoint | Pile Diameter 600mm
checkpoint-status |  |  | checkpoint | Pile Hole Plumb - Spirit level off kelly
checkpoint-status |  |  | checkpoint | Approval of Socket
text | 7b5688f8-3a5e-5085-a603-afdce6638994 |  | textbox | Pile Socket Length (mm)
label | 1c806d33-1f39-5884-a46e-1fd5e5242843 |  | note | Geotechnical Engineer will evaluate drill cuttings to confirm the socket length and founding level. The pile base is machine cleaned and certified by Browns Pilings geotechnical engineer or representative as nominated
checkpoint-status |  |  | checkpoint | Pile details entered
text | 239743c9-34c2-56b5-baa5-117d6457fb7f |  | textbox | Top of Steel (RL)
text | fde7aeac-6f0f-5f62-a698-142e5ae30ff4 |  | textbox | Length of Pile (m)
text | 197ac599-3f1a-5d1a-8d29-0cc883c0b746 |  | textbox | Top of Pile (RL)
checkpoint-status |  |  | checkpoint | Check for excessive water in hole
checkpoint-status |  |  | checkpoint | Pile Reinforcement
label | d858e6b0-2c41-5f91-b6c2-13df303972c0 |  | note | Pile Reinforcement Main Bars
label | 36794bb5-c84b-53e0-b7f5-9223dfef6bf2 |  | note | Pile Reinforcement Ligs
label | 539edb61-0aff-59fc-8023-431d34bff1cc |  | note | Pile Reinforcement Cage
label | 4b113518-d918-5d76-933a-8ead32297838 |  | note | Refer Structural Documentation. Attach photo of cage tag & refer schedule
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 8b9ca0e7-38f9-55f8-9b36-5304ed1332e2 |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | 3a55846e-b92b-5a66-8373-c900277c926b |  | button | Philip Chun Inspection | Yes, No, N/A
button | ad239903-a98f-564e-b0a3-f635e086aed1 |  | button | FSG Inspection | Yes, No, N/A
button | ff12890d-f8a2-5ae8-a8e9-d398ba5e4ec3 |  | button | 4D Inspection | Yes, No, N/A
button | 1d49075c-843f-5e29-a6b6-17c8d6e28877 |  | button | Dan Structures | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 1d8c8422-80f4-53d0-b6ac-8fd7e937d665 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | cb3b43b9-cd80-56af-ab06-7b63f4d41fef |  | button | Delta Group Representative Signed | Yes, No, N/A
button | bb0c8658-c5b0-50ec-9f83-d1873a75363b |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Retention Pile Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | 1b601046-235f-5e3e-a14b-b1fe9143150e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | 1dc97295-0df3-5315-9f94-f93c7704fe10 |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Pile Concrete Details Complete
button | fcd188ed-bc3b-5b95-ba2b-1b7054a1389c |  | button | Concrete Strength (MPa) | 40, 50, Other
text | dcd70cee-2180-5e67-8168-fd221db0369b |  | textbox | Other:
label | 801048d3-456a-578a-b7d8-e05e3155e9d5 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Cover 75mm
label | 773b701e-5e07-5c44-8d04-f1b7d0c2a4e5 |  | note | HOLD POINT - Inspection & Approval for Concrete Cover
checkpoint-status |  |  | checkpoint | Check Concrete Flow is directed clear of reinforcing (Subcontractor & MPX to witness
label | ef432fa5-2850-548a-ad34-a8d7b23c6bf4 |  | note | Concrete flow is placed by the free-fall method, carefully directed with a concreting guide down the centre of the shaft, clear of reinforcing cage
checkpoint-group |  |  | section | Retention Pile Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
checkpoint-status |  |  | checkpoint | Concrete Sample (this pile) Report Reference
label | e896bd76-b527-530e-ab83-21a086b7df5b |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | f555d8bb-a457-521e-8135-6098340263b8 |  | note | .. ..
text | 0cbd45ec-d736-5ca7-b3b2-fc4f80877ae0 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 4a3f6ec9-a428-52cb-b706-3efce9d03d52 |  | note | Type a Response & submit crack test report below
label | 1996d716-7960-5a69-90f6-ec9983cb4443 |  | note | .. ..
label | 8392a230-af9d-5fb0-9577-352fda70aefb |  | note | As Built Drawings - Transmitted seperately
label | 8e9e8c19-8150-5116-af4b-b8b6fcd4c235 |  | note | .. ..
button | 8f3c53ba-7bbc-5672-89ba-54e521329593 |  | button | Final Reo Cage & Concrete Levels checked | Yes, No, N/A
label | 46281a1b-e944-504a-b4eb-1057f17908e5 |  | note | Refer Schedule for a Table view of Heights/RLs below
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | 556a206b-98a5-5564-b7bb-3196fd633bfc |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 1ec29124-3056-59c4-a9c1-42b6709d91a1 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | 0ba12fcc-0232-53ad-9b16-bc89dd2498ce |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Pad Footing Reference - |  |  |  |  | Yes | Pad Footing - (NFH - V.290721) | 5e1a56de-4f38-47ac-8c83-eda8950c68a3
checkpoint-group |  |  | section | Pad Footing Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 532a2c44-992f-4cc0-b9b4-a249907e9dfd |  | textbox | Drawing & Revision Number(s): TBC
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
text | 3eb64fcf-6a8d-4068-9b2a-4346266ce9ee |  | textbox | Blinding RL
text | a479c298-b46f-456a-9f47-bd101ea06d23 |  | textbox | Top of Footing RL
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed by others
checkpoint-group |  |  | section | Pad Footing - Pre-Pour Inspection
checkpoint-status |  |  | checkpoint | Steel Reinforcement photo(s) taken
label | 25855c56-cf3a-407f-9cac-2a1c00eec05b |  | note | Photos attached below for each element
boolean | b4001818-7956-425f-844c-e35c685d297a |  | tickbox | Bottom Reo Placement photo(s) taken
boolean | df7a6ecf-4a93-4139-931f-f5fa1724c056 |  | tickbox | Side Face Reo Placement photo(s) taken
boolean | 8842e816-ab1f-4278-959b-af309d627ef3 |  | tickbox | Lig Reo Placement photo(s) taken
boolean | 6e0ce5eb-74e1-40d8-8ab5-b1ca2e4b85e6 |  | tickbox | Spacing & Lap Length photo(s) taken
boolean | 0c984b7a-b062-4202-919d-f898c93c4812 |  | tickbox | Column Starter Bars photo(s) taken
checkpoint-status |  |  | checkpoint | Cover Correct a sper Specifications
select | 7e241864-b34f-4baa-ba92-cb6facc0c69c |  | dropdown | Cover (mm) | 50, Other
text | 41c718f8-0700-4892-9d72-b720f52427d1 |  | textbox | Other
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 7429d2c5-d7df-4d37-9e0e-17f2b0a531fc |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | 2e605a0d-26f2-410f-a598-432b87ddff6c |  | button | Philip Chun Inspection | Yes, No, N/A
button | 00ce4041-a7ea-49d8-bb2b-7eb6bf3acae0 |  | button | FSG Inspection | Yes, No, N/A
button | 2f542728-a948-43aa-9922-e7f0ae6d7ee8 |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 05b7ef64-bb53-4591-a596-987ef462b5c1 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | cd13f1e8-e0d3-4a64-a3fc-7e428d2692dd |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 8de68182-a311-40f3-b53c-57d265a3ae7c |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Pad Footing Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | e3a6426c-adaa-4ee2-8cc8-5c43958e4a5f |  | textbox | Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | 5c06c9e0-e27e-4e61-bc27-91da97e98b6a |  | textbox | Docket Number
checkpoint-status |  |  | checkpoint | Concrete Details Complete
select | 7a4dd946-91dd-4865-a68f-129184923d3a |  | dropdown | Concrete Strength (MPa) | 50, Other
text | 75eb5146-98f6-4397-8f02-7b0dd4d1d2da |  | textbox | Other
label | de9e62ec-9d43-44a3-8d28-426ff3dbdd60 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Services within checked and accurate
label | c9b9eca5-0abd-4937-b345-c3e8e6f41e43 |  | note | Attach photo if required
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Pad Footing Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | aaeebbf1-6a2f-4848-ae7b-0d35efdf3435 |  | textbox | Concrete Sample Report Reference
label | 118c85cc-7fb4-4e51-a5d6-2592736abf4f |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | ed64e72f-9691-4ab9-aaf4-4ec462816aa3 |  | note | .. ..
text | 2988d104-0102-4646-99bf-d4c3a8a856c5 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | d78cd433-33a5-42ab-bc2f-529457916cc8 |  | note | Type a Response & submit crack test report below
label | 5dd78f22-fcd6-467f-93cf-4b855ca76ead |  | note | .. ..
button | 82233b98-3675-4bd8-a972-3d3e8777585d |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | 5c6e530c-7373-4e44-9391-1c0ed9afe219 |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
label | ccb2cfcd-d64c-4790-aa62-05156d21874a |  | note | Attach Signature Sign-offs below
button | 4cff4420-c265-4cd8-8dd1-bc1fee540f11 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 84040fc1-6733-42b0-9a34-9343af553b58 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | 3b9d5f61-220b-4e85-8924-c9afcaaff5ec |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-flat |  |  | checklist | (Input Date Range) |  |  |  |  | Yes | Concrete Document Attachment | 5eaa8b8b-c8be-493d-ba35-75dc83db9cd0
checkpoint-status |  |  | checkpoint | Documents attached for reference - Pass once attached
checklist-flat |  |  | checklist | Anchor (Type 1 Walls) - (NFH - V.100621) |  |  |  |  | Yes | Anchor (Type 1 Walls) - (NFH - V.100621) | 60ebd8fe-2831-44dd-b39c-f446bc34a3c6
checkpoint-status |  |  | checkpoint | Documentation & Setout
text | 07fd1d2b-47ca-5fbd-ae44-9e749c78e26c |  | textbox | Drawing & Revision Number(s): TBC
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-status |  |  | checkpoint | Anchors
text | 0784d791-c83a-52ed-a30f-f10335972bb3 |  | textbox | Anchor Type
text | ded929e7-24cf-580b-a1f5-5448c67a1587 |  | textbox | Anchor RL (m)
text | 96e678fa-91fb-586a-a8c4-f2063f8dae6b |  | textbox | Diameter (mm)
text | ef4d9c04-bc85-50f4-9dc8-960a805e61ce |  | textbox | Incline Angle (degrees)
text | 93f850e2-7393-558e-85ec-62d94332a033 |  | textbox | Free Length (m)
text | 9fb61e7d-351e-517c-850e-4556416b294d |  | textbox | Bond Length (m)
text | cf2b6468-130f-568f-800c-a035fd1cfbaf |  | textbox | Strands (no. of)
text | f5437be4-9ade-561e-9b56-c674887df851 |  | textbox | Spacing of Anchors (m)
checkpoint-status |  |  | checkpoint | Drill & Grout
text | ad2c063c-7ac0-5c2b-8322-0e819ffc87dc |  | textbox | Date Drilled
text | 688abe45-a462-5ca4-91b6-eb2f0471382e |  | textbox | Date Grouted
checkpoint-status |  |  | checkpoint | Calibration
text | 043e7cec-ff11-5d58-935d-32edd954b26c |  | textbox | Stressing Machine Serial Number
text | ecfa2fd8-7774-58d4-b655-f10aa4f70498 |  | textbox | Last Calibration Date
text | 86dd2f23-a6ac-5ab8-966c-a335857df10f |  | textbox | Date Stressed
text | 52189cf4-ebb1-5fea-bb00-733bc4506526 |  | textbox | Lock-off Load (kn)
checkpoint-status |  |  | checkpoint | Anchor De-Stress
text | 0ab29783-7edf-5380-a232-720aee3042ae |  | textbox | Anchor De-Stressed date
text | b0d3b614-dcdc-5fc6-8141-644e75d3c62c |  | textbox | Patching Date
checkpoint-status |  |  | checkpoint | Sign Off
label | fcf66686-4d94-54fd-98de-cabdf1eb7132 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 03bb7b1a-914a-59d6-a4ff-5be1359ad741 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 66ab7ef9-153b-5a78-8a1e-fcb29c454cd2 |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Pile Cap - (NFH - V.100621) |  |  |  |  | Yes | Pile Cap - (NFH - V.100621) | 67a69e3e-736b-474e-857f-7a4060b3fc4b
checkpoint-group |  |  | section | Pile Cap Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
label | 678d7b71-2bd5-554b-abbf-fb4f0491ee11 |  | note | Drawing ST-0-074-0PW00-000
text | b803da84-d6fa-57b1-90a9-9d7e86c4c4c6 |  | textbox | Revision Number
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
text | 59c25878-a694-5be1-b7af-e5c5706d0e2e |  | textbox | Blinding RL:
text | 2a1c0443-f9e8-51c1-ab7b-f9217b4a5ed0 |  | textbox | Top of Footing RL:
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed by others
checkpoint-group |  |  | section | Pile Cap Pre-Pour Inspection
checkpoint-status |  |  | checkpoint | Formwork/Edge formwork photo(s) taken
checkpoint-status |  |  | checkpoint | Pile Reo Length checked and referenced
text | 1b82f114-82e8-5108-8648-bb22c761e640 |  | textbox | Pile Length
checkpoint-status |  |  | checkpoint | Reinforcement checked and accurate to specifications
button | bae4dcfc-d092-57a6-98f0-d0621fdb3b20 |  | button | Bottom Reo Placement photo(s) taken | Yes, No, N/A
button | 6f004e84-5d42-5f9e-895f-16ed30109aea |  | button | Top Reo Placement photo(s) taken | Yes, No, N/A
button | de27f0c8-2b8e-51b4-bf8c-150ab0239fa0 |  | button | Side Face Reo Placement photo(s) taken | Yes, No, N/A
button | a568c03e-4657-5d23-9a90-f6145870a22c |  | button | Lig Reo Placement photo(s) taken | Yes, No, N/A
button | cc1cb433-dbf0-57b7-8525-201f539cdd7c |  | button | Spacing & Lap Length photo(s) taken | Yes, No, N/A
button | 41fdcb04-1699-5c30-be7a-5b1787735da5 |  | button | Column Starter Bars photo(s) taken | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Cover checked and referenced
text | bff20115-378d-5a8d-911a-f9fe75c139f8 |  | textbox | Cover (mm)
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 25f2ecdc-4e4c-5d51-b9ae-e9da86734ece |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | 683364b6-b339-5821-81c9-2b2130b7b5ea |  | button | Philip Chun Inspection | Yes, No, N/A
button | 76286898-99ce-50c7-8626-e29e3e96d30a |  | button | FSG Inspection | Yes, No, N/A
button | b3998214-1930-5bdb-990f-f2f44d2c260a |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 6c68bcdc-f1aa-5b6e-97e5-88aed5f42044 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 3e866494-b214-559e-be56-afa8bd03f896 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | edd71d7d-7348-57ab-bd15-5cb2150396a1 |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Pile Cap Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | a93d99e5-e5f4-5085-b587-a899f5acbc6f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | 130ba937-dd44-5cf8-b9ad-c58e355d34ad |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | a133b616-f058-5f1b-85a9-f9c61495ce9d |  | button | Concrete Strength (MPa) | 50, Other
text | 8b52d8a5-9bea-54b7-81da-9b6eea38f869 |  | textbox | Other:
label | e2c59fa3-023e-5db2-b464-e42120030ae3 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Services within
label | 8d42c4d2-1069-5906-92c0-8ca4325ff932 |  | note | Attach photo if required
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Pile Cap Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | 7577fbbc-be0d-5e72-85a8-963f24ccf613 |  | textbox | Concrete Sample Report Reference
label | cf3ad912-5bc7-57fe-855e-f1f5d54a9466 |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | ea1dd962-737b-5617-84a9-c97980598f03 |  | note | .. ..
text | c7d43314-f168-55e8-9777-1cf844125de8 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | fd39e26d-b1eb-528f-bd9d-f0907030041a |  | note | Type a Response & submit crack test report below
label | 925aa219-c653-5696-b333-150b92f0debb |  | note | .. ..
button | 32d03ec7-862d-5347-a1b6-51b5be78eb20 |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | 2b19b4f3-74e4-5a59-96ed-cff788ea267b |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | 93c6de6f-291f-5257-91df-73dfd38bd2de |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 4b7dfd1e-fd82-5503-bfef-acf960946997 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | aba5daf8-488c-5d22-86d1-e616018d9728 |  | button | Multiplex Representative Signed | Yes, No, N/A
button | 0e5b73b4-fe8d-5309-b2d9-c6c6249d9e87 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | c85d36e1-720d-51dc-bcb8-b8544ddce02d |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Soil Nails (Type 3 Walls) - (NFH - V.100621) |  |  |  |  | Yes | Soil Nails (Type 3 Walls) - (NFH - V.100621) | 7cc6dcdf-1717-440d-8724-675f04cc1388
checkpoint-group |  |  | section | Soil Nails (Type 3 Walls) Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | e2ea64ba-2ff7-5e2e-9acb-04437baa4395 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-group |  |  | section | Rockbolt (Type 3 Walls) Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Rockbolt Pre-Pour Inspection
text | 9f892501-a076-57dc-9302-e4973b21a905 |  | textbox | Height of Basalt Face (mm)
text | 6f6724a0-c6c2-5f49-8e67-daa6865a24b8 |  | textbox | Number of Rockbolt Rows Required
text | d4485ef4-bafa-5d9c-85c8-b9a5cc23d9d2 |  | textbox | Cog Length into Basalt (mm)
text | f232b2b8-c3ca-5a86-ba57-2bbe48af0425 |  | textbox | Cog Type & Dowel (N20, etc)
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | f445ab5e-a7f2-55ae-9657-3f1e50632509 |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | 236d7fbd-6d0c-5baa-af45-f8956d6ab240 |  | button | Philip Chun Inspection | Yes, No, N/A
button | fbbc4cef-de82-5ad0-9d55-48f556a285f1 |  | button | FSG Inspection | Yes, No, N/A
button | 2ab0dcea-a29a-5695-a8d2-ce23a0bd5e33 |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 05849b52-e790-5ee2-9ba0-133913151c5d |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 3af79e6a-a0b3-5892-a069-f8e222e1f4b3 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | f1465b09-f520-502b-b61a-20999494e21d |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Rockbolt (Type 3 Walls) Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of shotcrete
text | 8ea07882-5b7f-536a-aaca-d7450bf0d019 |  | textbox | (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | c94a9611-c46c-572b-9df7-93551cf6ccfe |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | 1d08cec4-57bc-51dc-9900-0ab7cf6722b0 |  | button | Concrete Strength (MPa) | 40, 50, Other
text | 5f99b4dc-294d-5936-a8b8-cf0d67f2d359 |  | textbox | Other:
label | e2cce492-3eb6-5599-bb7e-65bfb7a967ed |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Rockbolt (Type 3 Walls) Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | 145f8ee9-d3b9-5b1d-9a1d-449523a50f40 |  | textbox | Concrete Sample Report Reference
label | cb7365fe-9435-578c-aa72-c83c74c7165c |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | d357ded4-8066-5110-aa20-224a0ddc35e7 |  | note | .. ..
text | b86c7081-681d-58f4-9830-3a4613ab68cc |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 50c76034-0eb9-535e-95df-d8f5fbe9bb77 |  | note | Type a Response & submit crack test report below
label | 5232faeb-430b-59c3-ac4f-b6ef1721a38b |  | note | .. ..
button | cc7fe164-5549-5bc1-91cd-e7fa4f9874f0 |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | bc93e7a8-2625-50ba-a802-000953e2fec1 |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | a50aba39-f093-5074-87fc-e96519be4d89 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 55ea22e4-39fb-5e08-9f98-689c2684c600 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | e8664c5b-25cf-5800-a62b-a307328b9568 |  | button | Multiplex Representative Signed | Yes, No, N/A
button | a3a19d1f-74db-582f-96cf-49aad15dbb6b |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | 8aaf0935-df9d-5fdc-a753-36996b14f7d3 |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Foundation Pile - (NFH - V.100621) |  |  |  |  | Yes | Foundation Pile - (NFH - V.100621) | 8ba1191b-a37a-4627-adb6-13f7134c3a15
checkpoint-group |  |  | section | Foundation Pile Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
label | 28463596-5610-54eb-a533-cd4795319638 |  | note | Drawing ST-0-073-0PW00-000
text | dcbe2ce4-4503-5774-b529-81ea28ab7741 |  | textbox | Revision Number
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-group |  |  | section | Foundation Pile Information
checkpoint-status |  |  | checkpoint | Pile Diameter
text | 176d61f7-c191-555c-a4c3-f343ea283ffc |  | textbox | (mm)
checkpoint-status |  |  | checkpoint | Pile Hole Plumb - Spirit level off kelly
checkpoint-status |  |  | checkpoint | Approval of Socket
text | 4d3492c3-c0a7-5dbd-b0de-34038ea84092 |  | textbox | Pile Socket Length (mm)
label | df111ca5-771f-5059-8f60-ab2dadfc9072 |  | note | Browns Piling Geotechnical Engineer will evaluate drill cuttings to confirm the socket length and founding level. The pile base is machine cleaned and certified by Browns Piling's geotechnical engineer or representative as nominated
checkpoint-status |  |  | checkpoint | Pile details entered
text | cd44ea17-5fe5-5244-b52d-c8d3b1ba606c |  | textbox | Top of Steel RL (RL)
text | e61afe4f-5d00-57e4-912d-7a846c4b8a9c |  | textbox | Length of Pile (m)
text | 5b09cb53-09a8-58de-a3a9-a4477a80070c |  | textbox | Top of Pile (RL)
checkpoint-status |  |  | checkpoint | Check for excessive water in hole
checkpoint-group |  |  | section | Foundation Pile Reinforcement & Pre-Pour
checkpoint-status |  |  | checkpoint | Pile Reinforcement Main Bars photo(s) taken
label | a161a837-5938-50d7-9fdf-d3db79b16990 |  | note | Attach structural documentation
checkpoint-status |  |  | checkpoint | Pile Reinforcement Ligs photo(s) taken
label | 4126a5dc-e46c-5bea-b208-dff6ac5c3fea |  | note | Attach structural documentation
checkpoint-status |  |  | checkpoint | Pile Reinforcement Cage Length photo(s) taken
label | 4cfed3a9-5e44-51d3-bd3f-c7f428015d6f |  | note | Attach structural documentation
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 9acfdde8-ea67-5e7e-92ec-81df40cb08f1 |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | d0426f7d-6182-5cf5-9383-d1e550b7082d |  | button | Philip Chun Inspection | Yes, No, N/A
button | 7c7c7773-b43f-519b-8266-94b73c85ef31 |  | button | FSG Inspection | Yes, No, N/A
button | 03041f37-15c5-518f-977f-e86c521c6d2a |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | ee6ff50f-a470-51a4-8fa5-0cad257bd7d6 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 37a4cae0-414b-5816-a1ac-c99848070e92 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 98fd1697-6c37-5f8e-be3b-46107ee15e01 |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Foundation Pile Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | 87ba9f25-40bb-5da6-8290-74805e1ced90 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | dc76458f-3930-5ea3-b504-77f445f0c8e1 |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Pile Concrete Details Complete
button | 0693ef3d-66b4-5b44-9afa-6394185b1674 |  | button | Concrete Strength (MPa) | 40, 65, 75, Other
text | ba548126-6a5e-5b3d-bb1d-cb528ad07a19 |  | textbox | Other:
label | 94e9d110-8c96-5ef6-9b7c-c64273b47515 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Cover 75mm
label | 00b07bfb-8061-5402-9545-e82cd4abc4dd |  | note | HOLD POINT - Inspection & Approval for Concrete Cover
checkpoint-status |  |  | checkpoint | Check Concrete Flow is directed clear of reinforcing (Subcontractor & MPX to witness
label | c7997901-d0c1-5356-8c1b-6e818905828f |  | note | Concrete flow is placed by the free-fall method, carefully directed with a concreting guide down the centre of the shaft, clear of reinforcing cage
checkpoint-group |  |  | section | Foundation Pile Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | 9238cde4-0d5b-5db8-951d-a67da5c1eb35 |  | textbox | Concrete Sample (this pile) Report Reference
label | 9160964a-a2b7-53fd-b96c-56d93998da5d |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | 6492c846-176d-5cae-a987-9cde340b8d79 |  | note | .. ..
text | ae7a1aa6-a8bf-5689-b4c4-148a768d9c9b |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 81c03e27-85ac-5ddf-b91d-681b50735e9d |  | note | Type a Response & submit crack test report below
label | 03894f34-8e6c-5ae2-90d2-3b094a14501c |  | note | .. ..
label | 007b5e54-9a23-5262-adab-0bcfd4b90fc6 |  | note | As Built Drawings - Transmitted separately
label | fa8d65ab-87d4-5fbc-b722-0490fee4a40b |  | note | .. ..
button | 41bc052b-71a8-5e3f-8d48-17d393e03a86 |  | button | Final Reo Cage & Concrete Levels checked | Yes, No, N/A
label | 4ccb4f09-6763-5782-ae60-868f2ecacc33 |  | note | Refer Schedule for a Table view of Heights/RLs below
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | bb0714a0-c938-5811-887f-081d515d4342 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 583e69a9-885b-5131-a823-12d921ecdfb0 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | eb6472fc-a90c-56a2-b2cd-8c21d78ae65e |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Rafts - (NFH - V.100621) |  |  |  |  | Yes | Rafts - (NFH - V.100621) | 8e88c370-2cc5-458b-8650-16449544c7c9
checkpoint-group |  |  | section | Rafts Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 44f3c979-38b3-532c-99e6-8d4ac0643c3b |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
text | 277a7590-1245-5a55-a876-63a92b1839b0 |  | textbox | Blinding RL:
text | 721e17b1-278f-5328-85f5-96e8c050eb6f |  | textbox | Top of Footing RL:
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed by others
checkpoint-group |  |  | section | Rafts Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Reinforcement checked and accurate to specifications
button | 3528f8ec-c266-5a41-985f-f92690bd1cff |  | button | Reo Placement photo(s) taken | Yes, No, N/A
button | d1343c27-204c-5beb-ae9f-a47d6a6c3ce5 |  | button | Pile Reo Length photo(s) taken | Yes, No, N/A
button | 705ef59e-ddd2-541a-8113-593d873f7991 |  | button | Reo Size and Configuration photo(s) taken | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | d361aeff-db81-545d-862d-6f836dbec24d |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour and photos taken
button | 55a29bfb-51df-5e75-be4c-2751c6a57cee |  | button | Philip Chun Inspection | Yes, No, N/A
button | 106378a8-8dcc-5a7f-b9b1-4c6255df2ab8 |  | button | FSG Inspection | Yes, No, N/A
button | 2a095c1a-c78f-56c5-98de-b7b40cb36d2d |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | e658d5aa-ff74-59ca-9e49-c6a7e565d0e5 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 9f5ed863-3650-58a5-9e4c-0cb188cd8cc3 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 65e350e7-2f3e-52a6-b3c8-51439eb5800a |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Rafts Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of concrete
text | f1399632-e12a-5bfc-986c-47733e7d41d5 |  | textbox | (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | 5c7fc9fb-b93f-531a-9e40-98078357ca9f |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | ce343d33-e56d-53cb-8f51-7e531e178197 |  | button | Concrete Strength (MPa) | 40, 50, Other
text | 12acf004-df16-5d71-b0eb-0be935b36204 |  | textbox | Other:
label | 512bdbef-d187-54b8-827b-f7a5c0f01e66 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Rafts Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | 4cfa692e-408f-52db-81d9-ad9f374106b2 |  | textbox | Concrete Sample Report Reference
label | 0ebde872-9b50-51c1-9932-641245a25220 |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | a8ee084a-7025-52fa-acf6-04e5e24a06a2 |  | note | .. ..
text | fe18fe0f-9938-5999-8851-2d1722e88cfc |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | fa6c527f-5053-59c3-ae1e-5583a3d58aa8 |  | note | Type a Response & submit crack test report below
label | ba05a357-fd15-5633-aa8d-2613f8233992 |  | note | .. ..
button | ddad8719-f841-56fb-be04-660c2b8ed2d6 |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | cde96187-8451-58cd-ac0f-9a050bb9567e |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | ec7cba35-4cca-562f-974a-4586d587a7a4 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 8e7d71d7-0490-5072-9eac-6012dc290655 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | eafb09d6-b8bb-5b66-acf1-8e405b34cf87 |  | button | Multiplex Representative Signed | Yes, No, N/A
button | 96a7d975-dfba-5013-996b-7cd25327f12e |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | b11681ce-ef2f-53b5-a829-43aaf601e30d |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Ref Pile# - Pile#: |  |  |  |  | Yes | Capping Beam - (NFH - V.170521) | b15c4cf8-e88c-4df1-8a97-4243eb15bdcd
checkpoint-group |  |  | section | Capping Beam Pre Pour
checkpoint-no-status |  |  | checkpoint | Documentation & Setout
label | a3707675-af13-5a06-b8ea-68c3011d6e61 |  | note | Drawing & Revision Number(s): ST-0-070-0PW00-000 / C2, ST-0-070-0PW0A-001 /C2, ST-0-070-0PW0B-001 / C2, ST-0-070-0PW0C-001 / C2, ST-0-070-0PW99-031 / C2, ST-0-070-0PW99-032 / C2, ST-0-070-0PW99-033 / C2
text | df2c2ff2-29d8-57f6-893a-e1cd15acabb4 |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
button | f2b6507a-b55d-5f2a-9c06-87f25686f177 |  | button | Survey Set Out - Check Position - Provide report below | Yes, No, N/A
text | 87c0b842-7f71-5d59-bad1-7e377f98c463 |  | textbox | Blinding RL
text | 536d4aef-9184-5ecc-87b0-6179f084f9aa |  | textbox | Top of Capping Beam RL
checkpoint-status |  |  | checkpoint | Formwork and Reinforcing
button | 0946f5e3-5c6e-5f0e-9ce6-80df44691360 |  | button | Formwork/Edge formwork | Yes, No, N/A
button | 57a70b74-cc7f-58dd-aee8-011a04a797f3 |  | button | Bottom Reo Placement | Yes, No, N/A
button | 60fa5802-7019-52cf-b745-d307b54f2fc3 |  | button | Top Reo Placement | Yes, No, N/A
button | 71b8e6f7-3c26-5d88-8644-b5975a1f6d3b |  | button | Side Face Reo Placement | Yes, No, N/A
button | 03e3b63e-4bf9-5dbc-b135-a9506ec455d2 |  | button | Lig Reo Placement | Yes, No, N/A
button | 8d63c673-6fd6-55b2-aac8-392dd11368bd |  | button | Spacing & Lap Length | Yes, No, N/A
label | b2f6836c-a918-5fa0-b52d-82aa27f524d2 |  | note | Refer Structural Documentation & Attach Photos of Formwork, Main Reo, Reo Spacing & Lap Length
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 9ba3fb72-5fe4-5a40-b4b9-7ad9f42042bc |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | 6bc51f54-b85f-52a3-8c3f-5d75270f7020 |  | button | Philip Chun Inspection | Yes, No, N/A
button | 2676faea-0b2e-5235-9140-f4c10a97868a |  | button | FSG Inspection | Yes, No, N/A
button | 04c8949e-63f3-5e6f-a682-a6399a4f9e7c |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | c82f7965-d84e-5301-bafd-328ce970b63c |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | d7986938-e734-52d8-9373-4b94bd330cb3 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 534a6b64-c3c5-500f-ae87-55295b33f747 |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Capping Beam Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | 4800b4ea-be71-5604-9ef6-66c3f4483977 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | 28503ae8-62fe-5088-ab6a-93541f1d9ffa |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | 08a7e592-5253-5ff6-9a6d-69eaae251b96 |  | button | Concrete Strength (MPa) | 40, 50, Other
text | cde6a0ca-cb95-5f4e-bd81-358b24d7f6c9 |  | textbox | Other:
label | 8692a231-a4c7-5ae1-bfe3-b124d32d646d |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Cover 50mm
checkpoint-status |  |  | checkpoint | Services within
label | a23fbc00-0437-5722-9ce9-fb2030359185 |  | note | Attach photo if required
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Capping Beam Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | b2be3178-a019-5b0f-8480-81e9e1ec112d |  | textbox | Concrete Sample (this capping beam) Report Reference
label | d20e4111-f9e6-515d-9025-66380e194ea5 |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | a7f5640f-494a-5ff8-8809-7e569b8656a9 |  | note | .. ..
text | b7be91f0-6f4f-5655-89f6-73228512464c |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 93b68091-5a1b-553e-be73-699eda8107ce |  | note | Type a Response & submit crack test report below
label | e5b618b0-9cb7-54a8-ba57-c288a1204153 |  | note | .. ..
button | a5b77585-32d7-5269-a875-70227d1494cc |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | 74f164d9-e83c-5818-ba35-8470e29a4c55 |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | 657a0bbd-518c-5471-ad8b-d8bf8ddc0f1a |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 14afed7a-dce8-52b2-8273-192cee52c1d7 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | d4591c88-4add-5f27-99c6-e2de4a1fdc03 |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Shotcrete (Type 1) - (NFH - V.100621) |  |  |  |  | Yes | Shotcrete (Type 1) - (NFH - V.100621) | e47a8399-d697-4b6f-a90a-e7df18e294ca
checkpoint-group |  |  | section | Shotcrete (Type 1) Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 481338fd-820d-5a05-a27d-b003b0a6e55a |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-status |  |  | checkpoint | Waterproof Membrane
label | b264ce8e-a6e0-5338-b988-54469b42a167 |  | note | HOLDPOINT - CONTRACTOR / MPX SIGN OFF
checkpoint-group |  |  | section | Shotcrete (Type 1) Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Reinforcement checked and accurate to specifications
button | c394d2ce-2433-5a19-b0eb-8c20182a96b5 |  | button | Reo Placement photo(s) taken | Yes, No, N/A
button | e490a596-3d22-5a73-a9cf-49108d2274bf |  | button | Pile Reo Length photo(s) taken | Yes, No, N/A
button | 89245073-9bf2-5501-9b8d-5980d1dbb953 |  | button | Reo Size and Configuration photo(s) taken | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Shotcrete Thickness checked an referenced
label | fddbc3cf-1461-5344-b9d6-8dd122e504de |  | note | Thickness (mm)
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | a150ebc7-711e-5b52-b38d-ef5299acc387 |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour and photos taken
button | 0ecfeb77-2176-5cd9-ac94-ba1ec43a1ee1 |  | button | Philip Chun Inspection | Yes, No, N/A
button | 416ee1dd-3ef9-5020-9e29-5e035b1a9341 |  | button | FSG Inspection | Yes, No, N/A
button | 00d56bc3-416d-53af-8d94-8a3a39a6e4f2 |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Service Sign Offs Required
label | 27b2fffd-d053-52c9-9239-affc591e7989 |  | note | HOLD POINT - Service Sign offs are completed before Pour and photos taken
button | 2ad6501d-8e5e-5dbe-8c57-c7ce9f9088c8 |  | button | Hydraulic | Yes, No, N/A
button | 81853952-6733-5f6c-b997-29265d2e869e |  | button | Electric | Yes, No, N/A
button | 6ba2fa22-edb4-5290-9a48-4b14daea826f |  | button | Fire | Yes, No, N/A
button | 1db329be-54d4-5a7d-9b7d-499106cf9f88 |  | button | Security | Yes, No, N/A
button | c0544712-f8b8-510a-85ee-518523ac406d |  | button | Mechanical | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 8a5ca23e-0397-510e-8a4f-1f57ecacf11c |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 881f91e8-0116-5295-8d5f-76b601c89b3c |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 1bd22251-d37f-54ae-84ac-ebf40a727778 |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Shotcrete (Type 1) Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of shotcrete
text | edb51e91-0023-5449-a280-73f4d648b621 |  | textbox | (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | ec6baa80-6891-54bd-bd0b-5b7e4375fba0 |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | 6b276fde-26e7-5902-9760-2785963561c7 |  | button | Concrete Strength (MPa) | 50, Other
text | 977f5544-dfbe-524e-aaa4-f1444ba02900 |  | textbox | Other:
label | 948cfb9e-4c78-59f6-9830-ba7f2c88b370 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Shotcrete (Type 1) Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | d2959a4f-b09a-5693-95c2-496e19454fd0 |  | textbox | Concrete Sample Report Reference
label | c62a2c84-3006-53a3-ad6b-1f4430d74b89 |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | 8b934a27-9bb5-53d6-9256-d3d9e7c20cd0 |  | note | .. ..
text | 05b41541-53d3-5014-95a6-c4580b5a5b96 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 875b63fb-4acd-5008-be81-4fffc080042b |  | note | Type a Response & submit crack test report below
label | 0fe9abd0-9658-5bdc-a73f-e54bf1c7531c |  | note | .. ..
button | d1f402e8-73c2-5340-8a9e-c90b358a6c12 |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | d4cf6995-b3f8-571f-b6e8-43f5ca869aef |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | b2402b81-d4b5-511c-8d19-dd7d8888142b |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 821c14ab-7236-50b6-9efc-88f1bf1c18ea |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | 8c997c29-5ff6-50a7-bb37-aa0047ac9743 |  | button | Multiplex Representative Signed | Yes, No, N/A
button | a58aff13-57d2-5389-86a9-578c64441b58 |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | b4536484-3338-54a2-b9de-807cd9143273 |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | SOGs Reference - Grid Lines: |  |  |  |  | Yes | Slab On Ground - (NFH - V.030621) | f392afb5-ac45-45fb-89f9-5ec7b103b0d4
checkpoint-group |  |  | section | SOG Documentation & Setout
checkpoint-status |  |  | checkpoint | Documentation
text | 6a5a15b8-8834-5bcb-81f4-8322a453c436 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-status |  |  | checkpoint | Blinding RL:
checkpoint-status |  |  | checkpoint | Top of Slab RL:
checkpoint-group |  |  | section | SOG Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Slap Prep
button | 175aa4a7-82eb-5f19-b51b-50c79c73073a |  | button | Slap Prep Material | Class 4, other
checkpoint-status |  |  | checkpoint | Slap Prep Rolled - No protruding aggregates
checkpoint-status |  |  | checkpoint | Vapour Barrier placed, lapped and not pierced
checkpoint-status |  |  | checkpoint | Reinforcement checked and accurate to specifications
button | 0e30cfeb-0e27-579a-808b-aa540ae24286 |  | button | Reo Placement photo(s) taken | Yes, No, N/A
button | e1fbb2a7-5f96-55ac-9e5b-502e5546fd98 |  | button | Additional Reo photo(s) taken | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | c63a5619-bd71-5ba1-abfd-293f488ddf76 |  | note | HOLD POINT - Ensure Engineer/Building Surveyor Sign offs are completed before Pour and photos taken
button | 26c3b899-3b5d-5b39-b38f-3b6ec466ee5d |  | button | Philip Chun Inspection | Yes, No, N/A
button | 3fb165dd-518d-53e6-8cd7-0c9f04d1d07e |  | button | FSG Inspection | Yes, No, N/A
button | 80a14f54-8bba-519a-b91c-298539ce61a1 |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 676d8af5-63c1-5774-a362-c886635917bd |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 356dd72e-ba7a-5f39-90ae-9b584bdf2350 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | c13af670-a4e0-58a8-b264-fb751be61c46 |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | SOG Concrete Placement
checkpoint-status |  |  | checkpoint | Thickness of concrete
text | 02c3e11d-7a14-5a9a-a26c-642b4f2dba64 |  | textbox | (mm)
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | aa6513e5-640b-5fce-8e2f-f37bb7f1761d |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | 14f88a0e-f2c9-5639-8f97-5e153124e4e9 |  | button | Concrete Strength (MPa) | 32, 65, 80, other
text | c07ce586-a7d7-58c2-82d2-11e7625ea4ee |  | textbox | Other:
label | 7744c3d3-4352-55a2-b85c-4e99aa1b0c19 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | SOG Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | 95acb4c4-3c1b-5991-ad69-833d5a8d3567 |  | textbox | Concrete Sample Report Reference
label | ef3a8716-e411-5ed3-a06c-e360526502eb |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | 3927bb29-e160-5f94-beac-9e012e402f7a |  | note | .. ..
text | 528597ca-c0c5-5f17-b7d0-51076b050834 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 41e97ab3-062a-5701-9b4b-d0a4b2844bef |  | note | Type a Response & submit crack test report below
label | d690f8a9-32a5-53a3-a24c-dba3612a1ce8 |  | note | .. ..
button | ebc33e7d-c62c-52b3-b876-371e789e556c |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | 8584748a-df34-53ec-a9ff-8ec15e7fe13f |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | b5a7038e-dd45-5943-b1e0-4560130ae6cd |  | button | Delta Group Representative Signed | Yes, No, N/A
button | da53ab64-37bd-5faa-91dc-3d9d59927b68 |  | button | Multiplex Representative Signed | Yes, No, N/A
button | 4f86bac3-dc15-586b-83e4-c3959f32401c |  | button | Multiplex Representative Signed | Yes, No, N/A
checklist-sectioned |  |  | checklist | Column Ref Pile# - Pile#: |  |  |  |  | Yes | Columns - (NFH - V.120521) | f7a7afc6-6fe8-469e-a31e-6c84cbf7d8b9
checkpoint-group |  |  | section | Columns Pre Pour
checkpoint-status |  |  | checkpoint | Documentation: ST-0-080-1B20A-001[C7]
text | 8e3b284b-1c86-5692-b3b0-4b2ba4007141 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Survey Set Out - Check Position
checkpoint-status |  |  | checkpoint | Bondbreaker Installed
label | d6a5041d-b908-5346-ab3b-5ff06fee3c55 |  | note | HOLDPOINT - CONTRACTOR / MPX SIGN OFF
checkpoint-group |  |  | section | Column Pre Pour Inspection
checkpoint-status |  |  | checkpoint | Formwork and Reinforcing
button | 226670eb-a0b2-5120-86c9-1372c2076c47 |  | button | Formwork/Edge formwork | Yes, No, N/A
button | 1d7002ad-5e73-5edc-81fb-d2b29e8a71fc |  | button | Longitudinal Reo Placement | Yes, No, N/A
button | d3af3763-3965-5bfc-afa8-343856b00407 |  | button | Lig Reo Placement | Yes, No, N/A
button | 51afc5c7-1c28-58c7-ac74-72377c572834 |  | button | Spacing & Lap Length | Yes, No, N/A
label | eb90dfb3-b0b9-59c3-bf93-9e00dad570e7 |  | note | Refer Structural Documentation & Attach Photos of Formwork, Main Reo, Reo Spacing & Lap Length
checkpoint-status |  |  | checkpoint | Sign Offs Required
label | 22507038-94f2-5d94-9e1b-ff61e0a7f6f8 |  | note | HOLD POINT Ensure Engineer/Building Surveyor Sign offs are completed before Pour - Attach reports as applicable
button | d4cd9dee-d830-5215-9eab-2216d5919b20 |  | button | Philip Chun Inspection | Yes, No, N/A
button | ff1cc7b1-421d-538a-ba9d-cfaad9df12a8 |  | button | FSG Inspection | Yes, No, N/A
button | 180ca022-fcb4-5e96-8d1b-16e37898df83 |  | button | 4D Inspection | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Commencement of Pour - OK to Pour
label | 6d0c0b7c-d2f6-5976-a773-fd1c638518d7 |  | note | HOLD POINT - Pass once all pre-pour checks have been completed and ready to pour concrete
button | 25a6d430-2e60-56e6-893a-40ea3628b997 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 8cc4a2c8-626b-5989-a09e-7e39690d84fe |  | button | Multiplex Representative Signed | Yes, No, N/A
checkpoint-group |  |  | section | Columns Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour entered
text | b3f883da-750c-5478-a995-21ed932e950b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket photographed
text | d9c17675-eb2e-54d2-97e4-5fb3a4476458 |  | textbox | Docket Number:
checkpoint-status |  |  | checkpoint | Concrete Details Complete
button | 2fd59fce-b82e-50c7-bb16-b8691819790b |  | button | Concrete Strength (MPa) | 80, Other
text | 8aa0d831-ceb7-5979-822b-f8d47819ee12 |  | textbox | Other:
label | 717263b9-df5f-5a45-9e4d-4b4dff5c3718 |  | note | Concrete Batch mix strength and slump test - Refer Mix Design
checkpoint-status |  |  | checkpoint | Cover 50mm
checkpoint-status |  |  | checkpoint | Services within
label | 67f61ea9-143a-5800-bbbf-2fea34947f31 |  | note | Attach photo if required
checkpoint-status |  |  | checkpoint | Mud Map attached (to indicate date and location of pour)
checkpoint-group |  |  | section | Columns Post Pour - Sign Off / Handover
checkpoint-status |  |  | checkpoint | Post Pour Requirements - Pass Once Completed
text | e1d2457e-ae3b-518b-9cb2-883c7f67e462 |  | textbox | Concrete Sample (this capping beam) Report Reference
label | c4d18aec-f3d8-5fd0-b70d-d0f77df37296 |  | note | Concrete sampling is carried out at the rate of 1 sample (3 cylinders) per 50m3 poured
label | 344e38f5-bad5-5be0-b126-d887586dbdb9 |  | note | .. ..
text | 69a5da48-14a6-59f4-91d0-3839c9ce6027 |  | textbox | 28 Day Concrete Compressive Strength (MPa)
label | 5ccc5ded-961c-5e7a-a59b-40f6733c9f72 |  | note | Type a Response & submit crack test report below
label | e48e79fd-87c5-5243-943d-9090efc41a79 |  | note | .. ..
button | 7185ccdf-4937-5453-9442-28f5c87b8200 |  | button | As Built Drawings - Attached below | Yes, No, N/A
label | 7ff2a1c9-9dee-538d-a2c4-78b07ea19a2b |  | note | Table view of Heights/RLs
checkpoint-status |  |  | checkpoint | Post Pour Sign-Offs - As applicable
button | 1c76e1fb-ad18-5fae-b0e9-2ca99b711474 |  | button | Delta Group Representative Signed | Yes, No, N/A
button | 5a23935d-cc96-5878-aece-85b5bfcbabfc |  | button | Browns Piling Representative Signed | Yes, No, N/A
button | 44db4a95-6c7e-5d9a-8263-1db9ddd7f478 |  | button | Multiplex Representative Signed | Yes, No, N/A