## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 01 - Pile Caps | [5 empty] | ITP 01 - Pile Caps
section | Pile Cap Documentation & Setout
checkpoint | Documentation
label | Acceptance Criteria:
textbox | Drawing & Revision Number
checkpoint | Survey Set out - check position
label | Acceptance Criteria:
textbox | Binding RL
textbox | Top of Footing RL
checkpoint | Waterproofing membrane installed by other
section | Pile Cap Pre-Pour inspection
checkpoint | Pile Reo Length and Referenced
label | Acceptance Criteria:
textbox | Pile Length
textbox | Top of Steel
checkpoint | Pile Cap reinforcement check and accurate to specifications
label | Acceptance Criteria:
textbox | Bottom Reo
textbox | Top Reo
textbox | Column Start Bar
textbox | Cover
label | Comments/Attachment: Photos attached
checkpoint | Sign offs Required
label | Comments/Attachment: Hold Point - Ensure Engineer/Building surveyor/Department of Transport sign offs are completed before pour-Attached report as applicable.
holdpoint | HOLD POINT
checkpoint | Commencement of Pour
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
label | Comments/Attachment: Hold Point - Pass once all pre-pour checks have been completed and ready to pour concrete
holdpoint | HOLD POINT
section | Pile Cap Concrete Placement
checkpoint | Date of Pour Entered
label | Acceptance Criteria:
textbox | Date
checkpoint | Concrete Delivery Docket
label | Acceptance Criteria:
textbox | Docket Number
label | Comments/Attachment: Concrete Docket attached
checkpoint | Concrete Details Complete
label | Acceptance Criteria: Concrete Grade: VR 450/50
label | Comments/Attachment: Concrete Batch mix strength and slump test - refer Mix Design
checkpoint | Mud Map attached to indicate date and location of pour
label | Comments/Attachment: Attached Mud Map
section | Pile cap post pour-sign off/ Handover
checkpoint | Concrete testing
label | Acceptance Criteria:
label | • Slump at least one truck
label | • One set of 3 cylinders per 50m3 poured. Minimum compressive strength requirements:
label | – 1@ 3 days: 23MPA
label | – 1@ 7 days: 35MPA
label | – 1@28 days: 50MPA
label | • Maximum VPV values at 28days provided if required
label | Comments/Attachment: Attached Concrete compressive report, Attached as built drawing
checkpoint | Post Pour Signoffs
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
holdpoint | SIGN OFF
checklist | ITP 02 - Foundation Pile | [5 empty] | ITP 02 - Foundation Pile
section | Foundation Pile Documentation & Setout
checkpoint | Documentation
label | Acceptance Criteria:
textbox | Drawing & Revision Number
checkpoint | Survey Set out - check position
label | Acceptance Criteria:
textbox | Binding RL
textbox | Top of Footing RL
section | Foundation Pile Information
checkpoint | Pile Detail
label | Acceptance Criteria:
textbox | Pile Diameter
textbox | Top of Steel RL
textbox | Length of Pile (m)
textbox | Top of Pile (RL)
textbox | Pile Socket Length
checkpoint | Pile Hole Inspection
label | Acceptance Criteria: Check for excessive water in hole
checkpoint | Pile Reinforcement
label | Acceptance Criteria:
textbox | Main Bars
textbox | Ligs
textbox | Cage Length
label | Comments/Attachment: Photos attached
checkpoint | Sign offs Required
label | Comments/Attachment: Hold Point - Ensure Engineer/Building surveyor/Department of Transport sign offs are completed before pour-Attached report as applicable.
holdpoint | HOLD POINT
checkpoint | Commencement of Pour
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
label | Comments/Attachment: Hold Point - Pass once all pre-pour checks have been completed and ready to pour concrete
holdpoint | HOLD POINT
section | Foundation Pile Concrete Placement
checkpoint | Date of Pour Entered
label | Acceptance Criteria:
textbox | Date
checkpoint | Concrete Delivery Docket
label | Acceptance Criteria:
textbox | Docket Number
label | Comments/Attachment: Concrete Docket attached
checkpoint | Concrete Details Complete
label | Acceptance Criteria:
textbox | Concrete Grade:
label | Cover: 75mm
label | Comments/Attachment: Concrete Batch mix strength and slump test - refer Mix Design
checkpoint | Mud Map attached to indicate date and location of pour
label | Comments/Attachment: Attached Mud Map
section | Foundation Pile post pour-sign off/Handover
checkpoint | Concrete testing
label | Acceptance Criteria:
label | • Slump at least one truck
label | • One set of 3 cylinders per 50m3 poured.
textbox | 28 Day Concrete Compressive Strength (MPa)
label | Comments/Attachment: Attached Concrete compressive report, Attached as built drawing
checkpoint | Post Pour Signoffs
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
holdpoint | SIGN OFF
checklist | ITP 03 - Raft | [5 empty] | ITP 03 - Raft
section | Raft Documentation &Setout
checkpoint | Documentation
label | Acceptance Criteria:
textbox | Drawing & Revision Number
checkpoint | Survey Set out - check position
label | Acceptance Criteria:
textbox | Binding RL
textbox | Top of Footing RL
checkpoint | Waterproofing membrane installed by other
section | Raft Information
checkpoint | Raft Detail
label | Acceptance Criteria:
textbox | Length (mm)
textbox | Width (mm)
textbox | Depth (mm)
checkpoint | Raft Reinforcement
label | Acceptance Criteria:
textbox | Bottom Reo
textbox | Top Reo
textbox | Side Bar
textbox | Wall Stater Bars
label | Comments/Attachment: Photos attached
checkpoint | Sign offs Required
label | Comments/Attachment: Hold Point - Ensure Engineer/Building surveyor/Department of Transport sign offs are completed before pour-Attached report as applicable.
holdpoint | HOLD POINT
checkpoint | Commencement of Pour
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
label | Comments/Attachment: Hold Point - Pass once all pre-pour checks have been completed and ready to pour concrete
holdpoint | HOLD POINT
section | Raft Concrete Placement
checkpoint | Date of Pour Entered
label | Acceptance Criteria:
textbox | Date
checkpoint | Concrete Delivery Docket
label | Acceptance Criteria:
textbox | Docket Number
label | Comments/Attachment: Concrete Docket attached
checkpoint | Concrete Details Complete
label | Acceptance Criteria:
textbox | Concrete Grade
textbox | Cover
label | Comments/Attachment: Concrete Batch mix strength and slump test – refer Mix Design
checkpoint | Mud Map attached to indicate date and location of pour
label | Comments/Attachment: Attached Mud Map
section | Raft post pour-sign off/Handover
checkpoint | Concrete testing
label | Acceptance Criteria:
label | • Slump at least one truck
label | • One set of 3 cylinders per 50m3 poured.
textbox | 28 Day Concrete Compressive Strength (MPa)
label | Comments/Attachment: Attached Concrete compressive report, Attached as built drawing
checkpoint | Post Pour Signoffs
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
holdpoint | SIGN OFF
checklist | ITP 04 - Ground Beam | [5 empty] | ITP 04 - Ground Beam
section | Ground Beam Documentation &Setout
checkpoint | Documentation
label | Acceptance Criteria:
textbox | Drawing & Revision Number
checkpoint | Survey Set out - check position
label | Acceptance Criteria:
textbox | Binding RL
textbox | Top of Ground Beam RL
checkpoint | Waterproofing membrane installed by other
section | Ground Beam Information
checkpoint | Ground Beam Detail
label | Acceptance Criteria:
textbox | Length (mm)
textbox | Width (mm)
textbox | Depth (mm)
checkpoint | Ground Beam Reinforcement
label | Acceptance Criteria:
textbox | Main Bar
textbox | Side Bar
textbox | Ligature
label | Comments/Attachment: Photos attached
checkpoint | Sign offs Required
label | Comments/Attachment: Hold Point - Ensure Engineer/Building surveyor/Department of Transport sign offs are completed before pour-Attached report as applicable.
holdpoint | HOLD POINT
checkpoint | Commencement of Pour
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
label | Comments/Attachment: Hold Point - Pass once all pre-pour checks have been completed and ready to pour concrete
holdpoint | HOLD POINT
section | Ground Beam Concrete Placement
checkpoint | Date of Pour Entered
label | Acceptance Criteria:
textbox | Date
checkpoint | Concrete Delivery Docket
label | Acceptance Criteria:
textbox | Docket Number
label | Comments/Attachment: Concrete Docket attached
checkpoint | Concrete Details Complete
label | Acceptance Criteria:
textbox | Concrete Grade
textbox | Cover
label | Comments/Attachment: Concrete Batch mix strength and slump test - refer Mix Design
checkpoint | Mud Map attached to indicate date and location of pour
label | Comments/Attachment: Attached Mud Map
section | Ground Beam post pour-sign off/ Handover
checkpoint | Concrete testing
label | Acceptance Criteria:
label | • Slump at least one truck
label | • One set of 3 cylinders per 50m3 poured.
textbox | 28 Day Concrete Compressive Strength (Mpa)
label | Comments/Attachment: Attached Concrete compressive report, Attached as built drawing
checkpoint | Post Pour Signoffs
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
holdpoint | SIGN OFF
checklist | ITP 05 - Lift Pit | [5 empty] | ITP 05 - Lift Pit
section | Lift Pit Documentation & Setout
checkpoint | Documentation
label | Acceptance Criteria:
textbox | Drawing & Revision Number
checkpoint | Survey Set out - check position
label | Acceptance Criteria:
textbox | Binding RL
textbox | Top of Ground Beam RL
checkpoint | Waterproofing membrane installed by other
section | Lift Pit Information
checkpoint | Lift Pit Detail
label | Acceptance Criteria:
textbox | Base Length (mm)
textbox | Base Width (mm)
textbox | Thickness of base (mm)
textbox | Thickness of base (mm)
checkpoint | Lift Pit Reinforcement
label | Acceptance Criteria:
textbox | Lift Base Main Bar
textbox | Lift Base Side Bar
textbox | Lift Wall Main Bar
textbox | Lift Wall Conner Bar
label | Comments/Attachment: Photos attached
checkpoint | Sign offs Required
label | Comments/Attachment: Hold Point - Ensure Engineer/Building surveyor/Department of Transport sign offs are completed before pour-Attached report as applicable.
holdpoint | HOLD POINT
checkpoint | Commencement of Pour
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
label | Comments/Attachment: Hold Point - Pass once all pre-pour checks have been completed and ready to pour concrete
holdpoint | HOLD POINT
section | Lift Pit Concrete Placement
checkpoint | Date of Pour Entered
label | Acceptance Criteria:
textbox | Date
checkpoint | Concrete Delivery Docket
label | Acceptance Criteria:
textbox | Docket Number
label | Comments/Attachment: Concrete Docket attached
checkpoint | Concrete Details Complete
label | Acceptance Criteria:
textbox | Concrete Grade
textbox | Cover
label | Comments/Attachment: Concrete Batch mix strength and slump test - refer Mix Design
checkpoint | Mud Map attached to indicate date and location of pour
label | Comments/Attachment: Attached Mud Map
section | Lift Pit post pour-sign off/ Handover
checkpoint | Concrete testing
label | Acceptance Criteria:
label | Slump at least one truck
label | One set of 3 cylinders per 50m3 poured.
textbox | 28 Day Concrete Compressive Strength (MPa)
label | Comments/Attachment: Attached Concrete compressive report, Attached as built drawing
checkpoint | Post Pour Signoffs
label | Acceptance Criteria:
label | • Delta Group representative signed
label | • Multiplex representative signed
holdpoint | SIGN OFF