## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP - Basecourse |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
0 | Draft for Approval | 2022-12-22 |  | Gabriel Cirne |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Reviewed | 2023-07-13 |  | Emil |  | Comments by BBO |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
[10 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement & Surfacing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By | Comments
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
1.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence | Downer | Construction Pack | Prior to Works start | H | PE
1.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works start | H | SV
1.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
1.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable. | Downer | Internal Permits | Prior to activity being undertaken | H | SE
1.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable. | Downer | External Permits | Prior to commencment of activity | H | PE
1.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
1.01.07 | Subbase Approval | All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination | PS - Page 42 | ConQA | Before proceeding to the next layer | HP | ENG
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
2.01 | Basecourse aggregate
2.01.01 | Basecourse CBR | (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and; (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%. | TNZ M/4: 2006 | IANZ Lab Reports | 10,000m3 | HP | ENG
2.01.02 | Running Course Material Approval | The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter. The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED) | TNZ B/02: 2005 - 10.2 | IANZ Lab Reports | 1 test every stockpile | HP | ENG
2.01.03 | Basecourse MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer. | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | 1 test per material type | H | PE | Items included, subdivision from item "Sub-base Production Property Test Sampling"
2.01.04 | Crushing Resistance | The crushing resistance shall not be less than 130kN when the aggregate is tested | NZS 4407: 1991 Test 3.10. | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
2.01.05 | Weathering Resistance | The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested | NZS 4407: 1991 Test 3.11 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works | HP | ENG
2.01.06 | Particle Size Distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006. | TNZ M/4: 2006 | IANZ Lab Reports | 0 to 400m³ - 2 tests 400 to 1,500m³ - 3 tests 1,500 to 4,000m³ - 4 tests >4,000m³ - 1 test for each additional 1,000m³ | HP | ENG
2.01.07 | Sand Equivalent | The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test. If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above). The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6 | TNZ M/4: 2006, 4.2.1.1 | IANZ Lab Reports |  | HP | ENG
2.01.08 | Liquid Limit | The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2. | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.09 | Plasticity Index | The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4 | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.10 | Clay Index | The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5. | PS - 7.2.3 | IANZ Lab Reports |  | HP | ENG
2.01.11 | Accelerated Weathering Testing | If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis The levels of smectite clay minerals are not classified as “abundant” | In accordance with NZTA Standard Specification T20 Draft Specification | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
2.01.12 | Repeat Load Triaxial Test | In accordance with NZTA T15 | NZTA T15 | IANZ Lab Reports | 2 tests per source 4 weeks before use in the works. | HP | ENG
2.01.13 | Broken Face Content | The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407 : 1991, Test 3.14 Broken Face Test. | TNZ M/4: 2006, 4.2.2 | IANZ Lab Reports | 1 Test per Source | HP | ENG
SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
3.01 | Basecourse
3.01.01 | Average Uncompacted Layer Thickness | The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer. | TNZ B/02: 2005 - 7.3 | Survey / Level Checks | 1 test per 20m | I | SV / PE
3.01.02 | Basecourse MDD and OMC | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site. | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | IANZ Lab Reports | No less than 1 test every 5,000m³ (in place) | R | PE
3.01.03 | Plateau Density Test | The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Every plateau to be completed at start of works and witnessed by a member of BBO. | PS - Table 7.2 - 2.3 | Plateau Density Report | 5 tests per 10,000m2 | I | PE
3.01.04 | Plasticity Index | The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4 | PS - 7.2.3 | IANZ Lab Reports | 2 tests per 1000m3 (in place) | R | PE
3.01.05 | Clay Index | The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5. | PS - 7.2.3 | IANZ Lab Reports | 2 tests per 1000m3 (in place) | R | PE
3.01.06 | Sand Equivalent | The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test. If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above). The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6 | TNZ M/4: 2006, 4.2.1.1 | IANZ Lab Reports | 2 tests per 1000m3 (in place) | R | PE
3.01.07 | Particle size distribution | The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006. | TNZ M/4: 2006 | IANZ Lab Reports | 2 tests per 1000m3 (in place) | R | PE
3.01.08 | Basecourse Pavement Layer Compaction | Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter. | TNZ B/02: 2005 - 7.6 | NDM Report | Min 5 Tests per lot 1000m2 max lot size | I | PE
3.01.09 | Surface Shape | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | TNZ B/02: 2005 - 7.7 | Survey / Straight edge Report | Prior to sealing | I | SV / PE
3.01.10 | Holding Water | No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1% | TNZ B/02: 2005 - 7.7 | Visual Inspection / Site Note | Prior to sealing | I | SV / PE | Verification doc. Changed from Survey to Visual Inspection / Site note
3.01.11 | Maximum Width Variation | Unconstrained : –20 mm +100 mm Constrained : Zero | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Before Next layer or Surfacing | I | SV / PE
3.01.12 | Maximum Vertical Basecourse With Concrete Channel Variation | At or close to the lip of channel: –5 mm +5 mm At other locations on pavement: –5 mm +15 mm | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Before Surfacing | I | SV / PE
3.01.13 | Maximum Crossfall Variation | The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5% | TNZ B/02: 2005 - 5.1 | Survey / Level Checks | Before Surfacing | I | SV / PE
3.01.14 | Benkelman Beam | Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY | PS - 7.3.2 | Benkelman Beam Report | every 10m of each lane – staggered between left and right wheel path. | R | PE | Comment added at Acceptance "Information Only"
3.01.15 | NAASRA roughness | The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required) | TNZ B/02: 2005 - 7.7 | Test Report | Prior to sealing | R | PE | Comment added at Acceptance "Recommeded but not requeired"
3.01.16 | Running Course | If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface. | TNZ B/02: 2005 - 10.1 | Site Notes | Prior to sealing | S | SUP
3.01.17 | Surface Finish post sweeping | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | TNZ B/02: 2005 - 7.8 | Photos | Prior to sealing | R | PE
3.01.18 | Tie in into Existing Pavement | Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a). The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used. | TNZ B/02: 2005, 7.4 | photos, and survey data of undercut | Every tying into existing pavements | I | SV / PE
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.01 | Site Post Construction Activities
4.01.01 | Survey Records | Ensure all items have been surveyed and record. | PS - Page 42 | Records | Post construction | H | SV
4.01.02 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | PE