## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement & Surfacing - Rev A | itp |  |  |  |  | ITP - Pavement & Surfacing - Rev A
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works start
label | Activity - H
label | By - PE
checkpoint | 1.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works start
label | Activity - H
label | By - SV
checkpoint | 1.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint | 1.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to activity being undertaken
label | Activity - H
label | By - SE
checkpoint | 1.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to commencment of activity
label | Activity - H
label | By - PE
checkpoint | 1.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
checkpoint | 1.01.07 - Subbase Approval
label | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
label | Standard / Specification - PS - Page 42
label | Verifying Document - ConQA
label | Frequency - Before proceeding to the next layer
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint | 2.01.01 - Basecourse CBR
label | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
label | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.02 - Running Course Material Approval
label | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
label | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
label | Standard / Specification - TNZ B/02: 2005 - 10.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test every stockpile
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.03 - Basecourse MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test per material type
label | Activity - H
label | By - PE
checkpoint | 2.01.04 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
label | Standard / Specification - NZS 4407: 1991 Test 3.10.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.05 - Weathering Resistance
label | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
label | Standard / Specification - NZS 4407: 1991 Test 3.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.06 - Particle Size Distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.07 - Sand Equivalent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.08 - Liquid Limit
label | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.09 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.10 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.11 - Accelerated Weathering Testing
label | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
label | • The levels of smectite clay minerals are not classified as “abundant”
label | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.12 - Repeat Load Triaxial Test
label | Acceptance / Conformance Criteria - In accordance with NZTA T15
label | Standard / Specification - NZTA T15
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.13 - Broken Face Content
label | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
label | Standard / Specification - TNZ M/4: 2006, 4.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Test per Source
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
label | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | Standard / Specification - TNZ B/02: 2005 - 7.3
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.02 - Basecourse MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - No less than 1 test every 5,000m³ (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.03 - Plateau Density Test
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | • Every plateau to be completed at start of works and witnessed by a member of BBO.
label | Standard / Specification - PS - Table 7.2 - 2.3
label | Verifying Document - Plateau Density Report
label | Frequency - 5 tests per 10,000m2
label | Activity - I
label | By - PE
checkpoint | 3.01.04 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.05 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.06 - Sand Equivalent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.07 - Particle size distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
label | Standard / Specification - TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - I
label | By - PE
checkpoint | 3.01.09 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.10 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Visual Inspection / Site Note
label | Frequency - Prior to sealing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.11 - Maximum Width Variation
label | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
label | • Constrained : Zero
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Next layer or Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
label | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
label | • At other locations on pavement: –5 mm +15 mm
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.13 - Maximum Crossfall Variation
label | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.14 - Benkelman Beam
label | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Benkelman Beam Report
label | Frequency - every 10m of each lane – staggered between left and right wheel path.
label | Activity - R
label | By - PE
checkpoint | 3.01.15 - NAASRA roughness
label | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Activity - R
label | By - PE
checkpoint | 3.01.16 - Running Course
label | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
label | Standard / Specification - TNZ B/02: 2005 - 10.1
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - S
label | By - SUP
checkpoint | 3.01.17 - Surface Finish post sweeping
label | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Standard / Specification - TNZ B/02: 2005 - 7.8
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Activity - R
label | By - PE
checkpoint | 3.01.18 - Tie in into Existing Pavement
label | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
label | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
label | Standard / Specification - TNZ B/02: 2005, 7.4
label | Verifying Document - photos, and survey data of undercut
label | Frequency - Every tying into existing pavements
label | Activity - I
label | By - SV / PE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.01.01 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
label | Standard / Specification - PS - Page 42
label | Verifying Document - Records
label | Frequency - Post construction
label | Activity - H
label | By - SV
checkpoint | 4.01.02 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Activity - H
label | By - PE