## ITP-019
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # FHC-ITP-036
[10 empty] | Revision : 1 | Date : 26/04/2022
Client: |  | MRPA |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Tarneit - South East Car Park |  | Furniture & Bollard Installation | Name: Prateek Tandon |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  | 7428000
|  |  |  | Structure / Component: Tactiles, Bollards, Wheelstops | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Tarneit Railway Station | Date : 26/04/2022 |  | Date : 26/04/2022 |  |  | Date : 26/04/2022
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Reference Documents | Acceptance Criteria | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | IFC Drawings | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Furniture Type |  | IFC Drawings | Furniture to be installed: ☒ Wheel Stop ☒ Bike Hoops ☒ Bollards | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Service Identification |  | IFC Drawings | Check for any services in proximity to points of installation or coring for spigots | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Material Conformance |  | IFC Drawings | Concrete mix design to be approved in teambinder prior to pour. | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | IFC Drawings | Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections. | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Post & Foundations |  | Manufacturer Specification | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences. | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Positioning |  | IFC Drawings | All furniture to be positioned and installed as per IFC Drawings | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
3 | Finishing
3.1 | As-Built Survey |  | IFC Drawings | Has the furniture been installed as per the IFC drawings? Is the location of the furniture required to be included in the as-built survery | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on J16: Rodrigo Anchico: Write "N/A" to disable the cell.