## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-036 - Furniture & Bollard Installation Rev1 | itp |  |  |  |  | FHC-ITP-036 - Furniture & Bollard Installation Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Furniture Type
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Furniture to be installed:
note | ☒ Wheel Stop
note | ☒ Bike Hoops
note | ☒ Bollards
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Service Identification
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Material Conformance
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete mix design to be approved in teambinder prior to pour.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Post & Foundations
note | REFERENCE DOCUMENTS: Manufacturer Specification
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Positioning
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All furniture to be positioned and installed as per IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 3 - Finishing
checkpoint | 3.1 As-Built Survey
note | REFERENCE DOCUMENTS: IFC Drawings
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Has the furniture been installed as per the IFC drawings?
note | • Is the location of the furniture required to be included in the as-built survery
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: