## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-000 - Client Pre-Construction Checklist | itp |  |  |  |  | ITP-000 - Client Pre-Construction Checklist
section | Pre - Construction Works
checkpoint | 1.1 Asphalt - submission of asphalt mix design
note | FREQUENCY: Prior to commencing paving
note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
note | RECORD OF CONFORMITY: Superintendent approval via hold point release
note | HP
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
note | FREQUENCY: Prior to first concrete pour
note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix) with 100 mm slump.
note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379.
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
note | RECORD OF CONFORMITY: Superintendent approval via hold point release
note | HP
note | RESPONSIBILITY: FH Engineer / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 Welders qualifications & work methodology
note | FREQUENCY: Prior to commencing works
note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
note | • TLIW2012 Grind Rails
note | • TLIW3015 Weld Rails using Aluminothermic welding process
note | • TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
note | • Weld methodology to be submitted prior to commencement of works
note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Superintendent approval via hold point release
note | HP
note | RESPONSIBILITY: FH Engineer / Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: