## ITP
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | CON1006 Monteith Road bridge 256_7495 Bridge Replacement |  |  | Hold Point (H) | Review(R) | 0
Project No 7011 |  |  |  |  | Submit (S) | Surveillance (SU)
Approve(A)
Verify (V)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | WSP | DATE | COMMENTS
Piling
Preliminary
Shop Drawings | IFC Drawings / Particular Specification | Approved shop drawings prior to fabrication | Engineer | 5 Days before commencing fabrication | Approved by Engineer | H | H
Concrete Mix Design Approved | IFC Drawings / Particular Specification | Approval from Engineer | Engineer | Per Mix Design | Approved by Engineer | H | H
Pre cast Piles
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for each pile | Pre pour inspection checksheet | H | H
Abutment A Piles
Pile setout | IFC Drawings / Particular Specification | Visual Inspection | Enginner | After setout of each pile | As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75 | H | H
Driving Of Piles | IFC Drawings / Particular Specification | Visual Inspection | Engineer | For each Pile | Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet | W | W
Abutment B Piles
Pile setout | IFC Drawings / Particular Specification | Visual Inspection | Enginner | After setout of each pile | As per IFC Drawings. Top of Pile should be within tolerance iof 75mm Horizontally and 25mm Vertically. Maximum Daviation from vertical at any level shall not be more than 1:75 | H | H
Driving Of Piles | IFC Drawings / Particular Specification | Visual Inspection | Engineer | For each Pile | Pile shall be driven to an ultimate bearing capacity of 1000kN and a minimum embedment depth of 10.5m from top of abutment wall. Pile Installation Checksheet | W | W
Abutment and backwall
Preliminary
Concrete Mix Design Approved | IFC Drawings / Particular Specification | Approval from Engineer | Engineer | Per Mix Design | Approved by Engineer | H | H
Abutment A Construction
setout | IFC Drawings / Particular Specification | Visual Inspection | Enginner | For set out of each Abutment | As per IFC Drawings | W | H
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for Abutment | Pre pour inspection checksheet | H | H
Abutment B Construction
setout | IFC Drawings / Particular Specification | Visual Inspection | Enginner | For set out of each Abutment | As per IFC Drawings | W | H
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for Abutment | Pre pour inspection checksheet | H | H
Abutment A backwall Construction
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for Abutment | Pre pour inspection checksheet | H | H
Abutment C Backwall Construction
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for Abutment backwall | Pre pour inspection checksheet | H | H
Construction of Mortar Bearing Pad
Pre Pour Inspection | IFC Drawings / Particular Specification | Visual Inspection | Enginner | Pre pour inspection for Abutment | Pre pour inspection checksheet | H | H
Structural steel works
Sub contractor's ITP
Timber Work
Preliminary
Procurement | IFC Drawings / Particular Specification | Dockets | UCCL | For any timber ordered for project | All timber to meet specified grade and Moisture content as specified in particular specification | W | W
Installation | IFC Drawings / Particular Specification | Visual Inspection/Photos | Engineer | Random site visits | All timber and Fastners installed as per IFC Drawing | W | W
Reinstate Approaches
Preliminary
Backfill | IFC Drawings / Particular Specification | Clegg Test | UCCL/Engineer | 5 Tests per approach per layer | Clegg Impact value of 40 | W | W