## ITP 001
INSPECTION & TEST PLAN
|  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | 7000 - Contract 7674 SH10 Parapara Bridge Strengthening |  |  | Hold Point (H) | Review(R) | 0 | Sid Rudani | 2023-01-20
ITP 001 |  |  |  |  | Submit (S) | Surveillance (SU) | 1 | Sid Rudani | 2023-02-07
Approve(A)
Verify (V)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL | Beca | DATE | COMMENTS
Preliminary
Pre condition Survey | Project Specification PS1 | Visual markup | Engineer/UCCL | Before any Concrete repair work begins. | Documented as part of site discussion to mutually agree on extent of reapair required. Affected area to be mark. | H | H
Repairing of Spalled Concrete and Cracks Wider than 0.3mm | Project Specification PS1 | Visual | Engineer/UCCL | Engineer can Witness initial repairing procedure on site. Final inspection once repairing is done | Completed as per Technical specification Section-12. Concrete core sample to prove extent of crack injection if requested by Engineer. Work Completed by approved Contractor | SU | W
Shear Brackets
Anchor Pull out test | IFC Drawing | Test Reuslt/ Visual | Engineer/UCCL | Before Installation of Shear brackets | Anchors to meet 30KN Pull out force requirement as per Longitudinal sheat Bracket Fixing Note-1 | H | F
Procurement | IFC Drawings | Reinforcement Scanning/ Visual location of CJ | UCCL | Before placement of order for Shear Brackets | Confirm if there are any clashes with Anchor installation and reinforcement. If clash with reinforcement identified than report back to Engineer for further clarification. On site mark out plan will be submitted to engieer for review. | H | H
Fabrication | IFC Drawing/ Project Specification/ Techinacl Specification |  | Sub-Contractor | For all steel fabrication | Approved ITP for steel Fabrication Completed. And all relevant documents submitted as part of ITP | H | H
Installation | IFC Drawing/ Project Specification/ Techinacl Specification |  | Engineer/UCCL | For all Bracket Installation | Shear Bracket Installation Checksheet. One checksheeet/ Raw of bracket/ Span | SU | W
Post Tensioning
Fabrication of Brackets | IFC Drawing/ Project Specification/ Techinacl Specification |  | Sub-Contractor | For all steel fabrication | Approved ITP for steel Fabrication Completed. And all relevant documents submitted as part of ITP | H | H
Installation of Post Tensioning Brackets | IFC Drawings |  | Engineer/UCCL | For all bracket Installation | Installed as specified in Drawing 3911772-4309-SA-002 | H | W
Concrete Pour around Anchor Plates | IFC Drawing/ Project Specification/ Techinacl Specification | Visual | Engineer/UCCL | For Each Concrete Block (Engineer May like to witness first concrete pour) | Pre Pour Inspection Checklist completed. | H | W
Post Tensioning | IFC Drawing/ Project Specification/ Techinacl Specification |  | Engineer/UCCL | For all Post Tensioning Work | Approved ITP for Post Tensioning Completed. And all relevant documents submitted as part of ITP | H | H
Backfill or Reinstate Pavement
Crushing Strength | Project Specification/ Techinacl Specification | NZS 4407 Test 3.10 | IANZ accredited laboratory | Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site. | <10% fines passing 2.36mm under 110 KN load | H | H
Weathering Quality | Project Specification/ Techinacl Specification | NZS 4407 Test 3.11 | IANZ accredited laboratory | Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) | AA, AB., AC, BA, BB or CA | H | H
California Bearing Ratio | Project Specification/ Techinacl Specification | NZS 4407 Test 3.15 | IANZ accredited laboratory | Prior to agreement to Material Source and 1 Test per each 10000m3 of source material, Except for Premeabiility which should be carried out annually | 4 Day Soaked CBR not less than 60% (Test sample shall be compacted to 95-96% of MDD, NZS 4402 Test 4.1.3 Vibrating Hammer) | H | H
Spolid Density | Project Specification/ Techinacl Specification | NZS 4407 Test 3.7 | IANZ accredited laboratory | Prior to agreement to Material Source and 1 Test per each 1000m3 of source material | Report Only | H | H
Sand equivalent | Project Specification/ Techinacl Specification | NZS 4407 Test 3.6 | IANZ accredited laboratory | Compliance certificate < 12 months old or 2 Test per 1-400m3 lot size | ≥ 25 | H | H
Particle size distribution | Project Specification/ Techinacl Specification | NZS 4407 Test 3.8.1 | IANZ accredited laboratory | Compliance certificate < 12 months old. 2 Test per 1-400m3 lot size | As per contract documents for different material | H | H
Propotion of Broken Faces | Project Specification/ Techinacl Specification | NZS 4407 Test 3.14 | IANZ accredited laboratory | Compliance certificate < 12 months old or d for every 1000 m3 delivered to site. | Proportion of broken faces no less than 70% by weighjt in each of the three agreegate fractions between 37.5 or 63.0 and 4.75 Sieves (This requirement does not apply where the sub-basecourse is sourved from hard face quarry) | H | H
Clay Index | Project Specification/ Techinacl Specification | NZS 4407 Test 3.5 | IANZ accredited laboratory | Compliance certificate < 12 months old or . 2 Test per 1-400m3 lot size | Not Greater than 3 | H | H
Plasticity Index | Project Specification/ Techinacl Specification | NZS 4407 Test 3.4 | IANZ accredited laboratory | Compliance certificate < 12 months old or . 2 Test per 1-400m3 lot size | Not Greater Than 10 | H | H
Determination of MDD & OMC | Project Specification/ Techinacl Specification | NZS 4407 Test 3.1, Test 4.1..3 | IANZ accredited laboratory | Per source (Stockpile) - to be undertaken representative stockpiled aggregate | report value only | H | H
Compaction Testing | Project Specification/ Techinacl Specification | NZTA B/2 CI7.6 | UCCL | 1 Set if test (5 random test point per lot) of 1000m2 | Result Compliers with NZTA B/2 CI7.6. Sub-base layer compated to mean value of >/= 95% of MDD. Base course layer compatedmean value of >/= 98% of MDD. | H | H

## Shear Bracket Installation Chec
Shear Bracket Installation Check sheet | Date
Completed by
Description | Yes | No | NA
Surface Roughned to Minimum 2mm Amptitude
Drilled hole Depth Min Ø135mm
Drilled hole Clean and Dry
Sikadur UA31 Applied to bracket before Installation
Approved Chemical Epoxy insatlled as per Manufacture's specification
Minimum Number of required Threded rods installed per brackets
Nuts Tightened after epoxy cured
Any exposed cut end of threded anchors painted with ArmourZinc110